## BASIC
... Diisi Desain ... Agar diperhatikan spy timesheet masing2 personil bisa continue/tidak terputus krn terkait KPI Personil | [9 empty] | Diisi Planner
No | Tanggal Permintaan JC ditulis | Project | Task Name | Work Center | Schedule Start date | Schedule End date | Total Personil yang mengerjakan | PIC | JO | Kode Job Card | Keterangan | Planner
| DD / MM / YYYY | KODE PROYEK | REVISI KE - NO DOC / DWG - DESC PEKERJAAN | KODE BIRO - DESC BIRO | DD / MM / YYYY | DD / MM / YYYY | (DALAM ANGKA) | (NAMA) | (ANGKA) | JC010624 0001 |  | 023066812-Hashfi Moch Adam
CONTOH
1 | 14 May 2024 | W000308 | E90961.92020 - WEIGHT CONTROL BASIC (KB-02) | 1CM303 - Biro Basic Desain Kapal Permukaan | 2024-06-14 | 2024-06-21 | 2 |  |  | JC040624 0374 |  |  |  | 023066812-Hashfi Moch Adam
| 2025-03-04 | W000304 | E90961.92021 - WEIGHT CONTROL BASIC (KB-03) | Biro Desain Dasar Kapal Permukaan | 2025-03-03 | 2025-03-28 | 1 | Rahadian Lingga Pratama |  | JC040325 15904
| 2025-03-04 | Hospital Ship (UAE) | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-03-03 | 2025-03-14 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC050325 15995
| 2025-03-04 | Hospital Ship (UAE) | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-03-03 | 2025-03-14 | 1 | Irma Mahardhika PuTri Handoyo |  | JC050325 15994
| 2025-03-04 | Hospital Ship (UAE) | Technical Specification | Biro Desain Dasar Kapal Permukaan | 2025-03-03 | 2025-03-14 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC050325 15993
| 2025-03-04 | W000305 | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-03-03 | 2025-03-14 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC040325 15955
| 2025-03-03 | B250N009 | Tender Retubing HPH 3 Unit 1 PLTU Pelabuhan Ratu | Biro Desain Dasar Non Kapal | 2025-03-01 | 2025-03-05 | 3 | FM & TIM |  | JC100325 16371
| 2025-03-03 | B250N006 | Tender Eng. Proc. Cons. Trans. of Conductor Supp. Frame Duyung PSC - Conrad Asia Ltd-R2 | Biro Desain Dasar Non Kapal | 2025-03-03 | 2025-03-05 | 3 | BT & TIM |  | JC100325 16372
| 2025-03-10 | B250N009 | Tender Retubing HPH 3 Unit 1 PLTU Pelabuhan Ratu-R1 | Biro Desain Dasar Non Kapal | 2025-02-07 | 2025-03-12 | 3 | FM & TIM |  | JC100325 16373
| 2025-03-11 | B250N011 | Tender Pengadaan HE Cooling Vacum Pump | Biro Desain Dasar Non Kapal | 2025-02-10 | 2025-03-14 | 3 | RW & TIM |  | JC110325 16452
| 2025-03-13 | B240N072 | Tender Jacket Intake Head PT Amman Mineral -McConnell Dowell | Biro Desain Dasar Non Kapal | 2025-02-12 | 2025-03-17 | 3 | BT & TIM |  | JC140325 16533
| 2025-03-18 | Hospital Ship (UAE) | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-03-17 | 2025-03-28 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC190325 16768
| 2025-03-18 | W000308 | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-03-17 | 2025-03-28 | 1 | Irma Mahardhika PuTri Handoyo |  | JC190325 16769
| 2025-03-18 | B25N010 | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-03-17 | 2025-03-28 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC190325 16771
| 2025-03-18 | KSR 15 M | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-03-17 | 2025-03-28 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC190325 16772
| 2025-03-19 | B25N010 | Tender BMPP 3 (30MW) | Biro Desain Dasar Non Kapal | 2025-03-01 | 2025-03-29 | 4 | BT & TIM |  | JC250325 17045
| 2025-03-19 | B250N012. | Tender Tube Bundle PT KPI RU III Plaju tahun 2025 - PT KPI RU III Plaju tahun 2025 | Biro Desain Dasar Non Kapal | 2025-03-19 | 2025-03-25 | 3 | RW & TIM |  | JC250325 17046
| 2025-03-26 | B250N013 | Tender Pengadaan Material Tube bundle & Oil Cooler Assy. Unit HVU II Keb. Pit Stop Th. 2026 - PT KPI RU III Plaju | Biro Desain Dasar Non Kapal | 2025-03-25 | 2025-03-28 | 3 | RW & TIM |  | JC270325 17080
| 2025-03-27 | E250N002 | Fabrikasi Pontoon PLTAL 2x20kW - PT. PLN (Persero) Puslitbang - apr | Biro Desain Dasar Non Kapal | 2025-04-07 | 2025-04-30 | 6 | BT & TIM |  | JC110425 17653
2025-04-01
| 2025-04-07 | W000305 | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-04-07 | 2025-04-18 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC250425 18360
| 2025-04-07 | W000305 | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-04-07 | 2025-04-18 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC080425 17373
| 2025-04-07 | W000308 | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-04-07 | 2025-04-18 | 1 | Irma Mahardhika PuTri Handoyo |  | JC080425 17370
| 2025-04-07 | B25N010 | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-04-07 | 2025-04-18 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC250425 18361
| 2025-04-08 | B25N010 | Tender BMPP 3 (30MW) | Biro Desain Dasar Non Kapal | 2025-04-01 | 2025-04-30 | 5 | BEATri HandoyoCE, Ahmad Amirulloh, Muhammad Mirza, Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah |  | JC080425 17466
| 2025-04-08 | W000305 | weight control yard plan stage (KB03) | Biro Desain Dasar Kapal Permukaan | 2025-04-07 | 2025-04-30 | 1 | Rahadian Lingga Pratama |  | JC090425 17535
| 2025-04-08 | W000308 | weight control yard plan stage (KB03) | Biro Desain Dasar Kapal Permukaan | 2025-04-07 | 2025-04-30 | 1 | Rahadian Lingga Pratama |  | JC090425 17536
| 2025-04-08 | W000307 | weight control yard plan stage (KB03) | Biro Desain Dasar Kapal Permukaan | 2025-04-07 | 2025-04-30 | 1 | Rahadian Lingga Pratama |  | JC090425 17537
| 2025-04-09 | B250N013 | Tender Pengadaan Material Tube bundle & Oil Cooler Assy. Unit HVU II Keb. Pit Stop Th. 2026 | Biro Desain Dasar Non Kapal | 2025-04-01 | 2025-04-11 | 4 | BEATri HandoyoCE, Fendi Miranda, Ahmad Amirulloh, Mey Resty Nugraheni |  | JC110425 17654
| 2025-04-09 | B250N014 | Redundant HE 11-E-110/111 A/B - PT KPI RU VI Balongan | Biro Desain Dasar Non Kapal | 2025-04-01 | 2025-04-15 | 4 | RIDUWAN, ALIP, Muhammad Mirza, Ahmad Amirulloh |  | JC110425 17655
| 2025-04-14 | A24AOP01 | PENGEMBANGAN KAPAL PENGINDERAAN BAWAH/ATAS AIR - SKID & FLOORING | Biro Desain Dasar Non Kapal | 2025-04-01 | 2025-04-30 | UPDATE PERSONIL | ALIP, Nur Fuadi Afif Zaisyah, BEATri HandoyoCE |  | JC150425 17926
| 2025-04-15 | B250N015 | Tender Fabricate 2 off Super Screen Support Frame - PT Metso Technology Solutions | Biro Desain Dasar Non Kapal | 2025-04-15 | 2025-04-21 |  | Fendi Miranda, Luqman Chakim |  | JC150425 17936
| 2025-04-16 | B250N016 | Tender Pembuatan HE C3W PLTU Labuhan Angin - PT PLN Pusharlis | Biro Desain Dasar Non Kapal | 2025-04-16 | 2025-04-29 |  | RIDUWAN, Luqman Chakim, Tri Handoyo |  | JC170425 17993
| 2025-04-21 | A24AOP01 | PDHC Kapal penginderaan bawa/atas air 15 m | Biro Basic Design Kapal Selam | 2025-04-10 | 2025-04-30 |  | SIGIT ISKIYARSAH |  | JC280425 18516
| 2025-04-21 | F21ZAI54 | FASILITAS SHIPLIFT & DERMAGA PMN 21 | Biro Desain Dasar Non Kapal | 2025-04-14 | 2025-04-30 |  | Nur Fuadi Afif Zaisyah, Minarti Shinta Putri Utomo, Luqman Chakim, Mey Resty Nugraheni |  | JC280425 18507
| 2025-04-21 | W000308 | Tri Handoyom & Stability Calculation Progress R1 | Biro Desain Dasar Kapal Permukaan | 2025-04-21 | 2025-05-02 | 1 | Irma Mahardhika PuTri Handoyo |  | JC220425 18222
| 2025-04-21 | LCU LD Philippine | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2025-04-21 | 2025-05-02 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC250425 18363
| 2025-04-21 | W000304 | Ship Condition for Launching | Biro Desain Dasar Kapal Permukaan | 2025-04-21 | 2025-05-02 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC220425 18221
| 2025-04-21 | W000305 | General Arrangement Progress R3 | Biro Desain Dasar Kapal Permukaan | 2025-04-21 | 2025-05-02 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC220425 18220
2025-05-01
| 2025-05-02 | B250N017 | Tender Tangki Asam Sulfat PT. Petro Kimia Gersik | Biro Desain Dasar Non Kapal | 2025-04-28 | 2025-05-05 | 3 | BEATri HandoyoCE, RIDUWAN, Luqman Chakim |  | JC020525 18779
| 2025-05-02 | F21ZAI54 | FASILITAS SHIPLIFT & DERMAGA PMN 21-m | Biro Desain Dasar Non Kapal | 2025-05-01 | 2025-05-31 |  | Nur Fuadi Afif Zaisyah, Minarti Shinta Putri Utomo, Luqman Chakim, Mey Resty Nugraheni |  | JC070525 19053
| 2025-05-02 | B25N010 | Tender BMPP 3 (30MW) | Biro Desain Dasar Non Kapal | 2025-05-01 | 2025-05-31 | 6 | Agus Wibowo, BEATri HandoyoCE, Ahmad Amirulloh, Muhammad Mirza, Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah |  | JC050525 18982
| 2025-05-02 | E250N002 | Fabrikasi Pontoon PLTAL 2x20kW - PT. PLN (Persero) Puslitbang - m | Biro Desain Dasar Non Kapal | 2025-05-01 | 2025-05-31 | 5 | BEATri HandoyoCE, Tri Handoyo, Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah, Mey Resty Nugraheni |  | JC050525 18983
| 2025-05-02 | B250N014 | Redundant HE 11-E-110/111 A/B - PT KPI RU VI Balongan | Biro Desain Dasar Non Kapal | 2025-05-01 | 2025-05-05 | 4 | RIDUWAN, ALIP, Muhammad Mirza, Ahmad Amirulloh |  | JC050525 18984
| 2025-05-05 | A24AOP01 | PDHC Kapal penginderaan bawa/atas air 15 m | Biro Basic Design Kapal Selam | 2025-05-05 | 2025-05-31 | 1 | SIGIT ISKIYARSAH |  | JC050525 18985
| 2025-05-05 | Hospital Ship (UAE) | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-05-05 | 2025-05-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC050525 18986
| 2025-05-05 | KSR | Lightweight Estimation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-05-05 | 2025-05-30 | 2 | Moh. Hamzah SaTri Handoyoawansyah dan Ahmad MuhtArif Billah Ihyail Haqiil |  | JC050525 18987
| 2025-05-05 | KSR | Deadwight Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-05-05 | 2025-05-30 | 2 | Moh. Hamzah SaTri Handoyoawansyah dan Ahmad MuhtArif Billah Ihyail Haqiil |  | JC050525 18988
| 2025-05-05 | KSR | Tri Handoyom & Stability Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-05-05 | 2025-05-30 | 2 | Moh. Hamzah SaTri Handoyoawansyah dan Ahmad MuhtArif Billah Ihyail Haqiil |  | JC050525 18990
| 2025-05-05 | KSR | Speed Power Prediction (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-05-05 | 2025-05-30 | 2 | Moh. Hamzah SaTri Handoyoawansyah dan Ahmad MuhtArif Billah Ihyail Haqiil |  | JC050525 18992
| 2025-05-05 | W000308 | Tri Handoyom & Stability Calculation Progress R1 | Biro Desain Dasar Kapal Permukaan | 2025-05-05 | 2025-05-30 | 1 | Irma Mahardhika PuTri Handoyo |  | JC050525 18994
| 2025-05-05 | LCU LD Philippine | Compartement Room Napa | Biro Desain Dasar Kapal Permukaan | 2025-05-05 | 2025-05-30 | 1 | Irma Mahardhika PuTri Handoyo |  | JC050525 18996
| 2025-05-05 | BMPP 30MW | Lightweight Estimation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-05-05 | 2025-05-30 | 1 | Irma Mahardhika PuTri Handoyo |  | JC050525 18998
| 2025-05-05 | LCU LD Philippine | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2025-05-05 | 2025-05-30 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC050525 18981
| 2025-05-05 | PLTAL | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2025-05-05 | 2025-05-30 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC050525 18980
| 2025-05-05 | BMPP 30MW | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-05-05 | 2025-05-30 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC050525 18979
| 2025-05-05 | BMPP 30MW | Tonnage Calculation | Biro Desain Dasar Kapal Permukaan | 2025-05-05 | 2025-05-30 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC050525 18978
| 2025-05-05 | W000305 | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-05-05 | 2025-05-30 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC050525 18966
| 2025-05-05 | W000305 | Supporting analysis of basic design | Biro Desain Dasar Kapal Permukaan | 2025-05-02 | 2025-05-31 | 2 | Rahadian Lingga Pratama Arif Billah bilah |  | JC050525 18975
| 2025-05-05 | W000307 | Supporting analysis of basic design | Biro Desain Dasar Kapal Permukaan | 2025-05-02 | 2025-05-31 | 2 | Rahadian Lingga Pratama Arif Billah bilah |  | JC050525 18976
| 2025-05-05 | W000308 | Supporting analysis of basic design | Biro Desain Dasar Kapal Permukaan | 2025-05-02 | 2025-05-31 | 2 | Rahadian Lingga Pratama Arif Billah bilah |  | JC050525 18977
| 2025-05-07 | W000304-305 | KAPAL FRIGATE 140 M - AIR RESERVOIR | Biro Desain Dasar Non Kapal | 2025-05-01 | 2025-05-30 | 2 | Tri Handoyo, BEATri HandoyoCE |  | JC070525 19062
| 2025-05-07 | A24AOP01 | PDHC Kapal penginderaan bawa/atas air 15 m | Biro Basic Design Kapal Selam | 2025-05-02 | 2025-05-02 | 1 | SIGIT ISKIYARSAH |  | JC070525 19063
| 2025-05-13 | B250N018 | Pengadaaan Vessel Waste Heat Boiler Blew Down Drum 14V-8 Assy - PT. KPI Ref. Unit IV Cilacap | Biro Desain Dasar Non Kapal | 2025-05-09 | 2025-05-19 | 2 | BEATri HandoyoCE, Tri Handoyo |  | JC130525 19276
| 2025-05-14 | B250N019 | Fabricate 4 off Knelson Screen Support Frame and Side Plate - PT Metso Technology Solutions | Biro Desain Dasar Non Kapal | 2025-05-14 | 2025-05-23 | 2 | BEATri HandoyoCE, Luqman Chakim |  | JC200525 19626
| 2025-05-16 | B250N020 | Heat Exchanger dan Tube Bundle - PT KPI RU III Plaju | Biro Desain Dasar Non Kapal | 2025-05-16 | 2025-05-27 | 4 | Alif Junaidi, Muhammad Mirza, RIDUWAN, Fendi Miranda |  | JC200525 19627
| 2025-05-16 | B250N021 | Jasa Rerouting Instalasi Pipa BBM Pesangrahan UBP Bali - PT PLN IP | Biro Desain Dasar Non Kapal | 2025-05-16 | 2025-05-26 | 1 | Ahmad Amirulloh |  | JC200525 19630
| 2025-05-20 | E250N004 | Fabricate support Frame Superscreen (2 unit) - PT Metso Technology Solutions - 1 | Biro Desain Dasar Non Kapal | 2025-05-19 | 2025-05-31 | 2 | BEATri HandoyoCE, Luqman Chakim | 100 | JC210525 19663
| 2025-05-20 | E250N005 | Fabricate TertiAry Tri Handoyo Ratnaningtyas Screen Components ( 1 unit) - PT Metso Technology Solutions - 1 | Biro Desain Dasar Non Kapal | 2025-05-19 | 2025-05-31 | 2 | BEATri HandoyoCE, Luqman Chakim | 100 | JC210525 19664
| 2025-06-02 | E250N004 | Fabricate support Frame Superscreen (2 unit) - PT Metso Technology Solutions - 1 | Biro Desain Dasar Non Kapal | 2025-06-02 | 2025-06-30 | 2 | BEATri HandoyoCE, Luqman Chakim | 100 | JC020625 20192
| 2025-06-02 | B250N017 | Tender Tangki Asam Sulfat PT. Petro Kimia Gersik | Biro Desain Dasar Non Kapal | 2025-05-28 | 2025-06-03 | 3 | BEATri HandoyoCE, RIDUWAN, Luqman Chakim |  | JC020625 20254
| 2025-06-02 | E250N005 | Fabricate TertiAry Tri Handoyo Ratnaningtyas Screen Components ( 1 unit) - PT Metso Technology Solutions - 1 | Biro Desain Dasar Non Kapal | 2025-06-02 | 2025-06-30 | 2 | BEATri HandoyoCE, Luqman Chakim | 100 | JC020625 20252
| 2025-06-02 | A24AOP01 | PDHC Kapal penginderaan bawa/atas air 15 m | Biro Basic Design Kapal Selam | 2025-06-02 | 2025-06-30 | 1 | SIGIT ISKIYARSAH |  | JC020625 20258
| 2025-06-02 | W000306 | Dock operation manual | Biro Desain Dasar Kapal Permukaan | 2025-06-02 | 2025-06-30 | 1 | Rahadian Lingga Pratama |  | JC020625 20260
| 2025-06-02 | W000308 | Dock operation manual | Biro Desain Dasar Kapal Permukaan | 2025-06-02 | 2025-06-30 | 1 | Rahadian Lingga Pratama |  | JC020625 20261
| 2025-06-02 | W000306 | Damage control booklet | Biro Desain Dasar Kapal Permukaan | 2025-06-02 | 2025-06-30 | 1 | Arif Billah billah |  | JC020625 20262
| 2025-06-02 | W000308 | Damage control booklet | Biro Desain Dasar Kapal Permukaan | 2025-06-02 | 2025-06-30 | 1 | Arif Billah billah |  | JC020625 20263
| 2025-06-02 | Hospital Ship (UAE) | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-06-02 | 2025-06-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC030625 20268
| 2025-06-02 | W000305 | Sounding Table | Biro Desain Dasar Kapal Permukaan | 2025-06-02 | 2025-06-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC030625 20269
| 2025-06-02 | KSR | Lightweight Estimation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-06-02 | 2025-06-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC030625 20270
| 2025-06-02 | KSR | Tri Handoyom & Stability Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-06-02 | 2025-06-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC030625 20271
| 2025-06-02 | W000308 | Tri Handoyom & Stability Calculation Progress R1 | Biro Desain Dasar Kapal Permukaan | 2025-06-02 | 2025-06-30 | 1 | Irma Mahardhika PuTri Handoyo |  | JC030625 20273
| 2025-06-02 | BMPP 30MW | Tri Handoyom & Stability Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-06-02 | 2025-06-30 | 1 | Irma Mahardhika PuTri Handoyo |  | JC030625 20285
| 2025-06-02 | LCU LD Philippine | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2025-06-02 | 2025-06-30 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC030625 20286
| 2025-06-02 | LCU LD Philippine | Tri Handoyom & Stability Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-06-02 | 2025-06-30 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC030625 20335
| 2025-06-02 | W000305 | General Arrangement progress R3 | Biro Desain Dasar Kapal Permukaan | 2025-06-02 | 2025-06-30 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC030625 20336
| 2025-06-02 | W000305 | Deadwight Calculation Progres R1 | Biro Desain Dasar Kapal Permukaan | 2025-06-02 | 2025-06-30 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC030625 20337
| 2025-06-02 | KSR | Deadwight Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-06-02 | 2025-06-30 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC030625 20338
| 2025-06-02 | KSR | Speed Power Prediction (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-06-02 | 2025-06-30 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC030625 20339
| 2025-06-09 | B25N010 | Tender BMPP 3 (30MW) | Biro Desain Dasar Non Kapal | 2025-06-02 | 2025-06-30 | 7 | Agus Wibowo, BEATri HandoyoCE, Ahmad Amirulloh, Muhammad Mirza, Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah, Fendi Miranda |  | JC100625 20607
| 2025-06-26 | B250N022 | Tender budgetarry HPH 6 dan 7 PLTU banten 1 Suralaya | Biro Desain Dasar Non Kapal | 2025-06-25 | 2025-07-12 | 4 | Riduwan, Tri Handoyo, Alif Junaidi, Mey Resty Nugraheni |  | JC260625 21386
| 2025-06-30 | B25N010 | Tender BMPP 3 (30MW) | Biro Desain Dasar Non Kapal | 2025-07-01 | 2025-07-31 | 7 | Agus Wibowo, BEATri HandoyoCE, Ahmad Amirulloh, Muhammad Mirza, Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah, Fendi Miranda |  | JC010725 21563
| 2025-07-01 | Hospital Ship (UAE) | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-07-01 | 2025-07-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC010725 21633
| 2025-07-01 | KSR | Lightweight Estimation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-07-01 | 2025-07-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC010725 21636
| 2025-07-01 | KSR | Tri Handoyom & Stability Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-07-01 | 2025-07-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC010725 21637
| 2025-07-01 | Kapal Bom 8M | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-07-01 | 2025-07-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC010725 21638
| 2025-07-01 | W000304-305 | Sounding Table Progress R1 | Biro Desain Dasar Kapal Permukaan | 2025-07-01 | 2025-07-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC010725 21639
| 2025-07-01 | W000308 | Tri Handoyom & Stability Calculation Progress R1 | Biro Desain Dasar Kapal Permukaan | 2025-07-01 | 2025-07-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC010725 21640
| 2025-07-01 | BMPP 30MW | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-07-01 | 2025-07-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC010725 21641
| 2025-07-01 | BMPP 30MW | Capacity Plan (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-07-01 | 2025-07-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC010725 21642
| 2025-07-01 | LCU LD Philippine | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2025-07-01 | 2025-07-31 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC010725 21643
| 2025-07-01 | LCU LD Philippine | Tri Handoyom & Stability Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-07-01 | 2025-07-31 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC010725 21644
| 2025-07-01 | Kapal Bom 8M | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2025-07-01 | 2025-07-31 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC010725 21645
| 2025-07-01 | Improvement Tri Handoyomaran | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2025-07-01 | 2025-07-31 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC010725 21646
| 2025-07-01 | W000304-305 | General Arrangement progress R3 | Biro Desain Dasar Kapal Permukaan | 2025-07-01 | 2025-07-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC010725 21647
| 2025-07-01 | W000304-305 | Deadwight Calculation Progres R1 | Biro Desain Dasar Kapal Permukaan | 2025-07-01 | 2025-07-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC010725 21648
| 2025-07-01 | KSR | Deadwight Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-07-01 | 2025-07-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC010725 21649
| 2025-07-01 | KSR | Speed Power Prediction (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-07-01 | 2025-07-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC010725 21650
| 2025-07-01 | Kapal Bom 8M | Speed Power Prediction (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-07-01 | 2025-07-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC010725 21653
| 2025-07-02 | W000304-305 | Ship condition for launching | Biro Desain Dasar Kapal Permukaan | 2025-07-01 | 2025-07-31 | 1 | Rahadian Lingga Pratama |  | JC020725 21681
| 2025-07-02 | W000308 | Dock operation manual | Biro Desain Dasar Kapal Permukaan | 2025-07-01 | 2025-07-31 | 1 | Arif Billah billah |  | JC020725 21682
| 2025-06-02 | A24AOP01 | PDHC Kapal penginderaan bawa/atas air 15 m | Biro Basic Design Kapal Selam | 2025-07-01 | 2025-07-31 | 1 | SIGIT ISKIYARSAH |  | JC030725 21725
| 2025-07-09 | B250N022 | Pengadaan HPH 6 dan HPH 7 PLTU Banten 1 Suralaya | Biro Desain Dasar Non Kapal | 2025-07-01 | 2025-07-14 |  | RIDUWAN, Alif Junaidi, Tri Handoyo, Mey Resty Nugraheni |  | JC090725 22059
| 2025-07-09 | B250N023 | Pengadaan Condenser 93-E-405 | Biro Desain Dasar Non Kapal | 2025-07-01 | 2025-07-15 | 2 | BEATICE, Ahmad Amirulloh |  | JC090725 22065
| 2025-07-09 | B250N024 | Pengadaan HPH 8 PLTU Banten 1 Suralaya | Biro Desain Dasar Non Kapal | 2025-07-07 | 2025-07-21 | 3 | RIDUWAN, Alif Junaidi, Tri Handoyo, Mey Resty Nugraheni |  | JC090725 22066
| 2025-07-09 | F21ZAI54 | FASILITAS SHIPLIFT & DERMAGA PMN 21-JL | Biro Desain Dasar Non Kapal | 2025-07-01 | 2025-07-31 | 2 | Nur Fuadi Afif Zaisyah, Minarti Shinta Putri Utomo |  | JC090725 22067
| 2025-07-24 | B250N025 | Kapal Keruk CSD 30 Meter (Re-Tender) | Biro Desain Dasar Non Kapal | 2025-07-24 | 2025-07-28 | 2 | BEATICE, Tri Handoyo, Luqman Chakim |  | JC250725 22672
| 2025-07-24 | B250N023 | Pengadaan Condenser 93-E-405 | Biro Desain Dasar Non Kapal | 2025-07-24 | 2025-07-28 | 3 | EATri HandoyoCE, Ahmad Amirulloh |  | JC250725 22673
| 2025-07-25 | Hospital Ship (UAE) | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 01 Ags 2025 | 31 Ags 2025 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC280725 22870
| 2025-07-25 | KSR | Lightweight Estimation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 01 Ags 2025 | 31 Ags 2025 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC280725 22871
| 2025-07-25 | KSR | Tri Handoyom & Stability Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 01 Ags 2025 | 31 Ags 2025 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC280725 22872
| 2025-07-25 | Kapal Bom | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 01 Ags 2025 | 31 Ags 2025 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC280725 22873
| 2025-07-25 | W000304-305 | Sounding Table Progress R1 | Biro Desain Dasar Kapal Permukaan | 01 Ags 2025 | 31 Ags 2025 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC280725 22874
| 2025-07-25 | W000308 | Tri Handoyom & Stability Calculation Progress R1 | Biro Desain Dasar Kapal Permukaan | 01 Ags 2025 | 31 Ags 2025 | 1 | Irma Mahardhika PuTri Handoyo |  | JC280725 22875
| 2025-07-25 | LCU LD Philippine | Capacity Plan (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 01 Ags 2025 | 31 Ags 2025 | 1 | Irma Mahardhika PuTri Handoyo |  | JC280725 22876
| 2025-07-25 | LCU LD Philippine | Tri Handoyom & Stability Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 01 Ags 2025 | 31 Ags 2025 | 1 | Irma Mahardhika PuTri Handoyo |  | JC280725 22877
| 2025-07-25 | Tender FPB Bea Cukai | Capacity Plan (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 01 Ags 2025 | 31 Ags 2025 | 1 | Irma Mahardhika PuTri Handoyo |  | JC280725 22878
| 2025-07-25 | Tender FPB Bea Cukai | Lines Plan | Biro Desain Dasar Kapal Permukaan | 01 Ags 2025 | 31 Ags 2025 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC280725 22879
| 2025-07-25 | Kapal Bom | Lines Plan | Biro Desain Dasar Kapal Permukaan | 01 Ags 2025 | 31 Ags 2025 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC280725 22880
| 2025-07-25 | Improvement Tri Handoyomaran | Lines Plan | Biro Desain Dasar Kapal Permukaan | 01 Ags 2025 | 31 Ags 2025 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC280725 22881
| 2025-07-25 | W000304-305 | General Arrangement progress R3 | Biro Desain Dasar Kapal Permukaan | 01 Ags 2025 | 31 Ags 2025 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC280725 22882
| 2025-07-25 | KSR | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 01 Ags 2025 | 31 Ags 2025 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC280725 22883
| 2025-07-25 | Kapal Bom | Lightweight Estimation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 01 Ags 2025 | 31 Ags 2025 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC280725 22884
| 2025-07-25 | Kapal Bom | Deadwight Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 01 Ags 2025 | 31 Ags 2025 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC280725 22885
| 2025-07-25 | Kapal Bom | Tri Handoyom & Stability Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 01 Ags 2025 | 31 Ags 2025 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC280725 22886
| 2025-07-31 | E250N007 | Side Plate Knelson Screen - 26-A52-192 | Biro Desain Dasar Non Kapal | 01 Ags 2025 | 15 Ags 2025 | 2 | BEATICE, Luqman Chakim | 60 | JC010825 23074
| 2025-07-31 | E250N008 | Side Plate Knelson Screen - 26-A52-192 | Biro Desain Dasar Non Kapal | 18 Ags 2025 | 31 Ags 2025 | 2 | BEATICE, Luqman Chakim | 60 | JC110825 23479
| 2025-07-31 | A24AOP01 | PDHC MOCK-UP Kapal penginderaan bawa/atas air 15 m | Biro Basic Design Kapal Selam | 01 Agt 2025 | 30 Agt 2025 | 1 | SIGIT ISKIYARSAH |  | JC010825 23000
| 01 Agt 2025 | W000307 | General arrangement | Biro Desain Dasar Kapal Permukaan | 01 Agt 2025 | 30 Agt 2025 | 1 | Rahadian Lingga Pratama |  | JC010825 23001 | permintaan departemen extend penambahan date
| 01 Agt 2025 | E250N002 | Basic design review | Biro Desain Dasar Kapal Permukaan | 01 Agt 2025 | 30 Agt 2025 | 1 | Rahadian Lingga Pratama |  | JC010825 23084
| 01 Agt 2025 | W000305 | Weight control KB (03) | Biro Desain Dasar Kapal Permukaan | 01 Agt 2025 | 30 Agt 2025 | 1 | Arif Billah billah |  | JC010825 23003
| 01 Agt 2025 | W000307 | Damage control booklet | Biro Desain Dasar Kapal Permukaan | 01 Agt 2025 | 30 Agt 2025 | 1 | Arif Billah billah |  | JC010825 23004
| 05 Agt 2025 | Tender Tanker 3500 | Lines Plan | Biro Desain Dasar Kapal Permukaan | 05 Agt 2025 | 30 Agt 2025 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC060825 23336
| 05 Agt 2025 | Tender Tanker 6500 | Lines Plan | Biro Desain Dasar Kapal Permukaan | 05 Agt 2025 | 30 Agt 2025 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC060825 23337
| 05 Agt 2025 | Tender Tanker 6500 | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 05 Agt 2025 | 30 Agt 2025 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC060825 23338
| 05 Agt 2025 | Tender Tanker 6500 | LWT & DWT Calculation | Biro Desain Dasar Kapal Permukaan | 05 Agt 2025 | 30 Agt 2025 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC060825 23339
| 6 Agt 2025 | E250N009 | FABRICATE 2 OFF KNELSON SCREEN SUPPORT FRAME | Biro Desain Dasar Non Kapal | 11 Agt 2025 | 29 Agt 2025 | 2 | BEATICE, Luqman Chakim | 150 | JC130825 23616
| 6 Agt 2025 | B250N026 | Pengadaan Channel & Channel Cover Front & Rear Side Surface Condenser 12-E-111 | Biro Desain Dasar Non Kapal | 05 Agt 2025 | 06 Agt 2025 | 2 | Fendi Miranda, Alif Junaidi |  | JC060825 23341
| 13 Agt 2025 | B25N010 | Tender BMPP 3 (30MW) | Biro Desain Dasar Non Kapal | 2025-08-01 | 2025-08-31 | 7 | Agus Wibowo, BEATri HandoyoCE, Ahmad Amirulloh, Muhammad Mirza, Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah, Fendi Miranda |  | JC130825 23622
| 28 Agt 2025 | B250N027 | Pengadaan Heat Exchanger Item 30-E-1201 | Biro Desain Dasar Non Kapal | 2025-08-26 | 2025-09-04 | 2 | riduwan, Tri Handoyo |  | JC290825 24224
| 29 Agt 2025 | Hospital Ship (UAE) | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-09-01 | 2025-09-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC010925 24405
| 29 Agt 2025 | KSR | Lightweight Estimation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-09-01 | 2025-09-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC010925 24406
| 29 Agt 2025 | KSR | Tri Handoyom & Stability Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-09-01 | 2025-09-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC010925 24408
| 29 Agt 2025 | LCU LD Philippine | Napa Steel Calculation for Lightweight Estimation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-09-01 | 2025-09-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC010925 24410
| 29 Agt 2025 | W000308 | Tri Handoyom & Stability Calculation Progress R1 | Biro Desain Dasar Kapal Permukaan | 2025-09-01 | 2025-09-30 | 1 | Irma Mahardhika PuTri Handoyo |  | JC010925 24416
| 29 Agt 2025 | LCU LD Philippine | Tri Handoyom & Stability Calculation PreliminAry Tri Handoyo Ratnaningtyas | Biro Desain Dasar Kapal Permukaan | 2025-09-01 | 2025-09-30 | 1 | Irma Mahardhika PuTri Handoyo |  | JC010925 24418
| 29 Agt 2025 | W000304-305 | Watertight Integrity | Biro Desain Dasar Kapal Permukaan | 2025-09-01 | 2025-09-30 | 1 | Irma Mahardhika PuTri Handoyo |  | JC010925 24419
| 29 Agt 2025 | PLTAL | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2025-09-01 | 2025-09-30 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC010925 24422
| 29 Agt 2025 | Tender Tanker 6500 | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2025-09-01 | 2025-09-30 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC010925 24423
| 29 Agt 2025 | KSR | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2025-09-01 | 2025-09-30 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC010925 24424
| 29 Agt 2025 | Tender Tanker 6500 | Lightweight Estimation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-09-01 | 2025-09-30 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC010925 24425
| 29 Agt 2025 | W000304-305 | Citadel Scheme of Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-09-01 | 2025-09-30 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC010925 24428
| 29 Agt 2025 | W000304-305 | Capacity Plan | Biro Desain Dasar Kapal Permukaan | 2025-09-01 | 2025-09-30 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC010925 24432
| 29 Agt 2025 | KSR | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-09-01 | 2025-09-30 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC010925 24434
| 29 Agt 2025 | Kapal Bom | Tri Handoyom & Stability Calculation PreliminAry Tri Handoyo Ratnaningtyas | Biro Desain Dasar Kapal Permukaan | 2025-09-01 | 2025-09-30 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC010925 24436
| 1 Sept 2025 | A24AOP01 | PDHC MOCK-UP Kapal penginderaan bawa/atas air 15 m | Biro Basic Design Kapal Selam | 01 Sept 2025 | 30 Sept 2025 | 1 | SIGIT ISKIYARSAH |  | JC010925 24438
| 9 Sept 2025 | B250N028 | Pengadaan Tube bundle 20-E-102 M25PA25044A - PT KPI RU VI Balongan | Biro Desain Dasar Non Kapal | 08 Sept 2025 | 11 Sept 2025 | 2 | Riduwan, Alif Junaidi |  | JC100925 24845
| 18 Sept 2025 | E250N010 | Rerouting Pipa Penyalur BBM Pesanggaran Bali | Biro Desain Dasar Non Kapal | 18 Sept 2025 | 25 Sept 2025 | 2 | Ahmad Amirulloh, BeaTri Handoyoce |  | JC180925 25178
| 18 Sept 2025 | F21ZAI54 | FASILITAS SHIPLIFT & DERMAGA PMN 21-okt | Biro Desain Dasar Non Kapal | 2025-10-01 | 2025-10-30 | 4 | Nur Fuadi Afif Zaisyah, Minarti Shinta Putri Utomo, Luqman Chakim, Mey Resty Nugraheni |  | JC190925 25208
| 25 Sept 2025 | Kapal Ikan | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-10-01 | 2025-10-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC260925 25497
| 25 Sept 2025 | Kapal Ikan | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2025-10-01 | 2025-10-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC260925 25498
| 25 Sept 2025 | Kapal Ikan | Compartement Room in NAPA | Biro Desain Dasar Kapal Permukaan | 2025-10-01 | 2025-10-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC260925 25499
| 25 Sept 2025 | W000308 | Tri Handoyom & Stability Calculation Progress R1 | Biro Desain Dasar Kapal Permukaan | 2025-10-01 | 2025-10-30 | 1 | Irma Mahardhika PuTri Handoyo |  | JC260925 25500
| 25 Sept 2025 | Kapal Ikan | Lightweight Estimation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-10-01 | 2025-10-30 | 1 | Irma Mahardhika PuTri Handoyo |  | JC260925 25502
| 25 Sept 2025 | Kapal Ikan | Deadwight Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-10-01 | 2025-10-30 | 1 | Irma Mahardhika PuTri Handoyo |  | JC260925 25509
| 25 Sept 2025 | LCU LD Philippine | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2025-10-01 | 2025-10-30 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC011025 25741
| 25 Sept 2025 | Tender Tanker 6500 | Lightweight Estimation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-10-01 | 2025-10-30 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC011025 25742
| 25 Sept 2025 | W000304-305 | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-10-01 | 2025-10-30 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC011025 25743
| 25 Sept 2025 | KSR | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-10-01 | 2025-10-30 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC011025 25744
| 30 Sept 2025 | W000304-305 | Support technical analysis | Biro Desain Dasar Kapal Permukaan | 2025-10-01 | 2025-10-30 | 1 | Arif Billah billah |  | JC011025 25750
| 30 Sept 2025 | W000308 | Support technical analysis | Biro Desain Dasar Kapal Permukaan | 2025-10-01 | 2025-10-30 | 1 | R Rahadian Lingga Pratama |  | JC011025 25751
| 02 Oct 2025 | A24AOP01 | PDHC Kapal penginderaan bawa/atas air 15 m | Biro Basic Design Kapal Selam | 2025-10-01 | 2025-10-31 | 1 | SIGIT ISKIYARSAH |  | JC021025 25813
| 27 Oct 2025 | Kapal Klinik | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-10-31 | 30 Nop 2025 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC291025 26956
| 27 Oct 2025 | Kapal Klinik | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2025-10-31 | 30 Nop 2025 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC291025 26957
| 27 Oct 2025 | LCU LD Philippine | Napa Steel Calculation for Lightweight Estimation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-10-31 | 30 Nop 2025 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC291025 26958
| 27 Oct 2025 | W000308 | Tri Handoyom & Stability Calculation Progress R1 | Biro Desain Dasar Kapal Permukaan | 2025-10-31 | 30 Nop 2025 | 1 | Irma Mahardhika PuTri Handoyo |  | JC291025 26959
| 27 Oct 2025 | MRSS 143m | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-10-31 | 30 Nop 2025 | 1 | Irma Mahardhika PuTri Handoyo |  | JC291025 26960
| 27 Oct 2025 | Kapal Ikan | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2025-10-31 | 30 Nop 2025 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC291025 26961
| 27 Oct 2025 | Kapal Klinik | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2025-10-31 | 30 Nop 2025 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC291025 26962
| 27 Oct 2025 | LCU LD Philippine | Lines Plan for surface production | Biro Desain Dasar Kapal Permukaan | 2025-10-31 | 30 Nop 2025 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC291025 26963
| 27 Oct 2025 | W000304-305 | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-10-31 | 30 Nop 2025 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC291025 26964
| 27 Oct 2025 | KSR | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-10-31 | 30 Nop 2025 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC291025 26965
| 27 Oct 2025 | W000304-305 | Support technical analysis | Biro Desain Dasar Kapal Permukaan | 2025-10-31 | 29 Nop 2025 | 1 | Arif Billah billah |  | JC291025 26968
| 27 Oct 2025 | W000308 | Support technical analysis | Biro Desain Dasar Kapal Permukaan | 2025-10-31 | 29 Nop 2025 | 1 | R Rahadian Lingga Pratama |  | JC291025 26969
| 31 Oct 2025 | A24AOP01 | PDHC Kapal penginderaan bawa/atas air 15 m | Biro Basic Design Kapal Selam | 2025-11-01 | 2025-11-30 | 1 | SIGIT ISKIYARSAH |  | JC311025 27064
| 4 Nop 2025 | E250N011 | Pengadaan & Pemasangan HPH 2 Unit 2 PLTU LABUAN | Biro Desain Dasar Non Kapal | 2025-11-10 | 2026-08-27 | 4 | Riduwan, Luqman Chakim, Tri Handoyo, Nur Fuadi Afif Zaisyah |  | JC101125 27488 | jc extend untuk 10 nov-31 des 2025
| 21 Nop 2025 | JC Harkan | test report of inclining test - KRI NALA | Biro Desain Dasar Kapal Permukaan | 2025-11-24 | 2025-11-27 | 2 | R Rahadian Lingga Pratama, Arif Billah billah
| 28 Nop 2025 | Kapal Klinik | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2026-01-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC281125 28263 | 2025-12-31
| 28 Nop 2025 | Kapal Klinik | Capacity Plan | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2026-01-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC281125 28264 | 2025-12-31
| 28 Nop 2025 | Kapal Klinik | Lightweight Estimation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2026-01-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC281125 28265 | 2025-12-31
| 28 Nop 2025 | Kapal Klinik | Deadwight Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2026-01-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC281125 28266 | 2025-12-31
| 28 Nop 2025 | W000308 | Tri Handoyom & Stability Calculation Progress R1 | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2026-01-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC281125 28267 | 2025-12-31
| 28 Nop 2025 | MRSS 143m | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2026-01-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC281125 28268 | 2025-12-31
| 28 Nop 2025 | MRSS 143m | Lines Plan (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2026-01-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC281125 28269 | 2025-12-31
| 28 Nop 2025 | MRSS 143m | Lightweight Estimation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2026-01-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC281125 28270 | 2025-12-31
| 28 Nop 2025 | MRSS 143m | Deadwight Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2026-01-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC281125 28271 | 2025-12-31
| 28 Nop 2025 | Kapal Klinik | Lines Plan (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2026-01-31 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC281125 28274 | 2025-12-31
| 28 Nop 2025 | LCU LD Philippine | Lines Plan for surface production | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2026-01-31 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC281125 28275 | 2025-12-31
| 28 Nop 2025 | LCU LD Philippine | Tri Handoyom & Stability Calculation Progress R0 | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2026-01-31 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC281125 28276 | 2025-12-31
| 28 Nop 2025 | W000305 | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2026-01-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC281125 28277 | 2025-12-31
| 28 Nop 2025 | KSR | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2026-01-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC281125 28278 | 2025-12-31
| 28 Nop 2025 | KSR | Deadwight Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2026-01-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC281125 28279 | 2025-12-31
| 28 Nop 2025 | KSR | Lightweight Estimation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2026-01-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC281125 28280 | 2025-12-31
| 28 Nop 2025 | KSR | Tri Handoyom & Stability Calculation Progress R0 | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2026-01-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqiil |  | JC281125 28281 | 2025-12-31
| 28 Nop 2025 | W000304 | General Check persiapan Launching | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2026-01-31 | 4 | Moh. Hamzah SaTri Handoyoawansyah, Irma Mahardhika PuTri Handoyo, Ary Tri Handoyo Ratnaningtyas, Ahmad MuhtArif Billah Ihyail Haqiil |  | JC281125 28282 | 2025-12-31
| 28 Nop 2025 | W000304 | Ship condition for launching | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2025-12-31 | 1 | Arif Billah billah |  | JC281125 28259
| 28 Nop 2025 | W000304 | Weight control KB04 | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2025-12-31 | 1 | R Rahadian Lingga Pratama |  | JC281125 28260
| 28 Nop 2025 | W000306 | Support technical analysis | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2025-12-31 | 1 | Arif Billah billah |  | JC281125 28261
| 28 Nop 2025 | W000308 | Support technical analysis | Biro Desain Dasar Kapal Permukaan | 2025-12-01 | 2025-12-31 | 1 | R Rahadian Lingga Pratama |  | JC281125 28262
| 2025-12-01 | A24AOP01 | Pengembangan Kapal penginderaan bawa/atas air 15 m | Biro Basic Design Kapal Selam | 2025-12-01 | 2025-12-31 | 1 | SIGIT ISKIYARSAH |  | JC021225 28543
JANUAry Tri Handoyo Ratnaningtyas 2026
| 2025-12-31 | A24AOP01 | Pengembangan Kapal penginderaan bawa/atas air 15 m | Biro Basic Design Kapal Selam | 2026-01-01 | 2026-01-31 | 1 | SIGIT ISKIYARSAH |  | JC060126 30020
| 2026-01-02 | E250N011 | Mps, Mto, Det. Drawing, Shop Dwg, Cps, & Supervisi - Proyek HPH 2 Unit 2 PLTU Labuan | Biro Desain Dasar Non Kapal | 2026-01-01 | 2026-01-31 | 3 | Riduwan, Luqman Chakim, Tri Handoyo |  | JC020126 29816
| 2026-01-02 | E250N011 | Procedure Installation & Supervisi - Proyek HPH 2 Unit 2 PLTU Labuan | Biro Desain Dasar Non Kapal | 2026-01-01 | 2026-01-31 | 2 | Riduwan, Nur Fuadi Afif Zaisyah |  | JC020126 29817
| 2026-01-02 | TENDER - SUPPORT DATA MARKETING REKUM FOR HPH, VESSEL, EPCI, MANUFAKTURING, BMPP, FGPP, CCGT & JASA | Material List , General Arrangement & Dokumen pendukung marketing, Engineer Supervisi, Review Doc. | Biro Desain Dasar Non Kapal | 2026-01-01 | 2026-01-31 | 11 | Agus Wibowo, Fendi Miranda, Riduwan, Mey Resty Nugraheni, Ahmad Amirulloh, Muhammad Mirza, Tri Handoyo, Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah, Luqman Chakim, Alif Junaidi. |  | JC060126 30021
| 2026-01-02 | W000306 | Dock Operation procedure-update owner requirement | Biro Desain Dasar Kapal Permukaan | 2026-01-01 | 2026-01-31 | 1 | Rahadian Lingga Pratama |  | JC020126 29818
| 2026-01-02 | W000308 | Vehicle arrangement and deploy recovery scenario-update owner requirement | Biro Desain Dasar Kapal Permukaan | 2026-01-01 | 2026-01-31 | 1 | Rahadian Lingga Pratama |  | JC020126 29819
| 2026-01-02 | W000304 | Support technical analysis | Biro Desain Dasar Kapal Permukaan | 2026-01-01 | 2026-01-31 | 1 | Arif Billah billah |  | JC020126 29820
| 2026-01-06 | MRSS 163m | DWT & LWT Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-01-02 | 2026-01-09 | 1 | Irma Mahardhika PuTri Handoyo |  | JC060126 30022
| 2026-01-06 | Tanker 6500 DWT | DWT & LWT Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-01-02 | 2026-01-09 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC060126 30023
| 2026-01-06 | Frigate 143M | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2026-01-02 | 2026-01-09 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC060126 30019
| 2026-01-06 | Kapal Klinik | DWT & LWT Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-01-02 | 2026-01-09 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC060126 30025
| 2026-01-06 | B260N001 - EPCI Paus Biru Project - Medco Energi Sampang Pty Ltd | Dukungan pembuatan dok. teknis EPCI Paus Biru Project marketing rekum, Review Doc. & Material List Topside, Jacket | Biro Desain Dasar Non Kapal | 2026-01-05 | 2026-01-12 | 2 | Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah |  | JC060126 30030
| 2026-01-06 | B260N001 - EPCI Paus Biru Project - Medco Energi Sampang Pty Ltd | Dukungan pembuatan dok. teknis EPCI Paus Biru Project marketing rekum, Review Doc. & Material List ElecTri Handoyocal, Instrument, Safety | Biro Desain Dasar Non Kapal | 2026-01-05 | 2026-01-12 | 2 | Muhammad Mirza, Mey Resty Nugraheni |  | JC060126 30031
| 2026-01-06 | B260N001 - EPCI Paus Biru Project - Medco Energi Sampang Pty Ltd | Dukungan pembuatan dok. teknis EPCI Paus Biru Project marketing rekum, Review Doc. & Material List Mechanical & Instrument, Piping | Biro Desain Dasar Non Kapal | 2026-01-05 | 2026-01-12 | 2 | Fendi Miranda, Ahmad Amirulloh |  | JC060126 30032
| 2026-01-07 | B260N002 - Pengadaan HPH 1 Unit 2 & HPH 3 Unit 1 PLTU Labuan - PT PLN Indonesia Power | Material List & Det. Drawing Eng. | Biro Desain Dasar Non Kapal | 2026-01-07 | 2026-01-12 | 3 | Riduwan, Luqman Chakim, Tri Handoyo |  | JC080126 30086
| 2025-01-08 | W000309 | Pembuatan jig produksi untuk proyek SCORPNE-1 | Biro Basic Design Kapal Selam | 2026-01-01 | 2026-01-31 | 1 | SIGIT ISKIYARSAH |  | JC090126 30109
| 2026-01-09 | CORP2026 | Dukungan pembuatan dok. teknis | Biro Desain Dasar Kapal Permukaan | 2026-01-09 | 2026-01-31 | 2 | Arif Billah billah, Rahadian Lingga Pratama |  | JC090126 30117
| 2026-01-12 | Kapal Klinik | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2026-01-12 | 2026-01-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC130126 30286
| 2026-01-12 | Kapal Klinik | Deadwight Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-01-12 | 2026-01-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC130126 30287
| 2026-01-12 | W000304 | Freeboard Calculation | Biro Desain Dasar Kapal Permukaan | 2026-01-12 | 2026-01-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC130126 30299
| 2026-01-12 | W000308 | Tri Handoyom & Stability Calculation (TWS Analisys) | Biro Desain Dasar Kapal Permukaan | 2026-01-12 | 2026-01-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC130126 30305
| 2026-01-12 | MRSS 163m | Tri Handoyom & Stability Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-01-12 | 2026-01-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC130126 30321
| 2026-01-12 | Floating Dock | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2026-01-12 | 2026-01-31 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC130126 30322
| 2026-01-12 | Floating Dock | Lightweight Estimation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-01-12 | 2026-01-31 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC130126 30323
| 2026-01-12 | Floating Dock | Deadwight Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-01-12 | 2026-01-31 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC130126 30324
| 2026-01-12 | W000306-307 | Surface Lines plan for bow thruster | Biro Desain Dasar Kapal Permukaan | 2026-01-12 | 2026-01-31 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC130126 30325
| 2026-01-12 | Frigate 143M | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-01-12 | 2026-01-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC130126 30295 |  | NO JC RAMADHAN HOURS
| 2026-01-12 | KSR | Speed Power Analisys | Biro Desain Dasar Kapal Permukaan | 2026-01-12 | 2026-01-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC130126 30296
| 2026-02-02 | W000308 | DOCK OPERATION MANUAL | Biro Desain Dasar Kapal Permukaan | 2026-02-02 | 2026-02-28 | 1 | Rahadian Lingga Pratama |  | JC030226 31179 | jc utk 2-18 februari 2026 | JC180226 31659 | jc utk 19-28 februari 2026
| 2026-02-02 | SUPPORT DATA TENDER FOR MARKETING REKUMHAR - HPH, VESSEL, EPCI, MANUFAKTURING, BMPP, FGPP, CCGT & JASA. | Support Data for Marketing Rekumhar / HPH, VESSEL, EPCI, Manufacture, BMPP, FGPP, CCGT, Power Plant & Jasa - Mat. List , GA, Engineering, Supervisi, Review Document. | Biro Desain Dasar Non Kapal | 2026-02-01 | 2026-02-28 | 10 | Agus Wibowo, Fendi Miranda, Mey Resty Nugraheni, Ahmad Amirulloh, Muhammad Mirza, Tri Handoyo, Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah, Luqman Chakim, Alif Junaidi. |  | JC030226 31180 | jc utk 1-18 februari 2026 | no jc baru di bawah (273)
| 2026-02-02 | E250N011 Proyek HPH 2 Unit 2 PLTU Labuan | E250N011 Proyek HPH 2 Unit 2 PLTU Labuan - Mps, Mto, Det. Drawing, Shop Dwg, Cps, & Supervisi. | Biro Desain Dasar Non Kapal | 2026-02-01 | 2026-02-28 | 2 | Luqman Chakim, Tri Handoyo |  | JC180226 31771 | jc utk 1-18 februari 2026 | JC180226 31776 | jc utk 19-28 februari 2026
| 2026-02-02 | E250N011 Proyek HPH 2 Unit 2 PLTU Labuan | E250N011 Proyek HPH 2 Unit 2 PLTU Labuan - Procedure Installation & Supervisi | Biro Desain Dasar Non Kapal | 2026-02-01 | 2026-02-28 | 1 | Nur Fuadi Afif Zaisyah |  | JC180226 31773 | jc utk 1-18 februari 2026 | JC180226 31775 | jc utk 19-28 februari 2026
| 2026-02-02 | CORP2026 | Dukungan pembuatan dok. teknis | Biro Desain Dasar Kapal Permukaan | 2026-02-02 | 2026-02-28 | 2 | Arif Billah billah, Rahadian Lingga Pratama |  | JC030226 31181 | jc utk 2-18 februari 2026 | JC180226 31663 | jc utk 19-28 februari 2026
| 2026-02-02 | W000309 | Pembuatan jig produksi untuk proyek SCORPNE-1 | Biro Basic Design Kapal Selam | 2026-02-02 | 2026-02-28 | 1 | SIGIT ISKIYARSAH |  | JC030226 31182 | jc utk 2-18 februari 2026 | JC180226 31664 | jc utk 19-28 februari 2026
| 2026-02-02 | A24AOP01 | Pengembangan Kapal penginderaan bawa/atas air 15 m | Biro Basic Design Kapal Selam | 2026-02-02 | 2026-02-28 | 1 | SIGIT ISKIYARSAH |  | JC030226 31183 | jc utk 2-18 februari 2026 | JC180226 31666 | jc utk 19-28 februari 2026
| 2026-02-04 | Kapal Klinik | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-02-02 | 2026-02-28 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC040226 31188 | jc utk 2-18 februari 2026 | JC180226 31667 | jc utk 19-28 februari 2026
| 2026-02-04 | Kapal Layar Makassar | Deadwight Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-02-02 | 2026-02-28 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC040226 31189 | jc utk 2-18 februari 2026 | JC180226 31670 | jc utk 19-28 februari 2026
| 2026-02-04 | Kapal Layar Makassar | Lightweight Estimation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-02-02 | 2026-02-28 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC040226 31190 | jc utk 2-18 februari 2026 | JC180226 31671 | jc utk 19-28 februari 2026
| 2026-02-04 | W000308 | Tri Handoyom & Stability Calculation (TWS Analisys) | Biro Desain Dasar Kapal Permukaan | 2026-02-02 | 2026-02-28 | 1 | Irma Mahardhika PuTri Handoyo |  | JC040226 31191 | jc utk 2-18 februari 2026 | JC180226 31672 | jc utk 19-28 februari 2026
| 2026-02-04 | MRSS 163m | Tri Handoyom & Stability Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-02-02 | 2026-02-28 | 1 | Irma Mahardhika PuTri Handoyo |  | JC040226 31192 | jc utk 2-18 februari 2026 | JC180226 31673 | jc utk 19-28 februari 2026
| 2026-02-04 | Kapal ASDP 1100 Lane Meter | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-02-02 | 2026-02-28 | 1 | Irma Mahardhika PuTri Handoyo |  | JC040226 31193 | jc utk 2-18 februari 2026 | JC180226 31675 | jc utk 19-28 februari 2026
| 2026-02-04 | Kapal Makassar | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2026-02-02 | 2026-02-28 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC040226 31194 | jc utk 2-18 februari 2036 | JC180226 31677 | jc utk 19-28 februari 2026
| 2026-02-04 | Kapal Makassar | Speed Power Calculation | Biro Desain Dasar Kapal Permukaan | 2026-02-02 | 2026-02-28 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC040226 31195 | jc utk 2-18 februari 2026 | JC180226 31678 | jc utk 19-28 februari 2026
| 2026-02-04 | W000305 | General Arrangement R4 | Biro Desain Dasar Kapal Permukaan | 2026-02-02 | 2026-02-28 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC040226 31197 | jc utk 2-18 februari 2026 | JC180226 31685 | jc utk 19-28 februari 2026
| 2026-02-04 | W000305 | Tri Handoyom & Stability Calculation | Biro Desain Dasar Kapal Permukaan | 2026-02-02 | 2026-02-28 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC040226 31198 | jc utk 2-18 februari 2026 | JC180226 31686 | jc utk 19-28 februari 2026
| 2026-02-10 | SUPPORT DATA TENDER FOR MARKETING REKUMHAR - HPH, VESSEL, EPCI, MANUFAKTURING, BMPP, FGPP, CCGT & JASA. | Support Data for Marketing Rekumhar / HPH, VESSEL, EPCI, Manufacture, BMPP, FGPP, CCGT, Power Plant & Jasa - Mat. List , GA, Engineering, Supervisi, Review Document. | Biro Desain Dasar Non Kapal | 2026-02-19 | 2026-02-28 | 10 | Agus Wibowo, Fendi Miranda, Mey Resty Nugraheni, Ahmad Amirulloh, Muhammad Mirza, Tri Handoyo, Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah, Luqman Chakim, Alif Junaidi. |  | JC180226 31687 | jc utk 19-28 februari 2026
| 2026-02-20 | B260N004 - Pengadaan Tube Bundle, Tube HE, Shell & Tube HE PT. PERTAMINA CILACAP | B260N004 - MTO & Detail Drawing Eng. untuk 3 unit item 1. Pengadaan Tube Bundle PR 100068910 2. Pengadaan Tube HE PR 100067213 - M04426PL0010A 3. Pengadaan Shell & Tube HE PR 500051773 | Biro Desain Dasar Non Kapal | 2026-02-19 | 2026-02-23 | 3 | Fendi Miranda, Luqman Chakim, Tri Handoyo |  | JC200226 31860
| 2026-02-24 | B260N005 - Pekerjaan Revitalisasi Penstock 1 & 2 PLTA Ketenger Mrica | B260N005 - MTO & Det. Dwg Pekerjaan Revitalisasi Penstock 1 & 2 PLTA Ketenger - PLN IP UB Mrica | Biro Desain Dasar Non Kapal | 2026-02-19 | 2026-02-25 | 3 | Ahmad Amirulloh, Alif Junaidi, Nur Fuadi Afif Zaisyah |  | JC240226 32078
| 2026-02-26 | B260N005 - BudgetAry Tri Handoyo Ratnaningtyas Turnaround RU V Balikpapan | B260N005 - MTO & Drawing Tender BudgetAry Tri Handoyo Ratnaningtyas Turnaround RU V Balikpapan - 14 Unit penggantian unit Assy. HE dan Finfan | Biro Desain Dasar Non Kapal | 2026-02-26 | 2026-03-04 | 7 | Tri Handoyo, Luqman Chakim, Alip, Muhammad Mirza, Mey Resty Nugraheni, Ahmad Amirulloh, Fendi Miranda |  | JC270226 32201
| 2026-02-27 | B26N006 - EPCI MDK | B26N006 - Proses Doc. BOM, Drawing, Data Sheet, Spect. Tender EPCI MDK - HCML | Biro Desain Dasar Non Kapal | 2026-02-27 | 2026-03-17 | 6 | Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah, Muhammad Mirza, Ahmad Amirulloh, Mey Resty Nugraheni, Fendi Miranda |  | JC020326 32282
| 2026-03-02 | CORP2026 | Dukungan pembuatan dokumen teknis dan perhitungan basic desain support marketing | Biro Desain Dasar Kapal Permukaan | 2026-03-02 | 2026-03-31 | 2 | Arif Billah billah, Rahadian Lingga Pratama |  | JC020326 32340 | jc utk 2-19 Maret 2026 | JC250326 33107 | jc utk 25-31 Maret 2026
| 2026-03-02 | W000308 | Vehicle arrangement and deploy recovery scenario-update owner requirement | Biro Desain Dasar Kapal Permukaan | 2026-03-02 | 2026-03-31 | 2 | Arif Billah billah, Rahadian Lingga Pratama |  | JC020326 32355 | jc utk 2-19 Maret 2026 | JC250326 33108 | jc utk 25-31 Maret 2026
| 2026-03-02 | Kapal ASDP 1100 Lane Meter | Tri Handoyom & Stability Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-03-02 | 2026-03-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC020326 32420 | jc utk 2-19 Maret 2026 | JC250326 33109 | jc utk 25-31 Maret 2026
| 2026-03-02 | W000308 | Tri Handoyom & Stability Calculation (TWS Analisys) | Biro Desain Dasar Kapal Permukaan | 2026-03-02 | 2026-03-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC020326 32424 | jc utk 2-19 Maret 2026 | JC250326 33110 | jc utk 25-31 Maret 2026
| 2026-03-02 | Kapal ASDP 1100 Lane Meter | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-03-02 | 2026-03-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC020326 32421 | jc utk 2-19 Maret 2026 | JC250326 33115 | jc utk 25-31 Maret 2026
| 2026-03-02 | Water Taxi ASDP | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2026-03-02 | 2026-03-31 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC020326 32422 | jc utk 2-19 Maret 2026 | JC250326 33118 | jc utk 25-31 Maret 2026
| 2026-03-02 | Water Taxi ASDP | Tri Handoyom & Stability Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-03-02 | 2026-03-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC020326 32423 | jc utk 2-19 Maret 2026 | JC250326 33120 | jc utk 25-31 Maret 2026
| 2026-03-02 | W000309 | Pembuatan jig produksi untuk proyek SCORPNE-1 | Biro Basic Design Kapal Selam | 2026-03-02 | 2026-03-31 | 1 | SIGIT ISKIYARSAH |  | JC030326 32440 | jc utk 2-19 Maret 2026 | JC250326 33121 | jc utk 20-31 februari 2026
| 2026-03-02 | A24AOP01 | Pengembangan Kapal penginderaan bawa/atas air 15 m | Biro Basic Design Kapal Selam | 2026-03-02 | 2026-03-31 | 1 | SIGIT ISKIYARSAH |  | JC030326 32441 | jc utk 2-19 Maret 2026 | JC250326 33122 | jc utk 20-31 februari 2026
| 2026-03-02 | SUPPORT DATA TENDER FOR MARKETING REKUMHAR - HPH, VESSEL, EPCI, MANUFAKTURING, BMPP, FGPP, CCGT & JASA. | Support Data for Marketing Rekumhar / HPH, VESSEL, EPCI, Manufacture, BMPP, FGPP, CCGT, Power Plant & Jasa - Mat. List , GA, Engineering, Supervisi, Review Document. | Biro Desain Dasar Non Kapal | 2026-03-02 | 2026-03-18 | 10 | Agus Wibowo, Fendi Miranda, Mey Resty Nugraheni, Ahmad Amirulloh, Muhammad Mirza, Tri Handoyo, Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah, Luqman Chakim, Alif Junaidi. |  | JC160326 32970 | jc utk 2-19 Maret 2026
| 2026-03-04 | LCU LD Philippines | Capacity Plan | Biro Desain Dasar Kapal Permukaan | 2026-03-04 | 2026-03-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC040326 32529 | jc utk 4-19 Maret 2026 | JC250326 33123 | jc utk 25-31 Maret 2026
| 2026-03-04 | LCU LD Philippines | Tri Handoyom & Stability Calculation | Biro Desain Dasar Kapal Permukaan | 2026-03-04 | 2026-03-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC040326 32530 | jc utk 4-19 Maret 2026 | JC250326 33124 | jc utk 25-31 Maret 2026
| 2026-03-16 | B26N007 - Turnaround Pertamina RU VI Balongan | B260N007 - MTO & Drawing Tender BudgetAry Tri Handoyo Ratnaningtyas Turnaround RU VI Balongan | Biro Desain Dasar Non Kapal | 2026-03-19 | 2026-03-31 | 6 | Alif Junaidi, Luqman Chakim, Tri Handoyo, Mey Resty Nugraheni, Ahmad Amirulloh, Fendi Miranda |  | JC250326 33125
| 2026-03-16 | SUPPORT DATA TENDER FOR MARKETING REKUMHAR - HPH, VESSEL, EPCI, MANUFAKTURING, BMPP, FGPP, CCGT & JASA. | Support Data for Marketing Rekumhar / HPH, VESSEL, EPCI, Manufacture, BMPP, FGPP, CCGT, Power Plant & Jasa - Mat. List , GA, Engineering, Supervisi, Review Document. | Biro Desain Dasar Non Kapal | 2026-03-19 | 2026-03-31 | 4 | Agus Wibowo, Muhammad Mirza, Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah. |  | JC250326 33126
| 2026-03-30 | SUPPORT DATA FOR TENDER MARKETING REKUMHAR - HPH, VESSEL, EPCI, MANUFAKTUR, BMPP, FGPP, CCGT & JASA. | Support Data for Marketing Rekumhar / HPH, VESSEL, EPCI, Manufacture, BMPP, FGPP, CCGT, Power Plant & Jasa - Mat. List , GA, Engineering, Supervisi, Review Document. | Biro Desain Dasar Non Kapal | 2026-04-01 | 2026-04-30 | 10 | Agus Wibowo, Fendi Miranda, Mey Resty Nugraheni, Ahmad Amirulloh, Muhammad Mirza, Tri Handoyo, Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah, Luqman Chakim, Alif Junaidi. |  | JC010426 33472
| 2026-03-31 | Kapal ASDP | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-04-01 | 2026-04-30 | 3 | Moh. Hamzah SaTri Handoyoawansyah, Irma Mahardhika PuTri Handoyo, Ahmad MuhtArif Billah Ihyail Haqiil |  | JC010426 33473
| 2026-03-31 | Corvette Philipphine | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-04-01 | 2026-04-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC010426 33474
| 2026-03-31 | W000308 | Tri Handoyom & Stability Calculation (TWS Analisys) | Biro Desain Dasar Kapal Permukaan | 2026-04-01 | 2026-04-30 | 1 | Irma Mahardhika PuTri Handoyo |  | JC010426 33475
| 2026-03-31 | Kapal Pinisi Makassar | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2026-04-01 | 2026-04-30 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC010426 33476
| 2026-03-31 | Corvette Philipphine | Lines Plan (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-04-01 | 2026-04-30 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC010426 33477
| 2026-04-01 | W000309 | Pembuatan jig produksi untuk proyek SCORPNE-1 | Biro Basic Design Kapal Selam | 2026-04-01 | 2026-04-30 | 1 | SIGIT ISKIYARSAH |  | JC010426 33519
| 2026-04-01 | A24AOP01 | Pengembangan Kapal penginderaan bawa/atas air 15 m | Biro Basic Design Kapal Selam | 2026-04-01 | 2026-04-30 | 1 | SIGIT ISKIYARSAH |  | JC010426 33520
| 2026-04-02 | W000307 | General arrangement | Biro Desain Dasar Kapal Permukaan | 2026-04-02 | 2026-04-30 | 1 | Rahadian Lingga Pratama |  | JC020426 33555
| 2026-04-02 | CORP2026 | Kontingen PAL Runner | Biro Desain Dasar Kapal Permukaan | 2026-04-23 | 2026-04-26 | 1 | Rahadian Lingga Pratama |  | JC220426 34291
| 2026-04-29 | Kapal ASDP 500 Lane Meter | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-05-01 | 2026-05-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC300426 34572
| 2026-04-29 | Kapal ASDP 500 Lane Meter | Tri Handoyom & Stability Calculation | Biro Desain Dasar Kapal Permukaan | 2026-05-01 | 2026-05-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC300426 34573
| 2026-04-29 | Corvette Philipphine | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-05-01 | 2026-05-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC300426 34574
| 2026-04-29 | Geomarin V | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2026-05-01 | 2026-05-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC300426 34578
| 2026-04-29 | Pinisi Makassar | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2026-05-01 | 2026-05-31 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC300426 34579
| 2026-04-29 | Geomarin V | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2026-05-01 | 2026-05-31 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC300426 34580
| 2026-04-29 | Kapal ASDP 1100 Lane Meter | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-05-01 | 2026-05-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC300426 34575
| 2026-04-29 | Kapal ASDP 1100 Lane Meter | Tri Handoyom & Stability Calculation | Biro Desain Dasar Kapal Permukaan | 2026-05-01 | 2026-05-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC300426 34576
| 2026-04-29 | Kapal ASDP 250 Lane Meter | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-05-01 | 2026-05-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC300426 34577
| 2026-05-01 | W000309 | Pembuatan jig produksi untuk proyek SCORPNE-1 | Biro Basic Design Kapal Selam | 2026-05-01 | 2026-05-31 | 1 | SIGIT ISKIYARSAH |  | JC080526 34885
| 2026-04-01 | A26AOP01 | Kapal Selam Otomos (KSOT) Mass Product Tipe Surveilence | Biro Basic Design Kapal Selam | 2026-05-01 | 2026-05-31 | 1 | SIGIT ISKIYARSAH |  | JC080526 34889
| 2026-04-30 | SUPPORT DATA TENDER FOR MARKETING REKUMHAR - HPH, VESSEL, EPCI, MANUFAKTURING, BMPP, FGPP, CCGT & JASA. | Support Data for Marketing Rekumhar / HPH, HE, C3W, VESSEL, EPCI, Manufacture, BMPP, FGPP, CCGT, Power Plant & Jasa - Mat. List , GA, Engineering, Supervisi, Review Document. | Biro Desain Dasar Non Kapal | 2026-05-01 | 2026-05-31 | 10 | Agus Wibowo, Fendi Miranda, Mey Resty Nugraheni, Ahmad Amirulloh, Muhammad Mirza, Tri Handoyo, Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah, Luqman Chakim, Alif Junaidi. |  | JC040526 34767
| 2026-05-04 | Pinisi Makassar | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-05-04 | 2026-05-31 | 1 | Arif Billah billah |  | JC040526 34768
| 2026-05-04 | W000308 | Ship condition of floating | Biro Desain Dasar Kapal Permukaan | 2026-05-04 | 2026-05-31 | 1 | Arif Billah billah |  | JC040526 34770
| 2026-05-04 | W000306 | Ship condition of launching | Biro Desain Dasar Kapal Permukaan | 2026-05-04 | 2026-05-31 | 1 | Rahadian Lingga Pratama |  | JC040526 34771
| 2026-05-04 | Geomarin V | Basic design calculation | Biro Desain Dasar Kapal Permukaan | 2026-05-04 | 2026-05-31 | 1 | Rahadian Lingga Pratama |  | JC040526 34769
| 2026-05-04 | LNG 3000 CBM | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-05-04 | 2026-05-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC040526 34772
| 2026-05-04 | KSR | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2026-05-04 | 2026-05-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC040526 34783
| 2026-05-04 | KSR | Tri Handoyom & Stability Calculation | Biro Desain Dasar Kapal Permukaan | 2026-05-04 | 2026-05-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC040526 34784
| 2026-05-07 | E260N003 - Revitalisasi Penstok 1 dan 2 (Tahap 1) PLTA Ketenger | E260N003 - Drawing & Supervisi Revitalisasi Penstok 1 dan 2 (Tahap 1) PLTA Ketenger | Biro Desain Dasar Non Kapal | 2026-05-04 | 2026-05-31 | 2 | Alif Junaidi, Fendi Miranda |  | JC180526 35129
| 2026-05-11 | LNG 3000 CBM | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2026-05-04 | 2026-05-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC180526 35133
| 2026-04-25 | SUPPORT DATA TENDER FOR MARKETING REKUMHAR - HPH, VESSEL, EPCI, MANUFAKTURING, BMPP, FGPP, CCGT & JASA. | Support Data for Marketing Rekumhar / HPH, HE, C3W, VESSEL, EPCI, Manufacture, BMPP, FGPP, CCGT, Power Plant & Jasa - Mat. List , GA, Engineering, Supervisi, Review Document. | Biro Desain Dasar Non Kapal | 2026-06-01 | 2026-06-30 | 10 | Agus Wibowo, Fendi Miranda, Mey Resty Nugraheni, Ahmad Amirulloh, Muhammad Mirza, Tri Handoyo, Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah, Luqman Chakim, Alif Junaidi. |  | JC020626 35804
| 2026-05-25 | E260N003 - Revitalisasi Penstok 1 dan 2 (Tahap 1) PLTA Ketenger | E260N003 - Drawing & Supervisi Revitalisasi Penstok 1 dan 2 (Tahap 1) PLTA Ketenger | Biro Desain Dasar Non Kapal | 2026-06-01 | 2026-06-30 | 2 | Alif Junaidi, Fendi Miranda |  | JC020626 35802
| 2026-05-25 | E260N002 - CONRAD | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-06-01 | 2026-06-30 | 4 | Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah, Muhammad Mirza, Ahmad Amirulloh |  | JC020626 35803 | corp2026
| 2026-05-25 | E260N002 - CONRAD | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-06-01 | 2026-06-30 | 4 | Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah, Muhammad Mirza, Ahmad Amirulloh |  | JC050626 36061 | E260N002 - CONRAD
| 2026-05-29 | A26AOP01 | Kapal Selam Otomos (KSOT) Mass Product Tipe Surveilence | Biro Desain Dasar Kapal Selam | 2026-06-01 | 2026-06-30 | 1 | SIGIT ISKIYARSAH |  | JC020626 35806
| 2026-06-02 | E250N010 - PLTD UBP Bali | E250N010 - Jasa Site Supervisi Engineer Rerouting Pipa PLTD Pesanggaran UBP Bali | Biro Desain Dasar Non Kapal | 2026-06-01 | 2026-06-30 | 1 | Ahmad Amirulloh |  | JC020626 35825
| 2026-06-03 | LNG 3000 CBM | Spektek PreliminAry Tri Handoyo Ratnaningtyas | Biro Desain Dasar Pengembangan Desain | 2026-06-01 | 2026-06-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC040626 35974
| 2026-06-03 | LNG 3000 CBM | General Arrangement (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Pengembangan Desain | 2026-06-01 | 2026-06-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC040626 35975
| 2026-06-03 | W000306 | Ship Condition for Launching | Biro Desain Dasar Pengembangan Desain | 2026-06-01 | 2026-06-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC040626 35976
| 2026-06-03 | LNG 3000 CBM | Lines Plan | Biro Desain Dasar Pengembangan Desain | 2026-06-01 | 2026-06-30 | 1 | Irma Mahardhika PuTri Handoyo |  | JC040626 35977
| 2026-06-03 | ASDP 250 & 500 PAX | Lines Plan | Biro Desain Dasar Pengembangan Desain | 2026-06-01 | 2026-06-30 | 1 | Irma Mahardhika PuTri Handoyo |  | JC040626 35978
| 2026-06-03 | Geomarin V | Lines Plan | Biro Desain Dasar Pengembangan Desain | 2026-06-01 | 2026-06-30 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC040626 35979
| 2026-06-03 | LNG 3000 CBM | Lines Plan | Biro Desain Dasar Pengembangan Desain | 2026-06-01 | 2026-06-30 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC040626 35980
| 2026-06-03 | W000305 | General Arrangement | Biro Desain Dasar Pengembangan Desain | 2026-06-01 | 2026-06-30 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC040626 35981
| 2026-06-03 | KSR | General Arrangement | Biro Desain Dasar Pengembangan Desain | 2026-06-01 | 2026-06-30 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC040626 35982
| 2026-06-03 | KSR | Tri Handoyom & Stability Calculation | Biro Desain Dasar Pengembangan Desain | 2026-06-01 | 2026-06-30 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC040626 35983
| 2026-06-09 | M000313 | Deadwight Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-06-01 | 2026-06-30 | 1 | Rahadian Lingga Pratama |  | JC090626 36181 | Biro Desain Dasar Kapal Permukaan
| 2026-06-09 | W000308 | Ship condition for floating | Biro Desain Dasar Kapal Permukaan | 2026-06-01 | 2026-06-30 | 2 | Rahadian Lingga Pratama, Arif Billah Bilah |  | JC090626 36183 | Biro Desain Dasar Kapal Permukaan
| 2026-06-09 | W000306 | Ship condition for launching | Biro Desain Dasar Kapal Permukaan | 2026-06-01 | 2026-06-30 | 2 | Rahadian Lingga Pratama, Arif Billah Bilah |  | JC090626 36184 | Biro Desain Dasar Kapal Permukaan
| 2026-06-09 | M000313 | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2026-06-01 | 2026-06-30 | 1 | Rahadian Lingga Pratama |  | JC090626 36182 | Biro Desain Dasar Kapal Permukaan
| 2026-06-10 | M000312 | Tri Handoyom & Stability Calculation | Biro Desain Dasar Kapal Permukaan | 2026-06-01 | 2026-06-30 | 1 | Arif Billah |  | JC100626 36211 | Biro Desain Dasar Kapal Permukaan | JC300626 36950
| 2026-06-10 | R22FPBXA | Tri Handoyom & Stability Calculation | Biro Desain Dasar Kapal Permukaan | 2026-06-01 | 2026-06-30 | 1 | Rahadian Lingga Pratama |  | JC11062636281 | Biro Desain Dasar Kapal Permukaan
| 2026-06-10 | R23GNRCA | Tri Handoyom & Stability Calculation | Biro Desain Dasar Pengembangan Desain | 2026-06-01 | 2026-06-30 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC11062636283
| 2026-06-29 | SUPPORT DATA TENDER FOR MARKETING REKUMHAR - HPH, VESSEL, EPCI, MANUFAKTURING, BMPP, FGPP, CCGT & JASA. | Support Data for Marketing Rekumhar / HPH, HE, C3W, VESSEL, EPCI, Manufacture, BMPP, FGPP, CCGT, Power Plant & Jasa - Mat. List , GA, Engineering, Supervisi, Review Document. | Biro Desain Dasar Non Kapal | 2026-07-01 | 2026-07-31 | 10 | Agus Wibowo, Fendi Miranda, Mey Resty Nugraheni, Ahmad Amirulloh, Muhammad Mirza, Tri Handoyo, Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah, Luqman Chakim, Alif Junaidi. |  | JC010726 36999
| 2026-06-29 | E260N002 - CONRAD | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-07-01 | 2026-07-31 | 7 | Agus Wibowo, Fendi Miranda, Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah, Muhammad Mirza, Ahmad Amirulloh, Tri Handoyo |  | JC030726 37109
| 2026-06-29 | Kapal Ikan | Compartement Room in NAPA | Biro Desain Dasar Kapal Permukaan | 2026-07-01 | 2026-07-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC030726 37112
| 2026-06-29 | Kapal Ikan | Tri Handoyom & Stability Calculation | Biro Desain Dasar Kapal Permukaan | 2026-07-01 | 2026-07-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC030726 37113
| 2026-06-29 | LNG 3000 CBM | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2026-07-01 | 2026-07-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC030726 37114
| 2026-06-29 | LNG 3000 CBM | Tri Handoyom & Stability Calculation | Biro Desain Dasar Kapal Permukaan | 2026-07-01 | 2026-07-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC030726 37116
| 2026-06-29 | Kapal Ikan | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2026-07-01 | 2026-07-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC030726 37118
| 2026-06-29 | Geomarin V | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2026-07-01 | 2026-07-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC030726 37119
| 2026-06-29 | Corvette Philippine | Lines Plan | Biro Desain Dasar Kapal Permukaan | 2026-07-01 | 2026-07-31 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC030726 37120
| 2026-06-29 | KSR 20 meter | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2026-07-01 | 2026-07-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC030726 37121
| 2026-07-01 | M000313 | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2026-07-01 | 2026-07-31 | 1 | Rahadian Lingga Pratama |  | JC030726 37129
| 2026-07-01 | M000313 | Deadwight Calculation (PreliminAry Tri Handoyo Ratnaningtyas) | Biro Desain Dasar Kapal Permukaan | 2026-07-01 | 2026-07-18 | 1 | Rahadian Lingga Pratama |  | JC030726 37123
| 2026-07-01 | M000313 | Speed power prediction | Biro Desain Dasar Kapal Permukaan | 2026-07-13 | 2026-07-31 | 1 | Rahadian Lingga Pratama |  | JC030726 37124
| 2026-07-01 | M000313 | Tonnage calculation | Biro Desain Dasar Kapal Permukaan | 2026-07-01 | 2026-07-31 | 1 | Arif Billah |  | JC030726 37125
| 2026-07-01 | M000312 | Tri Handoyom & Stability Calculation-revisi 1 | Biro Desain Dasar Kapal Permukaan | 2026-07-01 | 2026-07-31 | 1 | Arif Billah |  | JC030726 37126
| 2026-07-01 | M000312 | General Arrangement | Biro Desain Dasar Kapal Permukaan | 2026-07-01 | 2026-07-31 | 1 | Arif Billah |  | JC030726 37127
| 2026-07-01 | A26AOP01 | Kapal Selam Otomos (KSOT) Mass Product Tipe Surveilence | Biro Desain Dasar Kapal Selam | 01 Julii 2026 | 2026-07-31 | 1 | SIGIT ISKIYARSAH |  | JC010726 37049
| 2026-07-13 | W000314 | NAPA Steel for input Cadmatic Outfitting | Biro Desain Dasar Pengembangan Desain | 2026-07-13 | 2026-07-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC160726 37691
| 2026-07-16 | KCR 60 Meter | mempelajari KCR 60 m dari Turki | Biro Desain Dasar Pengembangan Desain | 2026-07-01 | 2026-07-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC160726 37690
| 2026-07-16 | M000313 Geomarin V | Surface Rudder & Shaft propeler | Biro Desain Dasar Pengembangan Desain | 2026-07-06 | 2026-07-31 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC200726 37843
| 2026-07-16 | M000313 Geomarin V | Speed Power Prediction | Biro Desain Dasar Pengembangan Desain | 2026-07-08 | 2026-07-31 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC200726 37847
| 2026-07-16 | M000312 Pengawas dan Pelayaran Pulau | Surface rudder | Biro Desain Dasar Pengembangan Desain | 2026-07-09 | 2026-07-31 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC200726 37852
| 2026-07-16 | M000313 Geomarin V | Bonjean Table | Biro Desain Dasar Pengembangan Desain | 2026-07-20 | 2026-07-31 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC200726 37850
| 2026-07-22 | W000308 | General Arrangement | Biro Desain Dasar Pengembangan Desain | 2026-07-22 | 2026-07-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC220726 37920
| 2026-07-22 | W000308 | Room NAPA | Biro Desain Dasar Pengembangan Desain | 2026-07-22 | 2026-07-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC220726 37921
| 2026-07-22 | W000308 | Damage Stability Calculation | Biro Desain Dasar Pengembangan Desain | 2026-07-22 | 2026-07-31 | 1 | Irma Mahardhika PuTri Handoyo |  | JC220726 37922
| 2026-07-29 | A26AOP01 | EC30C.6A - ASSEMBLY DRAWING | Biro Desain Dasar Kapal Selam | 2026-08-01 | 2026-08-14 |  |  | 84 | JC050826 38522
| 2026-07-29 | A26AOP01 | EC30C.6C - NESTING PLATE | Biro Desain Dasar Kapal Selam | 2026-08-01 | 2026-08-31 | 1 | SIGIT ISKIYARSAH | 84 | JC050826 38523
| 2026-08-03 | M000313 Geomarin V | E90514.08012 VOLUME TABLE | Biro Desain dasar Kapal Permukaan | 2026-08-03 | 2026-08-07 | 1 | Arif Billah |  | JC030826 38413
| 2026-08-03 | M000313 Geomarin V | E90513.95013 - TONNAGE CALCULATION | Biro Desain dasar Kapal Permukaan | 2026-08-03 | 2026-08-07 | 1 | Arif Billah |  | JC030826 38440
| 2026-08-03 | M000313 Geomarin V | E10514.02011 - CAPACITY PLAN & DEADWEIGHT SCALE | Biro Desain dasar Kapal Permukaan | 2026-08-03 | 2026-08-07 | 1 | Rahadian Lingga Pratama |  | JC030826 38441
| 2026-08-03 | M000313 Geomarin V | E90513.95019 - FREEBOARD CALCULATION | Biro Desain dasar Kapal Permukaan | 2026-08-08 | 2026-08-14 | 1 | Rahadian Lingga Pratama |  | JC030826 38442
| 2026-08-03 | M000313 Geomarin V | E90791.95015 - Tri HandoyoM & STABILITY CALC | Biro Desain dasar Kapal Permukaan | 2026-08-08 | 2026-08-14 | 2 | Arif Billah - Rahadian Lingga Pratama |  | JC030826 38444
| 2026-08-03 | M000313 Geomarin V | E90791.95014 FLOODABLE LENGTH | Biro Desain dasar Kapal Permukaan | 2026-08-15 | 2026-08-24 | 2 | Arif Billah - Rahadian Lingga Pratama |  | JC030826 38445
| 2026-08-03 | SUPPORT DATA TENDER FOR MARKETING REKUMHAR - HPH, VESSEL, EPCI, MANUFAKTURING, BMPP, FGPP, CCGT & JASA. | Support Data for Marketing Rekumhar / HPH, HE, C3W, VESSEL, EPCI, Manufacture, BMPP, FGPP, CCGT, Power Plant & Jasa - Mat. List , GA, Engineering, Supervisi, Review Document. | Biro Desain Dasar Non Kapal | 2026-08-01 | 2026-08-31 | 10 | Agus Wibowo, Fendi Miranda, Mey Resty Nugraheni, Ahmad Amirulloh, Muhammad Mirza, Tri Handoyo, Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah, Luqman Chakim, Alif Junaidi. | minta tolong dibantu, mas hasfi | JC070826 38571
| 2026-08-03 | E260N002 - CONRAD STEEL STRUCTURE TOPSIDE & JACKET | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-08-01 | 2026-08-31 | 1 | Minarti Shinta Putri Utomo | 100 | JC070826 38572 | 5 jam / org / hr
| 2026-08-03 | E260N002 - CONRAD STEEL STRUCTURE TOPSIDE & JACKET | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-08-01 | 2026-08-31 | 1 | Tri Handoyo | 100 | JC070826 38577 | 5 jam / org / hr
| 2026-08-03 | E260N002 - CONRAD STEEL STRUCTURE TOPSIDE & JACKET | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-08-01 | 2026-08-31 | 1 | Alif Junaidi | 100 | JC070826 38578 | 5 jam / org / hr
| 2026-08-03 | E260N002 - CONRAD STEEL STRUCTURE TOPSIDE & JACKET | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-08-01 | 2026-08-31 | 1 | Luqman Chakim | 100 | JC070826 38580 | 5 jam / org / hr
| 2026-08-03 | E260N002 - CONRAD STEEL STRUCTURE TOPSIDE & JACKET | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-08-01 | 2026-08-31 | 1 | Mey Resty Nugraheni | 50 | JC070826 38581 | 5 jam / org / hr
| 2026-08-03 | E260N002 - CONRAD ELECTri HandoyoCAL & INSTRUMENT | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-08-01 | 2026-08-31 | 2 | Muhammad Mirza | 100 | JC070826 38583 | 5 jam / org / hr
| 2026-08-03 | E260N002 - CONRAD ELECTri HandoyoCAL & INSTRUMENT | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-08-01 | 2026-08-31 | 2 | Ahmad Amirulloh | 50 | JC070826 38584 | 5 jam / org / hr
| 2026-08-03 | E260N002 - MECHANICAL & PIPING, SAFETY | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-08-01 | 2026-08-31 | 3 | Fendi Miranda | 100 | JC070826 38585 | 5 jam / org / hr
| 2026-08-03 | E260N002 - MECHANICAL & PIPING, SAFETY | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-08-01 | 2026-08-31 | 3 | Ahmad Amirulloh | 50 | JC070826 38587 | 5 jam / org / hr
| 2026-08-03 | E260N002 - MECHANICAL & PIPING, SAFETY | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-08-01 | 2026-08-31 | 3 | Mey Resty Nugraheni | 50 | JC070826 38592 | 5 jam / org / hr
| 2026-08-03 | E260N002 - CONRAD SUPPORT DOK. PROJECT ENGINEER | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-08-01 | 2026-08-31 | 2 | Agus Wibowo | 100 | JC070826 38593 | 5 jam / org / hr
| 2026-08-03 | E260N002 - CONRAD SUPPORT DOK. PROJECT ENGINEER | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-08-01 | 2026-08-31 | 2 | Nur Fuadi Afif Zaisyah | 100 | JC070826 38594 | 5 jam / org / hr
| 2026-08-04 | LNG 3000 CBM | E90791.95015 - Tri HandoyoM & STABILITY CALC | Biro Desain Dasar Pengembangan Desain | 2026-08-01 | 2026-08-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah | 42 | JC050826 38517
| 2026-08-04 | LNG 3000 CBM | E10500.00003 - GENERAL ARRANGEMENT | Biro Desain Dasar Pengembangan Desain | 2026-08-01 | 2026-08-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah | 42 | JC050826 38518
| 2026-08-04 | W000304 | E90514.07023 - SOUNDING TABLE | Biro Desain Dasar Pengembangan Desain | 2026-08-01 | 2026-08-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah | 42 | JC050826 38519
| 2026-08-04 | W000306 | E90791.95015 - Tri HandoyoM & STABILITY CALC | Biro Desain Dasar Pengembangan Desain | 2026-08-01 | 2026-08-31 | 1 | Moh. Hamzah SaTri Handoyoawansyah | 42 | JC050826 38521
| 2026-08-04 | M000313 Geomarin V | E10500.00003 - GENERAL ARRANGEMENT | Biro Desain Dasar Pengembangan Desain | 2026-08-01 | 2026-08-31 | 1 | Irma Mahardhika PuTri Handoyo | 42 | JC050826 38524
| 2026-08-04 | W000308 | E10500.00003 - GENERAL ARRANGEMENT | Biro Desain Dasar Pengembangan Desain | 2026-08-01 | 2026-08-31 | 1 | Irma Mahardhika PuTri Handoyo | 42 | JC050826 38525
| 2026-08-04 | W000308 | Room NAPA | Biro Desain Dasar Pengembangan Desain | 2026-08-01 | 2026-08-31 | 1 | Irma Mahardhika PuTri Handoyo | 42 | JC050826 38526
| 2026-08-04 | W000308 | E90791.95024 - DAMAGE STABILITY CALC | Biro Desain Dasar Pengembangan Desain | 2026-08-01 | 2026-08-31 | 1 | Irma Mahardhika PuTri Handoyo | 42 | JC050826 38527
| 2026-08-04 | PELNI | E90961.92009 - LIGHTWEIGHT ESTIMATION | Biro Desain Dasar Pengembangan Desain | 2026-08-01 | 2026-08-31 | 1 | Ary Tri Handoyo Ratnaningtyas | 84 | JC050826 38531
| 2026-08-04 | PELNI | E90791.95015 - Tri HandoyoM & STABILITY CALC | Biro Desain Dasar Pengembangan Desain | 2026-08-01 | 2026-08-31 | 1 | Ary Tri Handoyo Ratnaningtyas | 84 | JC050826 38532
| 2026-08-04 | KSR | E10500.00003 - GENERAL ARRANGEMENT | Biro Desain Dasar Pengembangan Desain | 2026-08-01 | 2026-08-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqi | 56 | JC050826 38528
| 2026-08-04 | KSR | E90961.92021 - WEIGHT CONTROL 03 | Biro Desain Dasar Pengembangan Desain | 2026-08-01 | 2026-08-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqi | 56 | JC050826 38529
| 2026-08-04 | W000304 | E10500.00003 - GENERAL ARRANGEMENT | Biro Desain Dasar Pengembangan Desain | 2026-08-01 | 2026-08-31 | 1 | Ahmad MuhtArif Billah Ihyail Haqi | 56 | JC050826 38530
| 2026-08-06 | E260N003 - Revitalisasi Penstok 1 dan 2 (Tahap 1) PLTA Ketenger | E260N003 - Dukungan Produksi Supervisi Revitalisasi Penstok 1 dan 2 (Tahap 1) PLTA Ketenger | Biro Desain Dasar Non Kapal | 2026-08-06 | 2026-08-19 | 1 | Alif Junaidi | 120 | JC130826 38920
| 2026-08-24 | Kapal LNG 3000 CBM | Menghitung Weight Estimation dengan Napa Steel | Biro Desain Dasar Pengembangan Desain | 2026-08-24 | 2026-08-28 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC260826 39447
| 2026-08-28 | SUPPORT DATA TENDER FOR MARKETING REKUMHAR - HPH, VESSEL, EPCI, MANUFAKTURING, BMPP, FGPP, CCGT & JASA. | Support Data for Marketing Rekumhar / HPH, HE, C3W, VESSEL, EPCI, Manufacture, BMPP, FGPP, CCGT, Power Plant & Jasa - Mat. List , GA, Engineering, Supervisi, Review Document. | Biro Desain Dasar Non Kapal | 2026-09-01 | 2026-09-30 | 10 | Agus Wibowo, Fendi Miranda, Mey Resty Nugraheni, Ahmad Amirulloh, Muhammad Mirza, Tri Handoyo, Minarti Shinta Putri Utomo, Nur Fuadi Afif Zaisyah, Luqman Chakim, Alif Junaidi. | 800 | JC310826 39650
| 2026-08-28 | E260N002 - CONRAD STEEL STRUCTURE TOPSIDE & JACKET | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-09-01 | 2026-09-30 | 1 | Minarti Shinta Putri Utomo | 80 | JC310826 39651 | JC030926 39898
| 2026-08-28 | E260N002 - CONRAD STEEL STRUCTURE TOPSIDE & JACKET | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-09-01 | 2026-09-30 | 1 | Tri Handoyo | 80 | JC310826 39652 | JC030926 39899
| 2026-08-28 | E260N002 - CONRAD STEEL STRUCTURE TOPSIDE & JACKET | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-09-01 | 2026-09-30 | 1 | Alif Junaidi | 80 | JC310826 39653 | JC030926 39900
| 2026-08-28 | E260N002 - CONRAD STEEL STRUCTURE TOPSIDE & JACKET | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-09-01 | 2026-09-30 | 1 | Luqman Chakim | 80 | JC310826 39654 | JC030926 39901
| 2026-08-28 | E260N002 - CONRAD STEEL STRUCTURE TOPSIDE & JACKET | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-09-01 | 2026-09-30 | 1 | Mey Resty Nugraheni | 80 | JC310826 39655 | JC030926 39902
| 2026-08-28 | E260N002 - CONRAD ELECTri HandoyoCAL & INSTRUMENT | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-09-01 | 2026-09-30 | 1 | Muhammad Mirza | 80 | JC310826 39656 | JC030926 39903
| 2026-08-28 | E260N002 - MECHANICAL & PIPING, SAFETY | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-09-01 | 2026-09-30 | 1 | Fendi Miranda | 80 | JC310826 39657 | JC030926 39904
| 2026-08-28 | E260N002 - INSTRUMENT, MECHANICAL & PIPING, SAFETY | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-09-01 | 2026-09-30 | 1 | Ahmad Amirulloh | 80 | JC310826 39658 | JC030926 39905
| 2026-08-28 | E260N002 - SUPPORT PRODUKSI DOK. PROJECT ENGINEER CONRAD | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-09-01 | 2026-09-30 | 1 | Agus Wibowo | 80 | JC020926 39831 | JC030926 39906
| 2026-08-28 | E260N002 - SUPPORT PRODUKSI DOK. PROJECT ENGINEER CONRAD | E260N002 Proyek Conrad, Material List, Dukungan Dokument & Supervisi | Biro Desain Dasar Non Kapal | 2026-09-01 | 2026-09-30 | 1 | Nur Fuadi Afif Zaisyah | 80 | JC020926 39832 | JC030926 39907
| 2026-08-26 | A26AOP01 | EC10C.6A - ASSEMBLY DRAWING | Biro Desain Dasar Kapal Selam | 2026-09-01 | 2026-09-14 | 1 | SIGIT ISKIYARSAH |  | JC020926 39833
| 2026-08-26 | A26AOP01 | EC10C.6C - NESTING PLATE | Biro Desain Dasar Kapal Selam | 2026-09-14 | 2026-09-30 | 1 | SIGIT ISKIYARSAH |  | JC020926 39834
| 2026-08-31 | M000312 KPPP | E90513.95019 - FREEBOARD CALCULATION | Biro Desain dasar Kapal Permukaan | 2026-08-31 | 2026-09-05 | 1 | Arif Billah |  | JC310826 39746
| 2026-08-31 | M000312 KPPP | E10511.09017 - NAUTICAL PLAN | Biro Desain dasar Kapal Permukaan | 2026-08-31 | 2026-09-05 | 1 | Arif Billah |  | JC310826 39747
| 2026-08-31 | M000312 KPPP | E90961.92020 - WEIGHT CONTROL (KB02) | Biro Desain dasar Kapal Permukaan | 2026-08-31 | 2026-09-05 | 1 | Rahadian Lingga Pratama |  | JC310826 39748
| 2026-08-31 | M000312 KPPP | E90961.92021 - WEIGHT CONTROL (KB03) | Biro Desain dasar Kapal Permukaan | 2026-09-07 | 2026-09-14 | 1 | Rahadian Lingga Pratama |  | JC020926 39835
| 2026-08-31 | M000312 KPPP | E90961.92022 - WEIGHT CONTROL (KB04) | Biro Desain dasar Kapal Permukaan | 2026-09-14 | 2026-09-21 | 1 | Rahadian Lingga Pratama |  | JC020926 39836
| 2026-08-31 | M000312 KPPP | E90514.07023 - SOUNDING TABLE | Biro Desain dasar Kapal Permukaan | 2026-08-31 | 2026-09-05 | 1 | Rahadian Lingga Pratama |  | JC310826 39749
| 2026-08-31 | M000308 LPD UAE | E90961.92022 - WEIGHT CONTROL (KB04) | Biro Desain dasar Kapal Permukaan | 2026-08-31 | 2026-09-30 | 1 | Rahadian Lingga Pratama |  | JC310826 39751
| 2026-08-31 | M000313 Geomarin V | E10511.09017 - NAUTICAL PLAN | Biro Desain dasar Kapal Permukaan | 2026-09-05 | 2026-09-15 | 1 | Arif Billah |  | JC020926 39837
| 2026-08-31 | M000313 Geomarin V | E90514.07023 - SOUNDING TABLE | Biro Desain dasar Kapal Permukaan | 2026-09-05 | 2026-09-15 | 1 | Rahadian Lingga Pratama |  | JC020926 39838
| 2026-08-31 | Kapal LNG 3000 CBM | E90791.95015 - Tri HandoyoM & STABILITY CALC | Biro Desain Dasar Pengembangan Desain | 2026-09-01 | 2026-09-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC020926 39841
| 2026-08-31 | Kapal LNG 3000 CBM | E10500.00003 - GENERAL ARRANGEMENT | Biro Desain Dasar Pengembangan Desain | 2026-09-01 | 2026-09-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC020926 39847
| 2026-08-31 | W000304 | E90514. 07023 SOUNDING TABLE | Biro Desain Dasar Pengembangan Desain | 2026-09-01 | 2026-09-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC020926 39848
| 2026-08-31 | JW 1 & JW 2 | E90791.95015 - Tri HandoyoM & STABILITY CALC | Biro Desain Dasar Pengembangan Desain | 2026-09-01 | 2026-09-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC020926 39849
| 2026-08-31 | JW 1 & JW 2 | E10514.02011 - CAPACITY PLAN & DEADWEIGHT SCALE | Biro Desain Dasar Pengembangan Desain | 2026-09-01 | 2026-09-30 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC020926 39850
| 2026-08-31 | Kapal LNG 3000 CBM | Surface Object for Hull Weight Estimation | Biro Desain Dasar Pengembangan Desain | 2026-09-01 | 2026-09-30 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC020926 39851
| 2026-08-31 | Kapal Pelni | E10500.00003 - GENERAL ARRANGEMENT | Biro Desain Dasar Pengembangan Desain | 2026-09-01 | 2026-09-30 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC020926 39852
| 2026-08-31 | W000314 | E00510.06002 PRINCIPAL PARTICULAR | Biro Desain Dasar Pengembangan Desain | 2026-09-01 | 2026-09-30 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC020926 39853
| 2026-08-31 | W000314 | E90513.95013 TONNAGE CALCULATION | Biro Desain Dasar Pengembangan Desain | 2026-09-01 | 2026-09-30 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC020926 39854
| 2026-08-31 | W000314 | E16030.01018 POSITION OF DRAUGHT MARK | Biro Desain Dasar Pengembangan Desain | 2026-09-01 | 2026-09-30 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC020926 39855
| 2026-08-31 | W000304 | E10500.00003 - GENERAL ARRANGEMENT | Biro Desain Dasar Pengembangan Desain | 2026-09-01 | 2026-09-30 | 1 | Ahmad MuhtArif Billah Ihyail Haqi |  | JC020926 39858
| 2026-09-07 | M000313 Geomarin V | E90791.95016 CROSS CURVE OF STABILITY TABLE | Biro Desain dasar Kapal Permukaan | 2026-09-07 | 2026-09-15 | 1 | Arif Billah |  | JC080926 40074
| 2026-09-09 | W000304 | E90513. 95006 ; Hidrostatik Table ; Finish Plan | Biro Desain Dasar Pengembangan Desain | 2026-09-07 | 2026-09-18 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC110926 40290
| 2026-09-09 | W000304 | E16030.01018 ; Position of Draught Mark ; Finish Plan | Biro Desain Dasar Pengembangan Desain | 2026-09-07 | 2026-09-18 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC110926 40291
| 2026-09-09 | W000304 | E10513.05004 ; Lines Plan ; Finish Plan | Biro Desain Dasar Pengembangan Desain | 2026-09-07 | 2026-09-18 | 1 | Ary Tri Handoyo Ratnaningtyas |  | JC110926 40292
| 2026-09-09 | W000304 | E90791.95014 ; Floodable Length Calculation ; Finish Plan | Biro Desain Dasar Pengembangan Desain | 2026-09-10 | 2026-09-18 | 1 | Moh. Hamzah SaTri Handoyoawansyah |  | JC110926 40293

## Dept. SPL (HC)
Diisi Planner
No | Tanggal Permintaan JC ditulis | Project | Task Name | Work Center | Schedule Start date | Schedule End date | Total Personil yang mengerjakan | PIC | JO | Kode Job Card | Planner | Keterangan
| DD / MM / YYYY | KODE PROYEK | REVISI KE - NO DOC / DWG - DESC PEKERJAAN | KODE BIRO - DESC BIRO | DD / MM / YYYY | DD / MM / YYYY | (DALAM ANGKA) | (NAMA) | (ANGKA) | JC010624 0001 | 023066812-Hashfi Moch Adam
CONTOH
| 14 May 2024 | W000308 | E11800.03102 - GUN FOUNDATION | 1CK100 - Biro Desain Struktur Lambung | 2024-06-04 | 2024-06-13 | 2 |  |  | JC040624 0374 | 023066812-Hashfi Moch Adam
| 2025-03-06 | W000305 | E91002.97116 - FORWARD MOORING EQUIPMENT SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-03-03 | 2025-03-14 | 2 | Shihab & Pijar |  | JC060325 16078
| 2025-03-06 | W000305 | E91002.97118 - AFT MOORING EQUIPMENT SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-03-03 | 2025-03-14 | 2 | Bambang & Pijar |  | JC060325 16079
| 2025-03-06 | W000305 | E91002.97103 - SECONDARY GUN FOUNDATION SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-03-17 | 2025-04-11 | 2 | Shihab & Pijar |  | JC060325 16080
| 2025-03-06 | W000305 | E91002.97105 - AUXILIARY GUN FOUNDATION SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-03-17 | 2025-04-11 | 2 | Bambang & Pijar |  | JC060325 16081
| 2025-03-07 | A24AOP01 | R4 - E11002.03104 - FORE CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2025-03-03 | 2025-03-07 | 1 | Yuli K | 37:30 | JC080325 16242
| 2025-03-07 | A24AOP01 | EC70C,6A - RUDDER HORN | 1CK100 - Biro Desain Struktur Lambung | 2025-03-10 | 2025-03-14 | 1 | Yuli K |  | JC080325 16243
| 2025-03-10 | W000305 | E11001.03107 - TEMPORARY HOLES DETAILS | 1CK100 - Biro Desain Struktur Lambung | 2025-03-17 | 2025-03-28 | 1 | Yuli K |  | JC110325 16451
| 2025-03-12 | W000305 | E91002.97132 - AFT MAST SUPPORTING STRUCTURE REPORT (MODELLING SOLID WORK) | 1CK100 - Biro Desain Struktur Lambung | 2025-03-03 | 2025-03-10 | 1 | Agung |  | JC120325 16485
| 2025-03-12 | W000305 | E91002.97130 - FORE MAST SUPPORTING STRUCTURE REPORT (MODELLING SOLID WORK) | 1CK100 - Biro Desain Struktur Lambung | 2025-03-11 | 2025-03-19 | 1 | Agung |  | JC120325 16486
| 2025-03-12 | W000305 | E91002.97131 - MIDDLE MAST SUPPORTING STRUCTURE REPORT (MODELLING SOLID WORK) | 1CK100 - Biro Desain Struktur Lambung | 2025-03-20 | 2025-03-28 | 1 | Agung |  | JC120325 16487
| 2025-03-12 | W000308 | R1 - E11200.03100 - DOCKING PLAN | 1CK100 - Biro Desain Struktur Lambung | 2025-03-03 | 2025-03-14 | 1 | Ainy |  | JC140325 16529
| 2025-03-12 | W000305 | E11200.03100 - DOCKING PLAN | 1CK100 - Biro Desain Struktur Lambung | 2025-03-17 | 2025-04-11 | 1 | Ainy |  | JC120325 16489
| 2025-03-12 | W000308 | R2 - E11002.03107 - ACCOMODATION CONSTRUCTION OF 04~05 DECK (FR.103~FRONT WALL) (UPDATE OPENING PINTU) | 1CK100 - Biro Desain Struktur Lambung | 2025-03-03 | 2025-03-14 | 1 | Kasmiatin |  | JC140325 16530
| 2025-03-12 | W000308 | R2 - E11002.03302 - MIDDLE CONSTRUCTION OF 03 DECK | 1CK100 - Biro Desain Struktur Lambung | 2025-03-17 | 2025-03-28 | 1 | Kasmiatin |  | JC140325 16531
2025-04-01
| 2025-04-08 | W000305 | R2 - E91002.97113 - Fin Stabilizers Supporting Structure Analysis Report | 1CK100 - Biro Desain Struktur Lambung | 2025-04-07 | 2025-04-11 | 1 | Bambang |  | JC090425 17485
| 2025-04-08 | W000305 | R1 - E91002.97102- Main Gun Foundation Supporting Structure Report | 1CK100 - Biro Desain Struktur Lambung | 2025-04-14 | 2025-05-02 | 1 | Bambang |  | JC090425 17487
| 2025-04-08 | W000305 | R1 - E91002.97117 - Middle Mooring Equipment Supporting Structure | 1CK100 - Biro Desain Struktur Lambung | 2025-04-07 | 2025-04-11 | 1 | Pijar |  | JC090425 17488
| 2025-04-08 | W000305 | R1 - E91002.97104 - CWIS Foundation Supporting Structure Report | 1CK100 - Biro Desain Struktur Lambung | 2025-04-14 | 2025-05-02 | 1 | Pijar |  | JC090425 17489
| 2025-04-08 | W000305 | R2 - E90702.95032 - Seat Policies Document | 1CK100 - Biro Desain Struktur Lambung | 2025-04-07 | 2025-04-11 | 1 | Shihab |  | JC090425 17491
| 2025-04-08 | W000305 | E91002.97130 - FORE MAST SUPPORTING STRUCTURE REPORT (MODELLING SOLID WORK UPDATE) | 1CK100 - Biro Desain Struktur Lambung | 2025-04-14 | 2025-04-18 | 1 | Shihab |  | JC090425 17493
| 2025-04-08 | E190N025 | E11001.03100 - SCANTLING CALCULATION SUMMARY REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-04-21 | 2025-05-02 | 1 | Shihab |  | JC090425 17495
| 2025-04-08 | W000305 | R2 - E11002.03107 - MAST CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2025-04-07 | 2025-04-11 | 1 | Agung |  | JC090425 17500
| 2025-04-08 | W000305 | E11800.03115 - IFF ANTENNA FOUNDATION | 1CK100 - Biro Desain Struktur Lambung | 2025-04-14 | 2025-04-18 | 1 | Agung |  | JC090425 17501
| 2025-04-08 | W000305 | E11800.03116 - SURVEILENCE RADAR FOUNDATION | 1CK100 - Biro Desain Struktur Lambung | 2025-04-21 | 2025-04-25 | 1 | Agung |  | JC090425 17502
| 2025-04-08 | W000305 | E11800.03107 - FCS ANTENNA FOUNDATION (UPDATE MAKER) | 1CK100 - Biro Desain Struktur Lambung | 2025-04-28 | 2025-05-02 | 1 | Agung |  | JC090425 17503
| 2025-04-08 | E190N025 | E11111.03100 - SHELL EXPANSION (MODELLING SHELL PROFILE) | 1CK100 - Biro Desain Struktur Lambung | 2025-04-07 | 2025-04-11 | 1 | Yuli K |  | JC090425 17504
| 2025-04-08 | E190N025 | E11002.03101 - ENGINE ROOM CONSTRUCTION (MODELLING & OUTPUT 2D) | 1CK100 - Biro Desain Struktur Lambung | 2025-04-14 | 2025-04-30 | 1 | Yuli K |  | JC090425 17505
| 2025-04-08 | E190N025 | E11002.03103 - FORE CONSTRUCTION (MODELLING & OUTPUT 2D) | 1CK100 - Biro Desain Struktur Lambung | 2025-04-07 | 2025-04-30 | 1 | Kasmiatin |  | JC090425 17506
| 2025-04-28 | W000308 | E11800.03102 - GUN FOUNDATION | 1CK100 - Biro Desain Struktur Lambung | 2025-04-28 | 2025-05-02 | 1 | Agung |  | JC280425 18451
| 2025-04-28 | PLTAL | BLOCK DIVISION | 1CK100 - Biro Desain Struktur Lambung | 2025-04-14 | 2025-04-30 | 1 | Ainy |  | JC280425 18506
| 2025-04-29 | W000305 | R2 - E90702.95032 - Seat Policies Document | 1CK100 - Biro Desain Struktur Lambung | 2025-04-14 | 2025-04-30 | 1 | Shihab |  | JC290425 18591
| 2025-04-29 | E190N025 | E11002.03103 - FORE CONSTRUCTION (MODELLING & OUTPUT 2D) | 1CK100 - Biro Desain Struktur Lambung | 2025-04-14 | 2025-04-30 | 1 | Kasmiatin |  | JC290425 18592
| 2025-04-29 | E190N025 | E11002.03101 - ENGINE ROOM CONSTRUCTION (MODELLING & OUTPUT 2D) | 1CK100 - Biro Desain Struktur Lambung | 2025-04-18 | 2025-04-30 | 1 | Yuli K |  | JC290425 18598
| 2025-04-29 | W000308 | E91002.97104 - SHAFT BRACKET STRUCTURE ANALYSIS REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-04-11 | 2025-04-30 | 1 | Dea |  | JC290425 18621
| 2025-05-14 | W000305 | R3 - E91002.97108 - Engine Foundation and gearbox Seat Supporting Structure Analysis Report | 1CK100 - Biro Desain Struktur Lambung | 2025-05-02 | 2025-05-16 | 1 | Dea |  | JC140525 19331
| 2025-05-14 | W000305 | R1 -E91002.97118 - AFT Mooring Equipment Supporting Structure | 1CK100 - Biro Desain Struktur Lambung | 2025-05-19 | 2025-05-30 | 1 | Dea |  | JC140525 19332
| 2025-05-14 | W000305 | E91002.97103 - Secondary Gun Foundation Supporting Structure Report | 1CK100 - Biro Desain Struktur Lambung | 2025-05-02 | 2025-05-30 | 1 | Pijar |  | JC140525 19333
| 2025-05-14 | W000305 | R1 - E91002.97102 - Main Gun Foundation Supporting Structure Report | 1CK100 - Biro Desain Struktur Lambung | 2025-05-02 | 2025-05-09 | 1 | Bambang |  | JC140525 19335
| 2025-05-14 | W000305 | E91002.97131 - MIDDLE MAST SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-05-12 | 2025-05-23 | 2 | Bambang & ainy |  | JC140525 19338
| 2025-05-14 | W000305 | E91002.97130 - FORE MAST SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-05-26 | 2025-06-06 | 3 | Bambang & pijar & ainy |  | JC140525 19340
| 2025-05-14 | W000305 | R2 - E11002.03107 - MAST CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2025-05-05 | 2025-05-09 | 1 | Agung |  | JC140525 19341
| 2025-05-14 | W000305 | E11800.03107 - FCS ANTENNA FOUNDATION (UPDATE MAKER) | 1CK100 - Biro Desain Struktur Lambung | 2025-05-12 | 2025-05-21 | 1 | Agung |  | JC140525 19342
| 2025-05-14 | W000305 | E11800.03117 - FOUNDATION OF DECOY LAUNCHER | 1CK100 - Biro Desain Struktur Lambung | 2025-05-22 | 2025-05-30 | 1 | Agung |  | JC140525 19343
| 2025-05-14 | W000305 | R2 - E90702.95032 - Seat Policies Document | 1CK100 - Biro Desain Struktur Lambung | 2025-05-02 | 2025-05-30 | 1 | Shihab |  | JC140525 19344
| 2025-05-14 | W000305 | R3 - E11002.03105 - ACCOMODATION CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2025-05-02 | 2025-05-09 | 1 | Yuli K |  | JC140525 19346
| 2025-05-14 | W000305 | R3 - E11002.03102 - HELICOPTER HANGAR CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2025-05-12 | 2025-05-16 | 1 | Yuli K |  | JC140525 19352
| 2025-05-14 | W000305 | E11001.03107 - TEMPORARY HOLES DETAILS | 1CK100 - Biro Desain Struktur Lambung | 2025-05-19 | 2025-05-30 | 1 | Yuli K |  | JC140525 19353
| 2025-05-14 | E190N025 | REVIEW AND CEK GAMBAR - GAMBAR KEY PLAN & YARD PLAN | 1CK100 - Biro Desain Struktur Lambung | 2025-05-02 | 2025-05-30 | 1 | Kasmiatin |  | JC140525 19354
| 2025-05-14 | W000306 | R1 - E11002-03101 - ENGINE ROOM CONSTRUCTION (Update comment owner) | 1CK100 - Biro Desain Struktur Lambung | 2025-05-02 | 2025-05-09 | 1 | Ainy |  | JC140525 19359
| 2025-06-13 | W000305 | E91002.97125 -HELI DECK NET SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-06-09 | 2025-06-30 | 1 | Bambang |  | JC130625 20724
| 2025-06-13 | W000305 | E91002.97105 -BULKHEAD DEFLECTION IN WAY OF SHAFT SEALS REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-06-09 | 2025-06-13 | 1 | pijar |  | JC130625 20725
| 2025-06-13 | W000305 | E91002.97116 -FORWARD MOORING EQUIPMENT SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-06-16 | 2025-06-30 | 1 | pijar |  | JC130625 20727
| 2025-06-13 | W000305 | E91002.97117 - MIDDLE MOORING EQUIPMENT SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-06-02 | 2025-06-13 | 2 | Dea |  | JC130625 20728
| 2025-06-13 | W000305 | E91002.97118 - AFT MOORING EQUIPMENT SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-06-16 | 2025-06-30 | 2 | Dea |  | JC130625 20729
| 2025-06-13 | KPI 2025 | REVIEW AND CEK GAMBAR - GAMBAR KEY PLAN & YARD PLAN BMPP 3 | 1CK100 - Biro Desain Struktur Lambung | 2025-06-02 | 2025-06-30 | 1 | Kasmiatin |  | JC130625 20730
| 2025-06-13 | W000305 | E96000.92101 - WEIGHT CONTROL (KB-03) (HO) | 1CK100 - Biro Desain Struktur Lambung | 2025-06-02 | 2025-06-30 | 1 | Agung |  | JC130625 20737
| 2025-06-13 | W000305 | R1 - E11800.03114 - REINFORCEMENT UNDER MIDDLE MOORING DECK | 1CK100 - Biro Desain Struktur Lambung | 2025-06-02 | 2025-06-10 | 1 | Yuli K |  | JC130625 20731
| 2025-06-13 | W000305 | R1 - E11800.03110 - REINFORCEMENT UNDER AFT MOORING DECK | 1CK100 - Biro Desain Struktur Lambung | 2025-06-11 | 2025-06-19 | 1 | Yuli K |  | JC130625 20732
| 2025-06-13 | W000305 | R1 - E11800.03109 - REINFORCEMENT UNDER FORWARD MOORING DECK | 1CK100 - Biro Desain Struktur Lambung | 2025-06-20 | 2025-06-30 | 1 | Yuli K |  | JC130625 20733
| 2025-06-13 | W000305 | rev - EC122PS.6 PRODUCTION DRAWING 122 P/S (3D MODEL CADMATIC; ASSEMBLY DWG; LIFTING INFO) | 1CK100 - Biro Desain Struktur Lambung | 2025-06-02 | 2025-06-10 | 1 | Ainy |  | JC130625 20734
| 2025-06-13 | W000305 | rev - EC414PS.6 PRODUCTION DRAWING 414 P/S (3D MODEL CADMATIC; ASSEMBLY DWG; LIFTING INFO) | 1CK100 - Biro Desain Struktur Lambung | 2025-06-11 | 2025-06-19 | 1 | Ainy |  | JC130625 20735
| 2025-06-13 | W000305 | rev - EC424PS.6 PRODUCTION DRAWING 424 P/S (3D MODEL CADMATIC; ASSEMBLY DWG; LIFTING INFO) | 1CK100 - Biro Desain Struktur Lambung | 2025-06-20 | 2025-06-30 | 1 | Ainy |  | JC130625 20736
| 2025-07-07 | W000308 | LONGITUDINAL STRENGTH CALCULATION FOR LAUNCHING | 1CK100 - Biro Desain Struktur Lambung | 2025-07-01 | 2025-07-07 | 1 | Pijar |  | JC070725 21993
| 2025-07-07 | W000305 | E91002.97116 -FORWARD MOORING EQUIPMENT SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-07-08 | 2025-07-11 | 1 | Pijar |  | JC080725 21998
| 2025-07-07 | W000305 | R1 - E91002.97104 - CWIS Foundation Supporting Structure Report | 1CK100 - Biro Desain Struktur Lambung | 2025-07-14 | 2025-08-01 | 1 | Pijar |  | JC080725 21999
| 2025-07-07 | W000305 | LONGITUDINAL STRENGTH CALCULATION FOR LAUNCHING | 1CK100 - Biro Desain Struktur Lambung | 2025-07-01 | 2025-07-07 | 2 | Bambang & Dea |  | JC070725 21994
| 2025-07-07 | W000305 | E91002.97105 - AUXILIARY GUN FOUNDATION SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-07-08 | 2025-08-01 | 1 | Bambang |  | JC080725 22002
| 2025-07-07 | W000305 | R1 -E91002.97118 - AFT Mooring Equipment Supporting Structure | 1CK100 - Biro Desain Struktur Lambung | 2025-07-08 | 2025-07-18 | 1 | Dea |  | JC080725 22003
| 2025-07-07 | W000305 | E91002.97124 - REPLENISHMENT AT SEA (RAS) SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-07-21 | 2025-08-01 | 1 | Dea |  | JC080725 22026
| 2025-07-07 | W000305 | E11001.03115 - TEMPORARY HOLES DETAILS | 1CK100 - Biro Desain Struktur Lambung | 2025-07-01 | 2025-07-03 | 1 | Yuli K |  | JC070725 21995
| 2025-07-07 | W000305 | E11001.03116 - TEMPORARY HOLES DETAILS | 1CK100 - Biro Desain Struktur Lambung | 2025-07-04 | 2025-07-08 | 1 | Yuli K |  | JC080725 22005
| 2025-07-07 | W000305 | E11001.03117 - TEMPORARY HOLES DETAILS | 1CK100 - Biro Desain Struktur Lambung | 2025-07-09 | 2025-07-11 | 1 | Yuli K |  | JC080725 22006
| 2025-07-07 | W000305 | E11001.03118 - TEMPORARY HOLES DETAILS | 1CK100 - Biro Desain Struktur Lambung | 2025-07-14 | 2025-07-16 | 1 | Yuli K |  | JC080725 22007
| 2025-07-07 | W000305 | E11001.03119 - TEMPORARY HOLES DETAILS | 1CK100 - Biro Desain Struktur Lambung | 2025-07-17 | 2025-07-21 | 1 | Yuli K |  | JC080725 22008
| 2025-07-07 | W000305 | E11001.03120 - TEMPORARY HOLES DETAILS | 1CK100 - Biro Desain Struktur Lambung | 2025-07-22 | 2025-07-24 | 1 | Yuli K |  | JC080725 22009
| 2025-07-07 | W000305 | E11001.03121 - TEMPORARY HOLES DETAILS | 1CK100 - Biro Desain Struktur Lambung | 2025-07-25 | 2025-07-29 | 1 | Yuli K |  | JC080725 22010
| 2025-07-07 | W000305 | E11001.03122 - TEMPORARY HOLES DETAILS | 1CK100 - Biro Desain Struktur Lambung | 2025-07-30 | 2025-08-01 | 1 | Yuli K |  | JC080725 22011
| 2025-07-07 | W000305 | E21170.01100 - ESTIMATION MATERIAL PLATE (W305) | 1CK100 - Biro Desain Struktur Lambung | 2025-07-01 | 2025-08-01 | 1 | Ainy |  | JC080725 22012
| 2025-07-08 | KPI 2025 | Modelling Cadmatic Shell plate dan profile kapal LCU LD Philipine | 1CK100 - Biro Desain Struktur Lambung | 2025-07-01 | 2025-08-01 | 1 | Agung |  | JC090725 22057
| 2025-07-11 | W000308 | R2 - E11111.03100 - SHELL EXPANSION | 1CK100 - Biro Desain Struktur Lambung | 2025-07-01 | 2025-07-11 | 1 | bu tin |  | JC090725 22058
| 2025-07-11 | W000308 | R2 - E11001.03101 - CONSTRUCTION PROFILE AND DECK PLAN | 1CK100 - Biro Desain Struktur Lambung | 2025-07-14 | 2025-07-18 | 1 | bu tin |  | JC110725 22110
| 2025-07-11 | W000308 | R2 - E11002.03103 - FORE CONSTRUCTION OF BOTTOM~MAIN DECK (FR.162~FR.230) | 1CK100 - Biro Desain Struktur Lambung | 2025-07-21 | 2025-08-01 | 1 | bu tin |  | JC110725 22111
| 2025-07-08 | W000308 | E11002.03101 - ENGINE ROOM CONST. OF BOTTOM - MAIN DECK (FR. 60 - FR. 109) | 1CK100 - Biro Desain Struktur Lambung | 2025-08-02 | 2025-08-10 | 1 | bu tin |  | JC110825 23525
| 2025-07-08 | W000308 | E11002.03203 - FORE TANK DECK CONST. 01-02 DECK | 1CK100 - Biro Desain Struktur Lambung | 2025-08-11 | 2025-08-17 | 1 | bu tin |  | JC110825 23527
| 2025-07-08 | W000308 | E11002.03303 - FORE CONST 03 DECK | 1CK100 - Biro Desain Struktur Lambung | 2025-08-18 | 2025-08-24 | 1 | bu tin |  | JC110825 23547
| 2025-07-08 | W000308 | E11001.03101 - CONST. PROFILE AND DECK PLAN 01 AND 02 DECK | 1CK100 - Biro Desain Struktur Lambung | 2025-08-25 | 2025-08-31 | 1 | bu tin |  | JC110825 23551
| 2025-07-08 | W000305 | E11002.03101 - STEEL PLAN | 1CK100 - Biro Desain Struktur Lambung | 2025-08-02 | 2025-08-10 | 1 | Yuli K |  | JC110825 23553
| 2025-07-08 | W000305 | E11002.03102 - HELICOPTER HANGAR CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2025-08-11 | 2025-08-17 | 1 | Yuli K |  | JC110825 23558
| 2025-07-08 | W000305 | E11002.03103 - ENGINE ROOM CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2025-08-18 | 2025-08-24 | 1 | Yuli K |  | JC110825 23561
| 2025-07-08 | W000305 | E11002.03104 - FORE CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2025-08-25 | 2025-08-31 | 1 | Yuli K |  | JC110825 23562
| 2025-07-08 | W000305 | MODELLING SOLIDWORK - FOUND. OF TORPEDO LAUNCHER SYSTEM | 1CK100 - Biro Desain Struktur Lambung | 2025-08-02 | 2025-08-31 | 1 | Agung Laksono |  | JC110825 23565
| 2025-07-08 | W000305 | REPLENISHMENT AT SEA POINT STRUCTURE ANALYSIS REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-08-02 | 2025-08-31 | 1 | Dea Putri Ubaidah |  | JC110825 23568
| 2025-07-08 | W000305 | E91002.97103 - SECONDARY GUN | 1CK100 - Biro Desain Struktur Lambung | 2025-08-02 | 2025-08-17 | 1 | Pijar Kasih |  | JC110825 23569
| 2025-07-08 | W000305 | E91002.97102 - MAIN GUN | 1CK100 - Biro Desain Struktur Lambung | 2025-08-18 | 2025-08-31 | 1 | Pijar Kasih |  | JC110825 23570
| 2025-07-08 | W000305 | DECOY LAUNCHER SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-08-02 | 2025-08-31 | 1 | Bambang |  | JC110825 23571
| 2025-07-08 | W000308 | E21170.01100 - MATERIAL ESTIMATION (PLATE) | 1CK100 - Biro Desain Struktur Lambung | 2025-08-02 | 2025-08-10 | 1 | Nur Ainy |  | JC110825 23572
| 2025-07-08 | W000308 | E21170.01101 - MATERIAL ESTIMATION (Profile & Pillar) | 1CK100 - Biro Desain Struktur Lambung | 2025-08-11 | 2025-08-24 | 1 | Nur Ainy |  | JC110825 23573
| 2025-07-08 | W000307 | E21170.01100 - MATERIAL ESTIMATION (PLATE) | 1CK100 - Biro Desain Struktur Lambung | 2025-08-25 | 2025-08-31 | 1 | Nur Ainy |  | JC110825 23574
| 2025-09-09 | W000308 | E11002.03100 - STERN AND DOCK WELL BOTTOM CONSTRUCTION (AE~FR.59) | 1CK100 - Biro Desain Struktur Lambung | 2025-09-01 | 2025-09-05 | 1 | bu tin |  | JC100925 24846
| 2025-09-09 | W000308 | E11002.03200 - DOCK WELL CONSTRUCTION (AE~FR.59) | 1CK100 - Biro Desain Struktur Lambung | 2025-09-08 | 2025-09-19 | 1 | bu tin |  | JC100925 24847
| 2025-09-09 | W000308 | E11002.03300 - AFT CONSTRUCTION OF 03 DECK (AE~FR.109) | 1CK100 - Biro Desain Struktur Lambung | 2025-09-22 | 2025-09-30 | 1 | bu tin |  | JC100925 24848
| 2025-09-09 | W000307 | 3D MODEL CADMATIC SHELL PLATE AND SHELL PROFILE LCU LD PHILIPINE | 1CK100 - Biro Desain Struktur Lambung | 2025-09-01 | 2025-09-30 | 1 | Yuli K |  | JC100925 24849
| 2025-09-11 | W000307 | 3D MODEL SOLIDWORK V BRACKET LD PHILIPPINE | 1CK100 - Biro Desain Struktur Lambung | 2025-09-01 | 2025-09-12 | 1 | Agung |  | JC160925 25133
| 2025-09-11 | W000308 | 3D MODEL SOLIDWORK MAIN GUN FOUNDATION | 1CK100 - Biro Desain Struktur Lambung | 2025-09-15 | 2025-09-30 | 1 | Agung |  | JC160925 25135
| 2025-09-11 | W000305 | REVIEW & REKAP MATERIAL PROFILE DAN PLATE DARI NESTING PLATE DENGAN ESTIMASI FRIGATE 2 | 1CK100 - Biro Desain Struktur Lambung | 2025-09-01 | 2025-09-05 | 1 | Nur Ainy |  | JC160925 25138
| 2025-09-11 | W000305 | REV - EC155U.6 - PRODUCTION DRAWING BLOCK 155 P/S | 1CK100 - Biro Desain Struktur Lambung | 2025-09-08 | 2025-09-12 | 1 | Nur Ainy |  | JC160925 25139
| 2025-09-11 | W000305 | REV - EC154U.6 - PRODUCTION DRAWING BLOCK 154 P/S | 1CK100 - Biro Desain Struktur Lambung | 2025-09-15 | 2025-09-19 | 1 | Nur Ainy |  | JC160925 25140
| 2025-09-11 | W000305 | REV - EC512U.6 - PRODUCTION DRAWING BLOCK 512 P/S | 1CK100 - Biro Desain Struktur Lambung | 2025-09-22 | 2025-09-30 | 1 | Nur Ainy |  | JC190925 25250
| 2025-09-11 | W000305 | E91002.97123 - BOAT DAVIT SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-09-01 | 2025-09-05 | 1 | Pijar |  | JC160925 25145
| 2025-09-11 | W000305 | E91002.97116 - FORWARD MOORING EQUIPMENT SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-09-08 | 2025-09-19 | 1 | Pijar |  | JC160925 25146
| 2025-09-11 | W000305 | E91002.97102 - MAIN GUN SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-09-22 | 2025-09-30 | 1 | Pijar |  | JC160925 25147
| 2025-09-11 | W000305 | E91002.97118 - AFT MOORING EQUIPMENT SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-09-01 | 2025-09-12 | 1 | Dea |  | JC160925 25148
| 2025-09-11 | W000305 | E91002.97124 - REPLENISHMENT AT SEA (RAS) SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-09-15 | 2025-09-30 | 1 | Dea |  | JC160925 25149
| 2025-09-11 | W000305 | E91002.97129 - DECOY LAUNCHER SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-09-01 | 2025-09-12 | 1 | Bambang |  | JC160925 25150
| 2025-09-11 | W000305 | E91002.97128 - TERPEDO LAUNCHER SYSTEM (TLS) SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-09-15 | 2025-09-30 | 1 | Bambang |  | JC160925 25151
2025-10-01
| 2025-10-03 | W000308 | E11002.03100 - STERN AND DOCK WELL BOTTOM CONSTRUCTION (AE~FR.59) | 1CK100 - Biro Desain Struktur Lambung | 2025-10-01 | 2025-10-10 | 1 | bu tin |  | JC031025 25887
| 2025-10-03 | W000308 | E11002.03200 - DOCK WELL CONSTRUCTION (AE~FR.59) | 1CK100 - Biro Desain Struktur Lambung | 2025-10-13 | 2025-10-24 | 1 | bu tin |  | JC031025 25888
| 2025-10-03 | W000308 | E11002.03300 - AFT CONSTRUCTION OF 03 DECK (AE~FR.109) | 1CK100 - Biro Desain Struktur Lambung | 2025-10-27 | 2025-10-31 | 1 | bu tin |  | JC031025 25889
| 2025-10-03 | W000305 | E11800.03120 - DECK REINFORCEMENT FOR LESHING PORT HELICOPTER | 1CK100 - Biro Desain Struktur Lambung | 2025-10-01 | 2025-10-06 | 1 | Agung |  | JC031025 25890
| 2025-10-03 | W000308 | E11800.03105 - SECONDARY GUN FOUNDATION | 1CK100 - Biro Desain Struktur Lambung | 2025-10-07 | 2025-10-14 | 1 | Agung |  | JC031025 25891
| 2025-10-03 | W000308 | E11800.03108 - DECOY LAUNCHER FOUNDATION | 1CK100 - Biro Desain Struktur Lambung | 2025-10-15 | 2025-10-22 | 1 | Agung |  | JC031025 25892
| 2025-10-03 | W000308 | 3D MODEL SOLIDWORK DECOY LAUNCHER FOUNDATION | 1CK100 - Biro Desain Struktur Lambung | 2025-10-23 | 2025-10-31 | 1 | Agung |  | JC031025 25898
| 2025-10-03 | W000305 | REVIEW WEB/BULKHEAD/DECK PENETRATION DUCTING 2 DECK; 1 DECK | 1CK100 - Biro Desain Struktur Lambung | 2025-10-01 | 2025-10-13 | 1 | Yuli K |  | JC031025 25899
| 2025-10-03 | W000305 | REVIEW WEB/BULKHEAD/DECK PENETRATION DUCTING 01 DECK; 02 DECK & 03 DECK | 1CK100 - Biro Desain Struktur Lambung | 2025-10-14 | 2025-10-23 | 1 | Yuli K |  | JC031025 25900
| 2025-10-03 | W000305 | E11800.03121 - DECK REINFORCEMENT AND FOUNDATION OF RAS POST | 1CK100 - Biro Desain Struktur Lambung | 2025-10-24 | 2025-10-31 | 1 | Yuli K |  | JC031025 25901
| 2025-10-03 | W000305 | E91002.97128 - TERPEDO LAUNCHER SYSTEM (TLS) SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-10-01 | 2025-10-31 | 1 | Bambang |  | JC071025 26016
| 2025-10-03 | W000305 | rev - E91002.97105 - AUXILIARY GUN FOUNDATION SUPPORTING STRUCTURE ANALYSIS REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-10-13 | 2025-10-17 | 1 | Bambang |  | JC071025 26017
| 2025-10-03 | W000305 | E91002.97123 - BOAT DAVIT SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-10-01 | 2025-10-31 | 1 | Pijar |  | JC071025 26018
| 2025-10-03 | W000305 | rev - E91002.97103 - SECONDARY GUN SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-10-06 | 2025-10-10 | 1 | Pijar |  | JC071025 26019
| 2025-10-03 | W000305 | E91002.97124 - REPLENISHMENT AT SEA (RAS) SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-10-01 | 2025-10-03 | 1 | Dea |  | JC071025 26066
| 2025-10-03 | W000308 | E91002.97101 - MAIN GUN SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-10-06 | 2025-10-31 | 1 | Dea |  | JC071025 26067
| 2025-10-07 | W000308 | REKAP ESTIMASI PLATE W308 | 1CK100 - Biro Desain Struktur Lambung | 2025-10-01 | 2025-10-31 | 1 | Nur Ainy |  | JC071025 26068
| 2025-10-07 | W000307 | E11002.03106 - 03 DECK FORE CONSTRUCTION FR 117 - Forward | 1CK100 - Biro Desain Struktur Lambung | 2025-10-08 | 2025-10-10 | 1 | Nur Ainy |  | JC071025 26069
| 2025-10-07 | W000307 | E11002.03111 - FUNNEL CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2025-10-13 | 2025-10-14 | 1 | Nur Ainy |  | JC071025 26070
| 2025-10-07 | W000307 | E11613.10100 - SHAFT BRACKETS | 1CK100 - Biro Desain Struktur Lambung | 2025-10-15 | 2025-10-17 | 1 | Nur Ainy |  | JC071025 26071
2025-11-01
| 2025-11-03 | W000308 | E11002.03108 - ACCOMODATION OF TOP DECK (WHELL HOUSE) | 1CK100 - Biro Desain Struktur Lambung | 2025-11-03 | 2025-11-04 | 1 | Kasmiatin | 16 | JC071125 27412
| 2025-11-03 | W000308 | E11002.03110 - DECKHOUSE CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2025-11-05 | 2025-11-06 | 1 | Kasmiatin | 16 | JC071125 27413
| 2025-11-03 | W000308 | E11002.03102 - MIDDLE CONSTRUCTION FOR MODIFICATION TURN TABLE | 1CK100 - Biro Desain Struktur Lambung | 2025-11-07 | 2025-11-09 | 1 | Kasmiatin | 8 | JC071125 27414
| 2025-11-03 | W000306 | LCU LD PHILIPINNES - STANDART DRAWING PRODUCTION | 1CK100 - Biro Desain Struktur Lambung | 2025-11-10 | 2025-11-12 | 1 | Kasmiatin | 24 | JC071125 27415
| 2025-11-03 | W000306 | LCU LD PHILIPINNES - SUMMARY SCANTLING | 1CK100 - Biro Desain Struktur Lambung | 2025-11-13 | 2025-11-16 | 1 | Kasmiatin | 24 | JC071125 27416
| 2025-11-03 | W000306 | LCU LD PHILIPINNES - CHECKER MODELING, CONSTRUCTION PROFILE AND DECK PLAN | 1CK100 - Biro Desain Struktur Lambung | 2025-11-17 | 2025-11-30 | 1 | Kasmiatin | 88 | JC071125 27417
| 2025-11-03 | W000304 | E11002.03105 - ACCOMODATION CONSTRUCTION - ADDITIONAL B0X NAVIGATION LIGHTS | 1CK100 - Biro Desain Struktur Lambung | 2025-11-03 | 2025-11-09 | 1 | Yuli Kustiadi | 48 | JC071125 27418
| 2025-11-03 | W000304 | E11001.03131 - TEMPORARY HOLE ACCESS FOR EQUIPMENT FIRE EXTINGUSHING SYSTEM | 1CK100 - Biro Desain Struktur Lambung | 2025-11-10 | 2025-11-16 | 1 | Yuli Kustiadi | 48 | JC071125 27419
| 2025-11-03 | W000304 | E11001.03127 - TEMPORARY HOLE ACCESS FOR LOADING CAPSTAN MOORING | 1CK100 - Biro Desain Struktur Lambung | 2025-11-17 | 2025-11-23 | 1 | Yuli Kustiadi | 48 | JC071125 27420
| 2025-11-03 | W000304 | REVIEW HOLE REQUEST FOR STEEL DOOR | 1CK100 - Biro Desain Struktur Lambung | 2025-11-24 | 2025-11-26 | 1 | Yuli Kustiadi | 24 | JC071125 27423
| 2025-11-03 | W000304 | REVIEW HOLE REQUEST FOR INSPECTION COVER | 1CK100 - Biro Desain Struktur Lambung | 2025-11-27 | 2025-11-30 | 1 | Yuli Kustiadi | 24 | JC071125 27424
| 2025-11-03 | W000306 | LCU LD PHILIPINNES - E91002.97200 - SCANTLING CALCULATION | 1CK100 - Biro Desain Struktur Lambung | 2025-11-03 | 2025-11-30 | 1 | Pijar Kasih Leksono Putri | 160 | JC071125 27425
| 2025-11-03 | W000304 | REV.1 - E91002.97112 - SHAFT BRACKET AND STERN TUBE SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-11-03 | 2025-11-16 | 1 | Dea Putri Ubaidah | 88 | JC071125 27426
| 2025-11-03 | W000308 | E91002.97101 - MODELING MAIN GUN SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-11-17 | 2025-11-30 | 1 | Dea Putri Ubaidah | 96 | JC071125 27427
| 2025-11-03 | W000306 | LCU LD PHILIPINNES - MODELING CADMATIC SHELL PLATE AND PROFILE | 1CK100 - Biro Desain Struktur Lambung | 2025-11-03 | 2025-11-09 | 1 | Agung Laksono | 48 | JC071125 27428
| 2025-11-03 | W000306 | LCU LD PHILIPINNES - MODELING CONSTRUCTION PROFILE AND STEEL PLAN | 1CK100 - Biro Desain Struktur Lambung | 2025-11-10 | 2025-11-30 | 1 | Agung Laksono | 144 | JC071125 27429
| 2025-11-03 | W000306 | REV - E11002.03108 - ACCOM CONSTRUCTION (TOP DECK) | 1CK100 - Biro Desain Struktur Lambung | 2025-11-03 | 2025-11-09 | 1 | Nur Ainy Suntoro | 40 | JC071125 27430
| 2025-11-03 | W000306 | REV - E11002.03107 - ACCOM CONSTRUCTION (04 DECK - 05 DECK) | 1CK100 - Biro Desain Struktur Lambung | 2025-11-10 | 2025-11-16 | 1 | Nur Ainy Suntoro | 40 | JC071125 27431
| 2025-11-03 | W000305 | REV. ESTIMASI W00305 PLATE | 1CK100 - Biro Desain Struktur Lambung | 2025-11-17 | 2025-11-19 | 1 | Nur Ainy Suntoro | 24 | JC071125 27435
| 2025-11-03 | W000308 | REV. ESTIMASI W00308 PLATE | 1CK100 - Biro Desain Struktur Lambung | 2025-11-20 | 2025-11-23 | 1 | Nur Ainy Suntoro | 24 | JC071125 27436
| 2025-11-03 | W000306 | RENESTING BLOCK 134 | 1CK100 - Biro Desain Struktur Lambung | 2025-11-24 | 2025-11-25 | 1 | Nur Ainy Suntoro | 16 | JC071125 27432
| 2025-11-03 | W000306 | RENESTING BLOCK 224 | 1CK100 - Biro Desain Struktur Lambung | 2025-11-26 | 2025-11-27 | 1 | Nur Ainy Suntoro | 16 | JC071125 27433
| 2025-11-03 | W000306 | RENESTING BLOCK 524 | 1CK100 - Biro Desain Struktur Lambung | 2025-11-28 | 2025-11-30 | 1 | Nur Ainy Suntoro | 16 | JC071125 27434
2025-12-01
| 2025-12-01 | W000306 | LCU LD PHILIPINNES - CHECKER CONSTRUCTION PROFILE AND DECK PLAN | 1CK100 - Biro Desain Struktur Lambung | 2025-12-01 | 2025-12-03 | 1 | Kasmiatin | 24 | JC031225 28559
| 2025-12-01 | W000306 | LCU LD PHILIPINNES - CHECKER MIDHIP SECTION | 1CK100 - Biro Desain Struktur Lambung | 2025-12-04 | 2025-12-06 | 1 | Kasmiatin | 24 | JC031225 28560
| 2025-12-01 | W000306 | LCU LD PHILIPINNES - E11001.03100 - MIDSHIP SECTION | 1CK100 - Biro Desain Struktur Lambung | 2025-12-01 | 2025-12-06 | 1 | Yuli Kustiadi | 48 | JC031225 28561
| 2025-12-01 | W000304 | ANALISA (FEM) PENETRATION DUCTING WEB/GIRDER DECK 3 | 1CK100 - Biro Desain Struktur Lambung | 2025-12-01 | 2025-12-06 | 1 | Pijar Kasih Leksono Putri | 48 | JC031225 28564
| 2025-12-01 | W000308 | ANALISA (FEA) MODIFICATION TWS AREA REPORT | 1CK100 - Biro Desain Struktur Lambung | 2025-12-01 | 2025-12-06 | 1 | Dea Putri Ubaidah | 48 | JC031225 28563
| 2025-12-01 | W000306 | LCU LD PHILIPINNES - E11001.03101 - CONSTRUCTION PROFILE AND DECK PLAN | 1CK100 - Biro Desain Struktur Lambung | 2025-12-01 | 2025-12-06 | 1 | Agung Laksono | 48 | JC031225 28562
| 2025-12-01 | W000304 | NESTING BLOCK 641 | 1CK100 - Biro Desain Struktur Lambung | 2025-12-01 | 2025-12-03 | 1 | Nur Ainy Suntoro | 24 | JC031225 28565
| 2025-12-01 | W000304 | NESTING BLOCK 503 | 1CK100 - Biro Desain Struktur Lambung | 2025-12-04 | 2025-12-06 | 1 | Nur Ainy Suntoro | 24 | JC031225 28566
| 2025-12-08 | W000306 | LCU LD PHILIPINNES - CHECKER FRAME AND BULKHEAD | 1CK100 - Biro Desain Struktur Lambung | 2025-12-08 | 2025-12-13 | 1 | Kasmiatin | 48 | JC081225 28796
| 2025-12-08 | R22FPBXA | ENGINE FOUNDATION DRAWING | 1CK100 - Biro Desain Struktur Lambung | 2025-12-08 | 2025-12-13 | 1 | Yuli Kustiadi | 48 | JC081225 28835
| 2025-12-08 | W000304 | ANALISA (FEM) PENETRATION DUCTING WEB/GIRDER DECK 2 | 1CK100 - Biro Desain Struktur Lambung | 2025-12-08 | 2025-12-13 | 1 | Pijar Kasih Leksono Putri | 48 | JC081225 28814
| 2025-12-08 | W000308 | E11800.03102 - MAIN GUN 76 MM FOUNDATION GEOMETRY MODEL | 1CK100 - Biro Desain Struktur Lambung | 2025-12-08 | 2025-12-13 | 1 | Dea Putri Ubaidah | 48 | JC081225 28819
| 2025-12-08 | W000306 | LCU LD PHILIPINNES - E11201.03101 - TYPICAL FRAME AND BULKHEAD SECTION | 1CK100 - Biro Desain Struktur Lambung | 2025-12-08 | 2025-12-13 | 1 | Agung Laksono | 48 | JC081225 28825
| 2025-12-08 | W000304 | RENESTING BLOCK 503 | 1CK100 - Biro Desain Struktur Lambung | 2025-12-08 | 2025-12-09 | 1 | Nur Ainy Suntoro | 16 | JC081225 28830
| 2025-12-08 | W000304 | NESTING PLATE 631 | 1CK100 - Biro Desain Struktur Lambung | 2025-12-10 | 2025-12-11 | 1 | Nur Ainy Suntoro | 16 | JC081225 28831
| 2025-12-08 | W000306 | REKAP MATERIAL LIST 306 | 1CK100 - Biro Desain Struktur Lambung | 2025-12-12 | 2025-12-12 | 1 | Nur Ainy Suntoro | 8 | JC081225 28837
| 2025-12-15 | W000306 | LCU LD PHILIPINNES - CHECKER TYPICAL FRAME AND BULKHEAD SECTION (ENGINE ROOM AREA) | 1CK100 - Biro Desain Struktur Lambung | 2025-12-15 | 2025-12-15 | 1 | Kasmiatin | 8 | JC151225 29159
| 2025-12-15 | W000306 | LCU LD PHILIPINNES - CHECKER WHELL HOUSE CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2025-12-16 | 2025-12-19 | 1 | Kasmiatin | 32 | JC151225 29160
| 2025-12-15 | W000304 | E10500.03100 - DOCKING PLAN | 1CK100 - Biro Desain Struktur Lambung | 2025-12-15 | 2025-12-17 | 1 | Yuli K | 24 | JC151225 29161
| 2025-12-15 | W000304 | REVIEW WEB/BULKHEAD/DECK PENETRATION DUCTING AND CABLE | 1CK100 - Biro Desain Struktur Lambung | 2025-12-18 | 2025-12-19 | 1 | Yuli K | 16 | JC151225 29162
| 2025-12-15 | W000304 | ANALISA (FEM) PENETRATION DUCTING WEB/GIRDER BLOCK 433 | 1CK100 - Biro Desain Struktur Lambung | 2025-12-15 | 2025-12-17 | 1 | Pijar Kasih Leksono Putri | 24 | JC151225 29163
| 2025-12-15 | W000304 | ANALISA (FEM) PENETRATION DUCTING WEB/GIRDER 01 DECK | 1CK100 - Biro Desain Struktur Lambung | 2025-12-18 | 2025-12-19 | 1 | Pijar Kasih Leksono Putri | 16 | JC151225 29164
| 2025-12-15 | W000308 | E11800.03102 - MAIN GUN 76 MM FOUNDATION MODEL PREPARATION | 1CK100 - Biro Desain Struktur Lambung | 2025-12-15 | 2025-12-20 | 1 | Dea Putri Ubaidah | 48 | JC161225 29167
| 2025-12-15 | W000306 | LCU LD PHILIPINNES - UPDATE SURFACE AND SHELL | 1CK100 - Biro Desain Struktur Lambung | 2025-12-15 | 2025-12-16 | 1 | Agung Laksono | 16 | JC161225 29168
| 2025-12-15 | W000306 | LCU LD PHILIPINNES - UPDATE CONSTRUCTION PROFILE (WATER JET AREA) | 1CK100 - Biro Desain Struktur Lambung | 2025-12-17 | 2025-12-17 | 1 | Agung Laksono | 8 | JC161225 29169
| 2025-12-15 | W000306 | LCU LD PHILIPINNES - UPDATE TYPICAL FRAME AND BULKHEAD SECTION (WATER JET AREA) | 1CK100 - Biro Desain Struktur Lambung | 2025-12-18 | 2025-12-19 | 1 | Agung Laksono | 16 | JC161225 29171
| 2025-12-15 | W000304 | NESTING PLATE 244 | 1CK100 - Biro Desain Struktur Lambung | 2025-12-15 | 2025-12-15 | 1 | Nur Ainy Suntoro | 8 | JC161225 29172
| 2025-12-15 | W000304 | NESTING PLATE 325 | 1CK100 - Biro Desain Struktur Lambung | 2025-12-16 | 2025-12-17 | 1 | Nur Ainy Suntoro | 16 | JC161225 29174
| 2025-12-15 | W000304 | NESTING PLATE 333 | 1CK100 - Biro Desain Struktur Lambung | 2025-12-18 | 2025-12-19 | 1 | Nur Ainy Suntoro | 16 | JC161225 29175
| 2025-12-22 | W000304 | REVIEW DRAWING HELICOPTER HANGGAR CONSTRUCTION (HELI HANGGAR DOOR) | 1CK100 - Biro Desain Struktur Lambung | 2025-12-22 | 2025-12-23 | 1 | Yuli K | 16 | JC221225 29434
| 2025-12-22 | W000304 | E11001.03136 - TEMPORARY HOLE ACCESS FOR BRIDGE CONTROL CONSOLE | 1CK100 - Biro Desain Struktur Lambung | 2025-12-24 | 2025-12-26 | 1 | Yuli K | 24 | JC221225 29435
| 2025-12-22 | W000304 | ANALISA (FEM) PENETRATION DUCTING WEB/GIRDER BLOCK 531 | 1CK100 - Biro Desain Struktur Lambung | 2025-12-22 | 2025-12-26 | 1 | Pijar Kasih Leksono Putri | 40 | JC221225 29436
| 2025-12-22 | W000308 | E11800.03102 - MAIN GUN 76 MM FOUNDATION (BLAST 3D MODEL) | 1CK100 - Biro Desain Struktur Lambung | 2025-12-22 | 2025-12-26 | 1 | Dea Putri Ubaidah | 40 | JC221225 29438
| 2025-12-22 | W000306 | LCU LD PHILIPINNES -E11002.03110 WHEEL HOUSE CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2025-12-22 | 2025-12-26 | 1 | Agung Laksono | 40 | JC221225 29439
| 2025-12-22 | W000304 | NESTING PLATE BLOCK 514, 115, 114 | 1CK100 - Biro Desain Struktur Lambung | 2025-12-22 | 2025-12-26 | 1 | Nur Ainy Suntoro | 40 | JC221225 29437
| 2025-12-29 | W000306 | LCU LD PHILIPINNES - REV.1 E11001.03100 MIDSHIP SECTION | 1CK100 - Biro Desain Struktur Lambung | 2025-12-29 | 2025-12-31 | 1 | Yuli Kustiadi | 24 | JC291225 29626
| 2025-12-29 | W000308 | E11800.03102 - MAIN GUN 76 MM FOUNDATION (DECK BLAST ASSEMBELY) | 1CK100 - Biro Desain Struktur Lambung | 2025-12-29 | 2026-01-02 | 1 | Dea Putri Ubaidah | 32 | JC291225 29628
| 2025-12-29 | W000305 | NESTING PLATE BLOCK 632, 631, 511 | 1CK100 - Biro Desain Struktur Lambung | 2025-12-29 | 2026-01-02 | 1 | Nur Ainy Suntoro | 32 | JC291225 29629
2026-01-01
| 2026-01-02 | W000306 | LCU LD PHILIPINNES - REV E10742.03101 WELDING DETAIL & PROCEDURE | 1CK100 - Biro Desain Struktur Lambung | 2026-01-02 | 2026-01-05 | 1 | Yuli Kustiadi | 16 | JC060126 29990
| 2026-01-05 | R22PPCXA | SURVEY KONSTRUKSI SSM ATMACA KRI PARCHIM | 1CK100 - Biro Desain Struktur Lambung | 2026-01-06 | 2026-01-10 | 1 | Yuli Kustiadi | 40 | JC060126 30017
| 2026-01-05 | W000308 | UPDATE E11002.03107 ACCOMODATION CONSTRUCTION OF 04 - 05 DECK | 1CK100 - Biro Desain Struktur Lambung | 2026-01-05 | 2026-01-06 | 1 | Kasmiatin | 16 | JC060126 29992
| 2026-01-05 | W000308 | UPDATE E11002.03110 DECK HOUSE CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-01-07 | 2026-01-08 | 1 | Kasmiatin | 16 | JC060126 29993
| 2026-01-05 | W000304 | ANALISA (FEM) PENETRATION DUCTING WEB/GIRDER 2 DECK | 1CK100 - Biro Desain Struktur Lambung | 2026-01-02 | 2026-01-09 | 1 | Pijar Kasih Leksono Putri | 48 | JC060126 29994
| 2026-01-05 | W000308 | E11800.03102 - MAIN GUN 76 MM FOUNDATION (BOUNDARY CONDITION) | 1CK100 - Biro Desain Struktur Lambung | 2026-01-05 | 2026-01-10 | 1 | Dea Putri Ubaidah | 48 | JC060126 29997
| 2026-01-05 | W000304 | E11800.03123 - WING CONSTRUCTION ON FORE MAST | 1CK100 - Biro Desain Struktur Lambung | 2026-01-05 | 2026-01-10 | 1 | Agung Laksono | 48 | JC060126 29995
| 2026-01-05 | W000308 | REV ESTIMASI MATERIAL PLATE DAN PROFILE | 1CK100 - Biro Desain Struktur Lambung | 2026-01-05 | 2026-01-06 | 1 | Nur Ainy Suntoro | 16 | JC060126 29998
| 2026-01-05 | W000305 | REV NESTING BLOCK 222, 232, 502, 632 | 1CK100 - Biro Desain Struktur Lambung | 2026-01-07 | 2026-01-09 | 1 | Nur Ainy Suntoro | 24 | JC060126 29996
| 2026-01-09 | W000308 | REV E11002.03101 - ENGINE ROOM CONSTRUCTION OF BOTTOM - MAIN DECK (FR.60 - FR109) | 1CK100 - Biro Desain Struktur Lambung | 2026-01-09 | 2026-01-09 | 1 | Kasmiatin | 8 | JC090126 30143
| 2026-01-09 | W000304 | ANALISA (FEM) PENETRATION DUCTING WEB/GIRDER BLOCK 234, 244 | 1CK100 - Biro Desain Struktur Lambung | 2026-01-10 | 2026-01-10 | 1 | Pijar Kasih Leksono Putri | 8 | JC090126 30144
| 2026-01-12 | W000308 | MODIFICATION TWS - E11001.03101 - CONS PRO 02 AND 03 DECK | 1CK100 - Biro Desain Struktur Lambung | 2026-01-12 | 2026-01-16 | 1 | Kasmiatin | 32 | JC130126 30327
| 2026-01-12 | W000306 | TEMPORARY HOLE ACCESS FOR EQUIPMENT LO PURIFIER | 1CK100 - Biro Desain Struktur Lambung | 2026-01-12 | 2026-01-15 | 1 | Yuli Kustiadi | 32 | JC130126 30331
| 2026-01-12 | W000304 | ANALISA (FEM) PENETRATION DUCTING WEB/GIRDER 2 DECK BLOCK 433 | 1CK100 - Biro Desain Struktur Lambung | 2026-01-12 | 2026-01-16 | 1 | Pijar Kasih Leksono Putri | 32 | JC130126 30330
| 2026-01-12 | W000308 | E11800.03102 - MAIN GUN 76 MM FOUNDATION (MESHING) | 1CK100 - Biro Desain Struktur Lambung | 2026-01-12 | 2026-01-15 | 1 | Dea Putri Ubaidah | 32 | JC130126 30328
| 2026-01-12 | R22PPCXA | DRAWING SSM FOUNDATION AND DECK REINFORCEMENT | 1CK100 - Biro Desain Struktur Lambung | 2026-01-12 | 2026-01-15 | 1 | Agung Laksono | 32 | JC130126 30340 | JC Belum Masih Draft
| 2026-01-12 | W000305 | NESTING BLOCK 414, 515 | 1CK100 - Biro Desain Struktur Lambung | 2026-01-12 | 2026-01-13 | 1 | Nur Ainy Suntoro | 16 | JC130126 30342
| 2026-01-12 | W000306 | NESTING BLOCK 121 | 1CK100 - Biro Desain Struktur Lambung | 2026-01-14 | 2026-01-15 | 1 | Nur Ainy Suntoro | 16 | JC130126 30343
| 2026-01-19 | W000306 | LCU LD PHILIPINNES - E10500.03100 DOCKING PLAN | 1CK100 - Biro Desain Struktur Lambung | 2026-01-19 | 2026-01-20 | 1 | Yuli Kustiadi | 24 | JC200126 30526
| 2026-01-19 | W000308 | E21170.01100 - REKAP MATERIAL ESTIMATION (PLATE) | 1CK100 - Biro Desain Struktur Lambung | 2026-01-19 | 2026-01-20 | 1 | Nur Ainy Suntoro | 24 | JC200126 30527
| 2026-01-19 | W000306 | LCU LD PHILIPINNES - UPDATE CONSTRUCTION PROFILE AND DECK PLAN | 1CK100 - Biro Desain Struktur Lambung | 2026-01-19 | 2026-01-20 | 1 | Kasmiatin | 16 | JC200126 30558
| 2026-01-19 | W000308 | HANGGAR DOOR MACHINE - ACCOMODATION CONSTRUCTION 04-05 DECK | 1CK100 - Biro Desain Struktur Lambung | 2026-01-21 | 2026-01-23 | 1 | Kasmiatin | 24 | JC200126 30560
| 2026-01-19 | W000304 | UPDATE ANALISA (FEM) PENETRATION DUCTING WEB/GIRDER 1 DECK | 1CK100 - Biro Desain Struktur Lambung | 2026-01-19 | 2026-01-24 | 1 | Pijar Kasih Leksono Putri | 48 | JC200126 30562
| 2026-01-19 | W000308 | E11800.03102 - MAIN GUN 76 MM FOUNDATION (RUNNING LOAD CASE 1) | 1CK100 - Biro Desain Struktur Lambung | 2026-01-19 | 2026-01-24 | 1 | Dea Putri Ubaidah | 48 | JC200126 30561
| 2026-01-19 | W000306 | LCU LD PHILIPINNES -UPDATE SURFACE SHELL | 1CK100 - Biro Desain Struktur Lambung | 2026-01-19 | 2026-01-23 | 1 | Agung Laksono | 40 | JC200126 30559
| 2026-01-21 | W000304 | UPDATE WEB/BULKHEAD/DECK PENETRATION DUCTING (ADD SPIGOT) | 1CK100 - Biro Desain Struktur Lambung | 2026-01-21 | 2026-01-23 | 1 | Yuli Kustiadi | 24 | JC220126 30615
| 2026-01-21 | W000305 | UPDATE NESTING PLATE BLOCK 512,652,511 | 1CK100 - Biro Desain Struktur Lambung | 2026-01-21 | 2026-01-23 | 1 | Nur Ainy Suntoro | 24 | JC220126 30616
| 2026-01-26 | W000308 | UPDATE - E11001.03101 CONSTRUCTION PROFILE AND DECK | 1CK100 - Biro Desain Struktur Lambung | 2026-01-26 | 2026-01-27 | 1 | Kasmiatin | 16 | JC280126 30832
| 2026-01-26 | W000308 | UPDATE - E11002.03108 ACCOMODATION OF DECK (WHELL HOUSE) | 1CK100 - Biro Desain Struktur Lambung | 2026-01-28 | 2026-01-28 | 1 | Kasmiatin | 8 | JC280126 30833
| 2026-01-26 | W000308 | UPDATE - E11002.03110 DECKHOUSE CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-01-29 | 2026-01-30 | 1 | Kasmiatin | 16 | JC280126 30835
| 2026-01-26 | W000306 | LCU LD PHILIPINNES - UPDATE CADMATIC BOW RAMP CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-01-26 | 2026-01-31 | 1 | Yuli Kustiadi | 48 | JC280126 30838
| 2026-01-26 | W000304 | REPORT ANALISA (FEM) PENETRATION DUCTING WEB/GIRDER DECK 1 | 1CK100 - Biro Desain Struktur Lambung | 2026-01-26 | 2026-01-30 | 1 | Pijar Kasih Leksono Putri | 40 | JC280126 30843
| 2026-01-26 | W000308 | E11800.03102 - MAIN GUN 76 MM FOUNDATION (RUNNING GUN BLAST) | 1CK100 - Biro Desain Struktur Lambung | 2026-01-26 | 2026-01-31 | 1 | Dea Putri Ubaidah | 48 | JC280126 30837
| 2026-01-26 | W000304 | LCU LD PHILIPINNES - UPDATE CADMATIC ENGINE BAD CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-01-26 | 2026-01-30 | 1 | Agung Laksono | 40 | JC280126 30851
| 2026-01-26 | W000306 | NESTING PLATE BLOCK 233, 234 | 1CK100 - Biro Desain Struktur Lambung | 2026-01-26 | 2026-01-28 | 1 | Nur Ainy Suntoro | 24 | JC280126 30840
| 2026-01-26 | W000304 | NESTING PLATE BLOCK 651, 652 | 1CK100 - Biro Desain Struktur Lambung | 2026-01-29 | 2026-01-30 | 1 | Nur Ainy Suntoro | 24 | JC290126 30861
| 2026-01-29 | W000306 | LCU LD PHILIPINNES - UPDATE CONSTRUCTION PROFILE AND DECK PLAN | 1CK100 - Biro Desain Struktur Lambung | 2026-01-12 | 2026-01-15 | 1 | Agung Laksono | 32 | JC290126 30860
2026-02-01
| 2026-02-02 | W000306 | LCU LD PHILIPINNES - CHECKER E15755.03101 BOW RAMP CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-02-02 | 2026-02-03 | 1 | Kasmiatin | 16 | JC050226 31257
| 2026-02-02 | W000308 | HANGGAR DOOR MACHINE - UPDATE ACCOMODATION CONSTRUCTION 04-05 DECK | 1CK100 - Biro Desain Struktur Lambung | 2026-02-04 | 2026-02-04 | 1 | Kasmiatin | 8 | JC050226 31258
| 2026-02-02 | W000306 | LCU LD PHILIPINNES - CHECKER REV1 E11001.03101 CONSTRUCTION PROFILE & DECK PLAN | 1CK100 - Biro Desain Struktur Lambung | 2026-02-05 | 2026-02-05 | 1 | Kasmiatin | 8 | JC050226 31259
| 2026-02-02 | W000308 | TWS UPDATE - AFT CONSTRUCTION 03 DECK | 1CK100 - Biro Desain Struktur Lambung | 2026-02-06 | 2026-02-06 | 1 | Kasmiatin | 8 | JC050226 31260
| 2026-02-02 | R22FPBXA | DRAWING MAIN ENGINE FOUNDATION REINFORCEMENT | 1CK100 - Biro Desain Struktur Lambung | 2026-02-02 | 2026-02-14 | 1 | Yuli Kustiadi | 96 | JC260226 32185 | No JC belum Dibuatkan
| 2026-02-02 | W000304 | CALCULATION DESIGN LOAD OF MIDDLE MASS SUPPORT STRUCTURE | 1CK100 - Biro Desain Struktur Lambung | 2026-02-02 | 2026-02-04 | 1 | Pijar Kasih Leksono Putri | 24 | JC050226 31261
| 2026-02-02 | W000304 | CALCULATION DESIGN LOAD OF AFT MASS SUPPORT STRUCTURE | 1CK100 - Biro Desain Struktur Lambung | 2026-02-04 | 2026-02-06 | 1 | Pijar Kasih Leksono Putri | 24 | JC060226 31327
| 2026-02-02 | W000308 | E11800.03102 - MAIN GUN 76 MM FOUNDATION (RUNNING ALL LOAD CASE FIRING LOAD) | 1CK100 - Biro Desain Struktur Lambung | 2026-02-02 | 2026-02-07 | 1 | Dea Putri Ubaidah | 48 | JC050226 31263
| 2026-02-02 | W000306 | LCU LD PHILIPINNES - REV1 E11001.03101 CONSTRUCTION PROFILE & DECK PLAN | 1CK100 - Biro Desain Struktur Lambung | 2026-02-02 | 2026-02-07 | 1 | Agung Laksono | 48 | JC050226 31264
| 2026-02-02 | W000308 | ESTIMASI MATERIAL (PLATE) | 1CK100 - Biro Desain Struktur Lambung | 2026-02-02 | 2026-02-04 | 1 | Nur Ainy Suntoro | 24 | JC050226 31265
| 2026-02-02 | W000306 | ESTIMASI MATERIAL (PLATE) | 1CK100 - Biro Desain Struktur Lambung | 2026-02-05 | 2026-02-06 | 1 | Nur Ainy Suntoro | 16 | JC050226 31266
| 2026-02-09 | W000308 | TWS UPDATE - E11002.03200 DOCK WELL CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-02-09 | 2026-02-13 | 1 | Kasmiatin | 32 | JC100226 31467
| 2026-02-09 | W000306 | LCU LD PHILIPINNES - CHECKER CONSTRUCTION PROFILE & DECK PLAN R1 | 1CK100 - Biro Desain Struktur Lambung | 2026-02-12 | 2026-02-12 | 1 | Kasmiatin | 8 | JC100226 31470
| 2026-02-09 | W000306 | REV1 - E11613.10100 - SHAFT BRACKET | 1CK100 - Biro Desain Struktur Lambung | 2026-02-10 | 2026-02-10 | 1 | Yuli Kustiadi | 8 | JC100226 31471
| 2026-02-09 | W000304 | REV1 - E11800.03122 - REINFORCEMENT OF RAS STRONG POINT & CAPSTAN | 1CK100 - Biro Desain Struktur Lambung | 2026-02-11 | 2026-02-11 | 1 | Yuli Kustiadi | 8 | JC110226 31502
| 2026-02-09 | W000304 | REV2 - E90702.95032 - SEAT POLICIES DOCUMENT | 1CK100 - Biro Desain Struktur Lambung | 2026-02-09 | 2026-02-13 | 1 | Pijar Kasih Leksono Putri | 40 | JC110226 31503
| 2026-02-09 | W000308 | E11800.03102 - MAIN GUN 76 MM FOUNDATION (REPORT GUN BLAST) | 1CK100 - Biro Desain Struktur Lambung | 2026-02-09 | 2026-02-14 | 1 | Dea Putri Ubaidah | 48 | JC100226 31468
| 2026-02-09 | W000306 | YARD PLAN - E11800.03102 - GUN FOUNDATION | 1CK100 - Biro Desain Struktur Lambung | 2026-02-09 | 2026-02-11 | 1 | Agung Laksono | 24 | JC100226 31474
| 2026-02-09 | W000308 | GEOMETRY MODELING - E91002.97100 - DECOY FOUNDATION STRUCTURE | 1CK100 - Biro Desain Struktur Lambung | 2026-02-12 | 2026-02-14 | 1 | Agung Laksono | 24 | JC100226 31469
| 2026-02-09 | W000305 | NESTING PLATE - BLOCK 641, 541, 511 | 1CK100 - Biro Desain Struktur Lambung | 2026-02-09 | 2026-02-11 | 1 | Nur Ainy Suntoro | 24 | JC100226 31475
| 2026-02-09 | W000307 | ESTIMASI MATERIAL (PLATE) | 1CK100 - Biro Desain Struktur Lambung | 2026-02-12 | 2026-02-13 | 1 | Nur Ainy Suntoro | 16 | JC100226 31476
| 2026-02-18 | W000308 | TWS UPDATE - STEEL PLAN AND YARD PLAN UPDATE | 1CK100 - Biro Desain Struktur Lambung | 2026-02-18 | 2026-02-20 | 1 | Kasmiatin | 21 | JC190226 31845 | JC190226 31846 | normal hours | ramadhan hours
| 2026-02-18 | W000304 | REQUEST HOLE FOR BOX PANNEL DEGAUSSINGOU | 1CK100 - Biro Desain Struktur Lambung | 2026-02-18 | 2026-02-20 | 1 | Yuli Kustiadi | 21 | JC190226 31847 | JC190226 31848
| 2026-02-18 | W000304 | REV1 - E91002.97127 - BOAT DAVIT SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2026-02-18 | 2026-02-20 | 1 | Pijar Kasih Leksono Putri | 21 | JC190226 31849 | JC190226 31850
| 2026-02-18 | W000308 | E11800.03102 - MAIN GUN 76 MM FOUNDATION (REPORT GUN BLAST LC5-10) | 1CK100 - Biro Desain Struktur Lambung | 2026-02-18 | 2026-02-20 | 1 | Dea Putri Ubaidah | 21 | JC190226 31852 | JC190226 31853
| 2026-02-18 | W000306 | LCU LD PHILIPINNES - Lashing Padaye | 1CK100 - Biro Desain Struktur Lambung | 2026-02-18 | 2026-02-20 | 1 | Agung Laksono | 21 | JC190226 31854 | JC190226 31855
| 2026-02-18 | W000304 | SUMMARY OF ESTIMATION PROFILE & PLATE | 1CK100 - Biro Desain Struktur Lambung | 2026-02-18 | 2026-02-20 | 1 | Nur Ainy Suntoro | 21 | JC190226 31856 | JC190226 31857
| 2026-02-23 | W000308 | REV3 AFT CONSTRUCTION OF 03 DECK - UPDATE | 1CK100 - Biro Desain Struktur Lambung | 2026-02-23 | 2026-02-24 | 1 | Kasmiatin | 14 | JC240226 32090
| 2026-02-23 | W000308 | REV1 AFT MAST CONSTRUCTION - UPDATE | 1CK100 - Biro Desain Struktur Lambung | 2026-02-25 | 2026-02-26 | 1 | Kasmiatin | 14 | JC240226 32091
| 2026-02-23 | W000308 | REV1 ACCOMODATION OF TOP DECK (WHEEL HOUSE) - UPDATE | 1CK100 - Biro Desain Struktur Lambung | 2026-02-27 | 2026-02-27 | 1 | Kasmiatin | 8 | JC240226 32092
| 2026-02-23 | W000304 | E11001.03132 - TEMPORARY HOLES DETAIL - MECHANICAL EXHAUST ON 2 DECK PS | 1CK100 - Biro Desain Struktur Lambung | 2026-02-23 | 2026-02-27 | 1 | Yuli Kustiadi | 14 | JC240226 32093
| 2026-02-23 | W000304 | E11001.03133 - TEMPORARY HOLES DETAIL - MECHANICAL EXHAUST ON 2 DECK SB | 1CK100 - Biro Desain Struktur Lambung | 2026-02-23 | 2026-02-27 | 1 | Yuli Kustiadi | 14 | JC240226 32094
| 2026-02-23 | W000304 | E11001.03134 - TEMPORARY HOLES DETAIL - MECHANICAL SUPPLY ON 1 DECK PS | 1CK100 - Biro Desain Struktur Lambung | 2026-02-23 | 2026-02-27 | 1 | Yuli Kustiadi | 7 | JC240226 32095
| 2026-02-23 | W000304 | UPDATE - REV2 - E90702.95032 - SEAT POLICIES DOCUMENT | 1CK100 - Biro Desain Struktur Lambung | 2026-02-23 | 2026-02-27 | 1 | Pijar Kasih Leksono Putri | 14 | JC240226 32079
| 2026-02-23 | W000304 | UPDATE - REV1 - E91002.97127 - BOAT DAVIT SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2026-02-23 | 2026-02-27 | 1 | Pijar Kasih Leksono Putri | 21 | JC240226 32080
| 2026-02-23 | W000308 | E11800.03102 - MAIN GUN 76 MM FOUNDATION (REPORT GUN BLAST LC10-20) | 1CK100 - Biro Desain Struktur Lambung | 2026-02-23 | 2026-02-27 | 1 | Dea Putri Ubaidah | 35 | JC240226 32086
| 2026-02-23 | W000306 | UPDATE - LCU LD PHILIPINNES - REV1 E11201.03101 TYPICAL FRAME & BULKHEAD SECTION | 1CK100 - Biro Desain Struktur Lambung | 2026-02-23 | 2026-02-27 | 1 | Agung Laksono | 35 | JC240226 32089
| 2026-02-23 | W000305 | Nesting Plate Blok 422, 212, 224 | 1CK100 - Biro Desain Struktur Lambung | 2026-02-23 | 2026-02-27 | 1 | Nur Ainy Suntoro | 35 | JC260226 32186
2026-03-01
| 2026-03-02 | W000308 | TWS UPDATE - AFT CONSTRUCTION 03 DECK | 1CK100 - Biro Desain Struktur Lambung | 2026-03-02 | 2026-03-06 | 1 | Kasmiatin | 28 | JC060326 32554
| 2026-03-02 | W000306 | CHECKER - REV1 - E15755.03101 BOW RAMPS CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-03-02 | 2026-03-06 | 1 | Kasmiatin | 7 | JC060326 32555
| 2026-03-02 | W000308 | REV2 - E11800.03103 - MAIN ENGINE FOUNDATION | 1CK100 - Biro Desain Struktur Lambung | 2026-03-02 | 2026-03-06 | 1 | Yuli Kustiadi | 21 | JC060326 32563
| 2026-03-02 | W000304 | REV1 - E11001.03133 - TEMPORARY HOLES DETAIL - MECHANICAL EXHAUST ON 2 DECK SB | 1CK100 - Biro Desain Struktur Lambung | 2026-03-02 | 2026-03-06 | 1 | Yuli Kustiadi | 14 | JC060326 32559
| 2026-03-02 | W000304 | REV1 - CALCULATION OF BOAT DAVIT SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2026-03-02 | 2026-03-06 | 1 | Pijar Kasih Leksono Putri | 20 | JC060326 32560
| 2026-03-02 | W000306 | CALCULATION OF MAIN GUN FOUNDATION ANAYLSIS | 1CK100 - Biro Desain Struktur Lambung | 2026-03-02 | 2026-03-06 | 1 | Pijar Kasih Leksono Putri | 20 | JC060326 32556
| 2026-03-02 | W000308 | E11800.03102 - MAIN GUN 76 MM FOUNDATION (REPORT GUN BLAST LC25) | 1CK100 - Biro Desain Struktur Lambung | 2026-03-02 | 2026-03-06 | 1 | Dea Putri Ubaidah | 35 | JC060326 32564
| 2026-03-02 | W000306 | REV1 - LCU LD PHILIPINNES - E11201.03101 TYPICAL FRAME & BULKHEAD SECTION | 1CK100 - Biro Desain Struktur Lambung | 2026-03-02 | 2026-03-06 | 1 | Agung Laksono | 14 | JC060326 32557
| 2026-03-02 | W000304 | REV2 - E11002.03107 - MAST CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-03-02 | 2026-03-06 | 1 | Agung Laksono | 21 | JC060326 32561
| 2026-03-02 | W000304 | UPDATE NESTING PLATE - PROJECT FRIGATE | 1CK100 - Biro Desain Struktur Lambung | 2026-03-02 | 2026-03-06 | 1 | Nur Ainy Suntoro | 20 | JC060326 32562
| 2026-03-02 | W000306 | UPDATE NESTING PLATE - PROJECT LP PHILIPPINES | 1CK100 - Biro Desain Struktur Lambung | 2026-03-02 | 2026-03-06 | 1 | Nur Ainy Suntoro | 20 | JC060326 32558
| 2026-03-09 | W000308 | TWS UPDATE - DOCK WELL CONSTRUCTION (02 DECK) | 1CK100 - Biro Desain Struktur Lambung | 2026-03-09 | 2026-03-13 | 1 | Kasmiatin | 21 | JC130326 32800
| 2026-03-09 | W000308 | UPDATE - E11002.03110 - DECK HOUSE COUNSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-03-09 | 2026-03-13 | 1 | Kasmiatin | 14 | JC130326 32801
| 2026-03-09 | W000306 | REV1 - E11613.10100 - SHAFT BRACKETS | 1CK100 - Biro Desain Struktur Lambung | 2026-03-09 | 2026-03-13 | 1 | Yuli Kustiadi | 14 | JC120326 32785
| 2026-03-09 | W000306 | REV2 - E11002.03100 - AFT CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-03-09 | 2026-03-13 | 1 | Yuli Kustiadi | 7 | JC120326 32786
| 2026-03-09 | W000306 | REV2 - E11002.03110 - DECK HOUSE CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-03-09 | 2026-03-13 | 1 | Yuli Kustiadi | 14 | JC120326 32787
| 2026-03-09 | W000304 | REV.4 - E91002.97102 - MAIN GUN FOUNDATION (GUN BLAST LOAD) | 1CK100 - Biro Desain Struktur Lambung | 2026-03-09 | 2026-03-13 | 1 | Pijar Kasih Leksono Putri | 35 | JC120326 32789
| 2026-03-09 | W000308 | E91002.97107 - DECOY LAUNCHER SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2026-03-09 | 2026-03-13 | 1 | Dea Putri Ubaidah | 35 | JC120326 32791
| 2026-03-09 | W000306 | UPDATE - WING OF MAST CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-03-09 | 2026-03-13 | 1 | Agung Laksono | 35 | JC120326 32788
| 2026-03-09 | W000304 | UPDATE NESTING PLATE - MODULE 1, 4 | 1CK100 - Biro Desain Struktur Lambung | 2026-03-09 | 2026-03-13 | 1 | Nur Ainy Suntoro | 21 | JC120326 32790
| 2026-03-09 | W000308 | UPDATE NESTING PLATE - MODULE 5 | 1CK100 - Biro Desain Struktur Lambung | 2026-03-09 | 2026-03-13 | 1 | Nur Ainy Suntoro | 14 | JC120326 32792
| 2026-03-16 | W000308 | UPDATE - DECK HOUSE COUNSTRUCTION, MIDDLE 03 DECK, MIDDLE TANK 02 | 1CK100 - Biro Desain Struktur Lambung | 2026-03-16 | 2026-03-31 | 1 | Kasmiatin | 56 | JC300326 33348 | 16-17 MARET | JC300326 33349 | 25-31 MARET 26
| 2026-03-16 | W000306 | TEMPORARY HOLE DETAIL AHU NO. 4 | 1CK100 - Biro Desain Struktur Lambung | 2026-03-16 | 2026-03-31 | 1 | Yuli Kustiadi | 16 | JC300326 33360 | 16-17 MARET | JC300326 33361 | 25-31 MARET 26
| 2026-03-16 | W000306 | TEMPORARY HOLE DETAIL HELI REFUELING SYSTEM (P/S) | 1CK100 - Biro Desain Struktur Lambung | 2026-03-16 | 2026-03-31 | 1 | Yuli Kustiadi | 40 | JC300326 33363 | 16-17 MARET | JC300326 33362 | 25-31 MARET 26
| 2026-03-16 | W000 | PINISI - CALCULATION SCANTLING CONTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-03-16 | 2026-03-31 | 1 | Pijar Kasih Leksono Putri | 40 | JC300326 33383 | 16-17 MARET | JC300326 33384 | 25-31 MARET 26
| 2026-03-16 | W000308 | HOLE STIFFNESS CALCULATION | 1CK100 - Biro Desain Struktur Lambung | 2026-03-16 | 2026-03-31 | 1 | Pijar Kasih Leksono Putri | 16 | JC300326 33351 | 16-17 MARET | JC300326 33350 | 25-31 MARET 26
| 2026-03-16 | W000308 | E91002.97107 - DECOY LAUNCHER SUPPORTING STRUCTURE REPORT - BOUNDARY CONDITION | 1CK100 - Biro Desain Struktur Lambung | 2026-03-16 | 2026-03-31 | 1 | Dea Putri Ubaidah | 56 | JC300326 33353 | 16-17 MARET | JC300326 33355 | 25-31 MARET 26
| 2026-03-16 | W000308 | REV1 - MAIN GUN FOUNDATION | 1CK100 - Biro Desain Struktur Lambung | 2026-03-16 | 2026-03-31 | 1 | Agung Laksono | 56 | JC300326 33359 | 16-17 MARET | JC300326 33356 | 25-31 MARET 26
| 2026-03-16 | W000304 | UPDATE NESTING PLATE | 1CK100 - Biro Desain Struktur Lambung | 2026-03-16 | 2026-03-31 | 1 | Nur Ainy Suntoro | 16 | JC300326 33368 | 16-17 MARET | JC300326 33366 | 25-31 MARET 26
| 2026-03-16 | W000306 | UPDATE NESTING PLATE | 1CK100 - Biro Desain Struktur Lambung | 2026-03-16 | 2026-03-31 | 1 | Nur Ainy Suntoro | 40 | JC300326 33364 | 16-17 MARET | JC300326 33365 | 25-31 MARET 26
| 2026-03-18 | W000304 | REV NESTING PLATE BLOK 521 | 1CK100 - Biro Desain Struktur Lambung | 2026-03-18 | 2026-03-18 | 1 | Nur Ainy Suntoro | 8 | JC010426 33518
2026-04-01
| 2026-04-01 | W000308 | UPDATE - YARD PLAN (MODIFICATION TWS CONSTRUCTION) | 1CK100 - Biro Desain Struktur Lambung | 2026-04-01 | 2026-04-10 | 1 | Kasmiatin | 56 | JC100426 33853
| 2026-04-01 | W000304 | REV1 - E11001.03125 - TEMPORARY HOLE DETAIL - FOOT LIFT | 1CK100 - Biro Desain Struktur Lambung | 2026-04-01 | 2026-04-10 | 1 | Yuli Kustiadi | 24 | JC100426 33857
| 2026-04-01 | W000304 | REV1 - E11001.03126 - TEMPORARY HOLE DETAIL - PROVISION LIFT | 1CK100 - Biro Desain Struktur Lambung | 2026-04-01 | 2026-04-10 | 1 | Yuli Kustiadi | 32 | JC100426 33858
| 2026-04-01 | CORP2026 | MODULUS CALCULATION - HOLE STIFFNESS | 1CK100 - Biro Desain Struktur Lambung | 2026-04-01 | 2026-04-10 | 1 | Pijar Kasih Leksono Putri | 16 | JC100426 33860 | JC100426 33877
| 2026-04-01 | W000308 | ASDP ROPAX 1100 LANE MATER - CALCULATION SCANTLING CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-04-01 | 2026-04-10 | 1 | Pijar Kasih Leksono Putri | 40 | JC100426 33854 | JC100426 33878
| 2026-04-01 | W000308 | E91002.97107 - DECOY LAUNCHER SUPPORTING STRUCTURE REPORT - CONCLUSION | 1CK100 - Biro Desain Struktur Lambung | 2026-04-01 | 2026-04-10 | 1 | Dea Putri Ubaidah | 56 | JC100426 33855
| 2026-04-01 | W000304 | VERTICAL LAUNCHER SYSTEM (VLS) FOUNDATION | 1CK100 - Biro Desain Struktur Lambung | 2026-04-01 | 2026-04-10 | 1 | Agung Laksono | 56 | JC100426 33859
| 2026-04-01 | CORP2026 | CREATE PART NUMBER ALL PROJECT | 1CK100 - Biro Desain Struktur Lambung | 2026-04-01 | 2026-04-10 | 1 | Nur Ainy Suntoro | 24 | JC100426 33861
| 2026-04-01 | W000308 | ESTIMATION MATERIAL PLATE CARGO HANDLING | 1CK100 - Biro Desain Struktur Lambung | 2026-04-01 | 2026-04-10 | 1 | Nur Ainy Suntoro | 16 | JC100426 33856
| 2026-04-01 | KSOT | E21170.01100 - ESTIMATION MATERIAL PLATE | 1CK100 - Biro Desain Struktur Lambung | 2026-04-01 | 2026-04-10 | 1 | Nur Ainy Suntoro | 16 | JC100426 33863
| 2026-04-13 | W000308 | UPDATE - YARD PLAN (MODIFICATION TWS CONSTRUCTION) LEONARDO OPTION | 1CK100 - Biro Desain Struktur Lambung | 2026-04-13 | 2026-04-17 | 1 | Kasmiatin | 40 | JC170426 34089
| 2026-04-13 | W000304 | E11001.03138 - TEMPORARY HOLE DETAIL - TRANSFORMER ON 1 DECK | 1CK100 - Biro Desain Struktur Lambung | 2026-04-13 | 2026-04-17 | 1 | Yuli Kustiadi | 24 | JC170426 34090
| 2026-04-13 | W000304 | E11001.03139 - TEMPORARY HOLE DETAIL - TRANSFORMER ON 2 DECK | 1CK100 - Biro Desain Struktur Lambung | 2026-04-13 | 2026-04-17 | 1 | Yuli Kustiadi | 16 | JC170426 34091
| 2026-04-13 | W000304 | ARRANGEMENT LIFT BEAM E/R - MODEL 3D GEOMETRTY | 1CK100 - Biro Desain Struktur Lambung | 2026-04-13 | 2026-04-17 | 1 | Pijar Kasih Leksono Putri | 40 | JC170426 34085
| 2026-04-13 | W000308 | E11800.03102 - MAIN GUN 76 MM FOUNDATION ANALYSIS (UPDATE LOAD CASE ALL) | 1CK100 - Biro Desain Struktur Lambung | 2026-04-13 | 2026-04-17 | 1 | Dea Putri Ubaidah | 40 | JC170426 34087
| 2026-04-13 | W000304 | VERTICAL LAUNCHER SYSTEM (VLS) FOUNDATION - INTEGRATION TO STRUCTURE | 1CK100 - Biro Desain Struktur Lambung | 2026-04-13 | 2026-04-17 | 1 | Agung Laksono | 40 | JC170426 34086
| 2026-04-13 | W000304 | NESTING PLATE BLOK 631 | 1CK100 - Biro Desain Struktur Lambung | 2026-04-13 | 2026-04-17 | 1 | Nur Ainy Suntoro | 8 | JC170426 34092
| 2026-04-13 | W000306 | ESTIMATION MATERIAL KB-04 | 1CK100 - Biro Desain Struktur Lambung | 2026-04-13 | 2026-04-17 | 1 | Nur Ainy Suntoro | 8 | JC170426 34093
| 2026-04-13 | CORP2026 | KSOT - R1 - E21170.01100 - ESTIMATION MATERIAL PLATE | 1CK100 - Biro Desain Struktur Lambung | 2026-04-13 | 2026-04-17 | 1 | Nur Ainy Suntoro | 8 | JC170426 34094
| 2026-04-13 | CORP2026 | CREATE PART NUMBER ALL PROJECT | 1CK100 - Biro Desain Struktur Lambung | 2026-04-13 | 2026-04-17 | 1 | Nur Ainy Suntoro | 16 | JC170426 34095
| 2026-04-20 | R22FPBXA | FPB - DIESEL GENERATOR FOUNDATION DRAWING | 1CK100 - Biro Desain Struktur Lambung | 2026-04-20 | 2026-05-02 | 1 | Yuli Kustiadi | 96 | JC210426 34272 | PROJECT R41
| 2026-04-25 | W000304 | E91002.97136 LIFT BEAM IN ER SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2026-04-20 | 2026-04-30 | 1 | Pijar Kasih Leksono Putri | 63 | JC270426 34397
| 2026-04-25 | W000308 | STRENGTH ANALYSIS OF PRIMARY MEMBER WEB OPENING REPORT | 1CK100 - Biro Desain Struktur Lambung | 2026-04-20 | 2026-04-30 | 1 | Dea Putri Ubaidah | 63 | JC270426 34398
| 2026-04-25 | W000308 | REINFORCEMENT AHU (STEEL PLAN 03) | 1CK100 - Biro Desain Struktur Lambung | 2026-04-20 | 2026-04-22 | 1 | Kasmiatin | 21 | JC270426 34400
| 2026-04-25 | W000308 | AFT CONSTRUCTION OF O3 DECK | 1CK100 - Biro Desain Struktur Lambung | 2026-04-23 | 2026-04-25 | 1 | Kasmiatin | 21 | JC270426 34401
| 2026-04-25 | W000308 | DOCK WELL CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-04-27 | 2026-04-30 | 1 | Kasmiatin | 28 | JC270426 34403
| 2026-04-25 | W000308 | STERN & DOCK WELL BOTTOM CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-04-27 | 2026-04-30 | 1 | Kasmiatin | 20 | JC270426 34412
| 2026-04-25 | W000308 | STEEL PLAN 03 & 02 (UPDATE) | 1CK100 - Biro Desain Struktur Lambung | 2026-04-20 | 2026-04-30 | 1 | Kasmiatin | 40 | JC270426 34415
| 2026-04-25 | W000304-305 | E11800.03116 - WINGS CONSTRUCTION ON FORE MAST | 1CK100 - Biro Desain Struktur Lambung | 2026-04-20 | 2026-04-25 | 1 | Agung Laksono | 40 | JC270426 34417 | 42
| 2026-04-25 | W000304-305 | UPDATE NESTING PLATE | 1CK100 - Biro Desain Struktur Lambung | 2026-04-20 | 2026-04-30 | 1 | Nur Ainy Suntoro | 40 | JC270426 34423 | 21
| 2026-04-25 | W000308 | UPDATE NESTING PLATE | 1CK100 - Biro Desain Struktur Lambung | 2026-04-20 | 2026-04-30 | 1 | Nur Ainy Suntoro | 25 | JC270426 34427 | 28
| 2026-04-25 | W000306 | KB-04 UPDATE | 1CK100 - Biro Desain Struktur Lambung | 2026-04-20 | 2026-04-21 | 1 | Nur Ainy Suntoro | 20 | JC270426 34428 | 14
| 2026-04-25 | W000304 | VERTICAL LAUNCHER SYSTEM (VLS) - INTEGRATION OF ADDITION PLATFORM | 1CK100 - Biro Desain Struktur Lambung | 2026-04-27 | 2026-04-30 | 1 | Agung Laksono | 32 | JC270426 34503
2026-05-01
| 2026-05-04 | W000308 | UPDATE - YARD PLAN (MODIFICATION TWS - LEONARDO) | 1CK100 - Biro Desain Struktur Lambung | 2026-05-04 | 2026-05-08 | 1 | Kasmiatin | 40 | JC080526 34910
| 2026-05-04 | CORP2026 | M0312 KAPAL PINISI - CREATE MODELING CADMATIC SHELL AND DECK | 1CK100 - Biro Desain Struktur Lambung | 2026-05-04 | 2026-05-09 | 1 | Yuli Kustiadi | 56 | JC070526 34858
| 2026-05-04 | CORP2026 | M0312 KAPAL PINISI - CALCULATION SCANTLING CONTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-05-04 | 2026-05-08 | 1 | Pijar Kasih Leksono Putri | 40 | JC070526 34859
| 2026-05-04 | W000304 | STIFFNESS CALCULATION - MAIN GUN FOUNDATION | 1CK100 - Biro Desain Struktur Lambung | 2026-05-04 | 2026-05-08 | 1 | Dea Putri Ubaidah | 24 | JC080526 34868
| 2026-05-04 | W000304 | REV2 - RAS STRUCTURE ANALYSIS REPORT - COMMENCT CLASS REVIEW | 1CK100 - Biro Desain Struktur Lambung | 2026-05-04 | 2026-05-08 | 1 | Dea Putri Ubaidah | 16 | JC080526 34869
| 2026-05-04 | CORP2026 | M0312 KAPAL PINISI - CREATE MODELING CADMATIC BLOCK 111C | 1CK100 - Biro Desain Struktur Lambung | 2026-05-04 | 2026-05-09 | 1 | Agung Laksono | 48 | JC070526 34861
| 2026-05-04 | CORP2026 | CREATE PART NUMBER ALL PROJECT | 1CK100 - Biro Desain Struktur Lambung | 2026-05-04 | 2026-05-08 | 1 | Nur Ainy Suntoro | 24 | JC070526 34860
| 2026-05-04 | W000308 | UPDATE NESTING PLATE | 1CK100 - Biro Desain Struktur Lambung | 2026-05-04 | 2026-05-08 | 1 | Nur Ainy Suntoro | 16 | JC080526 34870
| 2026-05-11 | W000308 | UPDATE DRAWING REVISI (MIDSHIP SECTION, FORE MAST CONST, AFT MAST CONST) | 1CK100 - Biro Desain Struktur Lambung | 2026-05-11 | 2026-05-13 | 1 | Kasmiatin | 24 | JC180526 35263 | -
| 2026-05-11 | CORP2026 | M0312 KAPAL PINISI - CREATE MODELING CADMATIC SHELL AND 01, 02 DECK | 1CK100 - Biro Desain Struktur Lambung | 2026-05-11 | 2026-05-13 | 1 | Yuli Kustiadi | 32 | JC180526 35264
| 2026-05-11 | W000304 | E/R MONORIL CRANE SEATS STRUCTURE ANALYSIS - GEOMETRY MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-05-11 | 2026-05-13 | 1 | Pijar Kasih Leksono Putri | 24 | JC180526 35305
| 2026-05-11 | W000304 | REV2 - RAS STRUCTURE ANALYSIS REPORT - LOAD CONDITION | 1CK100 - Biro Desain Struktur Lambung | 2026-05-11 | 2026-05-13 | 1 | Dea Putri Ubaidah | 24 | JC180526 35306
| 2026-05-11 | CORP2026 | M0312 KAPAL PINISI - CREATE MODELING CADMATIC BLOCK 111C - INNER PART | 1CK100 - Biro Desain Struktur Lambung | 2026-05-11 | 2026-05-13 | 1 | Agung Laksono | 32 | JC180526 35265
| 2026-05-11 | CORP2026 | M0312 KAPAL PINISI - ESTIMATION MATERIAL LIST PROFILE & PLATE | 1CK100 - Biro Desain Struktur Lambung | 2026-05-11 | 2026-05-16 | 1 | Nur Ainy Suntoro | 32 | JC180526 35266
| 2026-05-18 | CORP2026 | M0312 KAPAL PINISI - OUTPUT KEYPLAN CADMATIC - MIDSHIP, SHELL EXPANSION, CONSPRO | 1CK100 - Biro Desain Struktur Lambung | 2026-05-18 | 2026-05-23 | 1 | Yuli Kustiadi | 48 | JC180526 35267
| 2026-05-18 | CORP2026 | M0313 GEOMARINE V - PREPARATION CALCULATION SCANTLING CONTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-05-18 | 2026-05-22 | 1 | Pijar Kasih Leksono Putri | 40 | JC180526 35268
| 2026-05-18 | W000304 | REV2 - RAS STRUCTURE ANALYSIS REPORT - LOAD CASE | 1CK100 - Biro Desain Struktur Lambung | 2026-05-18 | 2026-05-23 | 1 | Dea Putri Ubaidah | 48 | JC180526 35307
| 2026-05-18 | CORP2026 | M0312 KAPAL PINISI - CREATE MODELING CADMATIC BLOCK 422C | 1CK100 - Biro Desain Struktur Lambung | 2026-05-18 | 2026-05-23 | 1 | Agung Laksono | 48 | JC180526 35270
| 2026-05-18 | CORP2026 | M0312 KAPAL PINISI - CREATE NESTING PLATE | 1CK100 - Biro Desain Struktur Lambung | 2026-05-18 | 2026-05-23 | 1 | Nur Ainy Suntoro | 48 | JC180526 35271
| 2026-05-25 | CORP2026 | M0312 KAPAL PINISI - OUTPUT KEYPLAN CADMATIC - BULKHEAD SECTION | 1CK100 - Biro Desain Struktur Lambung | 2026-05-25 | 2026-05-30 | 1 | Yuli Kustiadi | 40 | JC260526 35591
| 2026-05-25 | CORP2026 | M0313 GEOMARINE V - CALCULATION SCANTLING CONTRUCTION - DESIGN LOAD | 1CK100 - Biro Desain Struktur Lambung | 2026-05-25 | 2026-05-30 | 1 | Pijar Kasih Leksono Putri | 32 | JC260526 35592
| 2026-05-25 | W000304 | REV2 - RAS STRUCTURE ANALYSIS REPORT | 1CK100 - Biro Desain Struktur Lambung | 2026-05-25 | 2026-05-30 | 1 | Dea Putri Ubaidah | 32 | JC260526 35595
| 2026-05-25 | CORP2026 | M0312 KAPAL PINISI - DRAWING CASTING AFT | 1CK100 - Biro Desain Struktur Lambung | 2026-05-25 | 2026-05-30 | 1 | Agung Laksono | 32 | JC260526 35593
| 2026-05-25 | CORP2026 | M0312 KAPAL PINISI - NESTING PLATE | 1CK100 - Biro Desain Struktur Lambung | 2026-05-25 | 2026-05-30 | 1 | Nur Ainy Suntoro | 32 | JC260526 35594
2026-06-01
| 2026-06-02 | CORP2026 | M000312 KAPAL PINISI - E11600.03101 SUPERSTRUCTURE AND DECK HOUSE CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-06-02 | 2026-06-13 | 1 | Kasmiatin | 72 | JC110626 36269
| 2026-06-02 | CORP2026 | M000312 KAPAL PINISI - CREATE MODELING CADMATIC BLOCK 322 - FORE PEAK | 1CK100 - Biro Desain Struktur Lambung | 2026-06-02 | 2026-06-06 | 1 | Yuli Kustiadi | 40 | JC110626 36270
| 2026-06-02 | CORP2026 | M000312 KAPAL PINISI - CREATE MODELING CADMATIC BLOCK 211 - ENGINE ROOM | 1CK100 - Biro Desain Struktur Lambung | 2026-06-08 | 2026-06-13 | 1 | Yuli Kustiadi | 56 | JC110626 36271
| 2026-06-02 | CORP2026 | M0313 GEOMARINE V - CALCULATION SCANTLING CONTRUCTION - DECK STRENGTH | 1CK100 - Biro Desain Struktur Lambung | 2026-06-02 | 2026-06-05 | 1 | Pijar Kasih Leksono Putri | 32 | JC110626 36272
| 2026-06-02 | CORP2026 | M000312 KAPAL PINISI - E11001.03102 NDE PLAN | 1CK100 - Biro Desain Struktur Lambung | 2026-06-08 | 2026-06-13 | 1 | Pijar Kasih Leksono Putri | 40 | JC110626 36273
| 2026-06-02 | CORP2026 | M0313 GEOMARINE V - DRAWING SCANTLING CONTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-06-02 | 2026-06-13 | 1 | Dea Putri Ubaidah | 80 | JC110626 36274
| 2026-06-02 | CORP2026 | M000312 KAPAL PINISI - CASTING MODEL STERN SECTION | 1CK100 - Biro Desain Struktur Lambung | 2026-06-02 | 2026-06-06 | 1 | Agung Laksono | 40 | JC110626 36275
| 2026-06-02 | CORP2026 | M000312 KAPAL PINISI - E11020.03401 AFT PEAK CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-06-08 | 2026-06-13 | 1 | Agung Laksono | 48 | JC110626 36276
| 2026-06-02 | CORP2026 | M000312 KAPAL PINISI - ESTIMATION MATERIAL | 1CK100 - Biro Desain Struktur Lambung | 2026-06-02 | 2026-06-12 | 1 | Nur Ainy Suntoro | 48 | JC120626 36287
| 2026-06-02 | CORP2026 | M000312 KAPAL PINISI - NESTI PLATE | 1CK100 - Biro Desain Struktur Lambung | 2026-06-08 | 2026-06-12 | 1 | Nur Ainy Suntoro | 40 | JC170626 36511
| 2026-06-15 | W000308 | UPDATE - YARD PLAN (MODIFICATION TWS - LEONARDO) | 1CK100 - Biro Desain Struktur Lambung | 2026-06-15 | 2026-06-19 | 1 | Kasmiatin | 40 | JC190626 36559
| 2026-06-15 | CORP2026 | M000312 KAPAL PINISI - E11020.03201 ENGINE ROOM CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-06-15 | 2026-06-20 | 1 | Yuli Kustiadi | 56 | JC190626 36560
| 2026-06-15 | CORP2026 | M0313 GEOMARINE V - CALCULATION SCANTLING CONTRUCTION - SUPERSTRUCTURE | 1CK100 - Biro Desain Struktur Lambung | 2026-06-15 | 2026-06-19 | 1 | Pijar Kasih Leksono Putri | 40 | JC190626 36561
| 2026-06-15 | CORP2026 | M0313 GEOMARINE V - DRAWING SCANTLING CONTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-06-15 | 2026-06-19 | 1 | Dea Putri Ubaidah | 40 | JC190626 36562
| 2026-06-15 | CORP2026 | M000312 KAPAL PINISI - CASTING MODEL STERN SECTION | 1CK100 - Biro Desain Struktur Lambung | 2026-06-15 | 2026-06-19 | 1 | Agung Laksono | 48 | JC190626 36563
| 2026-06-15 | CORP2026 | M000312 KAPAL PINISI - NESTING PLATE UPDATE | 1CK100 - Biro Desain Struktur Lambung | 2026-06-15 | 2026-06-19 | 1 | Nur Ainy Suntoro | 40 | JC190626 36564
| 2026-06-22 | W000308 | REVISI - E11002.03100 STERN AND DOCK WELL CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-06-22 | 2026-06-30 | 1 | Kasmiatin | 32 | JC260626 36797 | JC300626 36986
| 2026-06-22 | W000308 | REVISI - E11002.03200 DOCK WELL CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-06-22 | 2026-06-30 | 1 | Kasmiatin | 24 | JC260626 36798 | JC300626 36987
| 2026-06-22 | M000312 | E11020.03201 ENGINE ROOM CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-06-22 | 2026-06-30 | 1 | Yuli Kustiadi | 56 | JC270626 36808 | JC300626 36988
| 2026-06-22 | M000312 | REVISI - E11020.03101 MIDDLE CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-06-22 | 2026-06-30 | 1 | Yuli Kustiadi | 24 | JC270626 36809 | JC300626 36989
| 2026-06-22 | M000313 | GEOMARINE V BASIC HC - SEAM AND BUTT JOINT | 1CK100 - Biro Desain Struktur Lambung | 2026-06-22 | 2026-06-30 | 1 | Pijar Kasih Leksono Putri | 40 | JC270626 36810 | JC300626 36990
| 2026-06-22 | M000313 | GEOMARINE V BASIC HC - BRACKET END, THICKNESS DIRECTION | 1CK100 - Biro Desain Struktur Lambung | 2026-06-22 | 2026-06-30 | 1 | Pijar Kasih Leksono Putri | 16 | JC270626 36811 | JC300626 36991
| 2026-06-22 | M000313 | GEOMARINE V BASIC HC - PRIMARY STRUCTURE DETAIL | 1CK100 - Biro Desain Struktur Lambung | 2026-06-22 | 2026-06-30 | 1 | Dea Putri Ubaidah | 40 | JC270626 36812
| 2026-06-22 | M000313 | GEOMARINE V BASIC HC - SECONDARY STRUCTURE DETAIL | 1CK100 - Biro Desain Struktur Lambung | 2026-06-22 | 2026-06-30 | 1 | Dea Putri Ubaidah | 16 | JC270626 36813
| 2026-06-22 | W000304 | 3D MODELING ESM BLOCK CONSTRUCTION (PRELIMINARY) | 1CK100 - Biro Desain Struktur Lambung | 2026-06-22 | 2026-06-30 | 1 | Agung Laksono | 48 | JC270626 36814
| 2026-06-22 | W000304 | 3D MODELING UMBERELLA FOUNDATION (PRELIMINARY) | 1CK100 - Biro Desain Struktur Lambung | 2026-06-22 | 2026-06-30 | 1 | Agung Laksono | 16 | JC270626 36815
| 2026-06-22 | M000312 | UPDATE - NESTING PLATE | 1CK100 - Biro Desain Struktur Lambung | 2026-06-22 | 2026-06-30 | 1 | Nur Ainy Suntoro | 24 | JC270626 36816
| 2026-06-22 | W000307 | UPDATE - NESTING PLATE | 1CK100 - Biro Desain Struktur Lambung | 2026-06-22 | 2026-06-30 | 1 | Nur Ainy Suntoro | 16 | JC270626 36817
| 2026-06-22 | W000308 | UPDATE - MATERIAL LIST | 1CK100 - Biro Desain Struktur Lambung | 2026-06-22 | 2026-06-30 | 1 | Nur Ainy Suntoro | 16 | JC270626 36818
2026-07-01
| 2026-07-01 | W000308 | REVISI - KEY PLAN - E11001.03101 STEEL PLAN | 1CK100 - Biro Desain Struktur Lambung | 2026-07-01 | 2026-07-11 | 1 | Kasmiatin | 80 | JC080726 37338
| 2026-07-01 | M000313 | CHECKER 3D MODELING CADMATIC - CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-07-13 | 2026-07-24 | 1 | Kasmiatin | 64 | JC080726 37339
| 2026-07-01 | M000313 | CHECKER KEY PLAN - MIDSHIP, CONSPRO, SHELL EXPANSION | 1CK100 - Biro Desain Struktur Lambung | 2026-07-22 | 2026-07-31 | 1 | Kasmiatin | 64 | JC080726 37340
| 2026-07-01 | M000312 | MODEL CADMATIC - E11002.03113 RUDDER CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-07-01 | 2026-07-11 | 1 | Yuli Kustiadi | 88 | JC080726 37342
| 2026-07-01 | M000312 | MODEL CADMATIC - E11810.03102 MAST PEDESTAL AND DECK REINFORCEMENT | 1CK100 - Biro Desain Struktur Lambung | 2026-07-13 | 2026-07-18 | 1 | Yuli Kustiadi | 48 | JC080726 37343
| 2026-07-01 | M000312 | UPDATE REVISI MODEL CADMATIC - KEY PLAN AND YARD PLAN | 1CK100 - Biro Desain Struktur Lambung | 2026-07-20 | 2026-07-31 | 1 | Yuli Kustiadi | 96 | JC080726 37344
| 2026-07-01 | M000313 | CREATE STANDART DRAWING BIRO HC PROJECT GEOMARINE V | 1CK100 - Biro Desain Struktur Lambung | 2026-07-01 | 2026-07-04 | 1 | Pijar Kasih Leksono Putri | 32 | JC080726 37345
| 2026-07-01 | W000304 | REV - E91002.97102 - MAIN GUN FOUNDATION | 1CK100 - Biro Desain Struktur Lambung | 2026-07-06 | 2026-07-11 | 1 | Pijar Kasih Leksono Putri | 48 | JC080726 37346
| 2026-07-01 | W000304 | REV - E91002.97123 - BOAT DAVID STRUCTURE | 1CK100 - Biro Desain Struktur Lambung | 2026-07-13 | 2026-07-18 | 1 | Pijar Kasih Leksono Putri | 48 | JC080726 37347
| 2026-07-01 | W000304 | REV - ER LIFT BEAM SEAT ANALYSIS | 1CK100 - Biro Desain Struktur Lambung | 2026-07-20 | 2026-07-31 | 1 | Pijar Kasih Leksono Putri | 96 | JC090726 37376
| 2026-07-01 | W000308 | YARD PLAN SSM FOUNDATION | 1CK100 - Biro Desain Struktur Lambung | 2026-07-01 | 2026-07-04 | 1 | Dea Putri Ubaidah | 32 | JC080726 37349
| 2026-07-01 | W000308 | FEM ANALYSIS - FCS ANTENNA FOUNDATION | 1CK100 - Biro Desain Struktur Lambung | 2026-07-06 | 2026-07-15 | 1 | Dea Putri Ubaidah | 72 | JC080726 37350
| 2026-07-01 | W000308 | STIFFENES - FCS ANTENNA, MAIN GUN, SECONDARY, PASEO XLR | 1CK100 - Biro Desain Struktur Lambung | 2026-07-16 | 2026-07-25 | 1 | Dea Putri Ubaidah | 72 | JC080726 37351
| 2026-07-01 | W000308 | FEM ANALYSIS - SECONDARY GUN | 1CK100 - Biro Desain Struktur Lambung | 2026-07-27 | 2026-07-31 | 1 | Dea Putri Ubaidah | 40 | JC080726 37352
| 2026-07-01 | M000313 | CADMATIC MODELING - INNER PART UNDER 1 DECK | 1CK100 - Biro Desain Struktur Lambung | 2026-07-01 | 2026-07-11 | 1 | Agung Laksono | 88 | JC080726 37353
| 2026-07-01 | M000313 | CADMATIC MODELING - INNER PART UPPER 1 DECK | 1CK100 - Biro Desain Struktur Lambung | 2026-07-13 | 2026-07-18 | 1 | Agung Laksono | 48 | JC080726 37358
| 2026-07-01 | M000313 | CADMATIC MODELING - INNER PART WHEEL HOUSE | 1CK100 - Biro Desain Struktur Lambung | 2026-07-20 | 2026-07-25 | 1 | Agung Laksono | 48 | JC080726 37361
| 2026-07-01 | M000313 | CREATE KEY PLAN - MIDSHIP | 1CK100 - Biro Desain Struktur Lambung | 2026-07-27 | 2026-07-31 | 1 | Agung Laksono | 40 | JC080726 37363
| 2026-07-01 | M000312 | CREATE NESTING PLATE, NESTING BENDING, MATLIST | 1CK100 - Biro Desain Struktur Lambung | 2026-07-01 | 2026-07-11 | 1 | Nur Ainy Suntoro | 88 | JC080726 37364
| 2026-07-01 | M000312 | UPDATE NESTING PLATE PROJECT M000312 | 1CK100 - Biro Desain Struktur Lambung | 2026-07-13 | 2026-07-18 | 1 | Nur Ainy Suntoro | 48 | JC090726 37377
| 2026-07-01 | M000312 | UPDATE NESTING PLATE PROJECT W000308 | 1CK100 - Biro Desain Struktur Lambung | 2026-07-20 | 2026-07-25 | 1 | Nur Ainy Suntoro | 48 | JC080726 37366
| 2026-07-01 | M000312 | UPDATE NESTING PLATE, NESTING BENDING, MATLIST | 1CK100 - Biro Desain Struktur Lambung | 2026-07-27 | 2026-07-31 | 1 | Nur Ainy Suntoro | 40 | JC080726 37367
2026-08-01
| 2026-08-03 | W000308 | REV. 2 - E11002.03100 STERN & DOCK WELL BOTTOM CONSTRUCTION (AE-FR59) | 1CK100 - Biro Desain Struktur Lambung | 2026-08-03 | 2026-08-08 | 1 | Kasmiatin | 24 | JC110826 38756
| 2026-08-03 | W000308 | REV. 3 - E11002.03200 DOCK WELL CONSTRUCTION (AE-FR59) | 1CK100 - Biro Desain Struktur Lambung | 2026-08-03 | 2026-08-08 | 1 | Kasmiatin | 24 | JC110826 38758
| 2026-08-10 | W000308 | REV. 2 - E11002.03110 DECK HOUSE CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-08-10 | 2026-08-15 | 1 | Kasmiatin | 40 | JC110826 38761
| 2026-08-03 | W000305 | CHECK SHEET CASTING FOR USING V-BRACKET, I-BRACKET, STERNTUBE (SHAFT BRACKET) | 1CK100 - Biro Desain Struktur Lambung | 2026-08-03 | 2026-08-08 | 1 | Yuli Kustiadi | 48 | JC110826 38763
| 2026-08-10 | M000313 | E11010.03102 - CONSTRUCTION PROFILE AND DECK - CADMATIC MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-08-10 | 2026-08-15 | 1 | Yuli Kustiadi | 48 | JC110826 38764
| 2026-08-03 | M000313 | E91002.97200 - SCANTLING CALCULATION REPORT | 1CK100 - Biro Desain Struktur Lambung | 2026-08-03 | 2026-08-08 | 1 | Pijar Kasih Leksono Putri | 48 | JC110826 38765
| 2026-08-10 | W000304 | E91002.97123 - BOAT DAVIT SUPPORTING STRUCTURE REPORT - ANALYSIS UPDATE | 1CK100 - Biro Desain Struktur Lambung | 2026-08-10 | 2026-08-15 | 1 | Pijar Kasih Leksono Putri | 16 | JC110826 38766
| 2026-08-10 | M000312 | E11810.03102 - MAST PADESTAL AND DECK REINFORCEMENT - ANALYSIS STRUCTURE | 1CK100 - Biro Desain Struktur Lambung | 2026-08-10 | 2026-08-15 | 1 | Pijar Kasih Leksono Putri | 32 | JC110826 38771
| 2026-08-03 | W000308 | E91002.97110 - HEAD EO FCS (PASEO XLR) SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2026-08-03 | 2026-08-08 | 1 | Dea Putri Ubaidah | 48 | JC110826 38772
| 2026-08-10 | W000308 | E91002.97111 - GYRO ROOM SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2026-08-10 | 2026-08-15 | 1 | Dea Putri Ubaidah | 16 | JC110826 38775
| 2026-08-10 | W000308 | E91002.97112 - EOD RAM LOGIR SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2026-08-10 | 2026-08-15 | 1 | Dea Putri Ubaidah | 32 | JC110826 38776
| 2026-08-03 | M000313 | E11010.03101 - MIDSHIP SECTION - CADMATIC MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-08-03 | 2026-08-08 | 1 | Agung Laksono | 48 | JC110826 38777
| 2026-08-10 | W000304 | E11800.03101 - FOUNDATION OF VLS - SKETCH PRELIMINARY | 1CK100 - Biro Desain Struktur Lambung | 2026-08-10 | 2026-08-15 | 1 | Agung Laksono | 48 | JC110826 38778
| 2026-08-03 | M000312 | E11810.03102 - MAST PADESTAL AND DECK REINFORCEMENT - CADMATIC MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-08-03 | 2026-08-08 | 1 | Rama Ajimukti A | 48 | JC110826 38779
| 2026-08-10 | W000308 | E11002.03200 - DOCK WELL CONSTRUCTION (AE-FR59) - STERN RAMPS CARGO HANDLING | 1CK100 - Biro Desain Struktur Lambung | 2026-08-10 | 2026-08-15 | 1 | Rama Ajimukti A | 48 | JC110826 38780
| 2026-08-03 | W000314 | E11001.03101 - MIDSHIP SECTION - CADMATIC MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-08-03 | 2026-08-08 | 1 | Felix Adyatma Rosyadi | 48 | JC110826 38781
| 2026-08-10 | W000314 | E11010.03102 - CONSTRUCTION PROFILE AND DECK PLAN - CADMATIC MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-08-10 | 2026-08-15 | 1 | Felix Adyatma Rosyadi | 48 | JC110826 38782
| 2026-08-18 | W000308 | REV. 1 - E11002.03213 FORE PEAK TANK CONSTRUCTION OF BOTTOM | 1CK100 - Biro Desain Struktur Lambung | 2026-08-18 | 2026-08-31 | 1 | Kasmiatin | 32 | JC210826 39272
| 2026-08-18 | M000313 | E11600.03101 SUPERSTRUCTURE AND DECK HOUSE CONSTRUCTION - CADMATIC MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-08-18 | 2026-08-31 | 1 | Kasmiatin | 48 | JC210826 39273
| 2026-08-18 | M000312 | REV.1 - E11002.03113 RUDDER CONSTRUCTION | 1CK100 - Biro Desain Struktur Lambung | 2026-08-18 | 2026-08-31 | 1 | Yuli Kustiadi | 24 | JC210826 39274
| 2026-08-18 | W000304 | E11001.03143 - TEMPORARY HOLE DETAIL - CS 12 EQUIPMENT | 1CK100 - Biro Desain Struktur Lambung | 2026-08-18 | 2026-08-31 | 1 | Yuli Kustiadi | 24 | JC210826 39275
| 2026-08-18 | M000313 | E11020.03201 - ENGINE ROOM CONSTRUCTION - CADMATIC MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-08-18 | 2026-08-31 | 1 | Yuli Kustiadi | 64 | JC210826 39276
| 2026-08-18 | W000304 | E91002.97123 - BOAT DAVITS SUPPORTING STRUCTURE - RECALCULATE ANALYSIS | 1CK100 - Biro Desain Struktur Lambung | 2026-08-18 | 2026-08-31 | 1 | Pijar Kasih Leksono Putri | 64 | JC210826 39280
| 2026-08-18 | W000314 | E91002.97200 - SCANTLING CALCULATION | 1CK100 - Biro Desain Struktur Lambung | 2026-08-18 | 2026-08-31 | 1 | Pijar Kasih Leksono Putri | 24 | JC210826 39281
| 2026-08-18 | W000308 | REV.1 - E11800.03109 - FCS ANTENNA FOUNDATION | 1CK100 - Biro Desain Struktur Lambung | 2026-08-18 | 2026-08-31 | 1 | Dea Putri Ubaidah | 32 | JC210826 39283
| 2026-08-18 | W000308 | E91002.97113 - FCS ANTENNA SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2026-08-18 | 2026-08-31 | 1 | Dea Putri Ubaidah | 56 | JC210826 39285
| 2026-08-18 | W000304 | E11800.03101 - FOUNDATION OF VLS - PRELIMINARY MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-08-18 | 2026-08-31 | 1 | Agung Laksono | 40 | JC210826 39286
| 2026-08-18 | M000313 | E11020.03401 - AFT PEAK CONSTRUCTION - CADMATIC MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-08-18 | 2026-08-31 | 1 | Agung Laksono | 56 | JC210826 39287
| 2026-08-18 | W000308 | E11002.03202 - MIDDLE TANK DECK CONSTRUCTION 01-02 DECK - VEHICLE LIFT CARFO HANDLING | 1CK100 - Biro Desain Struktur Lambung | 2026-08-18 | 2026-08-31 | 1 | Rama Ajimukti A | 40 | JC210826 39288
| 2026-08-18 | M000312 | E11020.03301 - FORE PEAK CONSTRUCTION - PEDESTAL CADMATIC MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-08-18 | 2026-08-31 | 1 | Rama Ajimukti A | 56 | JC210826 39289
| 2026-08-18 | W000314 | E11201.03101 - TYPICAL FRAME AND BULKHEAD SECTION | 1CK100 - Biro Desain Struktur Lambung | 2026-08-18 | 2026-08-31 | 1 | Felix Adyatma Rosyadi | 40 | JC210826 39290
| 2026-08-18 | W000314 | E11002.03110 - WHEEL HOUSE CONSTRUCTION - CADMATIC MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-08-18 | 2026-08-31 | 1 | Felix Adyatma Rosyadi | 56 | JC210826 39291
2026-09-01
| 2026-09-01 | M000313 | E11600.03101 SUPERSTRUCTURE AND DECK HOUSE CONSTRUCTION - CADMATIC MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-09-01 | 2026-09-05 | 1 | Kasmiatin | 32 | JC140926 40398
| 2026-09-01 | M000313 | E11600.03101 SUPERSTRUCTURE AND DECK HOUSE CONSTRUCTION - YARD PLAN | 1CK100 - Biro Desain Struktur Lambung | 2026-09-07 | 2026-09-12 | 1 | Kasmiatin | 40 | JC140926 40401
| 2026-09-01 | M000312 | E11020.03301 - FORE PEAK CONSTRUCTION - CADMATIC MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-09-01 | 2026-09-05 | 1 | Yuli Kustiadi | 40 | JC140926 40402
| 2026-09-01 | M000312 | E11820.03101 - MAIN ENGINE FOUNDATION - CADMATIC MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-09-07 | 2026-09-12 | 1 | Yuli Kustiadi | 32 | JC140926 40404
| 2026-09-01 | W000314 | E19861.03102 - NDE POSITION | 1CK100 - Biro Desain Struktur Lambung | 2026-09-01 | 2026-09-05 | 1 | Pijar Kasih Leksono Putri | 32 | JC140926 40408
| 2026-09-01 | W000314 | E91002.97200 - SCANTLING CALCULATION - REPORT | 1CK100 - Biro Desain Struktur Lambung | 2026-09-07 | 2026-09-12 | 1 | Pijar Kasih Leksono Putri | 24 | JC140926 40411
| 2026-09-01 | W000308 | E91002.97113 - FCS ANTENNA SUPPORTING STRUCTURE REPORT - UPDATE COMMENT | 1CK100 - Biro Desain Struktur Lambung | 2026-09-01 | 2026-09-05 | 1 | Dea Putri Ubaidah | 32 | JC140926 40413
| 2026-09-01 | W000308 | E91002.97114 - SOFT GUN MOUNT (MIDDLE) SUPPORTING STRUCTURE REPORT | 1CK100 - Biro Desain Struktur Lambung | 2026-09-07 | 2026-09-12 | 1 | Dea Putri Ubaidah | 40 | JC140926 40418
| 2026-09-01 | M000313 | E11020.03401 - AFT PEAK CONSTRUCTION - CADMATIC MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-09-01 | 2026-09-05 | 1 | Agung Laksono | 40 | JC140926 40422
| 2026-09-01 | M000313 | E11020.03301 - FORE PEAK CONSTRUCTION - CADMATIC MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-09-07 | 2026-09-12 | 1 | Agung Laksono | 48 | JC140926 40428
| 2026-09-01 | W000308 | E25730.33102 - STERN RAMP DOOR - CADMATIC MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-09-01 | 2026-09-05 | 1 | Rama Ajimukti A | 40 | JC140926 40434
| 2026-09-01 | M000313 | FUNNEL CONSTRUCTION - CADMATIC MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-09-07 | 2026-09-12 | 1 | Rama Ajimukti A | 48 | JC140926 40435
| 2026-09-01 | W000314 | REV.1 - E11010.03102 - CONSTRUCTION PROFILE AND DECK PLAN - CADMATIC MODELING | 1CK100 - Biro Desain Struktur Lambung | 2026-09-01 | 2026-09-05 | 1 | Felix Adyatma Rosyadi | 40 | JC140926 40451
| 2026-09-01 | W000314 | REV.1 - E11001.03101 - MIDSHIP SECTION - YARD PLAN | 1CK100 - Biro Desain Struktur Lambung | 2026-09-07 | 2026-09-12 | 1 | Felix Adyatma Rosyadi | 48 | JC140926 40453

## Dept. SPL (PDHC)
Diisi Planner
No | Tanggal Permintaan JC ditulis | Project | Task Name | Work Center | Schedule Start date | Schedule End date | Total Personil yang mengerjakan | PIC | JO | Kode Job Card | Keterangan | Planner
| DD / MM / YYYY | KODE PROYEK | REVISI KE - NO DOC / DWG - DESC PEKERJAAN | KODE BIRO - DESC BIRO | DD / MM / YYYY | DD / MM / YYYY | (DALAM ANGKA) | (NAMA) | (ANGKA) | JC010624 0001 |  | 023066812-Hashfi Moch Adam
CONTOH
1 | 2024-07-01 | W000308 |  | 1CK300 - Biro Gambar Produksi Lambung | 2024-07-15 | 2024-07-31 | 1 |  |  | JC050724 4077 | 023066812-Hashfi Moch Adam
1 | 2025-03-05 | W0000304 - 305 | R0 - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-03 | 2025-03-29 | 1 | mila | 60 | JC060325 16082
2 |  | W0000306 - 307 | R0 - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-03 | 2025-03-29 | 1 | mila | 60 | JC060325 16083
3 |  | W0000308 | R0 - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-03 | 2025-03-29 | 1 | mila | 60 | JC060325 16084
4 |  | E190N025 / BMPP 3 | Review GA dan Modeling NAPA / Cadmatic | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-03 | 2025-03-29 | 1 | dyan | 40 | JC070325 16178
5 |  | W0000308 | REV - EC322U.6 - PROD. DWG 322 (P/S), 323 (P/S), 341 (C), 342 (C) ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-03 | 2025-03-15 | 1 | zakiyah | 80 | JC060325 16085
6 |  | W0000308 | REV - EC324U.6 - PROD. DWG 324 (P/S), 332 (P/S), 333 (P/S), 334 (P/S) ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-17 | 2025-03-29 | 1 | zakiyah | 80 | JC060325 16086
7 |  | W0000304 - 305 | REV - EC683C.6 - PROD. DWG 683( C ), 643 ( S ), 541 (P/S) ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-03 | 2025-03-15 | 1 | ayu | 80 | JC060325 16087
8 |  | W0000304 - 305 | REV - EC515C.6 - PROD. DWG 515( C ), 434 ( P/S ) ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-17 | 2025-03-29 | 1 | ayu | 80 | JC060325 16088
9 |  | W0000304 - 305 | R0 - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-03 | 2025-03-29 | 1 | rama | 60 | JC060325 16089
10 |  | W0000306 - 307 | R0 - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-03 | 2025-03-29 | 1 | rama | 60 | JC060325 16090
11 |  | W0000308 | R0 - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-03 | 2025-03-29 | 1 | rama | 60 | JC060325 16091
12 |  | W0000304 - 305 | REV - EC663S.6 - PROD. DWG 663 ( S ), 553 ( P/S ), 613 (C), 632 (P/S) ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-03 | 2025-03-15 | 1 | yusuf | 80 | JC060325 16092
13 |  | W0000304 - 305 | REV - EC113PS.6 - PROD. DWG 113( P/S ), 133 ( P/S ), 234 (P/S), 315 (P/S) ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-17 | 2025-03-29 | 1 | yusuf | 80 | JC060325 16094
14 |  | W0000304 - 305 | REV - EC524PS.6 - PROD. DWG 524 ( P/S ), 693 ( C ) ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-03 | 2025-03-15 | 1 | yadi | 80 | JC060325 16095
15 |  | W0000304 - 305 | REV - EC114PS.6 - PROD. DWG 114( P/S ), 333 ( C ) ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-17 | 2025-03-29 | 1 | yadi | 80 | JC060325 16096
16 |  | W0000304 - 305 | REV - EC132PS.6 - PROD. DWG 132 ( P/S ), 622 ( P/S ) ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-03 | 2025-03-15 | 1 | irwan | 80 | JC060325 16097
17 |  | W0000304 - 305 | REV - EC623C.6 - PROD. DWG 623 ( C ), 134 ( P/S ) ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-17 | 2025-03-29 | 1 | irwan | 80 | JC060325 16098
18 |  | W0000306 - 307 | REV - EC621U.6 - PROD. DWG 621 (P/S), 112 (P/S) ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-03 | 2025-03-15 | 1 | rois | 80 | JC080325 16235
19 |  | W0000306 - 307 | REV - EC622U.6 - PROD. DWG 622 (P/S), 623 (P/S) ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-17 | 2025-03-29 | 1 | rois | 80 | JC080325 16236
20 |  | W0000308 | REV - EC223UC.6 - PROD. DWG 223 (P/S), 111 (P/S), 124 (P/S), 132 (P/S), 114 (P/S) ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-03 | 2025-03-15 | 1 | roni | 80 | JC080325 16237
21 |  | W0000308 | REV - EC114U.6 - PROD. DWG 221 (P/S), 214 (P/S), 233 (P/S), 411 (P/S) ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-17 | 2025-03-29 | 1 | roni | 80 | JC080325 16238
22 |  | KPI 2024 | Support data pendukung mat list serta gambar produksi untuk project Frigate, LPD UAE, LD Phil | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-03 | 2025-03-29 | 1 | nizhar | 160 | JC080325 16240
23 |  | KPI 2024 | Support data pendukung mat list serta gambar produksi untuk project Frigate, LPD UAE, LD Phil | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-03 | 2025-03-29 | 1 | nur zak | 160 | JC080325 16241
24 |  | KPI 2024 |  | 1CK300 - Biro Gambar Produksi Lambung | 2025-03-17 | 2025-03-21 | 1 | mila | 60 | JC240325 16972
2025-04-01
1 | PERBANTUAN | KPI 2025 | E11002.03103 - FORE CONSTRUCTION (MODELLING & OUTPUT 2D) | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-07 | 2025-05-03 | 1 | yadi |  | JC300425 18642 |  | A
2 |  | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-07 | 2025-05-03 | 1 | mila |  | JC100425 17549 |  | A
3 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-07 | 2025-05-03 | 1 | mila |  | JC100425 17552 |  | A
4 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-07 | 2025-05-03 | 1 | mila |  | JC100425 17553 |  | A
5 |  | W0000308 | REV - EC324U.6 - PROD. DWG 324 (P/S), 332 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-07 | 2025-04-18 | 1 | zakiyah |  | JC100425 17554 |  | A
6 |  | W0000308 | REV - EC333U.6 - PROD. DWG 333 (P/S), 334 (P/S), 343 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-21 | 2025-05-03 | 1 | zakiyah |  | JC100425 17555 |  | A
7 |  | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-07 | 2025-05-03 | 1 | rama |  | JC100425 17556 |  | A
8 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-07 | 2025-05-03 | 1 | rama |  | JC100425 17557 |  | A
9 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-07 | 2025-05-03 | 1 | rama |  | JC100425 17558 |  | A
10 |  | W0000306 - 307 | R3 - EC213U.6 - PROD. DWG 213 (P/S), 511 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-07 | 2025-04-19 | 1 | rois |  | JC100425 17559 |  | A
11 |  | W0000308 | R1 - EC443U.6 - PROD. DWG 443 (P/S), 454 (P/S) ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-21 | 2025-05-03 | 1 | rois |  | JC100425 17560 |  | A
12 |  | W0000308 | CEK 3D MODEL, WBS, BLOK 231 (P/S), 123 (P/S), 111 (P/S) | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-07 | 2025-04-15 | 1 | roni |  | JC100425 17561 |  | A
13 |  | W0000308 | CEK 3D MODEL, WBS, BLOK 131 (P/S), 641 (P/S), 631 (P/S) | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-16 | 2025-04-24 | 1 | roni |  | JC100425 17562 |  | A
14 |  | W0000308 | CEK 3D MODEL, WBS, BLOK 611 (P/S), 621 (P/S) | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-25 | 2025-05-03 | 1 | roni |  | JC100425 17563 |  | A
15 |  | KPI 2025 | Support data pendukung mat list serta gambar produksi untuk project Frigate, LPD UAE, LD Phil | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-07 | 2025-05-03 | 1 | nizhar |  | JC300425 18639 |  | A
16 |  | KPI 2025 | Support data pendukung mat list serta gambar produksi untuk project Frigate, LPD UAE, LD Phil | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-07 | 2025-05-03 | 1 | nur zak |  | JC300425 18638 |  | A
17 |  | W0000304 - 305 | REV - EC633C.6 - PROD. DWG 633( C ), 523 (P/S), 111 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-07 | 2025-04-19 | 1 | ayu |  | JC100425 17590 |  | A
18 |  | W0000304 - 305 | REV - EC233PS.6 - PROD. DWG 233(P/S), 652 (P/S), 114 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-21 | 2025-05-03 | 1 | ayu |  | JC100425 17592 |  | A
19 |  | W0000304 - 305 | REV - EC221PS.6 - PROD. DWG 221( P/S ), 241 (P/S), 211 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-07 | 2025-04-19 | 1 | yusuf |  | JC100425 17593 |  | A
20 |  | W0000304 - 305 | REV - EC231PS.6 - PROD. DWG 231 (P/S), 121 (P/S), 512 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-21 | 2025-05-03 | 1 | yusuf |  | JC100425 17594 |  | A
21 |  | W0000304 - 305 | REV - EC424PS.6 - PROD. DWG 424 (P/S), 223 (P/S), 213 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-07 | 2025-04-19 | 1 | irwan |  | JC100425 17595 |  | A
22 |  | W0000304 - 305 | REV - EC433PS.6 - PROD. DWG 433 (P/S), 233 (P/S), 652 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-21 | 2025-05-03 | 1 | irwan |  | JC100425 17596 |  | A
23 |  | KPI 2025 | Mengisi RCSA 2025 | 1CK300 - Biro Gambar Produksi Lambung | 2025-04-07 | 2025-04-17 | 1 | mila |  | JC300425 18643
2025-05-01
1 |  | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-05 | 2025-05-31 | 1 | mila |  | JC090525 19201
2 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-05 | 2025-05-31 | 1 | mila |  | JC090525 19202
3 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-05 | 2025-05-31 | 1 | mila |  | JC090525 19203
4 |  | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-05 | 2025-05-31 | 1 | rama |  | JC090525 19204
5 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-05 | 2025-05-31 | 1 | rama |  | JC090525 19205
6 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-05 | 2025-05-31 | 1 | rama |  | JC090525 19206
7 |  | W0000308 | REV - EC121U.6 - PROD. DWG 121 (P/S), 131 (P/S), 133 (P/S), 112 (P/S),( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-05 | 17-May-25 | 1 | zakiyah |  | JC090525 19208
8 |  | W0000308 | REV - EC442U.6 - PROD. DWG 442 (P/S), 344 (P/S), 364 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-19 | 31-May-25 | 1 | zakiyah |  | JC090525 19209
9 |  | W0000308 | REV - EC422U.6 - PROD. DWG 422 (P/S), 452 (P/S), 641 (P/S), 511 (P/S),( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-05 | 17-May-25 | 1 | roni |  | JC090525 19214
10 |  | W0000308 | REV - EC323U.6 - PROD. DWG 323 (P/S), 353 (P/S), 313 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-19 | 31-May-25 | 1 | roni |  | JC090525 19215
11 |  | E250N002 | R0 - EC111C.6 - PROD. DWG 111 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-05 | 17-May-25 | 1 | ayu |  | JC150525 19384
12 |  | E250N002 | R0 - EC151U.6 - PROD. DWG 151 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-19 | 31-May-25 | 1 | ayu |  | JC130525 19252
13 |  | E250N002 | R0 - EC121C.6 - PROD. DWG 121 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-05 | 17-May-25 | 1 | yusuf |  | JC150525 19386
14 |  | E250N002 | R0 - EC131U.6 - PROD. DWG 131 (P/S), 141 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-19 | 31-May-25 | 1 | yusuf |  | JC150525 19387
15 |  | W0000304 - 305 | REV - EC514C.6 - PROD. DWG 514 (C), 623 (C), 693 (C), 111 (P/S) , ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-05 | 17-May-25 | 1 | irwan |  | JC130525 19263
16 |  | W0000304 - 305 | REV - EC112PS.6 - PROD. DWG112 (P/S), 122 (P/S), 313 (C), 212 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-19 | 31-May-25 | 1 | irwan |  | JC130525 19266
17 |  | KPI 2025 | Support data pendukung mat list serta gambar produksi untuk project Frigate, LPD UAE, LD Phil | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-05 | 2025-05-31 | 1 | nizhar |  | JC130525 19271
18 |  | KPI 2025 | Support data pendukung mat list serta gambar produksi untuk project Frigate, LPD UAE, LD Phil | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-05 | 2025-05-31 | 1 | nur zak |  | JC130525 19272
19 |  | KPI 2025 | E190N025 - E11002.03103 - FORE CONSTRUCTION (MODELLING & OUTPUT 2D) | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-05 | 2025-05-31 | 1 | yadi |  | JC130525 19273
20 |  | KPI 2025 | E190N025 - E11002.03103 - FORE CONSTRUCTION (MODELLING & OUTPUT 2D) | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-05 | 2025-05-31 | 1 | rois |  | JC130525 19274
21 |  | KPI 2025 | Mengisi RCSA 2025 | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-05 | 2025-05-10 | 1 | mila |  | JC130525 19275
22 |  | E250N002 | R0 - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-19 | 31-May-25 | 1 | mila |  | JC260525 19874
23 |  | E250N002 | R0 - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-05-19 | 31-May-25 | 1 | rama |  | JC260525 19875
1 |  | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-02 | 2025-06-30 | 1 | mila |  | JC120625 20668
2 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-02 | 2025-06-30 | 1 | mila |  | JC120625 20669
3 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-02 | 2025-06-30 | 1 | mila |  | JC120625 20670
4 |  | E250N002 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-02 | 2025-06-30 | 1 | mila |  | JC120625 20671
5 |  | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-02 | 2025-06-30 | 1 | rama |  | JC120625 20672
6 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-02 | 2025-06-30 | 1 | rama |  | JC120625 20674
7 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-02 | 2025-06-30 | 1 | rama |  | JC120625 20676
8 |  | E250N002 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-02 | 2025-06-30 | 1 | rama |  | JC120625 20677
9 |  | W0000308 | REV - EC214U.6 - PROD. DWG 214 (P/S), 224 (P/S), 234 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-02 | 2025-06-14 | 1 | zakiyah |  | JC120625 20678
10 |  | W0000308 | REV - EC424U.6 - PROD. DWG 424 (P/S), 434 (P/S), 444 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-16 | 2025-06-30 | 1 | zakiyah |  | JC120625 20679
11 |  | W0000308 | REV - EC212U.6 - PROD. DWG 212 (P/S), 123 (P/S), 114 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-02 | 2025-06-14 | 1 | roni |  | JC120625 20681
12 |  | W0000308 | REV - EC124U.6 - PROD. DWG 124 (P/S), 134 (P/S), 454 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-16 | 2025-06-30 | 1 | roni |  | JC120625 20682
13 |  | E250N002 | R0 - EC131U.6 - PROD. DWG 131 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-02 | 2025-06-30 | 1 | ayu |  | JC120625 20691
14 |  | W0000304 - 305 | REV - EC122PS.6 - PROD. DWG 122 (P/S), 413 (P/S), 414 (P/S), 424 (P/S) ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-02 | 2025-06-30 | 1 | ayu |  | JC120625 20692
15 |  | E250N002 | REV - EC121C.6 - PROD. DWG 121 (C), 111 (C), 141 (P/S), 151 (P/S, )( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-02 | 2025-06-30 | 1 | yusuf |  | JC120625 20693
16 |  | W0000304 - 305 | REV - EC651PS.6 - PROD. DWG 651 (P/S), 514 (P/S), 155(P/S), 244 (P/S) ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-02 | 2025-06-21 | 1 | irwan |  | JC120625 20694
17 |  | W0000304 - 305 | REV - EC224PS.6 - PROD. DWG224 (P/S), 234 (P/S), 144 (P/S), 324 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-16 | 2025-06-30 | 1 | irwan |  | JC120625 20695
18 |  | KPI 2025 | Support data pendukung mat list serta gambar produksi untuk project Frigate, LPD UAE, LD Phil | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-02 | 2025-06-30 | 1 | nizhar |  | JC120625 20697
19 |  | KPI 2025 | Support data pendukung mat list serta gambar produksi untuk project Frigate, LPD UAE, LD Phil | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-02 | 2025-06-30 | 1 | nur zak |  | JC120625 20698
20 |  | W0000304 - 305 | REV - EC503PS.6 - PROD. DWG 505 (P/S), 154 (P/S) ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-02 | 2025-06-14 | 1 | yadi |  | JC130625 20715
21 |  | KPI 2025 | KEY PLAN, YARD PLAN KSSR 18 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-16 | 2025-06-30 | 1 | yadi |  | JC130625 20716
22 |  | W0000304 - 305 | REV - EC513PS.6 - PROD. DWG 513 (P/S), 612 (P/S), 314 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-02 | 2025-06-30 | 1 | rois |  | JC120625 20705
23 |  | W0000308 | REV - EC213U.6 - PROD. DWG 213 (P/S), 233 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-06-02 | 2025-06-30 | 1 | rois |  | JC120625 20706
1 | 2025-07-04 | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-01 | 2025-07-31 | 1 | mila |  | JC040725 21761
2 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-01 | 2025-07-31 | 1 | mila |  | JC040725 21762
3 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-01 | 2025-07-31 | 1 | mila |  | JC040725 21763
4 |  | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-01 | 2025-07-31 | 1 | rama |  | JC040725 21764
5 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-01 | 2025-07-31 | 1 | rama |  | JC040725 21765
6 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-01 | 2025-07-31 | 1 | rama |  | JC040725 21766
7 |  | W0000308 | REV - EC321C.6 - PROD. DWG 321 (C), 331 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-01 | 2025-07-15 | 1 | zakiyah |  | JC040725 21767
8 |  | W0000308 | REV - EC341C.6 - PROD. DWG 341 (C), 342 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-16 | 2025-07-31 | 1 | zakiyah |  | JC040725 21786
9 |  | W0000308 | REV - EC311U.6 - PROD. DWG 311 (P/S), 622 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-01 | 2025-07-15 | 1 | roni |  | JC040725 21787
10 |  | W0000308 | REV - EC212U.6 - PROD. DWG 212 (P/S), 23 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-16 | 2025-07-31 | 1 | roni |  | JC040725 21788
11 |  | W0000304 - 305 | REV - EC613C.6 - PROD. DWG 613 (C), 542 (P/S), 524 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-01 | 2025-07-19 | 1 | ayu |  | JC040725 21789
12 |  | W0000304 - 305 | REV - EC155PS.6 - PROD. DWG 155 (P/S), 211 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-21 | 2025-07-31 | 1 | ayu |  | JC040725 21790
13 |  | W0000304 - 305 | REV - EC611PS.6 - PROD. DWG 611 (P/S), 333 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-01 | 2025-07-19 | 1 | yusuf |  | JC040725 21791
14 |  | W0000304 - 305 | REV - EC503PS.6 - PROD. DWG 503 (P/S), 663 (S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-21 | 2025-07-31 | 1 | yusuf |  | JC040725 21792
15 |  | W0000304 - 305 | REV - EC134PS.6 - PROD. DWG 134 (P/S),315 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-01 | 2025-07-19 | 1 | irwan |  | JC040725 21793
16 |  | W0000304 - 305 | REV - EC254PS.6 - PROD. DWG254 (P/S), 512 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-21 | 2025-07-31 | 1 | irwan |  | JC040725 21794
17 |  | W0000304 - 305 | REV - EC224PS.6 - PROD. DWG 224 (P/S), 234 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-01 | 2025-07-19 | 1 | rois |  | JC040725 21795
18 |  | W0000304 - 305 | REV - EC244U.6 - PROD. DWG 244 (P/S), 673 (P), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-21 | 2025-07-31 | 1 | rois |  | JC040725 21796
19 |  | KPI 2025 | Support data pendukung mat list serta gambar produksi untuk project Frigate, LPD UAE, LD Phil | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-01 | 2025-07-31 | 1 | nizhar |  | JC070725 21876
20 |  | KPI 2025 | Support data pendukung mat list serta gambar produksi untuk project Frigate, LPD UAE, LD Phil | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-01 | 2025-07-31 | 1 | nur zak |  | JC070725 21880
21 |  | KPI 2025 | KEY PLAN, YARD PLAN KSSR 18 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-01 | 2025-07-31 | 1 | yadi |  | JC070725 21885
22 |  | KPI 2025 | KEY PLAN, YARD PLAN KCB AUTONOMOUS 8 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-01 | 2025-07-31 | 1 | yadi |  | JC070725 21888
23 | 2025-07-30 | KPI 2025 | KEY PLAN, YARD PLAN KAPAL AUTONOMOUS 8 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-07-21 | 2025-07-31 | 1 | rama |  | JC300725 22950
1 | 2025-08-05 | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-01 | 2025-08-30 | 1 | mila |  | JC050825 23292
2 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-01 | 2025-08-30 | 1 | mila |  | JC050825 23293
3 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-01 | 2025-08-30 | 1 | mila |  | JC050825 23294
4 |  | E250N002 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-01 | 2025-08-30 | 1 | mila |  | JC050825 23295
5 |  | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-01 | 2025-08-30 | 1 | rama |  | JC050825 23296
6 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-01 | 2025-08-30 | 1 | rama |  | JC050825 23297
7 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-01 | 2025-08-30 | 1 | rama |  | JC050825 23298
8 |  | E250N002 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-01 | 2025-08-30 | 1 | rama |  | JC050825 23299
9 |  | KPI 2025 | REV - EC000U.6 - PD-HC KAPAL AUTONOMOUS 8 Meter, Nesting Plate, Apl, Matlist, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-01 | 2025-08-30 | 1 | rama |  | JC050825 23300
10 |  | W0000308 | REV - EC232U.6 - PROD. DWG 232 (P/S), 611 (P/S), 612 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-01 | 2025-08-16 | 1 | zakiyah |  | JC050825 23303
11 |  | W0000308 | REV - EC621U.6 - PROD. DWG 621 (P/S), 631 (P/S), 641 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-18 | 2025-08-30 | 1 | zakiyah |  | JC050825 23304
12 |  | W0000308 | REV - EC624U.6 - PROD. DWG 624 (P/S), 622 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-01 | 2025-08-16 | 1 | roni |  | JC050825 23305
13 |  | W0000308 | REV - EC632U.6 - PROD. DWG 632 (P/S), 653 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-18 | 2025-08-30 | 1 | roni |  | JC050825 23306
14 |  | W0000304 - 305 | REV - EC234PS.6 - PROD. DWG 234 (P/S), 122 (P/S), 523 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-01 | 2025-08-16 | 1 | ayu |  | JC050825 23307
15 |  | W0000304 - 305 | REV - EC542PS.6 - PROD. DWG 542 (P/S), 515 (C), 693 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-18 | 2025-08-30 | 1 | ayu |  | JC050825 23308
16 |  | W0000304 - 305 | REV - EC315PS.6 - PROD. DWG 315 (P/S), 641 (P/S), 414 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-01 | 2025-08-16 | 1 | irwan |  | JC050825 23309
17 |  | W0000304 - 305 | REV - EC513PS.6 - PROD. DWG 513 (P/S), 651 (P/S), 514 (C), 254 (P/S),( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-18 | 2025-08-30 | 1 | irwan |  | JC050825 23310
18 |  | W0000304 - 305 | REV - EC521PS.6 - PROD. DWG 521 (P/S), 324 (P/S), 155 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-01 | 2025-08-16 | 1 | rois |  | JC050825 23311
19 |  | W0000304 - 305 | REV - EC612PS.6 - PROD. DWG 612 (P/S), 623 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-18 | 2025-08-30 | 1 | rois |  | JC050825 23312
20 |  | E250N002 | REV - EC111C.6 - PROD. DWG 111 (C), 121 (C), 141 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-01 | 2025-08-23 | 1 | yusuf |  | JC050825 23314
21 |  | W0000304 - 305 | REV - EC613C.6 - PROD. DWG 613 (C), 244 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-25 | 2025-08-30 | 1 | yusuf |  | JC050825 23315
22 |  | KPI 2025 | KEY PLAN, YARD PLAN, PD-HC KAPAL AUTONOMOUS 8 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-01 | 2025-08-30 | 1 | yadi |  | JC050825 23316
23 |  | KPI 2025 | Support data pendukung mat list serta gambar produksi untuk project Frigate, LPD UAE, LD Phil, AUTONOMOUS 8 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-01 | 2025-08-30 | 1 | nizhar |  | JC050825 23317
24 |  | KPI 2025 | Support data pendukung mat list serta gambar produksi untuk project Frigate, LPD UAE, LD Phil, AUTONOMOUS 8 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-08-01 | 2025-08-30 | 1 | nur zak |  | JC050825 23318
2025-09-01
1 | 2025-09-13 | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-30 | 1 | mila |  | JC130925 24945
2 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-30 | 1 | mila |  | JC130925 24946
3 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-30 | 1 | mila |  | JC130925 24947
4 |  | E250N002 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-30 | 1 | mila |  | JC130925 24948
5 |  | KPI 2025 | Pengisian Identifikasi Resiko tahun 2026 di Website | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-30 | 1 | mila |  | JC130925 24949
6 |  | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-30 | 1 | rama |  | JC130925 24950
7 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-30 | 1 | rama |  | JC130925 24951
8 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-30 | 1 | rama |  | JC130925 24952
9 |  | E250N002 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-30 | 1 | rama |  | JC130925 24953
10 |  | W0000308 | REV - EC344U.6 - PROD. DWG 344 (P/S), 364 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-13 | 1 | zakiyah |  | JC130925 24954
11 |  | W0000308 | REV - EC511U.6 - PROD. DWG 511 (P/S), 525 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-15 | 2025-09-30 | 1 | zakiyah |  | JC130925 24955
12 |  | W0000308 | REV - EC624U.6 - PROD. DWG 624 (P/S), 452 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-13 | 1 | roni |  | JC130925 24956
13 |  | W0000308 | REV - EC612U.6 - PROD. DWG 611 (P/S), 653 (P/S), ( 3D model, Ass Dwg, Lift info ), 3D MODEL MODUL 4 | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-15 | 2025-09-30 | 1 | roni |  | JC130925 24957
14 |  | W0000305 | REV - EC322C.6 - PROD. DWG 322 (C), 541 (P/S), 155 (P/S), 214 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-15 | 1 | ayu |  | JC150925 25028
15 |  | W0000305 | REV - EC652PS.6 - PROD. DWG 652 (P/S), 653 (P/S), 643 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-15 | 1 | irwan |  | JC150925 25030
16 |  | W0000306 - 307 | REV - EC122U.6 - PROD. DWG 122 (P/S), 113 (P/S), 121 (P/S), 131 (C), 114 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-10 | 1 | rois |  | JC150925 25031
17 |  | W0000305 | REV - EC223PS.6 - PROD. DWG 223 (P/S), 663 (S), 673 (P), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-11 | 2025-09-30 | 1 | rois |  | JC150925 25032
18 |  | E250N002 | REV - EC111C.6 - PROD. DWG 111 (C), 121 (C), 131 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-30 | 1 | yusuf |  | JC150925 25059
19 |  | E250N002 | KEY PLAN, YARD PLAN, PONTOON PLTAL 2x20 kW | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-30 | 1 | yadi |  | JC150925 25060
20 |  | KPI 2025 | KEY PLAN, YARD PLAN, PDHC, PALAS - KAPAL AUTONOMOUS 8 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-30 | 1 | yadi |  | JC150925 25061
21 |  | KPI 2025 | KEY PLAN, YARD PLAN, PDHC, KSSR 18 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-30 | 1 | yadi |  | JC150925 25062
22 |  | KPI 2025 | Support data pendukung mat list serta gambar produksi untuk project Frigate, LPD UAE, LD Phil, AUTONOMOUS 8 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-30 | 1 | nizhar |  | JC150925 25063
23 |  | KPI 2025 | Support data pendukung mat list serta gambar produksi untuk project Frigate, LPD UAE, LD Phil, AUTONOMOUS 8 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-01 | 2025-09-30 | 1 | nur zak |  | JC150925 25064
24 |  | W0000305 | REV - EC402C.6 - PROD. DWG 402 (C), 222 (P/S), 232 (P/S), 233 (P/S), ( 3D model, Ass Dwg, Lift info ), REVIEW MODUL 2 | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-16 | 2025-09-30 | 1 | ayu |  | JC260925 25525
25 |  | W0000305 | REV - EC651PS.6 - PROD. DWG 651 (P/S), 652 (P/S), 512 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-09-16 | 2025-09-30 | 1 | irwan |  | JC260925 25526
2025-10-01
1 | 2025-10-08 | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-31 | 1 | mila |  | JC091025 26117
2 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-31 | 1 | mila |  | JC091025 26118
3 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-31 | 1 | mila |  | JC091025 26119
4 |  | E250N002 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-31 | 1 | mila |  | JC091025 26120 | extend date
5 |  | KPI 2025 | Pengisian Identifikasi Resiko tahun 2026 di Website | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-31 | 1 | mila |  | JC091025 26121
6 |  | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-31 | 1 | rama |  | JC091025 26122
7 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-31 | 1 | rama |  | JC091025 26123
8 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-31 | 1 | rama |  | JC091025 26124
9 |  | E250N002 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-31 | 1 | rama |  | JC091025 26125
10 |  | W0000308 | REV - EC324U.6 - PROD. DWG 324 (P/S), 352 (C), 521 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-15 | 1 | zakiyah |  | JC091025 26126
11 |  | W0000308 | REV - EC334U.6 - PROD. DWG 334 (P/S), 212 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-16 | 2025-10-31 | 1 | zakiyah |  | JC091025 26127
12 |  | W0000308 | REV - EC412U.6 - PROD. DWG 412 (P/S), 442 (P/S), 452 (P/S)( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-15 | 1 | roni |  | JC091025 26128
13 |  | W0000308 | REV - EC522U.6 - PROD. DWG 522 (P/S), 422 (P/S), 432 (P/S)( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-16 | 2025-10-31 | 1 | roni |  | JC091025 26129
14 |  | W0000305 | REV - EC514C.6 - PROD. DWG 514 (C), 515 (C), 413 (P/S), 503 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-31 | 1 | ayu |  | JC091025 26130
15 |  | W0000305 | REV - EC222PS.6 - PROD. DWG 222 (P/S), 232 (P/S), 231 (P/S), 511 (P/S), 214 (P/S), 512 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-31 | 1 | irwan |  | JC091025 26131
16 |  | W0000306 - 307 | REV - EC114U.6 - PROD. DWG 114 (P/S), 133 (P/S), 523 (C), 533 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-31 | 1 | rois |  | JC091025 26132
17 |  | W0000308 | REV - EC421C.6 - PROD. DWG 421 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-31 | 1 | rois |  | JC141025 26361 | jc baru
18 |  | E250N002 | REV - EC111C.6 - PROD. DWG 111 (C), 121 (C), 131 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-31 | 1 | yusuf |  | JC091025 26134
19 |  | E250N002 | KEY PLAN, YARD PLAN, PONTOON PLTAL 2x20 kW | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-31 | 1 | yadi |  | JC091025 26135
20 |  | KPI 2025 | KEY PLAN, YARD PLAN, PDHC, PALAS - KAPAL AUTONOMOUS 8 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-31 | 1 | yadi |  | JC091025 26136
21 |  | KPI 2025 | KEY PLAN, YARD PLAN, PDHC, KSSR 18 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-31 | 1 | yadi |  | JC091025 26137
22 |  | KPI 2025 | Develope Cadmatic Hull, Support data pendukung project Frigate, LD Phill, LPD UAE, AUTONOMOUS 8 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-31 | 1 | nizhar |  | JC091025 26138
23 |  | KPI 2025 | Develope Cadmatic Hull, Support data pendukung project Frigate, LD Phill, LPD UAE, AUTONOMOUS 8 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-10-01 | 2025-10-31 | 1 | nur zak |  | JC091025 26139
2025-11-01
1 |  | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-03 | 2025-11-29 | 1 | mila |  | JC101125 27576
2 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-03 | 2025-11-29 | 1 | mila |  | JC101125 27578
3 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-03 | 2025-11-29 | 1 | mila |  | JC101125 27580
4 |  | E250N002 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-03 | 2025-11-29 | 1 | mila |  | JC101125 27581
5 |  | KPI 2025 | MANAGEMENT RESIKO - MEMBUAT RCSA 2026 | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-03 | 2025-11-29 | 1 | mila |  | JC101125 27582
6 |  | W0000308 | REV - EC613C.6 - PROD. DWG 613 (C), 523 (P/S), 633 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-03 | 2025-11-15 | 1 | zakiyah |  | JC101125 27583
7 |  | W0000308 | REV - EC623C.6 - PROD. DWG 623 (C), 444 (P/S), 454 (P/S) ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-17 | 2025-11-29 | 1 | zakiyah |  | JC101125 27584
8 |  | W0000308 | REV - EC4XXU.6 - REVISI MODUL 4, MODIFIKASI BLOK TWS | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-03 | 2025-11-29 | 1 | roni |  | JC101125 27585
9 |  | W0000308 | REV - EC4XXU.6 - REVISI MODUL 4, MODIFIKASI BLOK TWS | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-03 | 2025-11-29 | 1 | rama |  | JC101125 27586
10 |  | W0000305 | REV - EC503PS.6 - PROD. DWG 503 (P/S), 533 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-03 | 2025-11-29 | 1 | ayu |  | JC101125 27587
11 |  | W0000305 | REV - EC144PS.6 - PROD. DWG 144 (P/S), 514 (P/S), 155 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-03 | 2025-11-29 | 1 | irwan |  | JC101125 27588
12 |  | W0000305 | REV - EC523PS.6 - PROD. DWG 523 (P/S), 524 (P/S), 693 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-03 | 2025-11-29 | 1 | yusuf |  | JC101125 27589
13 |  | E250N002 | REV - EC111C.6 - PROD. DWG 111 (C), 121 (C), 131 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-03 | 2025-11-29 | 1 | yusuf |  | JC101125 27590
14 |  | W0000306 - 307 | REV - EC613C.6 - PROD. DWG 613 (C), 113 (P/S), 412 (P/S), 413 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-03 | 2025-11-29 | 1 | rois |  | JC101125 27595
15 |  | W0000306 - JW1 307 | R0 - EC111C.6 - 3D MODEL 111 (C), 121 (C), 131 (C), 112 (C) | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-03 | 2025-11-29 | 1 | rois |  | JC101125 27596
16 |  | E250N002 | KEY PLAN, YARD PLAN, PONTOON PLTAL 2x20 kW | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-03 | 2025-11-29 | 1 | yadi |  | JC101125 27600
17 |  | KPI 2025 | KEY PLAN, YARD PLAN, PDHC, PALAS - KAPAL AUTONOMOUS 8 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-03 | 2025-11-29 | 1 | yadi |  | JC101125 27601
18 |  | KPI 2025 | KEY PLAN, YARD PLAN, PDHC, KSSR 18 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-03 | 2025-11-29 | 1 | yadi |  | JC101125 27602
19 |  | KPI 2025 | Develope Cadmatic Hull, Support data pendukung project Frigate, LD Phill, LPD UAE, AUTONOMOUS 8 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-03 | 2025-11-29 | 1 | nizhar |  | JC101125 27603
20 |  | KPI 2025 | Develope Cadmatic Hull, Support data pendukung project Frigate, LD Phill, LPD UAE, AUTONOMOUS 8 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-11-03 | 2025-11-29 | 1 | nur zak |  | JC101125 27604
2025-12-01
1 | 2025-12-03 | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-12-01 | 2025-12-31 | 1 | mila |  | JC031225 28569
2 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-12-01 | 2025-12-31 | 1 | mila |  | JC031225 28570
3 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-12-01 | 2025-12-31 | 1 | mila |  | JC031225 28571
4 |  | W0000306 - JW1 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-12-01 | 2025-12-31 | 1 | mila |  | JC031225 28572
5 |  | KPI 2025 | MANAGEMENT RESIKO - MEMBUAT RCSA 2026 | 1CK300 - Biro Gambar Produksi Lambung | 2025-12-01 | 2025-12-31 | 1 | mila |  | JC031225 28573
6 |  | KPI 2025 | FIRE BRIEFING & RISK AWARENESS RISK OFFICER BATCH II TAHUN 2025 | 1CK300 - Biro Gambar Produksi Lambung | 2025-12-05 | 2025-12-06 | 1 | mila |  | JC031225 28574
7 |  | W0000308 | REV - EC4XXU.6 - REVISI MODUL 4, MODIFIKASI BLOK TWS | 1CK300 - Biro Gambar Produksi Lambung | 2025-12-01 | 2025-12-31 | 1 | zakiyah |  | JC031225 28575
8 |  | W0000308 | REV - EC4XXU.6 - REVISI MODUL 4, MODIFIKASI BLOK TWS | 1CK300 - Biro Gambar Produksi Lambung | 2025-12-01 | 2025-12-31 | 1 | roni |  | JC031225 28576
9 |  | W0000308 | REV - EC4XXU.6 - REVISI MODUL 4, MODIFIKASI BLOK TWS | 1CK300 - Biro Gambar Produksi Lambung | 2025-12-01 | 2025-12-31 | 1 | rama |  | JC031225 28577
10 |  | W0000306 - 307 | REV - EC214U.6 - PROD. DWG 214 (P/S), 414 (P/S), 424 (P/S), 434 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-12-01 | 2025-12-31 | 1 | rois |  | JC031225 28578
11 |  | W0000306 - JW1 | R0 - EC111C.6 - 3D MODEL 111 (C), 121 (C), 131 (C), 112 (C) | 1CK300 - Biro Gambar Produksi Lambung | 2025-12-01 | 2025-12-31 | 1 | rois |  | JC031225 28579
12 |  | KPI 2025 | KEY PLAN, YARD PLAN, PDHC, PALAS - KAPAL AUTONOMOUS 8 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-12-01 | 2025-12-31 | 1 | yadi |  | JC031225 28580
13 |  | KPI 2025 | KEY PLAN, YARD PLAN, PDHC, KSSR 18 Meter | 1CK300 - Biro Gambar Produksi Lambung | 2025-12-01 | 2025-12-31 | 1 | yadi |  | JC031225 28581
14 | 2025-12-04 | W0000304 - 305 | REV - EC623C.6 - PROD. DWG 623 (C), 693 (C), 513 (P/S), 611 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-12-01 | 2025-12-31 | 1 | ayu |  | JC041225 28600
15 |  | W0000304 - 305 | REV - EC324PS.6 - PROD. DWG 324 (P/S), 631 (P/S), 621 (P/S), 632 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-12-01 | 2025-12-31 | 1 | irwan |  | JC041225 28601
16 |  | W0000304 - 305 | REV - EC532PS.6 - PROD. DWG 532 (P/S), 612 (P/S), 641 (P/S), 651 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-12-01 | 2025-12-31 | 1 | yusuf |  | JC041225 28602
17 | 2025-12-16 | W0000305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2025-12-01 | 2025-12-31 | 1 | mila |  | JC171225 29224
18 | 2025-12-19 | W0000306 - JW1 | R0 - EC131C.6 - 3D MODEL 131 (C), ( 3D model, Ass Dwg, Lift Info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-12-18 | 2025-12-31 | 1 | rama |  | JC191225 29266
19 | 2025-12-19 | W0000306 - JW1 | R0 - EC112C.6 - 3D MODEL 112 (C), ( 3D model, Ass Dwg, Lift Info ) | 1CK300 - Biro Gambar Produksi Lambung | 2025-12-18 | 2025-12-31 | 1 | zakiyah |  | JC191225 29267
2026-01-02
1 | 2026-01-07 | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-01-02 | 2026-01-31 | 1 | mila |  | JC080126 30068
2 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-01-02 | 2026-01-31 | 1 | mila |  | JC080126 30069
3 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-01-02 | 2026-01-31 | 1 | mila |  | JC080126 30070
4 |  | W0000306 - JW1 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-01-02 | 2026-01-31 | 1 | mila |  | JC080126 30071
5 |  | KPI 2025 | PENGISIAN MITIGASI RESIKO TAHUN 2026 | 1CK300 - Biro Gambar Produksi Lambung | 2026-01-02 | 2026-01-31 | 1 | mila |  | JC080126 30072
6 |  | W0000308 | REV - EC4XXU.6 - REVISI MODUL 4, MODIFIKASI BLOK TWS | 1CK300 - Biro Gambar Produksi Lambung | 2026-01-02 | 2026-01-31 | 1 | zakiyah |  | JC080126 30073
7 |  | W0000308 | REV - EC4XXU.6 - REVISI MODUL 4, MODIFIKASI BLOK TWS | 1CK300 - Biro Gambar Produksi Lambung | 2026-01-02 | 2026-01-31 | 1 | roni |  | JC080126 30077
8 |  | W0000308 | REV - EC341C.6 - PROD. DWG 341 (C), 342 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-01-02 | 2026-01-31 | 1 | roni |  | JC080126 30078
9 |  | W0000308 | REV - EC4XXU.6 - REVISI MODUL 4, MODIFIKASI BLOK TWS | 1CK300 - Biro Gambar Produksi Lambung | 2026-01-02 | 2026-01-31 | 1 | rama |  | JC080126 30080
10 |  | W0000306 - 307 | REV - EC623U.6 - PROD. DWG 623 (P/S), 511 (P/S), 621 (P/S), 114 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-01-02 | 2026-01-31 | 1 | rois |  | JC080126 30085
11 |  | W0000306 - JW1 | R0 - EC121C.6 - 121 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-01-02 | 2026-01-31 | 1 | rois |  | JC080126 30084
12 |  | W000311 | R0 - KEY PLAN, YARD PLAN, PDHC, KSSR 18 Meter, ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-01-02 | 2026-01-31 | 1 | yadi |  | JC080126 30087
13 |  | W0000304 - 305 | REV - EC611PS.6 - PROD. DWG 611 (P/S), 414 (P/S), 652 (P/S), 623 (P/S), 511 (P/S), ( Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-01-02 | 2026-01-31 | 1 | ayu |  | JC080126 30088
14 |  | W0000304 - 305 | REV - EC652PS.6 - PROD. DWG 652 (P/S), 611 (P/S), 623 (P/S), 513 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-01-02 | 2026-01-31 | 1 | irwan |  | JC080126 30089
15 |  | W0000304 - 305 | REV - EC511PS.6 - PROD. DWG 511 (P/S), 414 (P/S), 222 (P/S), 232 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-01-02 | 2026-01-31 | 1 | yusuf |  | JC080126 30090
16 |  | W0000306 - JW1 | R0 - EC131C.6 - 3D MODEL 131 (C), ( 3D model, Ass Dwg, Lift Info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-01-02 | 2026-01-31 | 1 | rama |  | JC080126 30083
17 |  | W0000306 - JW1 | R0 - EC112C.6 - 3D MODEL 112 (C), 121 (C), ( 3D model, Ass Dwg, Lift Info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-01-02 | 2026-01-31 | 1 | zakiyah |  | JC080126 30075
18 | 2026-01-26 | W0000306 - JW1 | R0 - EC131C.6 - 3D MODEL 111 (C), ( 3D model, Ass Dwg, Lift Info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-01-19 | 2026-01-31 | 1 | rama |  | JC260126 30681
NO JC RAMADHAN HOURS
2026-02-02
1 | 2026-02-11 | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-02-02 | 2026-02-28 | 1 | mila |  | JC120226 31513 | jc utk tgl 2-18 feb 2026 | JC180226 31746 | jc utk tgl 19-28 feb 2026
2 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-02-02 | 2026-02-28 | 1 | mila |  | JC120226 31514 | jc utk tgl 2-18 feb 2026 | JC180226 31748 | jc utk tgl 19-28 feb 2026
3 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-02-02 | 2026-02-28 | 1 | mila |  | JC120226 31515 | jc utk tgl 2-18 feb 2026 | JC180226 31750 | jc utk tgl 19-28 feb 2026
4 |  | W0000306 - JW1 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-02-02 | 2026-02-28 | 1 | mila |  | JC120226 31516 | jc utk tgl 2-18 feb 2026 | JC180226 31752 | jc utk tgl 19-28 feb 2026
5 |  | KPI 2025 | PENGISIAN MITIGASI RESIKO TAHUN 2026 | 1CK300 - Biro Gambar Produksi Lambung | 2026-02-02 | 2026-02-28 | 1 | mila |  | JC120226 31517 | jc utk tgl 2-18 feb 2026 | JC180226 31753 | jc utk tgl 19-28 feb 2026
6 |  | W000311 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-02-02 | 2026-02-28 | 1 | mila |  | JC120226 31519 | jc utk tgl 2-18 feb 2026 | JC180226 31756 | jc utk tgl 19-28 feb 2026
7 |  | W0000308 | REV - EC341C.6 - PROD. DWG 541 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-02-02 | 2026-02-28 | 1 | zakiyah |  | JC120226 31521 | jc utk tgl 2-18 feb 2026 | JC180226 31761 | jc utk tgl 19-28 feb 2026
8 |  | W0000308 | REV - EC4XXU.6 - REVISI MODUL 4, MODIFIKASI BLOK TWS | 1CK300 - Biro Gambar Produksi Lambung | 2026-02-02 | 2026-02-28 | 1 | zakiyah |  | JC120226 31522 | jc utk tgl 2-18 feb 2026 | JC180226 31764 | jc utk tgl 19-28 feb 2026
9 |  | W0000308 | REV - EC142C.6 - PROD. DWG 142 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-02-02 | 2026-02-28 | 1 | roni |  | JC120226 31523 | jc utk tgl 2-18 feb 2026 | JC180226 31785 | jc utk tgl 19-28 feb 2026
10 |  | W0000308 | REV - EC4XXU.6 - REVISI MODUL 4, MODIFIKASI BLOK TWS | 1CK300 - Biro Gambar Produksi Lambung | 2026-02-02 | 2026-02-28 | 1 | roni |  | JC120226 31524 | jc utk tgl 2-18 feb 2026 | JC180226 31786 | jc utk tgl 19-28 feb 2026
11 |  | W0000308 | REV - EC461C.6 - PROD. DWG 461 (C), ( Yard Plan, 3D model ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-02-02 | 2026-02-28 | 1 | rama |  | JC120226 31525 | jc utk tgl 2-18 feb 2026 | JC180226 31787 | jc utk tgl 19-28 feb 2026
12 |  | W0000306 - 307 | REV - EC214U.6 - PROD. DWG 214 (P/S), 224 (P/S), 124 (P/S), 622 (P/S), 412 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-02-02 | 2026-02-28 | 1 | rois |  | JC120226 31526 | jc utk tgl 2-18 feb 2026 | JC180226 31788 | jc utk tgl 19-28 feb 2026
13 |  | W0000306 - JW1 | R0 - EC111C.6 - 111 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-02-02 | 2026-02-28 | 1 | rois |  | JC120226 31527 | jc utk tgl 2-18 feb 2026 | JC180226 31789 | jc utk tgl 19-28 feb 2026
14 |  | W000311 | R0 - KEY PLAN, YARD PLAN, PDHC, KSSR 18 Meter, ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-02-02 | 2026-02-28 | 1 | yadi |  | JC120226 31520 | jc utk tgl 2-18 feb 2026 | JC180226 31790 | jc utk tgl 19-28 feb 2026
15 |  | W0000304 - 305 | REV - EC612PS.6 - PROD. DWG 612 (P/S), 652 (P/S), 613 (C), 512 (P/S), 503 (P/S), ( Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-02-02 | 2026-02-28 | 1 | ayu |  | JC120226 31528 | jc utk tgl 2-18 feb 2026 | JC180226 31791 | jc utk tgl 19-28 feb 2026
16 |  | W0000304 - 305 | REV - EC511PS.6 - PROD. DWG 511 (P/S), 512 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-02-02 | 2026-02-28 | 1 | irwan |  | JC120226 31529 | jc utk tgl 2-18 feb 2026 | JC180226 31792 | jc utk tgl 19-28 feb 2026
17 |  | W0000304 - 305 | REV - EC613PS.6 - PROD. DWG 613 (P/S), 652 (P/S), 612 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-02-02 | 2026-02-28 | 1 | yusuf |  | JC120226 31530 | jc utk tgl 2-18 feb 2026 | JC180226 31793 | jc utk tgl 19-28 feb 2026
2026-03-02
1 | 2026-03-11 | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-03-02 | 2026-03-31 | 1 | mila |  | JC110326 32749 | jc utk tgl 2-19 maret 2026 | JC260326 33156 | utk tgl 25-31 maret 2026
2 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-03-02 | 2026-03-31 | 1 | mila |  | JC110326 32750 | jc utk tgl 2-19 maret 2026 | JC260326 33157 | utk tgl 25-31 maret 2026
3 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-03-02 | 2026-03-31 | 1 | mila |  | JC110326 32751 | jc utk tgl 2-19 maret 2026 | JC260326 33158 | utk tgl 25-31 maret 2026
4 |  | W0000306 - JW1 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-03-02 | 2026-03-31 | 1 | mila |  | JC110326 32752 | jc utk tgl 2-19 maret 2026 | JC260326 33159 | utk tgl 25-31 maret 2026
5 |  | W000311 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-03-02 | 2026-03-31 | 1 | mila |  | JC110326 32753 | jc utk tgl 2-19 maret 2026 | JC260326 33160 | utk tgl 25-31 maret 2026
6 |  | CORP2026 | MEMBUAT RCSA 2026 Divisi Desain | 1CK300 - Biro Gambar Produksi Lambung | 2026-03-02 | 2026-03-31 | 1 | mila |  | JC110326 32754 | jc utk tgl 2-19 maret 2026 | JC260326 33161 | utk tgl 25-31 maret 2026
7 |  | W0000308 | REV - EC523U.6 - PROD. DWG 523 (P/S), 513 (C), 525 (C), 454 (P/S), 634 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-03-02 | 2026-03-31 | 1 | zakiyah |  | JC110326 32755 | jc utk tgl 2-19 maret 2026 | JC260326 33162 | utk tgl 25-31 maret 2026
8 |  | W0000308 | REV - EC4XXU.6 - REVISI MODUL 4, MODIFIKASI BLOK TWS | 1CK300 - Biro Gambar Produksi Lambung | 2026-03-02 | 2026-03-31 | 1 | zakiyah |  | JC110326 32756 | jc utk tgl 2-19 maret 2026 | JC260326 33163 | utk tgl 25-31 maret 2026
9 |  | W0000308 | REV - EC142C.6 - PROD. DWG 142 (C), 611 (P/S), 612 (P/S), 613 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-03-02 | 2026-03-31 | 1 | roni |  | JC110326 32757 | jc utk tgl 2-19 maret 2026 | JC260326 33164 | utk tgl 25-31 maret 2026
10 |  | W0000308 | REV - EC4XXU.6 - REVISI MODUL 4, MODIFIKASI BLOK TWS | 1CK300 - Biro Gambar Produksi Lambung | 2026-03-02 | 2026-03-31 | 1 | roni |  | JC110326 32758 | jc utk tgl 2-19 maret 2026 | JC260326 33165 | utk tgl 25-31 maret 2026
11 |  | W0000308 | R0 - EC461C.6 - CARGO HEADLING 461 (C), 132 (P), 153 (P/S) Yard Plan, 3D model ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-03-02 | 2026-03-31 | 1 | rama |  | JC110326 32762 | jc utk tgl 2-19 maret 2026 | JC260326 33166 | utk tgl 25-31 maret 2026
12 |  | W0000306 - 307 | REV - EC533U.6 - PROD. DWG 533 (P/S), 424 (P/S), 434 (P/S), 633 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-03-02 | 2026-03-31 | 1 | rois |  | JC110326 32763 | jc utk tgl 2-19 maret 2026 | JC260326 33167 | utk tgl 25-31 maret 2026
13 |  | W0000306 - JW1 | REV - EC111C.6 - 111 (C), 121 (C), 112(C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-03-02 | 2026-03-31 | 1 | rois |  | JC110326 32764 | jc utk tgl 2-19 maret 2026 | JC260326 33168 | utk tgl 25-31 maret 2026
14 |  | W000311 | REV - KEY PLAN, YARD PLAN, PDHC, KSR 18 Meter, ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-03-02 | 2026-03-31 | 1 | yadi/felix |  | JC110326 32765 | jc utk tgl 2-19 maret 2026 | JC260326 33169 | utk tgl 25-31 maret 2026
15 |  | W0000304 - 305 | REV - EC511PS.6 - PROD. DWG 511 (P/S), 503 (P/S), 153 (P/S), 154 (P/S), ( Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-03-02 | 2026-03-31 | 1 | ayu |  | JC110326 32766 | jc utk tgl 2-19 maret 2026 | JC260326 33170 | utk tgl 25-31 maret 2026
16 |  | W0000304 - 305 | REV - EC153PS.6 - PROD. DWG 153 (P/S), 154 (P/S), 155(P/S), 651 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-03-02 | 2026-03-31 | 1 | irwan |  | JC110326 32768 | jc utk tgl 2-19 maret 2026 | JC260326 33171 | utk tgl 25-31 maret 2026
17 |  | W0000304 - 305 | REV - EC511PS.6 - PROD. DWG 511 (P/S), 503 (P/S), 114 (P/S), 112 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-03-02 | 2026-03-31 | 1 | yusuf |  | JC110326 32769 | jc utk tgl 2-19 maret 2026 | JC260326 33172 | utk tgl 25-31 maret 2026
18 |  | W0000304 - 305 | R0 -E11672.33103 - Nesting Plate, Nc Code Detail of blast door equipment | 1CK300 - Biro Gambar Produksi Lambung | 2026-03-09 | 2026-03-31 | 1 | rama |  | JC170326 33047 | jc utk tgl 9-19 maret 2026 | JC310326 33439 | utk tgl 25-31 maret 2026
19 |  | W0000308 | R0 - EC461C.6 - CARGO HEADLING 461 (C), 132 (P), 153 (P/S) Yard Plan, 3D model ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-03-09 | 2026-03-31 | 1 | rois |  | JC250326 33104 | jc utk tgl 9-19 maret 2026 | JC250326 33151 | utk tgl 25-31 maret 2026
2026-04-01
1 | 2026-04-08 | W0000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | mila |  | JC080426 33812
2 |  | W0000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | mila |  | JC080426 33813
3 |  | W0000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | mila |  | JC080426 33814
4 |  | W0000306 - JW1 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | mila |  | JC080426 33815
5 |  | W000311 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | mila |  | JC090426 33826
6 |  | CORP2026 | MEMBUAT RCSA 2026 Divisi Desain | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | mila |  | JC090426 33828
7 |  | W0000308 | REV - E132U.6 - PROD. DWG 132 (P/S), 461 (C), 525 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | zakiyah |  | JC090426 33829
8 |  | W0000308 | REV - EC4XXU.6 - REVISI MODUL 4, MODIFIKASI BLOK TWS | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | zakiyah |  | JC090426 33830
9 |  | W0000308 | REV - EC613C.6 - PROD. DWG 613 (C), 142 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | roni |  | JC090426 33832
10 |  | W0000308 | REV - EC4XXU.6 - REVISI MODUL 4, MODIFIKASI BLOK TWS | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | roni |  | JC090426 33833
11 |  | W0000308 | R0 - EC133U.6 - CARGO HEADLING 133 (P/S), 134 (P/S), Yard Plan, 3D model | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | rama |  | JC090426 33835
12 |  | W0000306 - 307 | REV - EC424U.6 - PROD. DWG 424 (P/S), 434 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | rois |  | JC090426 33840
13 |  | W0000306 - JW1 | REV - EC111C.6 - 111 (C), 121 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | rois |  | JC090426 33841
14 |  | W0000308 | R0 - EC153U.6 - PROD DWG, CARGO HEADLING 153 (P/S), 122 (P/S), 123 (P/S) Yard Plan, 3D model | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | rois |  | JC090426 33836
15 |  | W000311 | REV - KEY PLAN, YARD PLAN, PDHC, KSR 18 Meter, ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | yadi/felix |  | JC090426 33827
16 |  | W0000304 - 305 | REV - EC542PS.6 - PROD. DWG 542 (P/S), ( Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | ayu |  | JC090426 33842
17 |  | W0000308 | REV - EC241U.6 - PROD. DWG 241 (P/S), 442 (P/S), ( Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | ayu |  | JC090426 33837
18 |  | W0000304 - 305 | REV - EC542PS.6 - PROD. DWG 542 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | irwan |  | JC090426 33843
19 |  | W0000308 | REV - EC453U.6 - PROD. DWG 453 (P/S), 442 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | irwan |  | JC090426 33838
20 |  | W0000308 | REV - EC241U.6 - PROD. DWG 241 (P/S), 461(P/S, )452 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-01 | 2026-04-30 | 1 | yusuf |  | JC090426 33839
21 |  | W0000306 - 307 | REV - EC313U.6 - PROD. DWG 313 (P/S), 314 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-04-17 | 2026-04-30 | 1 | zakiyah |  | JC210426 34253
2026-05-04
1 | 2026-05-14 | W000304 - 305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | mila |  | JC180526 35145
2 |  | W000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | mila |  | JC180526 35146
3 |  | W000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | mila |  | JC180526 35147
4 |  | M000312 | R0 - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | mila |  | JC180526 35148
5 |  | W000304 - 305 | REV - EC621PS.6 - PROD. DWG 621 (P/S), 611 (P/S), 511(P/S), 514(P/S) ( Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | ayu |  | JC180526 35149
6 |  | M000312 | R0 - EC521C.6 - PROD. DWG 521 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | ayu |  | JC180526 35150
7 |  | W000306 - 307 | REV - EC314U.6 - PROD. DWG 314 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | zakiyah |  | JC180526 35151
8 |  | W000308 | REV - E122U.6 - PROD. DWG 122 (P/S), 123 (P/S), ( Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | zakiyah |  | JC180526 35152
9 |  | M000312 | R0 - EC112CC.6 - PROD. DWG 112 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | zakiyah |  | JC180526 35153
10 |  | W000306 - 307 | REV - EC422U.6 - PROD. DWG 422 (P/S), 432 (P/S), 311 (C), 533 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | rois |  | JC180526 35154
11 |  | W000308 | REV - EC123U.6 - PROD DWG, CARGO HEADLING 123 (P/S), ( Yard Plan, 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | rois |  | JC180526 35155
12 |  | M000312 | R0 - EC121C.6 - PROD. DWG 121 (C), ( Yard Plan, 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | rois |  | JC180526 35156
13 |  | W000311 | REV - KEY PLAN, YARD PLAN, PDHC, KSR 18 Meter, ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | yadi/felix |  | JC180526 35157
14 |  | W000304 - 305 | REV - EC514CU.6 - PROD. DWG 514 (C), 611 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | yusuf |  | JC180526 35158
15 |  | M000312 | R0 - EC122C.6 - PROD. DWG 122 (C), ( Yard Plan, 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | yusuf |  | JC180526 35159
16 |  | W000306 - 307 | REV - E11002.03103 - Fore Construction ( pergeseran Ammo Lift ), Yard Plan | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | rama |  | JC180526 35160
17 |  | W000308 | REV - E11001.03101 - Construction Profile and Deck Plan, Cargo Headling Vehicle Lift, Update Maker | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | rama |  | JC180526 35161
18 |  | M000312 | R0 - Midship Section and Construction Profile, Key Plan | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | rama |  | JC180526 35162
19 |  | W000308 | REV - EC4XXU.6 - REVISI MODUL 4, MODIFIKASI BLOK TWS | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | roni |  | JC180526 35163
20 |  | W000304 - 305 | REV - EC621PS.6 - PROD. DWG 621 (P/S), 511(P/S), 542(P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | irwan |  | JC180526 35164
|  | W000308 | REV - EC453U.6 - PROD. DWG 453 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | irwan |  | JC180526 35165
22 |  | M000312 | R0 - EC212C.6 - PROD. DWG 212 (C), ( Yard Plan, 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-05-04 | 2026-05-30 | 1 | irwan |  | JC180526 35166
2026-06-05
1 | 2026-06-10 | W000305 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | mila |  | JC100626 36227
2 |  | W000306 - 307 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | mila |  | JC100626 36232
3 |  | W000308 | REV - EC000U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | mila |  | JC100626 36238
4 |  | M000312 | R0 - EC000C.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code, Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | mila |  | JC100626 36242
5 |  | W000305 | REV - EC423PS.6 - PROD. DWG 423(P/S) ( Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | ayu |  | JC100626 36231
6 |  | M000312 | R0 - EC111C.6 - PROD. DWG 111 (C), 422 (C) ( 3D model, Ass Dwg, Lift info ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | ayu |  | JC100626 36243
7 |  | W000306 - 307 | REV - EC323U.6 - PROD. DWG 323 (P/S), ( Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | zakiyah |  | JC100626 36233
8 |  | W000308 | REV - EC414U.6 - PROD. DWG 414 (P/S), ( Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | zakiyah |  | JC100626 36239
9 |  | M000312 | R0 - EC112C.6 - PROD. DWG 112 (C), 422 (C) ( 3D model, Ass Dwg, Lift info ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | zakiyah |  | JC100626 36244
10 |  | W000306 - 307 | REV - EC323U.6 - PROD. DWG 323 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | rois |  | JC100626 36235
11 |  | M000312 | R0 - EC121C.6 - PROD. DWG 121 (C), 422 (C) ( 3D model, Ass Dwg, Lift info ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | rois |  | JC100626 36245
12 |  | W000311 | REV - KEY PLAN, YARD PLAN, PDHC, KSR 18 Meter, ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | yadi/felix |  | JC100626 36249
13 |  | M000312 | R0 - EC511C.6 - PROD. DWG 511 (C), 512 (C), 521 (C) ( 3D model, Yard Plan ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | yadi/felix |  | JC100626 36246
14 |  | M000312 | R0 - EC122C.6 - PROD. DWG 122 (C), ( 3D model, Ass Dwg, Lift info ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | yusuf |  | JC100626 36247
15 |  | W000306 - 307 | REV - E15755.03101 - Bow Ramp constructon Yard Plan, LD PHILL - LCU | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | rama |  | JC100626 36237
16 |  | W000306 - 307 | REV - E11002.03103 - Fore Construction Yard Plan, blok 323 (P/S) Update Maker Winlass | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | rama |  | JC100626 36236
17 |  | W000308 | R0 - EC463C.6 - 463 (C) tern Ramp , 3D Model | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | rama |  | JC100626 36240
18 |  | W000308 | REV - EC4XXU.6 - REVISI MODUL 4, MODIFIKASI BLOK TWS | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | roni |  | JC100626 36241
19 |  | M000312 | R0 - EC111C.6 - PROD. DWG 111 (C), 212 (C), ( 3D model, Ass Dwg, Lift info ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | irwan |  | JC100626 36248
20 |  | W000308 | R0 - EC463C.6 - PROD. DWG 463 (C),153 (P/S),( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-06-01 | 2026-06-30 | 1 | rois |  | JC290626 36868
2026-07-10
1 | 2026-07-10 | W000304 - 305 | REV - EC515PS.6 - PROD. DWG 515(P/S) ( Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | ayu |  | JC130726 37508
2 |  | M000312 | R0 - EC111C.6 - PROD. DWG 111 (C), 122 (C), 422 (C) ( 3D model, Ass Dwg, Lift info ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | ayu |  | JC130726 37511
3 |  | M000313 | R0 - EC111C.6 - PROD. DWG 111 (C), ( 3D model, Check Dwg PDHC ), Geomarin III | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | ayu |  | JC130726 37513
4 |  | W000308 | REV - EC414U.6 - PROD. DWG 414 (P/S), ( Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | zakiyah |  | JC130726 37514
5 |  | M000312 | R0 - EC112C.6 - PROD. DWG 112 (C), 322 (C) ( 3D model, Ass Dwg, Lift info ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | zakiyah |  | JC130726 37515
6 |  | M000313 | R0 - EC121C.6 - PROD. DWG 121 (C), ( 3D model, Check Dwg PDHC ), Geomarin III | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | zakiyah |  | JC130726 37517
7 |  | W000306 - 307 | REV - EC312C.6 - PROD. DWG 312 (C), 131 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | rois |  | JC130726 37521
8 |  | W000308 | R0 - EC463C.6 - PROD. DWG 463 (C), 153 (P/S), 123 (P/S), ( 3D model, Ass Dwg, Lift info, Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | rois |  | JC130726 37522
9 |  | M000312 | R0 - EC121C.6 - PROD. DWG 121 (C), ( 3D model, Ass Dwg, Lift info ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | rois |  | JC130726 37532
10 |  | W000304 - 305 | REV - EC515PS.6 - PROD. DWG 515 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | yusuf |  | JC130726 37537
11 |  | M000312 | R0 - EC122C.6 - PROD. DWG 122 (C), 422 (C), ( 3D model, Ass Dwg, Lift info ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | yusuf |  | JC130726 37541
12 |  | M000313 | R0 - EC211C.6 - PROD. DWG 211 (C), ( 3D model, Ass Dwg, Lift info ), Geomarin III | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | yusuf |  | JC130726 37543
13 |  | W000308 | REV - EC624U.6 - PROD. DWG 624 (P/S), 631 (P/S), 632 (P/S), 364 (P/S), (3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | roni |  | JC130726 37547
14 |  | M000312 | R0 - EC111C.6 - PROD. DWG 111 (C), 212 (C), 512 (C), 521 (C), ( 3D model, Ass Dwg, Lift info ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | irwan |  | JC130726 37551
15 |  | M000313 | R0 - EC112C.6 - PROD. DWG 112 (C), ( Check Dwg PDHC ), Geomarin III | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | irwan |  | JC130726 37553
16 |  | W000311 | REV - KEY PLAN, YARD PLAN, PDHC, KSR 18 Meter, ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | yadi/felix |  | JC130726 37554
17 |  | M000312 | R0 - EC511C.6 - PROD. DWG 511 (C), 512 (C), 521 (C), 522 (C), ( 3D model, Yard Plan ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | yadi/felix |  | JC130726 37557
18 |  | M000313 | R0 - E11110.03101 - KEY PLAN SHELL EXPNASION 3D model, Geomarin III | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | yadi/felix |  | JC130726 37559
19 |  | W000308 | REV - EC463C.6 - 3D model, Yard Plan | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | rama |  | JC130726 37560
20 |  | M000313 | R0 - 3D model Inner part Upper deck | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | rama |  | JC130726 37561
21 |  | CORP 2026 | Melaksanakan Pelatihan Offset OF-02 FACM, Sefine Shipyard dan Design Company | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | mila |  | JC140726 37640
22 |  | M000312 | R0 - EC512C.6 - 512 (C), 522 (C), 122 (C), 121 (C), ( 3D model Pedestal, Tiang Mast ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-07-01 | 2026-07-31 | 1 | rama |  | JC230726 37956
2026-08-11
1 | 2026-08-10 | W000304 - 305 | REV - EC621PS.6 - 621(P/S), 541(P/S), 651(P/S), 424(P/S) Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | mila |  | JC180826 39094 JC190826 39177 |  | 07.00 - 15.00
2 |  | W000306 - 307 | REV - EC443U.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | mila |  | JC120826 38836 JC180826 39096 |  | 07.00 - 15.00
3 |  | W000308 | REV - EC414U.6 - 414(P/S), 413(P/S), 412(P/S), Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | mila |  | JC120826 38837 JC180826 39097 |  | 07.00 - 15.00
4 |  | M000312 | REV - EC112C.6 - 112 (C), 212 (C)Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | mila |  | JC120826 38838 |  | 07.30 - 16.30
5 |  | M000313 | R0 - EC111C.6 - Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | mila |  | JC120826 38839 |  | 07.30 - 16.30
6 |  | W000304 - 305 | REV - EC212PS.6 - PROD. DWG 212(P/S),222(P/S),424(P/S),505(P/S),611(P/S), ( Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | ayu |  | JC120826 38840 JC180826 39120 |  | 07.00 - 15.00
7 |  | M000312 | REV - EC212C.6 - PROD. DWG 212 (C), 422 (C), 521 (C) ( Check Dwg PDHC ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | ayu |  | JC120826 38841 |  | 07.30 - 16.30
8 |  | M000313 | R0 - EC111C.6 - PROD. DWG 111 (C), ( 3D model, Check Dwg PDHC ), Geomarin V | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | ayu |  | JC120826 38842 |  | 07.30 - 16.30
9 |  | W000308 | REV - EC414U.6 - PROD. DWG 414 (P/S), 413 (P/S), 412 (P/S), 613 (C)( Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | zakiyah |  | JC120826 38843 JC180826 39124 |  | 07.00 - 15.00
10 |  | M000312 | REV - EC111C.6 - PROD. DWG 111 (C), 511 (C), 322 (C), ( Check Dwg PDHC ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | zakiyah |  | JC120826 38844 |  | 07.30 - 16.30
11 |  | M000313 | R0 - EC111C.6 - PROD. DWG 111 (C), ( 3D model, Check Dwg PDHC ), Geomarin V | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | zakiyah |  | JC120826 38845 |  | 07.30 - 16.30
12 |  | W000306 - 307 | REV - EC443C.6 - PROD. DWG 443 (C), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | rois |  | JC120826 38846 JC180826 39130 |  | 07.00 - 15.00
13 |  | W000308 | REV - EC463C.6 - PROD. DWG 463 (C), 153 (P/S), ( 3D model, Ass Dwg, Lift info, Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | rois |  | JC120826 38847 JC180826 39133 |  | 07.00 - 15.00
14 |  | M000312 | REV - EC121C.6 - PROD. DWG 121 (C), ( 3D model, Ass Dwg, Lift info ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | rois |  | JC120826 38848 |  | 07.30 - 16.30
15 |  | W000304 - 305 | REV - EC503PS.6 - PROD. DWG 503 (P/S), ( 3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | yusuf |  | JC120826 38849 JC180826 39135 |  | 07.00 - 15.00
16 |  | M000312 | REV - EC422C.6 - PROD. DWG 422 (C), 511(C), 522 (C), ( 3D model, Ass Dwg, Lift info ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | yusuf |  | JC120826 38850 |  | 07.30 - 16.30
17 |  | M000313 | R0 - EC211C.6 - PROD. DWG 211 (C), ( 3D model, Ass Dwg, Lift info ), Geomarin V | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | yusuf |  | JC120826 38851 |  | 07.30 - 16.30
18 |  | W000308 | REV - EC414U.6 - PROD. DWG 414 (P/S), 413 (P/S), 412 (P/S), 613 (P/S), 612(P/S), (3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | roni |  | JC120826 38852 JC180826 39136 |  | 07.00 - 15.00
19 |  | M000312 | REV - EC212C.6 - PROD. DWG 212 (C), 521 (C), ( 3D model, Ass Dwg, Lift info ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | irwan |  | JC120826 38853 |  | 07.30 - 16.30
20 |  | W000305 | REV - EC611PS.6 - PROD. DWG 611 (P/S), (3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | irwan |  | JC120826 38854 |  | 07.30 - 16.30
21 |  | W000304 - 305 | REV - EC503PS.6 - 503(P/S), 322(P/S), Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | ainy |  | JC120826 38855 JC180826 39137 |  | 07.00 - 15.00
22 |  | W000306 - 307 | REV - EC213U.6 - 213 (P/S), Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | ainy |  | JC120826 38857 |  | 07.30 - 16.30
23 |  | W000308 | REV - EC512U.6 - 512(P/S), 523(P/S),522(P/S), Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | ainy |  | JC120826 38858 JC180826 39109 |  | 07.00 - 15.00
24 |  | M000312 | REV - EC511C.6 - 511(C), Estimasi material Plate&Profi Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | ainy |  | JC120826 38859 |  | 07.30 - 16.30
25 |  | M000313 | R0 - EC111C.6 - Estimasi material Plate&Profi, Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-08-01 | 2026-08-31 | 1 | ainy |  | JC120826 38861 |  | 07.30 - 16.30
2026-09-11
1 | 2026-09-11 | W000304 - 305 | REV - EC424PS.6 - 424(P/S), 652(P/S), 513(P/S), Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | mila |  | JC110926 40315
2 |  | W000306 - 307 | REV - EC313U.6 - 313(P/S), Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | mila |  | JC120926 40317
3 |  | W000308 | REV - EC414U.6 - 414(P/S), 413(P/S), 412(P/S), Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | mila |  | JC120926 40318
4 |  | M000312 | REV - EC112C.6 - 112 (C), 212 (C)Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code, Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | mila |  | JC120926 40319
5 |  | M000313 | R0 - EC111C.6 - 111 (C), Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code, Geomarin V | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | mila |  | JC120926 40320
6 |  | W000304 - 305 | REV - EC234PS.6 - PROD. DWG 234(P/S),214(P/S), ( 3D model, Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | ayu |  | JC120926 40321
7 |  | M000312 | REV - EC212C.6 - PROD. DWG 212 (C), 611 (C), 621 (C) ( 3D model, Check Dwg PDHC ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | ayu |  | JC120926 40322
8 |  | M000313 | R0 - EC111C.6 - PROD. DWG 111 (C), ( 3D model, Check Dwg PDHC ), Geomarin V | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | ayu |  | JC120926 40323
9 |  | W000308 | REV - EC344U.6 - PROD. DWG 344 (P/S), ( 3D model, Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | zakiyah |  | JC120926 40324
10 |  | M000312 | REV - EC121C.6 - PROD. DWG 121 (C), 111(C), 122 (C), ( 3D model, Check Dwg PDHC ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | zakiyah |  | JC120926 40325
11 |  | M000313 | R0 - EC211C.6 - PROD. DWG 211 (C), ( 3D model, Check Dwg PDHC ), Geomarin V | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | zakiyah |  | JC120926 40326
12 |  | W000306 - 307 | REV - EC213U.6 - PROD. DWG 213 (P/S), 313 (P/S), ( 3D model, Ass Dwg, Lift info, Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | rois |  | JC120926 40327
13 |  | W000308 | REV - EC134U.6 - PROD. DWG 134 (P/S), ( 3D model, Ass Dwg, Lift info, Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | rois |  | JC120926 40328
14 |  | M000313 | REV - EC211C.6 - PROD. DWG 211 (C), ( 3D model, Ass Dwg, Lift info ), Geomarin V | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | rois |  | JC120926 40329
15 |  | W000308 | REV - EC452U.6 - PROD. DWG 452 (P/S), 453(P/S), 461 (C), ( 3D model, Ass Dwg, Lift info, Check Dwg PDHC ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | yusuf |  | JC120926 40330
16 |  | M000312 | REV - EC211C.6 - PROD. DWG 211 (C), ( 3D model, Ass Dwg, Lift info ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | yusuf |  | JC120926 40331
17 |  | M000313 | R0 - EC211C.6 - PROD. DWG 211 (C), ( 3D model, Ass Dwg, Lift info ), Geomarin V | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | yusuf |  | JC120926 40332
18 |  | W000308 | REV - EC344U.6 - PROD. DWG 344 (P/S), 142 (C), 614 (P/S), 612 (P/S), 611(P/S), (3D model, Ass Dwg, Lift info ) | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | roni |  | JC120926 40333
19 |  | M000313 | R0 - EC312C.6 - PROD. DWG 312 (C), ( 3D model, Ass Dwg, Lift info ), Geomarin V | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | roni |  | JC120926 40334
20 |  | M000312 | REV - EC621C.6 - PROD. DWG 621 (C), ( 3D model, Ass Dwg, Lift info ), Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | irwan |  | JC120926 40335
21 |  | M000313 | R0 - EC111C.6 - PROD. DWG 111 (C), 121 (C), ( 3D model, Ass Dwg, Lift info ), Geomarin V | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | irwan |  | JC120926 40336
22 |  | W000304 - 305 | REV - EC611PS.6 - 611(P/S), Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | ainy |  | JC120926 40337
23 |  | W000306 - 307 | REV - EC213U.6 - 213(P/S), Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | ainy |  | JC120926 40338
24 |  | W000308 | REV - EC512U.6 - 512(P/S), 523(P/S),522(P/S), Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | ainy |  | JC120926 40339
25 |  | M000312 | REV - EC211C.6 - 211(C), Estimasi material Plate&Profi, Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code, Pinisi | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | ainy |  | JC120926 40340
26 |  | M000313 | R0 - EC111C.6 - Estimasi material Plate&Profi, Nesting Plate, Apl, Matlist, Nesting Rambu Bending, Nc Code, Geomarin V | 1CK300 - Biro Gambar Produksi Lambung | 2026-09-01 | 2026-09-30 | 1 | ainy |  | JC120926 40341

## Dept. SPL (HO)
... Diisi Desain ... Agar diperhatikan spy timesheet masing2 personil bisa continue/tidak terputus krn terkait KPI Personil | [9 empty] | Diisi Planner
No | Tanggal Permintaan JC ditulis | Project | Task Name | Work Center | Schedule Start date | Schedule End date | Total Personil yang mengerjakan | PIC | JO | Kode Job Card | Keterangan | Planner
| DD / MM / YYYY | KODE PROYEK | REVISI KE - NO DOC / DWG - DESC PEKERJAAN | KODE BIRO - DESC BIRO | DD / MM / YYYY | DD / MM / YYYY | (DALAM ANGKA) | (NAMA) | (ANGKA) | JC010624 0001 |  | 023066812-Hashfi Moch Adam
CONTOH
1 | 2024-06-20 | W006 | R2 - E11672.11100 - ARR'T OF STEEL DOOR | 1CK200 - Biro Desain Perlengkapan Lambung | 2024-06-03 | 2024-06-07 | 2 |  |  | JC040624 0374 |  | 023066812-Hashfi Moch Adam
2 | 3 Maret 2025 | W304-305 | E15825.33100 - DRUM FOR MOORING ROPE - R2 |  | 2025-03-03 | 2025-03-08 | 1 | Irene | 40 | JC060325 16105
3 |  |  | E15724.33200 - ARRT OF LIFT BEAM IN E/R - R3 |  | 2025-03-03 | 2025-03-05 | 1 | Farhan | 24 | JC060325 16106
4 |  |  | EZ212P.33200 - FOUND. OF EQUIPMENT ON BLOCK 212 (P) - R3 |  | 2025-03-06 | 2025-03-10 | 1 | Farhan | 24 | JC060325 16107
5 |  |  | EZ232S.33200 - FOUND. EQUIPMENT ON BLOCK 232 (S) - R2 |  | 2025-03-11 | 2025-03-13 | 1 | Farhan | 24 | JC060325 16108
6 |  |  | EZ241P.33200 - FOUND EQUIPMENT BLOCK 241 (P) - R3 |  | 2025-03-14 | 2025-03-18 | 1 | Farhan | 24 | JC060325 16109
7 |  |  | EZ131C.33200 - FOUND. EQUIPMENT BLOCK 131 (C) - R3 |  | 2025-03-19 | 2025-03-27 | 1 | Farhan | 56 | JC060325 16110
8 |  |  | E16222.33200 - ARRT & DETAIL OF MPFF |  | 2025-03-03 | 2025-03-08 | 1 | Bagus | 40 | JC060325 16111
9 |  |  | CEK GAMBAR, EVALUASI TEKNIS DAN KOORDINASI TEKNIS |  | 2025-03-17 | 2025-03-21 | 2 | Yudi, Wiwid | 40 | JC060325 16112
10 |  | W306-307 | E11674.11100 - ARRT OF MANHOLE - R3 |  | 2025-03-03 | 2025-03-05 | 1 | Karina | 24 | JC060325 16113
11 |  |  | E11674.33100 - DETAIL OF MANHOLE & VL - RA1 |  | 2025-03-06 | 2025-03-08 | 1 | Karina | 24 | JC060325 16114
12 |  |  | 3D MODEL VEHICLE LIFT |  | 2025-03-03 | 2025-03-05 | 1 | Sutan | 24 | JC060325 16115
13 |  |  | 3D MODEL TURN TABLE |  | 2025-03-06 | 2025-03-08 | 1 | Sutan | 24 | JC060325 16116
14 |  |  | CEK GAMBAR, EVALUASI TEKNIS DAN KOORDINASI TEKNIS |  | 2025-03-03 | 2025-03-07 | 2 | Yudi, Wiwid | 40 | JC060325 16117
15 |  |  | EZ221P.33200 - FOUND. EQUIPMENT BLOCK 221 (P) - RA1 |  | 2025-03-03 | 2025-03-05 | 1 | Indra | 24 | JC060325 16118
16 |  |  | EZ221S.33200 - FOUND. EQUIPMENT BLOCK 221 (S) - RA0 |  | 2025-03-06 | 2025-03-08 | 1 | Indra | 24 | JC060325 16119
17 |  |  | EZ231P.33200 - FOUND. EQUIPMENT BLOCK 231 (P) - R3 |  | 2025-03-10 | 2025-03-12 | 1 | Indra | 24 | JC060325 16120
18 |  |  | EZ231S.33200 - FOUND. EQUIPMENT BLOCK 231 (S) - R5 |  | 2025-03-13 | 2025-03-15 | 1 | Indra | 24 | JC060325 16121
19 |  |  | EZ622P.33200 - FOUND. EQUIPMENT ON BLOCK 622 (P) - R0 |  | 2025-03-17 | 2025-03-19 | 1 | Indra | 24 | JC060325 16123
20 |  |  | E10660.11400 - ACCOMM. ARRT OF MAIN DECK - R1 |  | 2025-03-03 | 2025-03-05 | 1 | Rizal | 24 | JC060325 16124
21 |  |  | E10660.11401 - ACCOMM. ARRT OF 01 DECK - R1 |  | 2025-03-06 | 2025-03-10 | 1 | Rizal | 24 | JC060325 16125
22 |  |  | E10660.11402 - ACCOMM. ARRT OF 02 DECK - R1 |  | 2025-03-11 | 2025-03-13 | 1 | Rizal | 24 | JC060325 16126
23 |  |  | E10660.11403 - ACCOMM. ARRT OF 03 DECK - R1 |  | 2025-03-14 | 2025-03-18 | 1 | Rizal | 24 | JC060325 16127
24 |  |  | E10660.11404 - ACCOMM. ARRT OF 04 DECK - R1 |  | 2025-03-19 | 2025-03-21 | 1 | Rizal | 24 | JC060325 16128
25 |  |  | E10660.11405 - ACCOMM. ARRT OF 05 DECK - R1 |  | 2025-03-24 | 2025-03-27 | 1 | Rizal | 24 | JC060325 16129
26 |  |  | CEK GAMBAR, EVALUASI TEKNIS DAN KOORDINASI TEKNIS |  | 2025-03-24 | 2025-03-27 | 2 | Yudi, Wiwid | 32 | JC060325 16130
27 |  | W308 | E16231.33403 - STAIRWAY IN ACCOMMODATION 03 DECK - R1 |  | 2025-03-03 | 2025-03-08 | 1 | Anam | 40 | JC060325 16131
28 |  |  | E16231.33404 - STAIRWAY IN ACCOMMODATION 04 DECK - R2 |  | 2025-03-10 | 2025-03-15 | 1 | Anam | 40 | JC060325 16132
29 |  |  | E16520.33505 - ARRT & DETAIL OF LEAD PLATE |  | 2025-03-10 | 2025-03-15 | 1 | Iyan | 40 | JC060325 16133
30 |  |  | CEK GAMBAR, EVALUASI TEKNIS DAN KOORDINASI TEKNIS |  | 2025-03-10 | 2025-03-14 | 2 | Yudi, Wiwid | 40 | JC060325 16134
31 |  | KPI | REVIEW GA & BUILD. SPEC FOR BRS UAE |  | 03 Mar 0202 | 2025-03-07 | 2 | Dinata, Iyan | 40 | JC060325 16135
|  | W304-305 | E11674,33100 - DETAIL OF MANHOLE & VL |  | 2025-03-10 | 2025-03-15 | 1 | Karina | 40 | JC110325 16442
|  |  | EZ6631,33108 - SEAT OF EQUIP. IN ELECT. EQUIP. ROOM NO. 8 |  | 2025-03-10 | 2025-03-19 | 1 | Irene | 64 | JC110325 16443
|  |  | E26631.33108 - ML FOR SEAT OF EQ. IN ELECT. EQ. ROOM NO. 8 |  | 2025-03-20 | 2025-03-22 | 1 | Irene | 24 | JC110325 16447
|  | W308 | E16032,33102 - TURN TABLE & VEHICLE MARK |  | 2025-03-10 | 2025-03-14 | 1 | Sutan | 40 | JC110325 16448
|  |  | E16221,33208 - ARRT OF FLOOR IN SHAFT TUNNEL - R1 |  | 2025-03-10 | 2025-03-15 | 1 | Bagus | 40 | JC110325 16449
|  | W304-305 | E16135.33300 - ARRT & DETAIL OF PORTABLE AWNING |  | 2025-03-10 | 2025-03-14 | 1 | Dinata | 40 | JC110325 16450
| 2025-03-18 | W304-305 | E16631,33113 - SEAT OF EQUIPMENT IN ELECT. EQUIP. ROOM NO. 13 |  | 2025-03-17 | 2025-03-25 | 1 | Karina | 56 | JC190325 16785
|  |  | E26631,33113 - MAT. LIST FOR SEAT OF EQUIPMENT IN ELECT. EQUIP. ROOM NO. 13 |  | 2025-03-26 | 2025-03-28 | 1 | Karina | 24 | JC190325 16788
|  |  | KAJIAN TEKNIS LIFERAFT< RAILING HALUAN & ANODE |  | 2025-03-17 | 2025-03-22 | 1 | Dinata | 40 | JC190325 16793
|  | W308 | E16231,33402 - STAIRWAY IN ACCOMM. 02 DECK - R2 |  | 2025-03-17 | 2025-03-23 | 1 | Anam | 40 | JC190325 16794 |  | JC240325 17009
|  |  | E16231,33401 - STAIRWAY IN ACCOMM. 01 DECK - R2 |  | 2025-03-24 | 2025-03-28 | 1 | Anam | 40 | JC190325 16795 |  | JC240325 17010
| 2023-03-21 | W304-305 | E16631,33110 - SEAT OF EQUIPMENT IN ELECT. EQUIP. ROOM NO. 10 |  | 2025-03-24 | 2025-03-28 | 1 | Irene | 40 | JC210325 16870
|  |  | E6315,01300 - PAINTING SCHEDULE - RA0 |  | 2025-03-20 | 2025-03-21 | 1 | Indra | 16 | JC210325 16871
|  |  | E16631,33104 - SEAT OF EQUIPMENT IN ELECT. EQUIP. ROO NO. 4 |  | 2025-03-24 | 2025-03-28 | 1 | Dinata | 40 | JC210325 16872
|  | W306-307 | EVATEK MEDICAL EQUIPMENT |  | 2025-03-24 | 2025-03-28 | 1 | Iyan | 40 | JC210325 16873
|  | W308 | EVATEK MEDICAL EQUIPMENT |  | 2025-03-17 | 2025-03-22 | 1 | Iyan | 40 | JC210325 16874
|  | A24OP01 | PAINTING SCHEDULE |  | 2025-03-24 | 2025-03-26 | 1 | Sutan | 24 | JC210325 16875
|  |  | MAT. LIST FOR PAINT |  | 2025-03-27 | 2025-03-28 | 1 | Sutan | 16 | JC210325 16876
| 2025-03-24 | W304-305 | E16724.33400 - DETAIL OF COVER PLATE IN DRY PROVISION STORE |  | 2025-03-17 | 2025-03-21 | 1 | Bagus | 40 | JC240325 16973
|  |  | 3D MODEL CIC ROOM & MACHINERY CONTROL ROOM |  | 2025-03-24 | 2025-03-28 | 1 | Bagus | 40 | JC240325 16974
|  | W306-307 | E22000.01200 - MAT. LIST FOR BOLT & NUT IN E/R |  | 2025-03-24 | 2025-03-26 | 1 | Indra | 24 | JC240325 16987
|  |  | EF433P.36100 - 433 (P) BLOCK PAINTING |  | 2025-03-27 | 2025-03-27 | 1 | Indra | 8 | JC240325 16988
|  |  | EF433S.36100 - 433 (S) BLOCK PAINTING |  | 2025-03-28 | 2025-03-28 | 1 | Indra | 8 | JC240325 16989
2025-04-01
| 2025-04-07 | W304-305 | E12590.32200 - ARRT & DETAIL OF SUPPORT EXHAUST GAS PIPE |  | 2025-04-07 | 2025-04-14 | 1 | Iyan | 48 | JC080425 17384
|  |  | EZ213P.33200 - FOUND. EQUIP. BLOCK 213P |  | 2025-04-07 | 2025-04-17 | 1 | Farhan | 80 | JC080425 17386
|  |  | E16631.33104 - SEAT OF EQUIPMENT IN ELECT. EQ. ROOM NO. 4 |  | 2025-04-07 | 2025-04-11 | 1 | Dinata | 40 | JC080425 17392
|  |  | E26631.33104 - ML FOR SEAT EQ. IN ELECT. EQ ROOM NO. 4 |  | 2025-04-14 | 2025-04-16 | 1 | Dinata | 24 | JC080425 17408
|  |  | E16110.33200 - DECK TRAY IN E/R |  | 2025-04-07 | 2025-04-12 | 1 | Indra | 40 | JC080425 17409
|  |  | E26110.33200 - ML FOR DECK TRAY IN E/R |  | 2025-04-14 | 2025-04-16 | 1 | Indra | 24 | JC080425 17414
|  |  | E16631.33103 - SEAT OF EQUIPMENT IN ELECT. EQ. ROOM NO. 3 |  | 2025-04-07 | 2025-04-19 | 1 | Irene | 80 | JC080425 17417
|  |  | E26631.33103 - ML FOR SEAT EQUIP. IN ELECT. EQ ROOM NO. 3 |  | 2025-04-21 | 2025-04-23 | 1 | Irene | 24 | JC080425 17419
|  |  | E16222,33400 - ARRT & DETAIL OF MPFF |  | 2025-04-07 | 2025-04-16 | 1 | Bagus | 64 | JC080425 17420
|  |  | E26222,33401 - ML FOR MPFF |  | 2025-04-17 | 2025-04-19 | 1 | Bagus | 24 | JC080425 17421
|  |  | E16222.33401 - ARRT & DETAIL OF RAISED FLOOR |  | 2025-04-21 | 2025-04-26 | 1 | Bagus | 40 | JC080425 17422
|  |  | E26222.33401 - ML FOR RAISED FLOOR |  | 2025-04-28 | 2025-04-30 | 1 | Bagus | 24 | JC080425 17423
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-04-14 | 2025-04-18 | 2 | Yudi, Wiwid | 32 | JC080425 17424
|  |  | E16020.33403 - LAMBANG GARUDA |  | 2025-04-07 | 2025-04-09 | 1 | Rizal | 24 | JC080425 17428
|  |  | E26020.33403 - ML FOR LAMBANG GARUDA |  | 2025-04-10 | 2025-04-11 | 1 | Rizal | 16 | JC080425 17429
|  |  | EZ233S.33200 - FOUND. EQUIP. BLOCK 233S |  | 2025-04-18 | 2025-04-30 | 1 | Farhan | 72 | JC080425 17431
|  |  | EZ5140.33200 - SEAT OF EQUIP. IN AHU ROOM NO. 4 (01LB1) |  | 2025-04-17 | 2025-04-30 | 1 | Indra | 80 | JC080425 17444 |  | PENDING, MENUNGGU DATA DARI MO
|  | W306-307 | E16011.33400 - ARRT OF MISCELLANEOUS JOINER FITTING & DETAIL |  | 2025-04-14 | 2025-04-18 | 1 | Rizal | 32 | JC080425 17449
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-04-21 | 2025-04-25 | 2 | Yudi, Wiwid | 40 | JC080425 17450
|  |  | E26000.37100 - ML FOR OTHER SUPPLIES (HULL PART) |  | 2025-04-23 | 2025-04-25 | 1 | Dinata | 24 | JC080425 17451
|  | W308 | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-04-07 | 2025-04-11 | 2 | Yudi, Wiwid | 40 | JC080425 17452
|  |  | E25724.33200 - ML FOR LIFT BEAM D/G IN AUXILIARY ROOM |  | 2025-04-07 | 2025-04-09 | 1 | Anam | 24 | JC080425 17453
|  |  | E25724.33202 - ML FOR LIFT BEAM MAIN ENGINE |  | 2025-04-10 | 2025-04-12 | 1 | Anam | 24 | JC080425 17454
|  |  | E11672.33104 - COVER INSPECTION HOLES - R1 |  | 2025-04-07 | 2025-04-12 | 1 | Karina | 40 | JC080425 17455
|  |  | E21672.33104 - ML FOR COVER INSPECTION HOLES - R1 |  | 2025-04-14 | 2025-04-16 | 1 | Karina | 24 | JC080425 17456
|  |  | E15724.33205 - LIFT BEAM FOR ELECTRIC PROPULSION |  | 2025-04-14 | 2025-04-19 | 1 | Anam | 40 | JC080425 17457
|  |  | E20770.02300 - ML FOR SAFETY EQUIPMENT |  | 2025-04-17 | 2025-04-22 | 1 | Dinata | 24 | JC080425 17458
|  |  | E16010.10100 - GENERAL OUTFITTING ARRT - R1 |  | 2025-04-24 | 2025-04-26 | 1 | Irene | 24 | JC080425 17459 |  | PENDING, MENUNGGU DATA DARI MO
|  |  | E16640.10100 - DAMAGE CONTROL PLAN - R1 |  | 2025-04-28 | 2025-04-30 | 1 | Irene | 24 | JC080425 17460
|  | A24OP01 | SHOP PRIMER & SAND BLASTING PAINTING CALCULATION |  | 2025-04-07 | 2025-04-09 | 1 | Sutan | 24 | JC080425 17463
|  |  | ML FOR SHOP PRIMER & SAND BLASTING PAINTING |  | 2025-04-10 | 2025-04-11 | 1 | Sutan | 16 | JC080425 17465
| 2025-04-17 | W304-305 | EZ4261.33100 - SEAT OF EQUIP. IN FWD GYRO ROOM |  | 2025-04-17 | 2025-04-18 | 1 | Karina | 16 | JC210425 18092
|  |  | E24261.33100 - MAT. LIST FOR SEAT OF EQUIP. IN FWD GYRO ROOM |  | 2025-04-19 | 2025-04-19 | 1 | Karina | 8 | JC210425 18093
|  |  | EZ4261.33101 - SEAT OF EQUIP. IN AFT GYRO ROOM |  | 2025-04-21 | 2025-04-22 | 1 | Karina | 16 | JC210425 18096
|  |  | E24261.33101 - MAT. LIST FOR SEAT OF EQUIP. IN AFT GYRO ROOM |  | 2025-04-23 | 2025-04-23 | 1 | Karina | 8 | JC210425 18103
|  |  | EZ5140.33205 - SEAT OF EQUIP. IN AHU ROOM NO. 5 (1CA1) |  | 2025-04-24 | 2025-04-26 | 1 | Karina | 24 | JC210425 18104
|  |  | E11672,33105 - STEEL LATICE DOOR - R2 |  | 2025-04-14 | 2025-04-17 | 1 | Sutan | 32 | JC210425 18105
|  |  | E17130,33101 - FITTING IN GUN BAY (1CA0) |  | 2025-04-28 | 2025-05-03 | 1 | Karina | 40 | JC210425 18137
|  | W306-307 | E16442,33401 - DETAIL OF UNIT TOILET (RAW MATERIAL) |  | 2025-04-21 | 2025-04-25 | 1 | Rizal | 40 | JC210425 18106
|  |  | E26442,33401 - MAT. LIST FOR DETAIL OF UNIT TOILET (RAW MATERIAL) |  | 2025-04-28 | 2025-04-30 | 1 | Rizal | 24 | JC210425 18108
|  | W308 | E25724.33205 - MAT. LIST FOR LIFT BEAM FOR TRANSFER ELECTRIC PROPULSION |  | 2025-04-21 | 2025-04-23 | 1 | Anam | 24 | JC210425 18110
|  |  | E15724.33206 - LIFT BEAM FOR E/R - R1 |  | 2025-04-24 | 2025-04-30 | 1 | Anam | 40 | JC210425 18111
|  |  | E16032.33104 - IN WATER SURVEY |  | 2025-04-21 | 2025-04-25 | 1 | Sutan | 40 | JC210425 18113
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-04-28 | 2025-05-02 | 2 | Yudi, Wiwid | 40 | JC210425 18214
| 2025-04-22 | W304-305 | EZ432P.33200 - FOUND. EQUIP. IN BLOCK 432 P - R4 |  | 2025-04-21 | 2025-04-23 | 1 | Iyan | 24 | JC230425 18280
|  |  | EZ432S.33200 - FOUND. EQUIP. IN BLOCK 432 S - R1 |  | 2025-04-24 | 2025-04-26 | 1 | Iyan | 24 | JC230425 18281
|  |  | E11503.33200 - ARRT & DETAIL OF EQUIP IN FUNNEL |  | 2025-04-28 | 2025-05-08 | 1 | Iyan | 64 | JC230425 18282
| 2025-04-25 | W304-305 | E11710.33100 - ARRT & DETAIL OF EQUIPMENT ON FORE MAST |  | 2025-04-24 | 2025-05-10 | 1 | Irene | 96 | JC250425 18369
|  |  | EZ4611.33100 - SEAT OF EQUIPMENT IN SONAR ROOM |  | 2025-04-22 | 2025-05-03 | 1 | Indra | 80 | JC250425 18370
|  | W308 | SHOP PRIMER & SAND BLASTING PAINTING CALCULATION |  | 2025-04-07 | 2025-04-09 | 1 | Sutan | 24 | JC250425 18371
|  |  | ML FOR SHOP PRIMER & SAND BLASTING PAINTING |  | 2025-04-10 | 2025-04-11 | 1 | Sutan | 16 | JC250425 18372
| 2025-04-28 | W304-305 | E16631.33104 - SEAT OF EQUIPMENT IN ELECT. EQ. ROOM NO. 4 |  | 2025-04-28 | 2025-04-30 | 1 | Dinata | 24 | JC280425 18562
|  | W306-307 | E16000.75100 - MAIN EQUIP LIST FOR HULL PART - RA4 |  | 2025-04-28 | 2025-04-28 | 1 | Sutan | 8 | JC280425 18563
|  | W308 | E16000.75100 - MAIN EQUIP LIST FOR HULL PART - RA1 |  | 2025-04-29 | 2025-04-30 | 1 | Sutan | 16 | JC280425 18564
2025-05-01
| 2025-04-30 | W304-305 | EZ6233,33101 - SEAT OF WHARFT LADDER - R2 |  | 2025-05-01 | 2025-05-03 | 1 | Anam | 16 | JC300425 18630
|  |  | E16020.33402 - TANDA KESATUAN |  | 2025-05-02 | 2025-05-06 | 1 | Rizal | 24 | JC300425 18631
|  |  | E26020.33402 - MAT. LIST FOR TANDA KESATUAN |  | 2025-05-07 | 2025-05-09 | 1 | Rizal | 24 | JC300425 18632
|  |  | E22000.01200 - MAT. LIST FOR BOLT & NUT IN E/R - R1 |  | 2025-05-09 | 2025-05-10 | 1 | Iyan | 16 | JC300425 18633
|  |  | EZ423P.33200 - FOUND. OF EQUIP IN BLOCK 423 P |  | 2025-05-01 | 2025-05-03 | 1 | Farhan | 24 | JC300425 18670
|  |  | EZ223P.33200 - FOUND. OF EQUIP. IN BLOCK 223 P |  | 2025-05-05 | 2025-05-10 | 1 | Farhan | 40 | JC300425 18705
|  |  | EZ223S.33200 - FOUND. OF EQUIP IN BLOCK 223 S |  | 2025-05-12 | 2025-05-17 | 1 | Farhan | 40 | JC020525 18721
|  |  | EZ243P.33200 - FOUND. OF EQUIP IN BLOCK 243 P |  | 2025-05-19 | 2025-05-24 | 1 | Farhan | 40 | JC020525 18722
|  |  | EZ243S.33200 - FOUND. OF EQUIP IN BLOCK 243 S |  | 2025-05-26 | 2025-05-31 | 1 | Farhan | 40 | JC020525 18723
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-05-05 | 2025-05-09 | 2 | Yudi, Wiwid | 40 | JC020525 18724
|  | W308 | E16311,33301 - FUNNEL PAINT MARKING |  | 2025-05-01 | 2025-05-06 | 1 | Sutan | 32 | JC300425 18634
|  |  | E26311,33301 - MAT. LIST FOR FUNNEL PAINT MARKING |  | 2025-05-07 | 2025-05-09 | 1 | Sutan | 24 | JC300425 18635
|  |  | E16370.11400 - ARRT OF JOINER WORK |  | 2025-05-02 | 2025-05-03 | 1 | Bagus | 16 | JC020525 18725
|  |  | E15724,33204 - LIFT BEAM FOR SHAFTING NO 1 & 2 - R1 |  | 2025-05-05 | 2025-05-07 | 1 | Anam | 24 | JC020525 18733
|  |  | E16221,33205 - ARRT OF FLOOR IN SHAFT ROOM - R1 |  | 2025-05-08 | 2025-05-10 | 1 | Anam | 24 | JC020525 18734
|  |  | E16231,33406 - ARRT & DETAIL OF STORMRAIL IN STAIRWAY - R2 |  | 2025-05-12 | 2025-05-17 | 1 | Anam | 40 | JC020525 18735
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-05-13 | 2025-05-16 | 2 | Yudi, Wiwid | 32 | JC020525 18736
|  | W304-305 | E17130,33101 - FITTING IN GUN BAY (1CA0) - R1 |  | 2025-05-05 | 2025-05-10 | 1 | Karina | 40 | JC050525 18929
|  |  | E17130,33101 - MAT. LIST FOR FITTING IN GUN BAY (1CA0) - R1 |  | 2025-05-12 | 2025-05-14 | 1 | Karina | 24 | JC050525 18931
|  |  | E1730,33102 - EQUIPMENT IN GUN BAY 1DA0 |  | 2025-05-15 | 2025-05-21 | 1 | Karina | 40 | JC050525 18932
|  |  | E27130,33102 - MAT. LIST FOR EQUIPMENT IN GUN BAY 1DA0 |  | 2025-05-22 | 2025-05-24 | 1 | Karina | 24 | JC050525 18933
|  |  | EZ4611.33100 - SEAT OF EQUIPMENT IN SONAR ROOM |  | 2025-05-05 | 2025-05-13 | 1 | Indra | 48 | JC050525 18934
|  |  | E24611.33100 - MAT. LIST FOR SEAT OF EQUIPMENT IN SONAR ROOM |  | 2025-05-14 | 2025-05-16 | 1 | Indra | 24 | JC050525 18935
|  |  | E16311,33301 - FUNNEL PAINT MARKING |  | 2025-05-19 | 2025-05-21 | 1 | Indra | 24 | JC050525 18936
|  |  | E26311,33301 - MAT. LIST FOR FUNNEL PAINT MARKING |  | 2025-05-22 | 2025-05-24 | 1 | Indra | 16 | JC050525 18942
|  |  | E16500,33400 - SECT. ROOM OF GALLEY, PANTRY & LAUNDRY |  | 2025-05-05 | 2025-05-10 | 1 | Bagus | 40 | JC050525 18943
|  |  | E16023,32300 - ARRT OF IMO SIGN |  | 2025-05-05 | 2025-05-09 | 1 | Dinata | 40 | JC050525 18944
|  |  | E16023,32301 - ARRT OF NBCD SIGN |  | 2025-05-19 | 2025-05-23 | 1 | Dinata | 40 | JC050525 18945
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-05-19 | 2025-05-23 | 2 | Yudi, Wiwid | 40 | JC050525 18946
|  | W306-307 | E16023,32300 - ARRT OF IMO SIGN |  | 2025-05-13 | 2025-05-16 | 1 | Dinata | 32 | JC050525 18947
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-05-26 | 2025-05-30 | 2 | Yudi, Wiwid | 32 | JC050525 18948
|  | W308 | E16311,33301 - FUNNEL PAINT MARKING |  | 2025-05-05 | 2025-05-07 | 1 | Sutan | 24 | JC050525 18949
|  |  | E26311,33301 - MAT. LIST FOR FUNNEL PAINT MARKING |  | 2025-05-08 | 2025-05-09 | 1 | Sutan | 16 | JC050525 18952
|  |  | EF643P.04300 - 643 P BLOCK PAINTING |  | 2025-05-12 | 2025-05-12 | 1 | Sutan | 8 | JC050525 18954
|  |  | EF643S.04300 - 643 S BLOCK PAINTING |  | 2025-05-13 | 2025-05-13 | 1 | Sutan | 8 | JC050525 18955
|  |  | EF614P.04300 - 614 P BLOCK PAINTING |  | 2025-05-14 | 2025-05-14 | 1 | Sutan | 8 | JC050525 18956
|  |  | EF614S.04300 - 614 S BLOCK PAINTING |  | 2025-05-15 | 2025-05-15 | 1 | Sutan | 8 | JC050525 18957
|  |  | E26023,33103 - MAT. LIST FOR TURN TABLE MARK & VEHICLE LIFT MARK |  | 2025-05-16 | 2025-05-16 | 1 | Sutan | 8 | JC050525 18958
|  |  | E16724,33400 - DETAIL OF COVER PLATE IN DRY PROV. STORE |  | 2025-05-12 | 2025-05-16 | 1 | Bagus | 32 | JC050525 18959
|  |  | E25724,33206 - MAT. LIST FOR LIFT BEAM IN E/R |  | 2025-05-19 | 2025-05-21 | 1 | Anam | 24 | JC050525 18965
|  |  | E26724,33400 - MAT. LIST FOR DETAIL OF COVER PLATE IN DRY PROV. STORE |  | 2025-05-19 | 2025-05-21 | 1 | Bagus | 24 | JC050525 18974
|  | W304-305 | E11710.33102 - ARRT & DET. OF EQUIPMENT ON AFT MAST |  | 2025-05-13 | 2025-05-24 | 1 | Irene | 72 | JC130525 19308
|  |  | E21710.33102 - MAT. LIST FOR DET. OF EQUIPMENT ON AFT MAST |  | 2025-05-26 | 2025-05-28 | 1 | Irene | 24 | JC130525 19311
|  |  | E25014.33200 - MAT. LIST FOR SCALE PLATE FOR TANK |  | 2025-05-13 | 2025-05-14 | 1 | Iyan | 16 | JC130525 19313
|  |  | E22590.33200 - MAT. LIST FOR SUPPORT EXHAUST GAS PIPE |  | 2025-05-15 | 2025-05-16 | 1 | Iyan | 16 | JC130525 19315
|  |  | E86332.51300 - ICCP SYSTEM |  | 2025-05-13 | 2025-05-14 | 1 | Rizal | 16 | JC130525 19316
|  |  | E86333.51300 - MGPS SYSTEM |  | 2025-05-15 | 2025-05-16 | 1 | Rizal | 16 | JC130525 19319
|  | KPI | E10770.02300 - SAFETY & FIRE CONTROL PLAN |  | 2025-05-26 | 2025-05-30 | 1 | Dinata | 32 | JC130525 19322
|  |  | E11674.11100 - ARRT & DETAIL OF MANHOLE & VERT. LADDER |  | 2025-05-19 | 2025-05-24 | 1 | Sutan | 40 | JC130525 19323
|  |  | E15824.11100 - ARRT OF MOORING |  | 2025-05-26 | 2025-05-31 | 1 | Sutan | 32 | JC130525 19324
|  | W304-305 | EZ6221,33200 - SEAT OF EQUIPMENT IN CASING TRUNK (2LA1) |  | 2025-05-19 | 2025-05-24 | 1 | Iyan | 40 | JC150525 19378
|  |  | EZ6221,33201 - SEAT OF EQUIPMENT IN CASING TRUNK (2MA5) |  | 2025-05-26 | 2025-05-31 | 1 | Iyan | 40 | JC150525 19379
|  |  | E16251,11400 - WINDOW PLAN - R2 |  | 2025-05-22 | 2025-05-24 | 1 | Bagus | 16 | JC150525 19381
|  |  | E16122,33400 - ARRT OF HANDRAIL IN ACCOMMODATION - R1 |  | 2025-05-19 | 2025-05-20 | 1 | Rizal | 16 | JC150525 19383
|  |  | E26122,33400 - MAT. LIST FOR HANDRAIL IN ACCOMMODATION - R1 |  | 2025-05-21 | 2025-05-22 | 1 | Rizal | 16 | JC150525 19389
|  |  | E26254,32400 - MAT. LIST FOR WINDOW WIPER, CVS & SUNSCREEN - R3 |  | 2025-05-23 | 2025-05-23 | 1 | Rizal | 8 | JC150525 19391
|  |  | EZ6631,33120 - SEAT OF EQUIP. IN ELECT. EQUIP. ROOM NO. 20 |  | 2025-05-26 | 2025-06-03 | 1 | Karina | 56 | JC150525 19392
|  |  | EZ6623,33101 - SEAT OF EQUIP. IN RADIO ROOM |  | 2025-05-29 | 2025-06-07 | 1 | Irene | 56 | JC150525 19394
|  |  | E16621,33400 - ARRT OF PILOT CHAIR - R2 |  | 2025-05-26 | 2025-05-28 | 1 | Rizal | 24 | JC150525 19396
|  |  | E26621,33400 - MAT. LIST FOR PILOT CHAIR - R1 |  | 2025-05-30 | 2025-05-30 | 1 | Rizal | 8 | JC150525 19397
| 2025-05-19 | W308 | E16233,33203 - ARRT & DETAIL OF LADDER IN E/R - R2 |  | 2025-05-22 | 2025-05-24 | 1 | Anam | 24 | JC190525 19574
|  |  | E16233,33201 - ARRT & DETAIL OF LADDER IN CHILLER & REFRIGERANT PLANT ROOM - R1 |  | 2025-05-26 | 2025-05-28 | 1 | Anam | 24 | JC190525 19575
|  |  | E16233,33201 - ARRT & DETAIL OF LADDER IN FRESH WATER GEN. ROOM - R1 |  | 2025-05-29 | 2025-05-31 | 1 | Anam | 24 | JC190525 19576
|  | KPI | PLATFORM SHIFT LIFT |  | 2025-05-02 | 2025-05-31 | 1 | Diva | 152 | JC190525 19577
| 2025-05-27 | W304-305 | EZ4611,33101 - SEAT OF EQUIPMENT IN SONAR WATER FILTER (2AA0) |  | 2025-05-26 | 2025-05-31 | 1 | Indra | 40 | JC270525 19940
|  |  | EZ1801,33108 - SEAT OF EQUIPMENT IN PASSAGE WAY (2LA3) |  | 2025-05-26 | 2025-05-28 | 1 | Bagus | 24 | JC270525 19941
|  |  | EZ1801,33109 - SEAT OF EQUIPMENT IN PASSAGE WAY (2LA4) |  | 2025-05-29 | 2025-05-31 | 1 | Bagus | 24 | JC270525 19942
| 2025-06-03 | W304-305 | EZ1801,33103 - SEAT OF EQUIPMENT IN PASSAGE WAY (2MBO) |  | 2025-06-04 | 2025-06-07 | 1 | Karina | 24 | JC030625 20340
|  |  | E96000,92101 - WEIGHT KONTROL (KB - 03) |  | 2025-06-02 | 2025-06-07 | 1 | Sutan | 32 | JC030625 20341
|  |  | EZ1801,33113 - SEAT OF EQUIP. IN DIESEL DRIVEN FIRE PUMP NO.1 (2BA1) |  | 2025-06-02 | 2025-06-04 | 1 | Farhan | 24 | JC030625 20342
|  |  | EZ1801,33114 - SEAT OF EQUIP. IN DIESEL DRIVEN FIRE PUMP NO.2 (2PA5) |  | 2025-06-05 | 2025-06-10 | 1 | Farhan | 24 | JC030625 20343
|  |  | E16023,32301 - ARRT OF NBCD SIGN |  | 2025-06-02 | 2025-06-05 | 1 | Dinata | 32 | JC030625 20344
|  |  | E26621,33400 - MAT. LIST FOR PILOT CHAIR - R1 |  | 2025-06-02 | 2025-06-02 | 1 | Rizal | 8 | JC030625 20345
|  |  | E16621,33400 - ARRT OF PILOT CHAIR - R2 |  | 2025-06-03 | 2025-06-05 | 1 | Rizal | 24 | JC030625 20347
|  |  | EZ1801,33115 - SEAT OF EQUIPMENT IN PASSAGE WAY (2HZ2) |  | 2025-06-02 | 2025-06-07 | 1 | Indra | 32 | JC030625 20348
|  |  | EZ1801,33118 - SEAT OF EQUIPMENT IN BAGGAGE STORE NO. 1 (2FA4) |  | 2025-06-02 | 2025-06-07 | 1 | Bagus | 32 | JC030625 20349
|  | W308 | E16231,33406 - ARRT & DETAIL OF STORMRAIL IN STAIRWAY - R2 |  | 2025-06-02 | 2025-06-07 | 1 | Anam | 32 | JC030625 20313
|  |  | EVATEK MEDICAL EQUIPMENT |  | 2025-06-02 | 2025-06-07 | 1 | Iyan | 32 | JC030625 20314
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-06-02 | 2025-06-05 | 2 | Yudi, Wiwid | 32 | JC030625 20346
| 2025-06-08 | W304-305 | EZ6631,33117 - SEAT OF EQUIP. IN ELECT. EQUIP. ROOM NO. 17 |  | 2025-06-09 | 2025-06-12 | 1 | Karina | 32 | JC090625 20493
|  |  | EZ6631.33119 - SEAT OF EQUIP. IN ELECT. EQUIP ROOM NO. 19 |  | 2025-06-13 | 2025-06-14 | 1 | Karina | 16 | JC090625 20494
|  |  | E11710.33101 - ARRT & DET. OF EQUIPMENT ON MIDDLE MAST |  | 2025-06-09 | 2025-06-14 | 1 | Irene | 40 | JC090625 20495
|  |  | 3D MODEL BLAST DOOR |  | 2025-06-09 | 2025-06-14 | 1 | Sutan | 40 | JC090625 20496
|  |  | EZ6221.33202 - FOUND. OF EQUIPMENT IN CASING TRUNK (2JZ2) |  | 2025-06-09 | 2025-06-14 | 1 | Iyan | 40 | JC090625 20497
|  |  | EZ1801.33114 - SEAT OF EQUIP IN DIESEL DRIVEN FIRE PUMP NO, 2 (2PA5) |  | 2025-06-09 | 2025-06-10 | 1 | Farhan | 16 | JC090625 20498
|  |  | EZ312C.33200 - FOUND. OF EQUIP. IN BLOCK 312 (C) - R1 |  | 2025-06-11 | 2025-06-17 | 1 | Farhan | 40 | JC090625 20499
|  |  | EZ241S.33200 - FOUND. OF EQUIP. IN BLOCK 241 (S) - R5 |  | 2025-06-18 | 2025-06-19 | 1 | Farhan | 16 | JC090625 20500
|  |  | EZ131C.33200 - FOUND. OF EQUIP. IN BLOCK 131 (C) - R4 |  | 2025-06-20 | 2025-06-21 | 1 | Farhan | 16 | JC090625 20521
|  |  | EZ222P.33200 - FOUND. OF EQUIP. IN BLOCK 222 (P) - R1 |  | 2025-06-23 | 2025-06-28 | 1 | Farhan | 40 | JC090625 20528
|  |  | EZ152P.33200 - FOUND. OF EQUIP. IN BLOCK 152 (P) - R0 |  | 2025-06-30 | 2025-07-02 | 1 | Farhan | 24 | JC090625 20530
|  |  | EZ432P.33200 - FOUND. OF EQUIP. IN BLOCK 432 (P) - RA0 |  | 2025-07-03 | 2025-07-05 | 1 | Farhan | 24 | JC090625 20546
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-06-09 | 2025-06-13 | 3 | Yudi, Wiwid, Dinata | 40 | JC090625 20547
|  |  | EZ1801,33115 - SEAT OF EQUIPMENT IN PASSAGE WAY (2HZ2) |  | 2025-06-09 | 2025-06-11 | 1 | Bagus | 24 | JC090625 20550
|  |  | EZ1801,33116 - SEAT OF EQUIPMENT IN PASSAGE WAY (2JZ4) |  | 2025-06-12 | 2025-06-14 | 1 | Bagus | 24 | JC090625 20551
|  |  | EZ1233,33100 - SEAT OF EQUIPMENT IN ESC. TRUNK (2/4LA4) |  | 2025-06-09 | 2025-06-11 | 1 | Indra | 24 | JC090625 20552
|  |  | E12590.33200 - ARRT & DET. OF SUPPORT EXH. GAS PIPE |  | 2025-06-16 | 2025-06-21 | 1 | Iyan | 40 | JC090625 20581
|  | W308 | E26231.33400 - MAT. LIST FOR STAITWAY IN ACCOMM. - R2 |  | 2025-06-09 | 2025-06-10 | 1 | Anam | 16 | JC090625 20589
|  |  | E15724,33206 - LIFT BEAM FOR ENG. ROOM - R2 |  | 2025-06-11 | 2025-06-14 | 1 | Anam | 24 | JC090625 20590
|  |  | E11672.11100 - ARRT OFF STEEL DOOR - R3 |  | 2025-06-16 | 2025-06-17 | 1 | Karina | 16 | JC090625 20591
|  |  | E21672.33100 - MAT. LIST FOR STEEL DOOR - R1 |  | 2025-06-18 | 2025-06-21 | 1 | Karina | 24 | JC090625 20592
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-06-16 | 20 June 1015 | 3 | Yudi, Wiwid, Dinata | 40 | JC090625 20593
|  |  | E26233,33203 - MAT. LIST FOR LADDER IN ENG. ROOM |  | 2025-06-16 | 2025-06-18 | 1 | Anam | 24 | JC090625 20594
|  |  | E26233,33202 - MAT. LIST FOR LADDER IN CHILLER & STP ROOM |  | 2025-06-19 | 2025-06-21 | 1 | Anam | 24 | JC090625 20595
|  |  | E26233,33201 - MAT. LIST FOR LADDER IN CHILLER & REFRIGERANT PLANT ROOM |  | 2025-06-23 | 2025-06-25 | 1 | Anam | 24 | JC090625 20596
|  |  | E26233,33200 - MAT. LIST FOR LADDER INFRESH WATER GENERATOR ROOM |  | 2025-06-26 | 2025-06-28 | 1 | Anam | 24 | JC090625 20599
|  |  | E16250.33400 - STEEL WALL OPENING FOR WINDOW - R3 |  | 2025-06-09 | 2025-06-10 | 1 | Rizal | 16 | JC090625 20602
|  | KPI | 3D MODEL PLATFORM SHIFT LIFT |  | 2025-06-02 | 2025-06-13 | 1 | Diva | 80 | JC090625 20603
|  |  | 3D MODEL PLTAL |  | 2025-06-16 | 2025-06-30 | 1 | Diva | 88 | JC090625 20604
|  | W306-307 | E16370.11400 - ARRT OF JOINER WORK - R2 |  | 2025-06-11 | 2025-06-13 | 1 | Rizal | 24 | JC090625 20548
| 2025-06-13 | W304-305 | E11672.33103 - DETAIL OF BLAST DOOR |  | 2025-06-16 | 2025-06-25 | 1 | Sutan | 64 | JC130625 20720
|  |  | E21672.33103 - MAT. LIST FOR DETAIL OF BLAST DOOR |  | 2025-06-26 | 2025-06-28 | 1 | Sutan | 24 | JC130625 20721
|  |  | EZ6623,33101 - SEAT OF EQUIP. IN RADIO ROOM |  | 2025-06-12 | 2025-06-21 | 1 | Indra | 56 | JC130625 20722
| 2025-06-16 | W304-305 | EZ6631.33101 - FOUND. OF EQUIP. IN ELECTRONIC EQUIP ROOM NO. 1 |  | 2025-06-16 | 2025-06-21 | 1 | Irene | 40 | JC170625 20972
|  |  | EZ5820.33100 - FOUND. OF EQUIP. IN AFT MOORING AREA |  | 2025-06-16 | 2025-06-17 | 1 | Bagus | 16 | JC170625 20973
|  |  | EZ1801.33119 - FOUND. OF EQUIP IN PASSAGE WAY (2KA1) |  | 2025-06-18 | 2025-06-19 | 1 | Bagus | 16 | JC170625 20975
|  |  | EZ1801.33120 - FOUND. OF EQUIP IN PASSAGE WAY (2KA2) |  | 2025-06-20 | 2025-06-21 | 1 | Bagus | 16 | JC170625 20976
|  |  | E16402.11403 - LIST OF GALLEY, PANTRY & LAUNDRY FURNITURE - R1 |  | 2025-06-16 | 2025-06-17 | 1 | Rizal | 16 | JC170625 20977
|  | W308 | E16402.11403 - LIST OF GALLEY, PANTRY & LAUNDRY FURNITURE - R1 |  | 2025-06-18 | 2025-06-20 | 1 | Rizal | 24 | JC170625 20998
| 2025-06-23 | W304-305 | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-06-23 | 2025-06-26 | 2 | Yudi, Wiwid | 32 | JC230625 21253
|  |  | EZ6632.33100 - FOUND. OF EQUIP. IN SWITCHBOARD ROOM FORE |  | 2025-06-23 | 2025-06-28 | 1 | Karina | 40 | JC230625 21247
|  |  | EZ6631.33102 - FOUND. OF EQUIP. IN ELECTRONIC EQUIP ROOM NO. 2 |  | 2025-06-23 | 2025-07-05 | 1 | Irene | 80 | JC230625 21248
|  |  | E16723.33301 - ARRT & DETAIL OF RACK FOR SPARE PORTABLE FIRE EXT'R |  | 2025-06-23 | 2025-06-26 | 1 | Dinata | 32 | JC230625 21250
|  |  | E16311,33302 - PAINT AREA COMPARTMENT |  | 2025-06-23 | 2025-07-05 | 1 | Indra | 80 | JC230625 21251
|  |  | E25820.33101 - ML FOR FOUND. OF EQUIP. IN AFT MOORING AREA |  | 2025-06-23 | 2025-06-24 | 1 | Bagus | 16 | JC230625 21254
|  |  | E21801.33119 - ML FOR FOUND. OF EQUIP IN PASSAGE WAY (2KA1) |  | 2025-06-25 | 2025-06-26 | 1 | Bagus | 16 | JC230625 21255
|  |  | E21801.33120 - ML FOR FOUND. OF EQUIP IN PASSAGE WAY (2KA2) |  | 2025-06-27 | 2025-06-28 | 1 | Bagus | 16 | JC230625 21256
|  |  | E26241.33400 - MAT. LIST FOR FOLDING FOOR |  | 2025-06-23 | 2025-06-24 | 1 | Rizal | 16 | JC230625 21257
|  |  | E26723.33301 - ML FOR RACK FOR SPARE PORTABLE FIRE EXT'R |  | 2025-06-30 | 2025-07-01 | 1 | Dinata | 16 | JC230625 21258
|  |  | EZ6632.33101 - FOUND. OF EQUIP. IN SWITCHBOARD ROOM AFT |  | 2025-06-30 | 2025-07-05 | 1 | Karina | 40 | JC240625 21263
|  |  | E11672.33103 - DETAIL OF BLAST DOOR |  | 2025-06-30 | 2025-07-05 | 1 | Sutan | 40 | JC240625 21264
|  |  | E10660.10403 - ACCOMM. ARRT OF 01 DECK - R1 |  | 2025-06-30 | 2025-07-04 | 1 | Rizal | 40 | JC240625 21265
|  |  | EZ7130. 33101 - FOUND. OF EQUIP. IN RIFLE STORE |  | 2025-06-26 | 2025-06-28 | 1 | Iyan | 24 | JC240625 21266
|  |  | EZ6631.33108 - FOUND. OF EQUIP. IN ELECTRONIC ROOM NO. 8 - R1 |  | 2025-06-30 | 2025-07-02 | 1 | Iyan | 24 | JC240625 21268
|  |  | EZ6720,33101 - FOUND. OF EQUIP. IN RATION PACK STOWAGE |  | 2025-07-03 | 2025-07-05 | 1 | Iyan | 24 | JC240625 21269
|  | W306-307 | E16221.33207 - ARRT OF PLATFORM IN ENG. CASING - R1 |  | 2025-06-30 | 2025-07-02 | 1 | Anam | 24 | JC240625 21271
|  | W308 | E26241.33400 - MAT. LIST FOR FOLDING FOOR |  | 2025-06-25 | 2025-06-26 | 1 | Rizal | 16 | JC230625 21260
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-06-30 | 2025-07-04 | 2 | Yudi, Wiwid | 40 | JC240625 21272
|  |  | E16233.33202 - ARRT OF LADDER IN CHILLER & STP ROOM - R1 |  | 2025-07-03 | 2025-07-05 | 1 | Anam | 24 | JC240625 21276
|  | KPI | REVIEW BRS UAE |  | 2025-06-23 | 2025-06-25 | 1 | Iyan | 24 | JC230625 21259
|  |  | REVIEW BRS UAE |  | 2025-07-02 | 2025-07-04 | 1 | Dinata | 24 | JC230625 21261
|  | W304-305 | E26631.33115 - ML FOR FOUND. OF EQUIP. IN PASSAGE WAY (2HZ2) |  | 2025-06-30 | 2025-07-01 | 1 | Bagus | 16 | JC300625 21513
|  |  | E21801,33118 - ML FOR FOUND. OF EQUIP. IN BAGGAGE STORE NO. 1 (2FA4) |  | 2025-07-02 | 2025-07-03 | 1 | Bagus | 16 | JC300625 21524
|  |  | E21801.33116 - ML FOR FOUND. OF EQUIP IN PASSAGE WAY (2JZ4) |  | 2025-07-04 | 2025-07-05 | 1 | Bagus | 16 | JC300625 21527
|  |  | EZ5820.33100 - FOUND. OF EQUIP. IN AFT MOORING AREA |  | 2025-07-07 | 2025-07-12 | 1 | Karina | 40 | JC300625 21532
|  |  | EZ5820.33102 - FOUND. OF EQUIP. IN FORE MOORING AREA (1AA0-E) |  | 2025-07-14 | 2025-07-17 | 1 | Karina | 32 | JC300625 21533
|  |  | EZ5820.33102 - ML FOR FOUND. OF EQUIP. IN FORE MOORING AREA (1AA0-E) |  | 2025-07-18 | 2025-07-19 | 1 | Karina | 16 | JC300625 21552
|  |  | EZ6631,33118 - FOUND. OF EQUIP. IN ELECT. EQUIP. ROOM NO. 16 |  | 2025-07-07 | 2025-07-12 | 1 | Iyan | 40 | JC300625 21553
|  |  | EZ4380,33100 - FOUND. OF EQUIP. IN MCR & DCHQ (2KA0) |  | 2025-07-14 | 2025-07-19 | 1 | Iyan | 40 | JC300625 21554
|  |  | EZ1801,33111 - FOUND. OF EQUIPMENT IN PASSAGE WAY (2JA3) |  | 2025-07-07 | 2025-07-10 | 1 | Bagus | 32 | JC010725 21605
|  |  | E21801,33111 - ML FOR FOUND. OF EQUIPMENT IN PASSAGE WAY (2JA3) |  | 2025-07-11 | 2025-07-12 | 1 | Bagus | 16 | JC010725 21606
|  |  | E16311,01301 - LIST OF PAINT FOR SPARE |  | 2025-07-07 | 2025-07-10 | 1 | Indra | 32 | JC010725 21607
|  |  | E26311.01301 - MAT. LIST FOR LIST OF PAINT FOR SPARE |  | 2025-07-11 | 2025-07-12 | 1 | Indra | 16 | JC010725 21608
|  |  | EVATEK RHIB |  | 2025-07-07 | 2025-07-08 | 1 | Dinata | 16 | JC010725 21609
|  |  | EZ1801,33107 - FOUND. OF EQUIP. IN STAIRWAY (2GA4) |  | 2025-07-14 | 2025-07-17 | 1 | Bagus | 32 | JC010725 21610
|  |  | E21801,33107 - ML FOR FOUND. OF EQUIP. IN STAIRWAY (2GA4) |  | 2025-07-18 | 2025-07-19 | 1 | Bagus | 16 | JC010725 21618
|  |  | E10660.10402 - ACCOMM. ARRT OF 1 DECK - R1 |  | 2025-07-07 | 2025-07-11 | 1 | Rizal | 40 | JC010725 21619
|  |  | E16500,33401 - FOUND. OF GALLEY, PANTRY & LAUNDRY EQUIPMENT |  | 2025-07-14 | 2025-07-17 | 1 | Rizal | 32 | JC010725 21620
|  |  | E16500.33401 - ML FOR FOUND. OF GALLEY, PANTRY & LAUNDRY EQUIPMENT |  | 2025-07-18 | 2025-07-18 | 1 | Rizal | 8 | JC010725 21621
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-07-07 | 2025-07-11 | 2 | Yudi, Wiwid | 40 | JC010725 21622
|  | W306-307 | EVATEK LCU |  | 2025-07-09 | 2025-07-11 | 1 | Dinata | 32 | JC010725 21623
|  | W304-305 | E16233,33200 - DET. OF VL IN COMPT. E.F,G,H ON 4 DECK - R2 |  | 2025-07-07 | 2025-07-12 | 1 | Farhan | 40 | JC020725 21700
|  |  | EZ433P.33200 - FOUND. OF EQUIP IN BLOCK 433 (P) |  | 2025-07-14 | 2025-07-17 | 1 | Farhan | 32 | JC020725 21701
|  |  | EZ223S.33200 - FOUND. OF EQUIP IN BLOCK 223 (S) - R1 |  | 2025-07-18 | 2025-07-26 | 1 | Farhan | 48 | JC020725 21702
|  |  | EZ243P.33200 - FOUND. OF EQUIP IN BLOCK 243 (P) - R1 |  | 2025-07-28 | 2025-07-30 | 1 | Farhan | 24 | JC020725 21703
|  |  | EZ233S.33200 - FOUND. OF EQUIP IN BLOCK 233 (S) - R1 |  | 2025-07-31 | 2025-08-02 | 1 | Farhan | 24 | JC020725 21704
|  |  | E11503,33200 - ARRT & DET. OF EQUIPMENT IN FUNNEL - R1 |  | 2025-07-07 | 2025-07-12 | 1 | Anam | 40 | JC020725 21705
|  |  | EZ7531,33100 - FOUND. OF EQUIP. IN TORPEDO & STORE (01JA3) |  | 2025-07-07 | 2025-07-12 | 1 | Irene | 40 | JC020725 21706
|  |  | EZ7531,33101 - FOUND. OF EQUIP. IN TORPEDO & STORE (01JA4) |  | 2025-07-14 | 2025-07-19 | 1 | Irene | 40 | JC020725 21708
|  |  | E16120,33100 - ARRT OF RAILING - R3 |  | 2025-07-21 | 2025-07-26 | 1 | Irene | 40 | JC020725 21709
|  |  | E16120,33101 - DETAIL OF RAILING - R4 |  | 2025-07-28 | 2025-07-31 | 1 | Irene | 32 | JC020725 21710
|  |  | E26120.33101 - MAT. LIST FOR DETAIL OF RAILING - R4 |  | 2025-08-01 | 2025-08-02 | 1 | Irene | 16 | JC020725 21711
|  |  | E16311,33102 - PAINT AREA COMPARTMENT |  | 2025-07-14 | 2025-07-19 | 1 | Indra | 40 | JC020725 21713
|  |  | E16332,33200 - ARRT OF ICCP ANODE |  | 2025-07-11 | 2025-07-15 | 1 | Sutan | 24 | JC020725 21714
|  |  | E10660,10401 - ACCOMM. ARRT OF 2 DECK - R1 |  | 2025-07-21 | 2025-07-25 | 1 | Rizal | 40 | JC020725 21715
|  |  | E10660,10400 - ACCOMM. ARRT OF 3 DECK - R1 |  | 2025-07-28 | 2025-08-01 | 1 | Rizal | 40 | JC020725 21716
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-07-21 | 2025-07-25 | 3 | Yudi, Wiwid, Dinata | 40 | JC020725 21717
|  | W308 | E16233,33203 - ARRT & DETAIL OF LADDER IN E/R - R2 |  | 2025-07-14 | 2025-07-19 | 1 | Anam | 40 | JC020725 21718
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-07-14 | 2025-07-18 | 3 | Yudi, Wiwid, Dinata | 40 | JC020725 21719
|  |  | EF232P.04300 - 232 P BLOCK PAINTING - R3 |  | 2025-07-07 | 2025-07-07 | 1 | Sutan | 8 | JC020725 21720
|  |  | EF232S.04300 - 232 S BLOCK PAINTING - R3 |  | 2025-07-08 | 2025-07-08 | 1 | Sutan | 8 | JC020725 21721
|  |  | EF132P.04300 - 232 P BLOCK PAINTING - R3 |  | 2025-07-09 | 2025-07-09 | 1 | Sutan | 8 | JC020725 21722
|  |  | EF132S.04300 - 132 S BLOCK PAINTING - R3 |  | 2025-07-10 | 2025-07-10 | 1 | Sutan | 8 | JC020725 21723
|  | KPI | 3D MODEL PIPING PLTAL |  | 2025-07-01 | 2025-08-01 | 1 | Diva | 192 | JC020725 21707
|  | W304-305 | E21672,33103 - ML FOR BLAST DOOR |  | 2025-07-16 | 2025-07-18 | 1 | Sutan | 24 | JC070725 21982
|  |  | E11672,33105 - STEEL LATICE DOOR - R2 |  | 2025-07-21 | 2025-07-23 | 1 | Sutan | 24 | JC070725 21983
|  |  | E21672,33105 - ML FOR STEEL LATICE DOOR - R2 |  | 2025-07-24 | 2025-07-25 | 1 | Sutan | 16 | JC070725 21984
|  |  | EZ6720,33100 - FOUND. OF EQUIP. IN DIVERS STORE (2PA2) |  | 2025-07-21 | 2025-07-23 | 1 | Karina | 24 | JC070725 21986
|  |  | EZ6741,33100 - FOUND. OF EQUIP. IN HANGAR (1LA0) |  | 2025-07-24 | 2025-07-26 | 1 | Karina | 24 | JC070725 21988
|  |  | E21801,33109 - SEAT OF EQUIPMENT IN PASSAGE WAY (2LA4) |  | 2025-07-21 | 2025-07-22 | 1 | Bagus | 16 | JC070725 21990
|  |  | E21801,33110 - SEAT OF EQUIPMENT IN PASSAGE WAY (2LA3) |  | 2025-07-23 | 2025-07-24 | 1 | Bagus | 16 | JC070725 21991
|  |  | EZ5820,33102 - FOUND. OF EQUIP IN FORE MOORING AREA (1AA0-E) |  | 2025-07-25 | 2025-07-29 | 1 | Bagus | 24 | JC080725 22014
|  |  | EZ6720,33100 - FOUND. OF EQUIP. IN DIVERS STORE (2PA4) |  | 2025-07-30 | 2025-08-01 | 1 | Bagus | 24 | JC080725 22015
|  |  | E26720,33100 - ML FOR FOUND. OF EQUIP. IN DIVERS STORE (2PA4) |  | 2025-08-02 | 2025-08-02 | 1 | Bagus | 8 | JC080725 22016
|  |  | EZ6721,33101 - FOUND. OF EQUIP. IN HAWSER STORE (2PA3) |  | 2025-07-28 | 2025-08-02 | 1 | Karina | 40 | JC080725 22017
|  |  | E16032,32301 - ARRT OF CBRN SIGN - R1 |  | 2025-07-28 | 2025-08-01 | 1 | Dinata | 40 | JC080725 22019
|  | W304-305 | E16221,33204 - ARRT & DETAIL OF GRATING IN ENGINE CASING - R1 |  | 2025-07-21 | 2025-07-29 | 1 | Iyan | 56 | JC180725 22405
|  |  | E16221,33204 - ML FOR DETAIL OF GRATING IN ENGINE CASING - R1 |  | 2025-07-30 | 2025-07-31 | 1 | Iyan | 16 | JC180725 22408
|  |  | E15710,33101 - DETAIL OF RAS EQUIPMENT |  | 2025-08-01 | 2025-08-16 | 1 | Iyan | 96 | JC180725 22409
|  |  | EZ6723,33100 - FOUND. OF EQUIP. IN FOAM ROOM (01MZ3) |  | 2025-08-18 | 2025-08-21 | 1 | Iyan | 32 | JC180725 22410
|  |  | E26723,33100 - ML FOR FOUND. OF EQUIP. IN FOAM ROOM (01MZ3) |  | 2025-08-22 | 2025-08-23 | 1 | Iyan | 16 | JC180725 22413
|  |  | E12590.33200 - ARRT & DET. OF SUPPORT EXH. GAS PIPE - R1 |  | 2025-08-25 | 6 Sept 2025 | 1 | Iyan | 80 | JC180725 22414
|  | W306-307 | E16221,33207 - ARRT OF PLATFORM IN ENGINE CASING - R1 |  | 2025-07-21 | 2025-07-26 | 1 | Anam | 40 | JC180725 22415
|  | W308 | E16231,33406 - ARRT & DETAIL OF STORMRAIL IN STAIRWAY - R2 |  | 2025-07-28 | 2025-08-02 | 1 | Anam | 40 | JC180725 22417
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-07-28 | 2025-08-01 | 2 | Yudi, Wiwid | 40 | JC180725 22418
| 2025-07-24 | W304-305 | EZ6624,33100 - FOUND. OF EQUIP. IN RADIO ROOM (02FA1) |  | 2025-07-21 | 2025-07-26 | 1 | Indra | 40 | JC240725 22630
|  |  | E86332.51300 - ICCP SYSTEM |  | 2025-08-04 | 2025-08-06 | 1 | Sutan | 24 | JC240725 22634
|  |  | E86333.51300 - MGPS SYSTEM |  | 2025-08-07 | 2025-08-08 | 1 | Sutan | 16 | JC240725 22635
|  |  | EZ4611,33100 - SEAT OF EQUIPMENT IN SONAR ROOM (3BA0) - R1 |  | 2025-07-28 | 2025-08-02 | 1 | Indra | 40 | JC240725 22638
|  |  | E16440.33400 - STEEL COAMING FOR WET AREA - R1 |  | 2025-08-04 | 2025-08-06 | 1 | Bagus | 24 | JC240725 22640
|  |  | E16400.33400 - STEEL COAMING FOR DRY AREA - R1 |  | 2025-08-07 | 2025-08-09 | 1 | Bagus | 24 | JC240725 22642
|  |  | EZ6721.33101 - FOUND. OF EQUIP. IN HAWSER & CBRN STORE (2BA0) |  | 2025-08-04 | 2025-08-09 | 1 | Karina | 40 | JC240725 22645
|  |  | E16021.33400 - IMO NUMBER |  | 2025-08-04 | 2025-08-08 | 1 | Rizal | 40 | JC240725 22646
|  |  | E16020.33403 - LAMBANG GARUDA |  | 2025-08-11 | 2025-08-12 | 1 | Rizal | 16 | JC240725 22647
|  | W306-307 | E25730,51104 - ML FOR CARGO LIFT |  | 2025-08-11 | 2025-08-13 | 1 | Sutan | 24 | JC240725 22648
|  |  | E25730,51105 - ML FOR RHIB DAVIT |  | 2025-08-14 | 2025-08-16 | 1 | Sutan | 24 | JC240725 22651
|  | W308 | E21672,33104 - ML FOR COVER INSPECTION HOLES (RM) - R2 |  | 2025-07-28 | 2025-07-30 | 1 | Sutan | 24 | JC240725 22652
|  |  | EF122P.04300 - 122 P BLOCK PAINTING - R2 |  | 2025-07-31 | 2025-07-31 | 1 | Sutan | 8 | JC240725 22654
|  |  | EF122S.04300 - 122 S BLOCK PAINTING - R2 |  | 2025-08-01 | 2025-08-01 | 1 | Sutan | 8 | JC240725 22655
|  | KPI | 3D MODEL PIPING SHIFLIFT |  | 2025-08-04 | 2025-08-29 | 1 | Diva | 160 | JC240725 22656
| 2025-08-04 | W304-305 | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-08-04 | 2025-08-08 | 2 | Yudi, Wiwid | 40 | JC040825 23199
|  |  | EZ5140,33204 - FOUND. OF EQUIP. IN AC ROOM NO 2 & 3 (1CA1) |  | 2025-08-04 | 2025-08-09 | 1 | Farhan | 40 | JC040825 23200
|  |  | EZ5140,33205 - FOUND. OF EQUIP. IN AC ROOM NO 6 (1JZ0) |  | 2025-08-11 | 2025-08-16 | 1 | Farhan | 40 | JC040825 23201
|  |  | EZ5140,33202 - FOUND. OF EQUIP. IN AC ROOM NO 4 & 5 (01GZ0) |  | 2025-08-18 | 2025-08-23 | 1 | Farhan | 40 | JC040825 23202
|  |  | EZ5140,33203 - FOUND. OF EQUIP. IN AC ROOM NO 7 (01LB1) |  | 2025-08-25 | 2025-08-30 | 1 | Farhan | 40 | JC040825 23203 | Permintaan extend sampai 6 Sept.
|  |  | E16023,32301 - ARRT OF NBCD SIGN - R1 |  | 2025-08-04 | 2025-08-08 | 1 | Dinata | 40 | JC040825 23205
|  |  | REVIEW COMMENT LR - SAFETY PLAN |  | 2025-08-11 | 2025-08-15 | 1 | Dinata | 40 | JC040825 23207
|  |  | REVIEW COMMENT LR - ESCAPE WAY PLAN |  | 2025-08-18 | 2025-08-22 | 1 | Dinata | 40 | JC040825 23223
|  |  | EF542C.36100 - 542 C BLOCK PAINTING |  | 2025-08-04 | 2025-08-04 | 1 | Indra | 8 | JC040825 23225
|  |  | EF155C.36100 - 155 C BLOCK PAINTING |  | 2025-08-05 | 2025-08-05 | 1 | Indra | 8 | JC040825 23235
|  |  | EF613C,36100 - 613 C BLOCK PAINTING - R2 |  | 2025-08-06 | 2025-08-06 | 1 | Indra | 8 | JC040825 23238
|  |  | EF515C.36100 - 515 C BLOCK PAINTING - R2 |  | 2025-08-07 | 2025-08-07 | 1 | Indra | 8 | JC040825 23240
|  |  | EF693C,36100 - 693 C BLOCK PAINTING - R2 |  | 2025-08-08 | 2025-08-08 | 1 | Indra | 8 | JC040825 23245
|  |  | EF612P.36100 - 612 P BLOCK PAINTING - R2 |  | 2025-08-09 | 2025-08-09 | 1 | Indra | 8 | JC040825 23246
|  |  | EF612S.36100 - 612 S BLOCK PAINTING - R2 |  | 2025-08-11 | 2025-08-11 | 1 | Indra | 8 | JC040825 23248
|  |  | EF513P,36100 - 513 P BLOCK PAINTING - R2 |  | 2025-08-12 | 2025-08-12 | 1 | Indra | 8 | JC040825 23249
|  |  | EF513S,36100 - 513 S BLOCK PAINTING - R2 |  | 2025-08-13 | 2025-08-13 | 1 | Indra | 8 | JC040825 23251
|  |  | EF514C.36100 - 514 C BLOCK PAINTING - R2 |  | 2025-08-14 | 2025-08-14 | 1 | Indra | 8 | JC040825 23253
|  |  | EF623C,36100 - 623 C BLOCK PAINTING - R2 |  | 2025-08-15 | 2025-08-15 | 1 | Indra | 8 | JC040825 23254
|  | W306-307 | E16640,11100 - DAMAGE CONTROL PLAN - R1 |  | 2025-08-04 | 2025-08-09 | 1 | Irene | 40 | JC040825 23255
|  |  | E16000,10100 - GENERAL OUTFITTING ARRT - R2 |  | 2025-08-11 | 2025-08-16 | 1 | Irene | 40 | JC040825 23256
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-08-18 | 2025-08-22 | 2 | Yudi, Wiwid | 40 | JC040825 23257
|  |  | EVALUATION & REVIEW CARGO HANDLING |  | 2025-08-18 | 2025-08-30 | 1 | Sutan | 80 | JC040825 23258
|  |  | E17118.33400 - ARRT & DETAIL OF RIFLE STORE - R1 |  | 2025-08-11 | 2025-08-16 | 1 | Bagus | 40 | JC040825 23259
|  | W308 | EVALUATION & UPDATE POSITION OF FOUND, LADDER & FLOOR IN E/R |  | 2025-08-04 | 2025-08-16 | 1 | Anam | 80 | JC040825 23260
|  |  | E11672,11100 - ARRT OF STEEL DOOR - R3 |  | 2025-08-11 | 2025-08-16 | 1 | Karina | 40 | JC040825 23261
|  |  | E21672,33100 - MAT. LIST FOR STEEL DOOR - R1 |  | 2025-08-18 | 2025-08-20 | 1 | Karina | 24 | JC040825 23262
|  |  | E16442,33401 - DETAIL OF UNIT TOILET |  | 2025-08-13 | 2025-08-19 | 1 | Rizal | 40 | JC040825 23263
|  |  | E26442,33401 - MAT. LIST FOR DETAIL OF UNIT TOILET (RAW MATERIAL) |  | 2025-08-20 | 2025-08-22 | 1 | Rizal | 24 | JC040825 23271
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-08-11 | 2025-08-15 | 2 | Yudi, Wiwid | 40 | JC040825 23272
| 18 Agust 2025 | W304-305 | E12590,32201 - ARRT OF EXHAUST GAS PIPE (S) |  | 18 Agust 2025 | 30 Agust 2025 |  | Anam | 80 | JC190825 23876 | Permintaan extend sampai 6 Sept.
|  |  | EZ1802,33104 - FOUND OF EQUIP ON EXTERNAL BRIDGE WING |  | 18 Agust 2025 | 23 Agust 2025 |  | Irene | 40 | JC190825 23878
|  |  | EZ1802,33103 - FOUND OF EQUIP ON EXPOSED 02 DECK |  | 21 Agust 2025 | 27 Agust 2025 |  | Karina | 40 | JC190825 23880
|  |  | UPDATING 3D CADMATIC FOR ACCOMODATION |  | 18 Agust 2025 | 30 Agust 2025 |  | Bagus | 80 | JC190825 23879
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 25 Agust 2025 | 29 Agust 2025 |  | Yudi, Wiwid | 40 | JC190825 23890
|  |  | E21802,33104 - MAT. LIST FOR FOUND OF EQUIP ON EXTERNAL BRIDGE WING |  | 25 Agust 2025 | 27 Agust 2025 |  | Irene | 24 | JC190825 23891
|  |  | E11300,33101 - PLATFORM FOR AUXILIARY GUN 03 DECK |  | 28 Agust 2025 | 3 Sept 2025 |  | Irene | 40 | JC190825 23892
|  |  | E21300,33101 - MAT. LIST FOR PLATFORM FOR AUXILIARY GUN 03 DECK |  | 4 Sept 2025 | 6 Sept 2025 |  | Irene | 24 | JC190825 23893
|  |  | EZ1802.33103 - MAT. LIST FOR FOUND OF EQUIP ON EXPOSED 02 DECK |  | 28 Agust 2025 | 3 Sept 2025 |  | Karina | 24 | JC190825 23896
|  |  | 3D MODEL RHIB DAVIT |  | 25 Agust 2025 | 30 Agust 2025 |  | Dinata | 40 | JC190825 23897
|  |  | E16024,02300 - HAZARDOUS ZONE - R2 |  | 1 Sept 2025 | 6 Sept 2025 |  | Dinata | 40 | JC190825 23898
|  |  | E16011,33400 - ARRT OF MISCELLANEOUS FITTING & DETAIL |  | 25 Agust 2025 | 29 Agust 2025 |  | Rizal | 40 | JC190825 23899
|  |  | E26011,33400 - MAT. LIST FOR MISCELLANEOUS FITTING & DETAIL |  | 1 Sept 2025 | 3 Sept 2025 |  | Rizal | 24 | JC190825 23900
| 27 Agust 2025 | W304-305 | E16311.33102 - PAINT AREA COMPARTMENT - R1 |  | 18 Agust 2025 | 30 Agust 2025 |  | Indra | 80 | JC270825 24179
| 03 Sept 2025 | W304-305 | E12590,32201 - ARRT OF EXHAUST GAS PIPE (S) |  | 1 Sept 2025 | 13 Sept 2025 |  | Anam | 80 | JC040925 24561
|  |  | EZ4611,33101 - SEAT OF EQUIPMENT IN SONAR WATER FILTER (2AA0) - R2 |  | 1 Sept 2025 | 4 Sept 2025 |  | Indra | 32 | JC040925 24562
|  |  | E24611,33101 - ML FOR SEAT OF EQUIPMENT IN SONAR WATER FILTER (2AA0) - R1 |  | 5 Sept 2025 | 6 Sept 2025 |  | Indra | 16 | JC040925 24563
|  |  | EZ1233,33108 - FOUND. OF EQUIPMENT IN TRUNK (02/3JZ3) |  | 1 Sept 2025 | 3 Sept 2025 |  | Farhan | 24 | JC040925 24564
|  |  | EZ1233,33107 - FOUND. OF EQUIPMENT IN TRUNK (02/3JY3) |  | 4 Sept 2025 | 6 Sept 2025 |  | Farhan | 24 | JC040925 24565
|  |  | EZ1233,33103 - FOUND. OF EQUIPMENT IN TRUNK (02/2LY4) |  | 8 Sept 2025 | 10 Sept 2025 |  | Farhan | 24 | JC040925 24566
|  |  | EZ1233,33106 - FOUND. OF EQUIPMENT IN TRUNK (02/3lb2) |  | 11 Sept 2025 | 13 Sept 2025 |  | Farhan | 24 | JC040925 24567
|  |  | EZ1233,33104 - FOUND. OF EQUIPMENT IN TRUNK (02/2JZ2) |  | 15 Sept 2025 | 20 Sept 2025 |  | Farhan | 40 | JC040925 24568
|  |  | EZ1233,33105 - FOUND. OF EQUIPMENT IN TRUNK (02/2LA1) |  | 22 Sept 2025 | 27 Sept 2025 |  | Farhan | 40 | JC040925 24569
|  |  | E21233,33105 - ML FOR FOUND. OF EQUIPMENT IN TRUNK (02/2LA1) |  | 29 Sept 2025 | 30 Sept 2025 |  | Farhan | 16 | JC040925 24570
|  |  | EZ1801,33135 - FOUND. OF EQUIP. IN AIR FILTER CLEANING (02LB1) |  | 1 Sept 2025 | 4 Sept 2025 |  | Karina | 32 | JC080925 24802
|  |  | E21801,33135 - ML FOR FOUND. OF EQUIP. IN AIR FILTER CLEANING (02LB1) |  | 5 Sept 2025 | 6 Sept 2025 |  | Karina | 16 | JC080925 24803
|  |  | EZ6631,33104 - FOUND. OF EQUIP. IN ELECT. EQUIP. ROOM NO. 4 - R1 |  | 8 Sept 2025 | 10 Sept 2025 |  | Karina | 24 | JC040925 24571
|  |  | EZ1801,33100 - FOUND. OF EQUIP. IN PASSAGEWAY (2NZ4) - R1 |  | 11 Sept 2025 | 13 Sept 2025 |  | Karina | 24 | JC040925 24572
|  |  | EZ6721,33100 - FOUND. OF EQUIP. IN HAWSER & CBRN STORE (2BA0) - R1 |  | 15 Sept 2025 | 24 Sept 2025 |  | Karina | 64 | JC040925 24573
|  |  | EZ6631,33119 - FOUND. OF EQUIP. IN ELECTRIC ROOM NO. 3 (2LZ1) - R1 |  | 25 Sept 2025 | 27 Sept 2025 |  | Karina | 24 | JC040925 24595
|  |  | E26721,33100 - ML FOR FOUND. OF EQUIP. IN HAWSER & CBRN STORE (2BA0) - R1 |  | 29 Sept 2025 | 30 Sept 2025 |  | Karina | 16 | JC040925 24596
|  |  | E11300,33102 - PLATFORM FOR AUXILIARY GUN 02 DECK |  | 8 Sept 2025 | 13 Sept 2025 |  | Irene | 40 | JC040925 24599
|  |  | E21300,33102 - MAT. LIST FOR PLATFORM FOR AUXILIARY GUN 02 DECK |  | 15 Sept 2025 | 17 Sept 2025 |  | Irene | 24 | JC040925 24600
|  |  | E11672,33104 - COVER INSPECTION HOLES - R2 |  | 18 Sept 2025 | 20 Sept 2025 |  | irene | 24 | JC040925 24602
|  |  | E21672,33104 - ML FOR COVER INSPECTION HOLES - R2 |  | 22 Sept 2025 | 22 Sept 2025 |  | irene | 8 | JC040925 24603
|  |  | EZ6631,33102 - FOUND. OF EQUIP. IN ELECT. EQUIP. ROOM NO. 2 - R2 |  | 23 Sept 2025 | 27 Sept 2025 |  | Irene | 32 | JC080925 24800
|  |  | E26631,33102 - ML FOR FOUND. OF EQUIP. IN ELECT. EQUIP. ROOM NO. 2 - R2 |  | 29 Sept 2025 | 30 Sept 2025 |  | Irene | 16 | JC080925 24801
|  |  | RISET BLAST DOOR |  | 1 Sept 2025 | 6 Sept 2025 |  | Sutan | 40 | JC040925 24597
|  |  | RISET RCS RHIB DAVIT & MONORAIL |  | 8 Sept 2025 | 20 Sept 2025 |  | Sutan | 80 | JC040925 24605
|  |  | 3D MODEL HANGAR DOOR |  | 22 Sept 2025 | 27 Sept 2025 |  | Sutan | 40 | JC040925 24606
|  |  | 3D MODEL ACC. LADDER |  | 29 Sept 2025 | 2025-10-04 |  | Sutan | 40 | JC040925 24607
|  |  | E16720,33300 - ARRT & DET. OF FIRE 7REPAIR PARTY POST |  | 8 Sept 2025 | 13 Sept 2025 |  | Dinata | 40 | JC040925 24608
|  |  | E10770,02300 - SAFETY PLAN - R2 |  | 15 Sept 2025 | 20 Sept 2025 |  | Dinata | 40 | JC040925 24609
|  |  | E14360,02300 - FIRE CONTROL PLAN - R1 |  | 22 Sept 2025 | 27 Sept 2025 |  | Dinata | 40 | JC040925 24610
|  |  | E26720,33300 - ML FOR DET. OF FIRE 7REPAIR PARTY POST |  | 29 Sept 2025 | 30 Sept 2025 |  | Dinata | 16 | JC040925 24611
|  |  | EZ3041,33100 - HANGER FOR CABLE |  | 17 Sept 2025 | 20 Sept 2025 |  | Indra | 32 | JC040925 24612
|  |  | E23041,33100 - MAT. LIST FOR HANGER FOR CABLE |  | 22 Sept 2025 | 23 Sept 2025 |  | Indra | 16 | JC040925 24613
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 8 Sept 2025 | 12 Sept 2025 |  | Yudi, Wiwid | 40 | JC040925 24614
|  |  | 3D MODEL FOOD LIFT & PROV. LIFT |  | 1 Sept 2025 | 10 Sept 2025 |  | Bagus | 64 | JC040925 24598
|  |  | E26370,11400 - ML FOR JOINER WORK - R2 |  | 11 Sept 2025 | 13 Sept 2025 |  | Bagus | 16 | JC040925 24618
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 29 Sept 2025 | 2025-10-03 |  | Yudi, Wiwid | 40 | JC040925 24619
|  |  | E16241,33400 - FOLDING DOOR |  | 4 Sept 2025 | 10 Sept 2025 |  | Rizal | 40 | JC040925 24615
|  |  | E16020,33402 - TANDA KESATUAN - R1 |  | 18 Sept 2025 | 19 Sept 2025 |  | Rizal | 16 | JC080925 24700
|  |  | E16442,33401 - DETAIL OF UNIT TOILET (RAW MATERIAL) - R2 |  | 22 Sept 2025 | 24 Sept 2025 |  | Rizal | 24 | JC080925 24707
|  |  | E21671,11100 - ML FOR HATCH & VERTICAL LADDER - R2 |  | 15 Sept 2025 | 17 Sept 2025 |  | Anam | 24 | JC080925 24708
|  |  | E15710,33101 - DETAIL OF RAS EQUIPMENT |  | 15 Sept 2025 | 27 Sept 2025 |  | Iyan | 80 | JC080925 24715
|  |  | E25710,33101 - MAT. LIST FOR DETAIL OF RAS EQUIPMENT |  | 29 Sept 2025 | 30 Sept 2025 |  | Iyan | 16 | JC080925 24719
|  | W306-307 | EZ3041,33100 - HANGER FOR CABLE |  | 24 Sept 2025 | 27 Sept 2025 |  | Indra | 32 | JC080925 24724
|  |  | E23041,33100 - MAT. LIST FOR HANGER FOR CABLE |  | 29 Sept 2025 | 30 Sept 2025 |  | Indra | 16 | JC080925 24736
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 15 Sept2025 | 19 Sept 2025 |  | Yudi, Wiwid | 40 | JC080925 24738
|  |  | 3D MODEL FOOD LIFT |  | 26 Sept 2025 | 30 Sept 2025 |  | Bagus | 32 | JC080925 24742
|  |  | E27118,33400 - MAT. LIST FOR RIFLE STORE - R3 |  | 25 Sept 2025 | 26 Sept 2025 |  | Rizal | 16 | JC080925 24750
|  |  | E16700,33400 - RACK FOR STORE & LOCKER - R3 |  | 29 Sept 2025 | 30 Sept 2025 |  | Rizal | 16 | JC080925 24751
|  | W308 | EZ3041,33100 - HANGER FOR CABLE |  | 8 Sept 2025 | 13 Sept 2025 |  | Indra | 40 | JC080925 24749
|  |  | E23041,33100 - MAT. LIST FOR HANGER FOR CABLE |  | 15 Sept 2025 | 16 Sept 2025 |  | Indra | 16 | JC080925 24752
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 1 Sept 2025 | 5 Sept 2025 |  | Yudi, Wiwid | 40 | JC040925 24616
|  |  | 3D MODEL FOOD LIFT & PASSENGER LIFT |  | 15 Sept 2025 | 20 Sept 2025 |  | Bagus | 40 | JC080925 24753
|  |  | E16221,33101 - ARRT FLOOR IN BOW THRUSTER - R1 |  | 22 Sept 2025 | 25 Sept 2025 |  | Bagus | 32 | JC080925 24754
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 22 Sept 2025 | 26 Sept 2025 |  | Yudi, Wiwid | 40 | JC080925 24756
|  |  | E16241,33400 - FOLDING DOOR |  | 11 Sept 2025 | 17 Sept 2025 |  | Rizal | 40 | JC080925 24757
|  |  | EZ231P,33200 - FOUND. OF EQUIPMENT IN BLOCK 231 (P) - R5 |  | 18 Sept 2025 | 24 Sept 2025 |  | Anam | 40 | JC080925 24758
|  |  | E2342C.33200 - ML FOR FOUND. OF EQUIP. ON BLOCK 342 (C) |  | 25 Sept 2025 | 27 Spet 2025 |  | Anam | 24 | JC080925 24759
|  |  | E2222P.33200 - ML FOR FOUND. OF EQUIP. ON BLOCK 222 (P) - R1 |  | 29 Sept 2025 | 30 Sept 2025 |  | Anam | 16 | JC080925 24762
|  |  | RISET RECOMPRESSION CHAMBER & MEDICAL EQUIPMENT |  | 8 Sept 2025 | 13 Sept 2025 |  | Iyan | 40 | JC040925 24617
|  | KPI | 3D MODEL OUTFITTING PLTAL |  | 1 Sept 2025 | 30 Sept 2025 |  | Diva | 176 | JC040925 24604
|  | W304-305 | EZ1802,33100 - FOUND. OF EQUIP. IN EXPOSED 02 DECK |  | 2025-10-01 | 2025-10-04 |  | Karina | 32 | JC011025 25764
|  |  | E11672,33104 - COVER INSPECTION HOLES - R5 |  | 2025-10-01 | 2025-10-04 |  | Irene | 32 | JC011025 25765
|  |  | E16315,01300 - PAINTING SCHEDULE - RA0 |  | 2025-10-01 | 2025-10-04 |  | Indra | 32 | JC011025 25770
|  |  | E16400.33400 - STEEL COAMING FOR DRY AREA - R1 |  | 2025-10-01 | 2025-10-04 |  | Bagus | 32 | JC011025 25772
|  | W304-305 | EZ241S,33200 - FOUND. OF EQUIP. BLOCK 241 (S) - RA1 |  | 2025-10-01 | 2025-10-04 |  | Farhan | 32 | JC071025 26020
|  |  | EZ131C,33200 - FOUND. OF EQUIP. BLOCK 131 (C) - R5 |  | 2025-10-06 | 2025-10-11 |  | Farhan | 40 | JC071025 26021
|  |  | EZ232S,33200 - FOUND. OF EQUIP. BLOCK 232 (S) - RA1 |  | 2025-10-13 | 2025-10-18 |  | Farhan | 40 | JC071025 26022
|  |  | EZ212P,33200 - FOUND. OF EQUIP. BLOCK 212 (P) - RA3 |  | 2025-10-20 | 2025-10-25 |  | Farhan | 40 | JC071025 26023
|  |  | EZ222S,33200 - FOUND. OF EQUIP. BLOCK 222 (S) - R2 |  | 2025-10-27 | 2025-10-29 |  | Farhan | 24 | JC071025 26024
|  |  | EZ433P,33200 - FOUND. OF EQUIP. BLOCK 433 (P) - R1 |  | 2025-10-30 | 2025-11-01 |  | Farhan | 24 | JC071025 26025
|  |  | E10770,02300 - SAFETY PLAN - R2 |  | 2025-10-01 | 2025-10-04 |  | Dinata | 32 | JC071025 26026
|  |  | E14360,02300 - FIRE CONTROL PLAN - R1 |  | 2025-10-06 | 2025-10-11 |  | Dinata | 40 | JC071025 26027
|  |  | E16024,02300 - HAZARDOUS ZONE - R2 |  | 2025-10-13 | 2025-10-18 |  | Dinata | 40 | JC071025 26028
|  |  | E10773,10300 - ESCAPE WAY PLAN - R2 |  | 2025-10-20 | 2025-10-25 |  | Dinata | 40 | JC071025 26029
|  |  | E16023,32300 - ARRT OF IMO SIGN |  | 2025-10-27 | 2025-10-30 |  | Dinata | 32 | JC071025 26030
|  |  | E26023,32300 - MAT. LIST FOR IMO SIGN |  | 2025-10-31 | 2025-11-01 |  | Dinata | 16 | JC071025 26031
|  |  | EZ6631,33107 - FOUND. OF EQUIP. IN ELECT. EQUIP. ROOM NO. 7 - R1 |  | 2025-10-01 | 2025-10-04 |  | Iyan | 32 | JC071025 26032
|  |  | E12590,32201 - ARRT OF EXHAUST GAS PIPE (S) |  | 2025-10-01 | 2025-10-04 |  | Anam | 32 | JC071025 26033
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-10-20 | 2025-10-24 |  | Yudi, Wiwid | 40 | JC141025 26383 |  | jc baru
|  |  | E11672,33107 - ENCLOSURE ROOM FOR BLAST TEST OF BLAST DOOR |  | 2025-10-06 | 2025-10-10 |  | Sutan | 40 | JC071025 26036
|  |  | E21672,33107 - ML FOR ENCLOSURE ROOM FOR BLAST TEST OF BLAST DOOR |  | 2025-10-13 | 2025-10-15 |  | Sutan | 24 | JC071025 26037
|  |  | EZ1802,33104 - FOUND. OF EQUIP. IN FORE MAST 05 DECK |  | 2025-10-06 | 2025-10-11 |  | Karina | 40 | JC071025 26038
|  |  | EZ1802,33102 - FOUND. OF EQUIP. ON BRIDGE ROOF |  | 2025-10-13 | 2025-10-25 |  | Karina | 80 | JC071025 26039
|  |  | E21802,33100 - ML FOR FOUND. OF EQUIP. IN EXPOSED 02 DECK |  | 2025-10-27 | 2025-10-29 |  | Karina | 24 | JC071025 26040
|  |  | E21802,33102 - ML FOR FOUND. OF EQUIP. ON BRIDGE ROOF |  | 2025-10-30 | 2025-11-01 |  | Karina | 24 | JC071025 26042
|  |  | E21672,33104 - ML FOR COVER INSPECTION HOLE - R4 |  | 2025-10-06 | 2025-10-07 |  | Irene | 16 | JC071025 26047
|  |  | EZ6631,33102 - FOUND. OF EQUIP. IN ELECT. EQUIP. ROOM NO. 2 - R3 |  | 2025-10-08 | 2025-10-11 |  | Irene | 24 | JC071025 26049
|  |  | E16440.33400 - STEEL COAMING FOR WET AREA - R1 |  | 2025-10-06 | 2025-10-11 |  | Bagus | 40 | JC071025 26051
|  | W306-307 | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 2025-10-06 | 2025-10-10 |  | Yudi, WIwid | 40 | JC071025 26052
|  |  | EZ223P.33200 - FOUND. OF EQUIPMENT ON BLOCK 223 (P) |  | 2025-10-06 | 2025-10-08 |  | Indra | 24 | JC071025 26053
|  |  | EZ223S.33200 - FOUND. OF EQUIPMENT ON BLOCK 223 (S) |  | 2025-10-09 | 2025-10-11 |  | Indra | 24 | JC071025 26054
|  |  | EZ6500,33400 - FOUND. OF GALLEY, PANTRY & LAUNDRY EQUI[PMENT |  | 2025-10-06 | 2025-10-10 |  | Rizal | 40 | JC071025 26055
|  |  | E26500,33400 - MAT. LIST FOR FOUND. OF GALLEY, PANTRY & LAUNDRY EQUI[PMENT |  | 2025-10-13 | 2025-10-15 |  | Rizal | 24 | JC071025 26056
|  | W308 | REVIEW MEDICAL EQUIPMENT |  | 2025-10-06 | 2025-10-11 |  | Iyan | 40 | JC071025 26059
|  |  | E16221,33203 - ARRT OF FLOOR IN AUXILIARY ROOM - R1 |  | 2025-10-06 | 2025-10-11 |  | Anam | 40 | JC071025 26060
|  |  | E16221,33204 - ARRT OF FLOOR IN ENGINE ROOM - R1 |  | 2025-10-13 | 2025-10-18 |  | Anam | 40 | JC071025 26061
|  |  | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 2025-10-13 | 2025-10-17 |  | Yudi, Wiwid | 40 | JC071025 26062
|  |  | E10660,10404 - ACCOMMODATION ARRT 04 DECK - R2 |  | 2025-10-01 | 2025-10-03 |  | Rizal | 24 | JC071025 26063
|  |  | E26311,91301 - ML FOR PIPING SYSTEM PAINTING |  | 2025-10-16 | 2025-10-18 |  | Sutan | 24 | JC071025 26064
|  |  | E16311,91301 - PIPING SYSTEM PAINTING |  | 2025-10-20 | 2025-10-25 |  | Sutan | 40 | JC071025 26065
|  | KPI | 3D MODEL OUTFITTING PLTAL |  | 2025-10-06 | 2025-10-31 |  | Diva | 152 | JC091025 26164
|  | W304-305 | E11672,33104 - COVER INSPECTION HOLES - RA0 |  | 2025-10-13 | 2025-10-18 |  | Irene | 40 | JC141025 26384
|  |  | E21672,33400 - MAT. LIST FOR COVER INSPECTION HOLE - R5 |  | 2025-10-20 | 2025-10-21 |  | irene | 16 | JC141025 26385
|  |  | E16222,33401 - ARRT & DET. OF RAISED FLOOR - R1 |  | 2025-10-20 | 2025-10-23 |  | Bagus | 32 | JC141025 26386
|  |  | E26222,33401 - MAT. LIST FOR RAISED FLOOR - R1 |  | 2025-10-24 | 2025-10-25 |  | Bagus | 8 | JC141025 26387
|  |  | E15710,33101 - DETAIL OF RAS EQUIPMENT |  | 2025-10-13 | 2025-10-18 |  | Iyan | 40 | JC141025 26388
|  |  | E25710,33101 - MAT. LIST FOR DETAIL OF RAS EQUIPMENT |  | 2025-10-20 | 2025-10-22 |  | Iyan | 24 | JC141025 26389
|  | W306-307 | EZ221P.33200 - FOUND. OF EQUIP. IN BLOCK 221 (P) |  | 2025-10-13 | 2025-10-18 |  | Indra | 40 | JC141025 26390
|  |  | EZ221S.33200 - FOUND. OF EQUIP. IN BLOCK 221 (S) |  | 2025-10-20 | 2025-10-25 |  | Indra | 40 | JC141025 26391
|  |  | E2221P.33200 - MAT. LIST FOR FOUND. OF EQUIP. IN BLOCK 221 (P) |  | 2025-10-27 | 2025-10-29 |  | Indra | 24 | JC141025 26392
|  |  | E2221S.33200 - MAT. LIST FOR FOUND. OF EQUIP. IN BLOCK 221 (S) |  | 2025-10-30 | 2025-11-01 |  | Indra | 24 | JC141025 26393
|  |  | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 2025-10-27 | 2025-10-31 |  | Yudi, Wiwid | 40 | JC141025 26398
|  | W308 | E16221,33101 - ARRT FLOOR IN BOW THRUSTER - R2 |  | 2025-10-13 | 2025-10-18 |  | Bagus | 40 | JC141025 26394
|  |  | E16402,11400 - LIST OF ALU FURNITURE - R2 |  | 2025-10-16 | 2025-10-17 |  | Rizal | 16 | JC141025 26395
|  |  | E26402,11400 - MAT. LIST FOR ALU FURNITURE - R2 |  | 2025-10-20 | 2025-10-21 |  | Rizal | 16 | JC141025 26397
| 2025-10-21 | W304-305 | E16231,33405 - STAIRWAY IN ACCOMM. 02 DECK - R5 |  | 2025-10-22 | 2025-10-25 |  | Irene | 24 | JC211025 26691
|  |  | E16231,33403 - STAIRWAY IN ACCOMM. 1 DECK - R5 |  | 2025-10-27 | 2025-10-30 |  | Irene | 32 | JC211025 26692
|  |  | E16231,33404 - STAIRWAY IN ACCOMM. 01 DECK - R5 |  | 2025-10-31 | 2025-11-04 |  | Irene | 24 | JC211025 26693
|  |  | E22590,33200 - ML FOR SUPPORT EXHAUST - R2 |  | 2025-10-23 | 2025-10-25 |  | Iyan | 24 | JC211025 26694
|  |  | E15710,33101 - DETAIL OF RAS EQUIPMENT |  | 2025-10-27 | 2025-11-01 |  | Iyan | 40 | JC211025 26696
|  |  | E10660,10404 - ACCOMMODATION ARRT 03 DECK - R1 |  | 2025-10-22 | 2025-10-24 |  | Rizal | 24 | JC211025 26697
|  |  | E10660,10402 - ACCOMMODATION ARRT 1 DECK - R1 |  | 2025-10-27 | 2025-10-31 |  | Rizal | 40 | JC211025 26698
|  |  | E10660,10404 - ACCOMMODATION ARRT 02 DECK - R1 |  | 2025-10-27 | 2025-11-01 |  | Bagus | 40 | JC211025 26699
|  | W306-307 | E16640,11100 - DAMAGE CONTROL PLAN - R1 |  | 2025-10-27 | 2025-11-01 |  | Anam | 40 | JC211025 26705
|  |  | REVIEW RO-RO EQUIPMENT |  | 2025-10-27 | 2025-10-31 |  | Sutan | 40 | JC211025 26706
|  | W308 | EZ111S.33200 - FOUND. OF EQUIP IN BLOCK 111 (S) - RA3 |  | 2025-10-20 | 2025-10-25 |  | Anam | 40 | JC211025 26707
|  |  | E16221,33101 - ARRT FLOOR IN BOW THRUSTER - R2 |  | 2025-10-13 | 2025-10-18 |  | Bagus | 40 | JC211025 26708
| 5 Nop 2025 | W304-305 | 3D MODEL WINDOW WIPER |  | 3 Nop 2025 | 4 Nop 2025 |  | Bagus | 16 | JC051125 27270
|  |  | E16251,33400 - STEEL WALL OPENING FOR WINDOW - R2 |  | 5 Nop 2025 | 8 Nop 2025 |  | Bagus | 24 | JC051125 27271
|  |  | EZ6631,33110 - FOUND. OF EQUIP. IN ELECTRIC ROOM NO. 10 - R2 |  | 5 Nop 2025 | 8 Nop 2025 |  | Irene | 24 | JC051125 27272
|  |  | E11710,33100 - ARRT & DETAIL OF EQUIPMENT IN FORE MAST |  | 10 Nop 2025 | 15 Nop 2025 |  | Irene | 40 | JC051125 27273
|  |  | E14220,10100 - ARRT OF NAVIGATION & SIGNAL LIGHTS - R3 |  | 17 Nop 2025 | 22 Nop 2025 |  | Irene | 40 | JC051125 27274
|  |  | E21710,33100 - ML FOR DETAIL OF EQUIPMENT IN FORE MAST |  | 24 Nop 2025 | 26 Nop 2025 |  | Irene | 24 | JC051125 27275
|  |  | EZ3317,33100 - FOUND. OF SIDE LIGHT |  | 27 Nop 2025 | 2025-12-02 |  | Irene | 40 | JC051125 27276
|  |  | EZ6631,33104 - FOUND. OF EQUIP. IN ELECT. EQUIP. ROOM NO. 4 - R2 |  | 3 Nop 2025 | 4 Nop 2025 |  | Karina | 16 | JC051125 27277
|  |  | EZ6631,33120 - FOUND. OF EQUIP. IN ELECTRIC ROOM NO 4 - R3 |  | 5 Nop 2025 | 6 Nop 2025 |  | Karina | 16 | JC051125 27278
|  |  | EZ6631,33107 - FOUND. OF EQUIP. IN ELECT. EQUIP. ROOM NO. 7 - R3 |  | 7 Nop 2025 | 8 Nop 2025 |  | Karina | 16 | JC051125 27279
|  |  | EZ6632,33100 - FOUND. OF EQUIP. IN SWITCHBOARD ROOM FORE - R4 |  | 10 Nop 2025 | 11 Nop 2025 |  | Karina | 16 | JC051125 27280
|  |  | EZ6632,33101 - FOUND. OF EQUIP. IN SWITCHBOARD ROOM AFT - R3 |  | 12 Nop 2025 | 13 Nop 2025 |  | Karina | 16 | JC051125 27281
|  |  | EZ1801,33126 - ML FOR FOUND. OF EQUIP. IN STAIRWAY - R1 |  | 14 Nop 2025 | 15 Nop 2025 |  | Karina | 16 | JC051125 27282
|  |  | EZ6621,33100 - FOUND. OF EQUIP. IN BRIDGE |  | 17 Nop 2025 | 19 Nop 2025 |  | Karina | 24 | JC051125 27283
|  |  | EZ6626,33100 - FOUND. OF EQUIP. IN HELI CONTROL ROOM - R1 |  | 20 Nop 2025 | 22 Nop 2025 |  | Karina | 24 | JC051125 27284
|  |  | E41672,72103 - TP & TR OF BLAST DOOR |  | 3 Nop 2025 | 5 Nop 2025 |  | Sutan | 24 | JC051125 27285
|  |  | E11693,33100 - ARRT & DETAIL OF MONORAIL DOOR |  | 10 Nop 2025 | 15 Nop 2025 |  | Sutan | 24 | JC051125 27286
|  |  | E21693,33100 - ML FOR DETAIL OF MONORAIL DOOR |  | 17 Nop 2025 | 19 Nop 2025 |  | Sutan | 24 | JC051125 27287
|  |  | EZ5140,33201 - FOUND. OF EQUIP. IN AC ROOM NO 1 |  | 3 Nop 2025 | 5 Nop 2025 |  | Farhan | 24 | JC051125 27288
|  |  | EZ1801,33137 - FOUND. OF EQUIP. IN EXTINGUISHER ROOM |  | 6 Nop 2025 | 8 Nop 2025 |  | Farhan | 24 | JC051125 27291
|  |  | EZ241P,33200 - FOUND. OF EQUIP. BLOCK 241 (P) - RA1 |  | 10 Nop 2025 | 12 Nop 2025 |  | Farhan | 24 | JC061125 27296
|  |  | EZ211S,33200 - FOUND. OF EQUIP. BLOCK 211 (S) - R4 |  | 13 Nop 2025 | 15 Nop 2025 |  | Farhan | 24 | JC061125 27297
|  |  | EZ241S,33200 - FOUND. OF EQUIP. BLOCK 241 (S) - RA1 |  | 17 Nop 2025 | 19 Nop 2025 |  | Farhan | 24 | JC061125 27298
|  |  | EZ211P,33200 - FOUND. OF EQUIP. BLOCK 211 (P) - R5 |  | 20 Nop 2025 | 22 Nop 2025 |  | Farhan | 24 | JC061125 27299
|  |  | E15724,33201 - LIFT BEAM FOR DG IN E/R - R1 |  | 24 Nop 2025 | 26 Nop 2025 |  | Farhan | 24 | JC061125 27316
|  |  | E15724,33202 - LIFT BEAM 2T FOR M/E - R1 |  | 27 Nop 2025 | 29 Nop 2025 |  | Farhan | 24 | JC061125 27317
|  |  | E16032,32301 - ARRT OF CBRN SIGN - R1 |  | 3 Nop 2025 | 8 Nop 2025 |  | Dinata | 40 | JC061125 27318
|  |  | E16135,33300 - ARRT & DETAIL OF PORTABLE AWNING - R1 |  | 10 Nop 2025 | 13 Nop 2025 |  | Dinata | 24 | JC061125 27319
|  |  | E26135,33300 - ML FOR DETAIL OF PORTABLE AWNING - R1 |  | 14 Nop 2025 | 15 Nop 2025 |  | Dinata | 16 | JC061125 27320
|  |  | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 10 Nop 2025 | 14 Nop 2025 |  | Iyan, Yudi, Wiwid | 40 | JC061125 27321
|  |  | 3D WINDOW WIPER |  | 3 Nop 2025 | 5 Nop 2025 |  | Bagus | 24 | JC061125 27322
|  |  | E16251,33400 - STEEL WALL OPENING FOR WINDOW - R2 |  | 6 Nop 2025 | 8 Nop 2025 |  | Bagus | 24 | JC061125 27323
|  |  | E10660,10403 - ACCOMM. ARRT 01 DECK - R1 |  | 10 Nop 2025 | 15 Nop 2025 |  | Bagus | 40 | JC061125 27324
|  |  | E16251,11400 - WINDOW PLAN - R3 |  | 10 Nop 2025 | 12 Nop 2025 |  | Rizal | 24 | JC061125 27325
|  |  | E16440.33400 - STEEL COAMING FOR WET AREA - R1 |  | 17 Nop 2025 | 22 Nop 2025 |  | Rizal | 40 | JC061125 27327
|  | W306-307 | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 17 Nop 2025 | 22 Nop 2025 |  | Dinata, Iyan, Yudi, Wiwid | 40 | JC061125 27329
|  |  | EZ122S.33200 - FOUND. OF EQUIP. IN BLOCK 122 (S) - R2 |  | 3 Nop 2025 | 8 Nop 2025 |  | Anam | 40 | JC061125 27330
|  |  | 3D MODEL LCU |  | 3 Nop 2025 | 28 Nop 2025 |  | Diva | 160 | JC071125 27348
|  |  | EVATEK MEDICAL EQUIPMENT |  | 3 Nop 2025 | 4 Nop 2025 |  | Iyan | 16 | JC071125 27349
|  |  | E16000,75101 - MAIN EQUIPMENT LIST LCU FOR HULL PART |  | 5 Nop 2025 | 8 Nop 2025 |  | Iyan | 24 | JC071125 27353
|  |  | EZ611P.33200 - FOUND. OF EQUIP. IN BLOCK 611 (P) - R1 |  | 3 Nop 2025 | 5 Nop 2025 |  | Indra | 24 | JC071125 27354
|  |  | EZ611S.33200 - FOUND. OF EQUIP. IN BLOCK 611 (S) - R1 |  | 6 Nop 2025 | 8 Nop 2025 |  | Indra | 24 | JC071125 27355
|  |  | EZ612P.33200 - FOUND. OF EQUIP. IN BLOCK 612 (P) - R1 |  | 10 Nop 2025 | 15 Nop 2025 |  | Indra | 40 | JC071125 27361
|  |  | EZ612S.33200 - FOUND. OF EQUIP. IN BLOCK 612 (S) - R1 |  | 17 Nop 2025 | 22 Nop 2025 |  | Indra | 40 | JC071125 27362
|  |  | EZ231P.33200 - FOUND. OF EQUIP. IN BLOCK 231 (P) - R2 |  | 24 Nop 2025 | 29 Nop 2025 |  | Indra | 40 | JC071125 27363
|  |  | E16011,33400 - ARRT OF MISCELLANEOUS - R1 |  | 3 Nop 2025 | 7 Nop 2025 |  | Rizal | 40 | JC071125 27364
|  |  | E16221,33207 - ARRT OF PLATFORM IN ENG. CASING - R1 |  | 10 Nop 2025 | 22 Nop 2025 |  | Anam | 80 | JC071125 27437
|  | W308 | E11672,33100 - ARRT OF WTD SLIDING DOOR - R3 |  | 6 Nop 2025 | 8 Nop 2025 |  | Sutan | 24 | JC071125 27365
|  |  | CEK GAMBAR, EVALUASI TEKINS & KOORDINASI TEKNIS |  | 3 Nop 2025 | 7 Nop 2025 |  | Yudi, Wiwid | 40 | JC071125 27366
|  |  | E16311,91302 - SHOP PRIMER FOR GALV. PIPE (FOT 3 & FO SETL TK) CALC |  | 24 Nop 2025 | 26 Nop 2025 |  | Sutan | 24 | JC071125 27367
|  |  | E26311,91302 - ML FOR SHOP PRIMER FOR GALV. PIPE (FOT 3 & FO SETL TK) CALC |  | 27 Nop 2025 | 28 Nop 2025 |  | Sutan | 16 | JC071125 27368
|  |  | CEK GAMBAR, EVALUASI TEKINS & KOORDINASI TEKNIS |  | 24 Nop 2025 | 28 Nop 2025 |  | Dinata, Iyan, Yudi, Wiwid | 40 | JC071125 27369
|  |  | E16250,11400 - WINDOW PLAN - R5 |  | 17 Nop 2025 | 18 Nop 2025 |  | Bagus | 16 | JC071125 27370
|  |  | E16251,33400 - STEEL WALL OPENING FOR WINDOW - R3 |  | 19 Nop 2025 | 22 Nop 2025 |  | Bagus | 24 | JC071125 27371
|  |  | E26250,11400 - ML FOR WINDOW - R5 |  | 13 Nop 2025 | 14 Nop 2025 |  | Rizal | 16 | JC071125 27374
|  | E250N002 | E11674,11100 - ARRT & DETAIL OF MANHOLE & VL - R1 |  | 20 Nop 2025 | 22 Nop 2025 |  | Sutan | 24 | JC061125 27300 | proyek 304
|  | W304-305 | E13210,33100 - DRUM FOR SHORE CONNECTION - R4 |  | 24 Nop 2025 | 26 Nop 2025 |  | Anam | 24 | JC201125 27934
|  |  | E16222,33400 - ARRT & DET. OF MPFF - R1 |  | 24 Nop 2025 | 29 Nop 2025 |  | Bagus | 40 | JC201125 27935
|  |  | E16022,33401 - SHIP NAME BOARD |  | 24 Nop 2025 | 28 Nop 2025 |  | Rizal | 40 | JC201125 27936
|  |  | EZ6621,33100 - FOUND. OF EQUIP. IN BRIDGE (03EA0) - R1 |  | 24 Nop 2025 | 29 Nop 2025 |  | Karina | 40 | JC201125 27937
|  | W306-307 | EZ221S.33200 - FOUND. OF EQUIP. IN BLOCK 221 (S) - RA2 |  | 27 Nop 2025 | 29 Nop 2025 |  | Anam | 24 | JC201125 27938
| 2025-12-01 | W304-305 | E96000.92102 - WEIGHT CONTROL (KB04) |  | 2025-12-01 | 2025-12-06 |  | Karina | 40 | JC011225 28474
|  |  | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 2025-12-01 | 2025-12-06 |  | Iyan, Dinata | 40 | JC011225 28475
|  |  | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 2025-12-01 | 2025-12-05 |  | Yudi, Wiwid | 40 | JC021225 28506
|  | W306-307 | E16311,01301 - LIST OF PAINT FOR SPARE |  | 2025-12-01 | 2025-12-04 |  | Indra | 32 | JC011225 28494
|  |  | E26311,01301 - MAT. LIST FOR PAINT FOR SPARE |  | 2025-12-05 | 2025-12-06 |  | Indra | 18 | JC011225 28495
|  |  | EZ221P.33200 - FOUND. OF EQUIP. IN BLOCK 221 (P) - RA1 |  | 2025-12-01 | 2025-12-03 |  | Anam | 24 | JC021225 28507
|  |  | E96000,92101 - WEIGHT KONTROL (KB03) |  | 2025-12-08 | 2025-12-13 |  | Dinata | 40 | JC021225 28508
|  |  | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 2025-12-08 | 2025-12-13 |  | Iyan, Yudi, Wiwid | 40 | JC021225 28509
|  | W308 | EZ1802,33101 - FOUND. OF EQUIP. IN EXP. DECK (4C41) - 05 DECK |  | 2025-12-04 | 2025-12-10 |  | Anam | 40 | JC021225 28534
|  |  | E21802,33101 - ML FOR FOUND. OF EQUIP. IN EXP. DECK (4C41) - 05 DECK |  | 2025-12-11 | 2025-12-13 |  | Anam | 24 | JC021225 28537
|  |  | EZ1802,33102 - FOUND. OF EQUIP. IN EXP. DECK (4C32) - 05 DECK |  | 2025-12-15 | 2025-12-20 |  | Anam | 40 | JC021225 28538
|  |  | E21802,33102 - ML FOR FOUND. OF EQUIP. IN EXP. DECK (4C32) - 05 DECK |  | 2025-12-22 | 2025-12-24 |  | Anam | 24 | JC021225 28539 | extend tgl 25, extend JO (32)
|  |  | E16311,01301 - LIST OF PAINT FOR SPARE |  | 2025-12-01 | 2025-12-03 |  | Sutan | 24 | JC021225 28540
|  |  | E26311,01301 - ML FOR LIST OF PAINT FOR SPARE |  | 2025-12-04 | 2025-12-05 |  | Sutan | 16 | JC021225 28541
|  |  | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 2025-12-15 | 2025-12-20 |  | Dinata, Iyan, Yudi, Wiwid | 40 | JC021225 28542
| 2025-12-05 | W304-305 | 3D MODEL TEMPORARY COVER ON FORE MAST |  | 2025-12-03 | 2025-12-04 |  | Irene | 16 | JC051225 28624
|  |  | E11672,33104 - COVER INSPECTION HOLE - RA1 |  | 2025-12-05 | 2025-12-06 |  | Irene | 16 | JC051225 28625
|  |  | E21672,33104 - ML FOR COVER INSPECTION HOLE - RA0 |  | 2025-12-08 | 2025-12-08 |  | Irene | 8 | JC051225 28626
|  |  | E16221,33200 - ARRT OF FLOOR IN FWD E/R - R1 |  | 2025-12-01 | 2025-12-06 |  | Farhan | 40 | JC051225 28627
|  |  | E16221,33202 - ARRT OF FLOOR IN AFT LOWER E/R - R1 |  | 2025-12-08 | 2025-12-13 |  | Farhan | 40 | JC051225 28628
|  |  | EZ432P.33200 - FOUND. OF EQUIP. IN BLOCK 432 (P) - RA3 |  | 2025-12-15 | 2025-12-16 |  | Farhan | 16 | JC051225 28629
|  |  | EZ212P.33200 - FOUND. OF EQUIP. IN BLOCK 212 (P) - RA4 |  | 2025-12-17 | 2025-12-20 |  | Farhan | 24 | JC051225 28630
|  |  | EZ232S,33200 - FOUND. OF EQUIP. IN BLOCK 232 (S) - RA2 |  | 2025-12-22 | 2025-12-31 |  | Farhan | 56 | JC051225 28631
|  |  | 3D MODEL ACCOMMODATION FURNITURE ALL DECK |  | 2025-12-01 | 2025-12-20 |  | Bagus | 120 | JC051225 28632
|  |  | E16000,10400 - COMPARTMENT NUMBERING SYSTEM |  | 2025-12-01 | 2025-12-05 |  | Rizal | 40 | JC051225 28633
|  |  | E16022,33401 - SHIP NAME BOARD |  | 2025-12-08 | 2025-12-12 |  | Rizal | 40 | JC051225 28634
|  |  | E10660,10403 - ACCOMM. ARRT OF 01 DECK - R1 |  | 2025-12-15 | 2025-12-19 |  | Rizal | 40 | JC051225 28635
|  |  | E10660,10404 - ACCOMM. ARRT OF 02 DECK - R1 |  | 2025-12-22 | 2025-12-26 |  | Rizal | 32 | JC051225 28636
|  |  | E10660,10405 - ACCOMM. ARRT OF 03 DECK - R1 |  | 2025-12-29 | 2025-12-31 |  | Rizal | 24 | JC051225 28637
|  |  | E11693,33100 - ARRT & DETAIL OF MONORAIL DOOR - R1 |  | 2025-12-08 | 2025-12-12 |  | Sutan | 40 | JC051225 28638
|  |  | E11672,33107 - ENCLOSURE ROOM FOR BLAST TEST OF BLAST DOOR - R1 |  | 2025-12-15 | 2025-12-17 |  | Sutan | 24 | JC051225 28639
|  |  | E21672,33107 - ML FOR ENCLOSURE ROOM FOR BLAST TEST OF BLAST DOOR - R1 |  | 2025-12-18 | 2025-12-19 |  | Sutan | 16 | JC051225 28642
|  |  | E41672,72103 - TP & TR OF BLAST DOOR - R1 |  | 2025-12-22 | 2025-12-24 |  | Sutan | 24 | JC051225 28643 | extend tgl 26, extend JO (40)
|  | LCU | E11674,32100 - ARRT & DETAIL OF MANHOLE & VL |  | 2025-12-08 | 2025-12-11 |  | Karina | 32 | JC051225 28644
|  |  | E21674,32100 - ML FOR OF MANHOLE & VL |  | 2025-12-12 | 2025-12-13 |  | Karina | 16 | JC051225 28645
|  |  | E16132,32100 - ARRT & DETAIL OF CAR LASHING |  | 2025-12-15 | 2025-12-18 |  | Karina | 32 | JC051225 28646
|  |  | E26132,32100 - ML FOR CAR LASHING |  | 2025-12-19 | 2025-12-20 |  | Karina | 16 | JC051225 28647
|  |  | E16221,33200 - ARRT & DETAIL OF FLOOR IN E/R |  | 2025-12-22 | 2025-12-27 |  | Iyan | 32 | JC051225 28648
|  |  | E16233,33200 - ARRT & DETAIL OF LADDER IN E/R |  | 2025-12-29 | 2025-12-31 |  | Iyan | 24 | JC051225 28649
|  | W306-307 | EZ221P. 33200 - FOUND. OF EQUIP. IN BLOCK 221 (P) - RA1 |  | 2025-12-08 | 2025-12-13 |  | Indra | 40 | JC051225 28650
|  |  | EZ221S.33200 - FOUND. OF EQUIP. IN BLOCK 221 (S) - RA1 |  | 2025-12-15 | 2025-12-20 |  | Indra | 40 | JC051225 28651
|  |  | EZ231P.33200 - FOUND. OF EQUIP. IN BLOCK 231 (P) - R4 |  | 2025-12-22 | 2025-12-27 |  | Indra | 32 | JC051225 28652
|  |  | EZ231S,33200 - FOUND. OF EQUIP. IN BLOCK 231 (S) - RA1 |  | 2025-12-29 | 2025-12-31 |  | Indra | 24 | JC051225 28653
|  | W308 | EZ4200,33100 - FOUND. OF EQUIP. IN GYRO ROOM |  | 2025-12-09 | 2025-12-11 |  | Irene | 24 | JC051225 28654
|  |  | EZ6631,33108 - FOUND. OF EQUIP. IN ELECTRONIC ROOM NO. 8 |  | 2025-12-12 | 2025-12-13 |  | Irene | 16 | JC051225 28655
|  |  | EZ6631,33109 - FOUND. OF EQUIP. IN ELECTRONIC ROOM NO. 9 |  | 2025-12-15 | 2025-12-17 |  | Irene | 24 | JC051225 28656
|  |  | EZ6631,33103 - FOUND. OF EQUIP. IN ELECTRONIC ROOM NO. 3 |  | 2025-12-18 | 2025-12-20 |  | Irene | 24 | JC051225 28657
|  |  | EZ6631,33101 - FOUND. OF EQUIP. IN ELECTRONIC ROOM NO. 1 |  | 2025-12-22 | 2026-01-03 |  | Irene | 64 | JC081225 28758
| 2025-12-22 | W304-305 | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 2025-12-22 | 2025-12-24 |  | Yudi, Wiwid | 24 | JC221225 29318
|  | W304-305 | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 2025-12-29 | 2026-01-02 |  | Yudi, Wiwid | 32 | JC221225 29319
|  | LCU | E11672,32100 - ARRT & DETAIL OF ALUMINUM DOOR |  | 2025-12-22 | 2025-12-24 |  | Karina | 24 | JC221225 29320
|  |  | E21672,32100 - ML FOR ALUMINUM DOOR |  | 2025-12-25 | 2025-12-27 |  | Karina | 16 | JC221225 29321
|  |  | E16350,11301 - INSULATION PLAN |  | 2025-12-22 | 2025-12-24 |  | Dinata | 24 | JC221225 29322
|  |  | E16350,11300 - FIRE PROTECTION |  | 2025-12-29 | 2026-01-02 |  | Dinata | 32 | JC221225 29323
|  |  | E16250,11400 - WINDOW PLAN |  | 2025-12-22 | 2025-12-24 |  | Bagus | 24 | JC221225 29324
|  |  | E26250,11400 - ML FOR WINDOW |  | 2025-12-25 | 2025-12-27 |  | Bagus | 16 | JC221225 29325
|  | W311 | E11672,32100 - ARRT & DETAIL OF ALUMINUM DOOR |  | 2025-12-29 | 2026-01-02 |  | Karina | 32 | JC221225 29326
|  |  | E16250,11400 - WINDOW PLAN |  | 2025-12-29 | 2026-01-02 |  | Bagus | 32 | JC221225 29327
|  | W308 | E11693,33100 - ARRT & DETAIL OF MONORAIL DOOR |  | 2025-12-29 | 2026-01-02 |  | Sutan | 32 | JC221225 29347
|  |  | EZ222P,33200 - FOUND. OF EQUIP. BLOCK 222 (P) - R5 |  | 2025-12-26 | 2025-12-27 |  | Anam | 16 | JC221225 29420
|  |  | EZ112S.33200 - FOUND. OF EQUIP BLOCK 112 (S) - R2 |  | 2025-12-29 | 2026-01-02 |  | Anam | 32 | JC221225 29421
2026-01-01
| 2026-01-06 | W304-305 | Cek gambar, evaluasi teknis & koordinasi teknis |  | 2026-01-02 | 2026-01-31 |  | Yudi, Wiwid | 40 | JC060126 29983
|  |  | Menyelesaikan gambar pondasi Frigate |  | 2026-01-02 | 2026-01-31 |  | Karina, Irene, Farhan | 40 | JC060126 29984
|  |  | Menyelesaikan gambar yard plan & prod. drawing Frigate |  | 2026-01-02 | 2026-01-31 |  | Sutan | 56 | JC060126 30003
|  |  | Menyelesaikan gambar yard plan & prod. drawing Frigate |  | 2026-01-02 | 2026-01-31 |  | Dinata | 32 | JC060126 30004
|  | W306-307 | Cek gambar, evaluasi teknis & koordinasi teknis proyek LDP & LCU |  | 2026-01-02 | 2026-01-31 |  | Yudi, Wiwid | 40 | JC060126 30005
|  |  | Menyelesaikan gambar yard plan & production drawing LCU |  | 2026-01-02 | 2026-01-31 |  | Karina | 96 | JC060126 30006
|  |  | Menyelesaikan gambar yard plan & prod. drawing LDP & LCU |  | 2026-01-02 | 2026-01-31 |  | Dinata, Sutan | 64 | JC060126 30007
|  |  | Menyelesaikan gambar yard plan & prod. drawing LDP & LCU |  | 2026-01-02 | 2026-01-31 |  | Iyan | 128 | JC060126 30008
|  |  | Menyelesaikan gambar yard plan & prod. drawing LDP & LCU |  | 2026-01-02 | 2026-01-31 |  | Indra | 136 | JC060126 30009
|  |  | Menyelesaikan gambar yard plan & prod. drawing LCU |  | 2026-01-02 | 2026-01-31 |  | Farhan | 68 | JC060126 30010
|  |  | Menyelesaikan gambar yard plan & prod. drawing LCU |  | 2026-01-02 | 2026-01-31 |  | Bagus, Rizal | 88 | JC060126 30011
|  | W3008 | Cek gambar, evaluasi teknis & koordinasi teknis |  | 2026-01-02 | 2026-01-31 |  | Yudi, Wiwid, Dinata | 40 | JC060126 30012
|  |  | Menyelesaikan gambar pondasi Al Maryah |  | 2026-01-02 | 2026-01-31 |  | Anam | 176 | JC060126 30013
|  |  | Menyelesaikan gambar pondasi AL Maryah |  | 2026-01-02 | 2026-01-31 |  | Irene | 136 | JC060126 30014
|  |  | menyelesaikan gambar yard plan & prod. drawing AL Maryah |  | 2026-01-02 | 2026-01-31 |  | Sutan | 56 | JC060126 30015
|  |  | Menyelesaikan gambar yard plan & prod. drawing Al Maryah |  | 2026-01-02 | 2026-01-31 |  | Iyan | 48 | JC060126 30016
|  | CORP2026 | Menyelesaikan gambar yard plan & prod. drawing KSSR |  | 2026-01-02 | 2026-01-31 |  | Bagus, Rizal | 88 | JC060126 30026
|  |  | Cek gambar, evaluasi teknis & koordinasi teknis KSSR |  | 2026-01-02 | 2026-01-31 |  | Yudi, Wiwid | 40 | JC060126 30027
|  |  | Menyelesaikan gambar yard plan & prod. drawing KSSR |  | 2026-01-02 | 2026-01-31 |  | Karina, Dinata, Indra | 40 | JC060126 30028
|  |  | Menyelesaikan gambar yard plan & prod. drawing KSSR |  | 2026-01-02 | 2026-01-31 |  | Farhan | 68 | JC060126 30029 |  | NO JC RAMADHAN HOURS
2026-02-01
|  | W304-305 | Cek gambar, evaluasi teknis & koordinasi teknis |  | 1 Febr 2026 | 28 Febr 2026 |  | Yudi, Wiwid | 36 | JC070126 30057 | jc utk 1-18 februari 2026 jo sisa 14 jam | JC180226 31796 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar-gambar pondasi |  | 1 Febr 2026 | 28 Febr 2026 |  | Irene, Karina | 40 | JC070126 30058 | jc utk 1-18 februari 2026 jo sisa 16 jam | JC180226 31798 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar-gambar yard plan & prod. drawing |  | 1 Febr 2026 | 28 Febr 2026 |  | Farhan, Sutan | 56 | JC070126 30059 | jc utk 1-18 februari 2026 jo sisa 21 jam | JC180226 31799 | jc utk 19 - 28 februari 2026
|  | W306-307 | Cek gambar, evaluasi teknis & koordinasi teknis LDP & LCU |  | 1 Febr 2026 | 28 Febr 2026 |  | Yudi, Wiwid | 36 | JC070126 30060 | jc utk 1-18 februari 2026 jo sisa 14 jam | JC180226 31800 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  | 1 Febr 2026 | 28 Febr 2026 |  | Farhan, Sutan | 56 | JC070126 30066 | jc utk 1-18 februari 2026 jo sisa 21 jam | JC180226 31801 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing LDP & LCU |  | 1 Febr 2026 | 28 Febr 2026 |  | Dinata, Iyan | 96 | JC070126 30067 | jc utk 1-18 februari 2026 jo sisa 36 jam | JC180226 31803 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing LDP & LCU |  | 1 Febr 2026 | 28 Febr 2026 |  | Indra | 120 | JC090126 30112 | jc utk 1-18 februari 2026 jo sisa 40 jam | JC180226 31804 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing LCU |  | 1 Febr 2026 | 28 Febr 2026 |  | Rizal | 72 | JC090126 30113 | jc utk 1-18 februari 2026 jo sisa 28 jam | JC190226 31811 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing LCU |  | 1 Febr 2026 | 28 Febr 2026 |  | Bagus | 80 | JC090126 30114 | jc utk 1-18 februari 2026 jo sisa 25 jam | JC190226 31812 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing LCU |  | 1 Febr 2026 | 28 Febr 2026 |  | Karina | 60 | JC090126 30115 | jc utk 1-18 februari 2026 jo sisa 20 jam | JC190226 31813 | jc utk 19 - 28 februari 2026
|  | W308 | Cek gambar, evaluasi teknis & koordinasi teknis |  | 1 Febr 2026 | 28 Febr 2026 |  | Yudi, Wiwid | 36 | JC090126 30122 | jc utk 1-18 februari 2026 jo sisa 14 jam | JC190226 31823 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar-gambar pondasi |  | 1 Febr 2026 | 28 Febr 2026 |  | Anam | 160 | JC090226 31361 | jc utk 1-18 februari 2026 jo sisa 56 jam | JC190226 31824 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar-gambar pondasi |  | 1 Febr 2026 | 28 Febr 2026 |  | Irene | 120 | JC090226 31362 | jc utk 1-18 februari 2026 jo sisa 40 jam | JC190226 31825 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  | 1 Febr 2026 | 28 Febr 2026 |  | Dinata, Iyan | 32 | JC090226 31364 | jc utk 1-18 februari 2026 jo sisa 16 jam | JC190226 31828 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  | 1 Febr 2026 | 28 Febr 2026 |  | Sutan | 48 | JC090226 31365 | jc utk 1-18 februari 2026 jo sisa 16 jam | JC190226 31829 | jc utk 19 - 28 februari 2026
|  | W311 | Cek gambar, evaluasi teknis & koordinasi teknis |  | 1 Febr 2026 | 28 Febr 2026 |  | Yudi, Wiwid | 36 | JC020226 31095 | jc utk 1-18 februari 2026 jo sisa 14 jam | JC190226 31830 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing KSSR |  | 1 Febr 2026 | 28 Febr 2026 |  | Karina | 60 | JC020226 31096 | jc utk 1-18 februari 2026 jo sisa 15 jam | JC190226 31831 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing KSSR |  | 1 Febr 2026 | 28 Febr 2026 |  | Dinata, Iyan | 32 | JC020226 31097 | jc utk 1-18 februari 2026 jo sisa 16 jam | JC190226 31833 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing KSSR |  | 1 Febr 2026 | 28 Febr 2026 |  | Farhan | 48 | JC020226 31098 | jc utk 1-18 februari 2026 jo sisa 16 jam | JC190226 31834 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing KSSR |  | 1 Febr 2026 | 28 Febr 2026 |  | Indra | 40 | JC020226 31099 | jc utk 1-18 februari 2026 jo sisa 16 jam | JC190226 31835 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing KSSR |  | 1 Febr 2026 | 28 Febr 2026 |  | Rizal | 72 | JC020226 31101 | jc utk 1-18 februari 2026 jo sisa 28 jam | JC190226 31836 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gamabr yard plan & prod. drawing KSSR |  | 1 Febr 2026 | 28 Febr 2026 |  | Bagus | 80 | JC020226 31102 | jc utk 1-18 februari 2026 jo sisa 25 jam | JC190226 31837 | jc utk 19 - 28 februari 2026
2026-03-01
| 2026-03-02 | W304-305 | Cek gambar, evaluasi teknis & koordinasi teknis |  | 2026-03-02 | 2026-03-17 |  | Yudi , Wiwid | 21 | JC020326 32284 | JC260326 33187
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Dinata, Sutan, Karin, Iyan, | 28 | JC020326 32286 | JC260326 33188
[8 empty] | Farhan, Rizal | 28 | JC020326 32287 | JC260326 33189
|  | W306-307 | Cek gambar, evaluasi teknis & koordinasi teknis LDP & LCU |  | 2026-03-02 | 2026-03-17 |  | Yudi, Wiwid | 28 | JC020326 32302 | JC260326 33190
|  |  | Menyelesaikan gambar yard plan & prod. drawing LDP & LCU |  |  |  |  | Dinata, Indra, Sutan , Karin | 28 | JC020326 32306 | JC260326 33191
[8 empty] | Iyan, Farhan, Rizal | 28 | JC020326 32308 | JC260326 33192
|  | W308 | Cek gambar, evaluasi teknis & koordinasi teknis |  | 2026-03-02 | 2026-03-17 |  | Yudi, Wiwid | 28 | JC020326 32312 | JC260326 33193
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Dinata, Indra, Sutan , Karin | 28 | JC020326 32318 | JC260326 33194
[8 empty] | Iyan, Farhan, Rizal | 28 | JC020326 32319 | JC260326 33195
[8 empty] | Irene, Anam | 84 | JC020326 32320 | JC260326 33196
[8 empty] | Bagus | 42 | JC020326 32321 | JC260326 33197
|  | W311 | Cek gambar, evaluasi teknis & koordinasi teknis |  | 2026-03-02 | 2026-03-17 |  | Yudi, Wiwid | 21 | JC020326 32324 | JC260326 33198
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Indra | 28 | JC020326 32329 | JC260326 33199
[8 empty] | Bagus | 42 | JC020326 32331 | JC260326 33200
2026-04-01
| 2026-04-01 | W304-305 | Menyelesaikan gambar yard plan & prod. drawing |  | 2026-04-01 | 2026-04-30 |  | Iyan, Dinata, Rizal, Farhan | 40 | JC010426 33505
[8 empty] | Karina, Sutan | 80 | JC010426 33506
|  |  | Cek gambar, evaluasi teknis & koordinasi teknis |  |  |  |  | Yudi, Wiwid | 40 | JC010426 33507
|  | W306-307 | Menyelesaikan gambar yard plan & prod. drawing |  | 2026-04-01 | 2026-04-30 |  | Karina, Dinata, Indra, Rizal, Iyan, Farhan | 80 | JC010426 33508
[8 empty] | Bagus | 40 | JC010426 33509
|  |  | Cek gambar, evaluasi teknis & koordinasi teknis |  |  |  |  | Yudi, Wiwid | 40 | JC010426 33512
|  | W308 | Menyelesaikan gambar yard plan & prod. drawing |  | 2026-04-01 | 2026-04-30 |  | Anam, Irene | 160 | JC010426 33513
[8 empty] | Iyan, Bagus, Sutan, Dinata, Rizal, Farhan | 40 | JC010426 33514
|  |  | Cek gambar, evaluasi teknis & koordinasi teknis |  |  |  |  | Yudi, Wiwid | 40 | JC010426 33515
|  | W311 | Menyelesaikan gambar yard plan &prod. drawing |  | 2026-04-01 | 2026-04-30 |  | Bagus | 80 | JC010426 33516
|  |  | Cek gambar, evaluasi teknis & koordinasi teknis |  |  |  |  | Yudi, Wiwid | 40 | JC010426 33517
| 2026-04-06 | W306-307 | Menyelesaikan gambar yard plan &prod. drawing |  | 2026-04-01 | 2026-04-30 |  | Sutan | 40 | JC060426 33662
|  | W308 | Menyelesaikan gambar yard plan &prod. drawing |  | 2026-04-01 | 2026-04-30 |  | Indra | 80 | JC060426 33661
|  | W306-307 | Menyelesaikan gambar yard plan &prod. drawing |  | 2026-04-01 | 2026-04-30 |  | Indra | 32 | JC290426 34554
2026-05-01
| 2026-05-01 | W304-305 | Menyelesaikan gambar yard plan & prod. drawing |  | 2026-05-01 | 2026-05-31 |  | Karina, Farhan, Sutan | 120 | JC300426 34617
|  | W306-307 | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Dinata, Indra | 80 | JC300426 34618
|  | W308 | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Iyan, Anam, Irene | 120 | JC300426 34619
[8 empty] | Karina, Sutan, Dinata | 40 | JC300426 34620
| 2026-05-11 | M312 | Cek gambar, evaluasi teknis & koordinasi teknis |  |  |  |  | Yudi, Wiwid | 30 | JC110526 34924
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Rizal, Bagus | 60 | JC110526 34925
[8 empty] | Indra | 50 | JC110526 34926
[8 empty] | Farhan, Dinata | 20 | JC110526 34927
|  | W304-305 | Cek gambar, evaluasi teknis & koordinasi teknis |  |  |  |  | Yudi, Wiwid | 30 | JC110526 34928
|  | W306-307 | Cek gambar, evaluasi teknis & koordinasi teknis |  |  |  |  | Yudi, Wiwid, Iyan | 30 | JC110526 34929
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Rizal, Bagus, Anam, Irene | 40 | JC110526 34930
|  | W308 | Cek gambar, evaluasi teknis & koordinasi teknis |  |  |  |  | Yudi, Wiwid | 40 | JC110526 34931
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Rizal, Bagus | 40 | JC110526 34932
2026-06-01
| 2026-06-01 | M312 | Cek gambar, evatek & koordinasi teknik |  | 2026-06-01 | 2026-06-30 |  | Yudi, Wiwid | 40 | JC020626 35745
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Iyan, Karina, Indra, Rizal, Bagus, Sutan | 60 | JC020626 35747
[8 empty] | Farhan, Irene, Dinata | 40 | JC020626 35746
|  | W304-305 | Cek gambar, evatek & koordinasi teknik |  |  |  |  | Yudi, Wiwid | 20 | JC020626 35748
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Karina | 60 | JC020626 35749
[8 empty] | Sutan | 30 | JC020626 35750
[8 empty] | Farhan, Dinata | 40 | JC020626 35751
|  | W306-307 | Cek gambar, evatek & koordinasi teknik |  |  |  |  | Yudi, Wiwid | 20 | JC020626 35754
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Farhan, Anam, Dinata | 40 | JC020626 35752
[8 empty] | Indra | 60 | JC020626 35753
|  | W308 | Cek gambat, evatek & koordinasi teknik |  |  |  |  | Yudi, Wiwid | 40 | JC020626 35755
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Iyan | 80 | JC020626 35757
[8 empty] | Bagus | 60 | JC020626 35758
[8 empty] | Sutan, Dinata, Rizal | 40 | JC020626 35760
[8 empty] | Anam, Irene | 160 | JC020626 35761
|  | Corp2026 | Cek gambar, evatek & koordinasi teknik |  |  |  |  | Yudi, Wiwid | 40 | JC020626 35762
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Iyan | 60 | JC020626 35764
[8 empty] | Karina, Sutan, Farhan, Rizal, Bagus, Indra | 80 | JC020626 35766
[8 empty] | Dinata | 40 | JC020626 35767
2026-07-01
| 2026-07-01 | M312 | Cek gambar, evatek & koordinasi teknik |  | 2026-07-01 | 2026-07-31 |  | Yudi | 40 | JC070726 37297
|  |  | Menyelesaikan gambar yard plan & prod. Drawing |  |  |  |  | Sutan | 60 | JC070726 37302
[8 empty] | Anam | 126 | JC070726 37303
[8 empty] | Karina | 60 | JC070726 37304
[8 empty] | Iren | 126 | JC070726 37305
|  | W304-305 | Cek gambar, evatek & koordinasi teknik |  |  |  |  | Yudi | 40 | JC070726 37306
|  |  | Menyelesaikan gambar yard plan & prod. Drawing |  |  |  |  | Karina | 60 | JC070726 37307
[8 empty] | Farhan | 60 | JC070726 37308
[8 empty] | Sutan | 120 | JC070726 37309
|  | W306-307 | Cek gambar, evatek & koordinasi teknik |  |  |  |  | Yudi | 40 | JC070726 37310
|  |  | Menyelesaikan gambar yard plan & prod. Drawing |  |  |  |  | Karina | 126 | JC070726 37311
[8 empty] | Sutan | 60 | JC070726 37312
|  | W308 | Cek gambar, evatek & koordinasi teknik |  |  |  |  | Yudi | 40 | JC070726 37313
|  |  | Menyelesaikan gambar yard plan & prod. Drawing |  |  |  |  | Farhan | 60 | JC070726 37314
[8 empty] | Anam, Iren | 120 | JC070726 37315
|  | Corp2026 | Cek gambar, evatek & koordinasi teknik |  |  |  |  | Yudi | 40 | JC070726 37320
|  |  | Menyelesaikan gambar yard plan & prod. Drawing |  |  |  |  | Farhan | 126 | JC070726 37321
2026-08-01
| 2026-08-12 | W308 | RA0 - EZ112S.33200 - FOUNDATION EQUIPMENT ON BLOCK 112 (S) |  | 2026-08-01 | 2026-08-05 |  | Anam | 32 | JC120826 38863
|  |  | R3 - EZ112S.33200 - FOUNDATION EQUIPMENT ON BLOCK 112 (P) |  | 2026-08-06 | 2026-08-10 |  |  | 32 | JC120826 38865
|  |  | R1 - E12590.33200 - ARR'T & DETAIL OF SUPPORT EXHAUST GAS PIPE M/E (3D MODEL CADMATIC) |  | 2026-08-18 | 2026-08-31 |  |  | 84 | JC120826 38867
|  | W306 | R1 - EZ6624.33100 - FOUND. OF EQUIP. IN RADIO ROOM - 05 DECK |  | 2026-08-11 | 2026-08-13 |  |  | 21 | JC120826 38869
|  |  | R0 - EZ6621.33100 - FOUND. OF EQUIP. IN BRIDGE - 05 DECK |  | 2026-08-14 | 2026-08-17 |  |  | 21 | JC120826 38870
|  | W308 | EZ3000.33106 - FOUND OF EQUIPMENT IN ELECTRIC ROOM NO.6 (12F22) |  | 2026-08-01 | 2026-08-05 |  | Irene | 32 | JC120826 38876
|  |  | EZ3000.33105- FOUND OF EQUIPMENT IN ELECTRIC ROOM NO.5 S (7F11) |  | 2026-08-06 | 2026-08-10 |  |  | 32 | JC120826 38878
|  | W304 | RA3 - E11672.33104 - COVER INSPECTION HOLES |  | 2026-08-11 | 2026-08-15 |  |  | 44 | JC120826 38879
|  |  | RA0 - E16231.33403 - STAIRWAY IN ACCOMODATION 1 DECK |  | 2026-08-17 | 2026-08-25 |  |  | 65 | JC120826 38882
|  |  | E11672.33104-RA4-COVER INSPECTION HOLES |  | 2026-08-26 | 2026-08-31 |  |  | 44 | JC120826 38886
|  | M312 | E85800.51100 - ANCHOR, CHAIN & MOORING ROPE - EVATEK PENAWARAN |  | 2026-08-03 | 2026-08-07 |  | Masyhudi | 35 | JC120826 38887
|  | W306 | E86235.51100 - ACCOMODATION LADDER - EVATEK APPROVAL DRAWING |  | 2026-08-18 | 2026-08-24 |  |  | 35 | JC120826 38889
|  | W308 | E85880.51100 - HELI SAFETY NET AND HELI LASHING PARTS - EVATEK APPROVAL DRAWING |  | 2026-08-26 | 2026-08-31 |  |  | 28 | JC120826 38890
|  |  | E81691.51100 - HELI HANGAR DOOR - EVATEK APPROVAL DRAWING |  | 2026-08-10 | 2026-08-14 |  |  | 35 | JC140826 38956
|  | Corp2026 A26AOP01 | R1 - EZ1800.33200 - FOUNDATION OF COMPENSATING TANK AND EMERGENCY BLOWING TANK NO.1 & 2 |  | 2026-08-01 | 2026-08-06 |  | Farhan | 35 | JC120826 38891
|  |  | R0 - EZ1800.33201 - FOUNDATION OF BILGE PUMP NO.1 |  | 2026-08-07 | 2026-08-11 |  |  | 32 | JC120826 38892
|  |  | R0 - EZ1800.33202 - FOUNDATION OF BILGE PUMP NO.2 |  | 2026-08-12 | 2026-08-15 |  |  | 32 | JC120826 38893
|  |  | R0 - EZ1800.33203 - FOUNDATION OF SW. PUMP NO.1 & 2 FOR COMPENSATING TANK |  | 2026-08-17 | 2026-08-20 |  |  | 32 | JC120826 38894
|  |  | R0 - EZ1800.33204 - FOUNDATION OF SW. COOLING PUMP 1 & 2 |  | 2026-08-21 | 2026-08-25 |  |  | 32 | JC120826 38896
|  |  | R0 - EZ1800.33205 - FONDATION OF MOTOR CONTROLLER |  | 2026-08-26 | 2026-08-31 |  |  | 35 | JC120826 38897
|  | W304 | R0 - EZ7132.33100-FOUND OF EQUIP IN CIWS (03MB0) |  | 2026-08-01 | 2026-08-05 |  | Karina | 34 | JC130826 38921
|  |  | R0 - EZ1802.33109-PLATFORM 0N EXPOSE "03" DECK |  | 2026-08-06 | 2026-08-15 |  |  | 73 | JC130826 38922
|  |  | R0 - EZ6512.33100-FOUND OF EQUIP IN SCULLERY (1GB2) |  | 2026-08-17 | 2026-08-20 |  |  | 36 | JC130826 38923
|  |  | EZ6551.33100-FOUND OF EQUIP IN GALLEY (1GB0) |  | 2026-08-21 | 2026-08-25 |  |  | 32 | JC130826 38926
|  |  | EZ6741.33100-FOUND OF EQUIP IN HANGAR (1LA0) |  | 2026-08-26 | 2026-08-31 |  |  | 42 | JC130826 38927
|  | W308 | E81672.50102 - BLAST DOOR - EVATEK APPROVAL DWG |  | 2026-08-01 | 2026-08-06 |  | Sutan | 34 | JC130826 38928
|  |  | E31672.50102 - BLAST DOOR |  | 2026-08-13 | 2026-08-14 |  |  | 12 | JC130826 38929
|  | W306 | E81672.50102 - BLAST DOOR - EVATEK APPROVAL DWG |  | 2026-08-07 | 2026-08-12 |  |  | 34 | JC130826 38930
|  |  | R2 - E15833.33101 - CRADLE OF LCU & MPAC |  | 2026-08-15 | 2026-08-22 |  |  | 50 | JC260826 39457
|  |  | R1 - E25833,33101 - ML FOR CRADLE OF LCU & MPAC |  | 2026-08-24 | 2026-08-25 |  |  | 12 | JC260826 39458
|  |  | RA2 - E16232.33100 - ARR'T OF ST. LADDER |  | 2026-08-26 | 2026-08-31 |  |  | 32 | JC260826 39459
2026-09-01
| 2026-09-02 | M312 | R0 - E16120.33100 - ARR'T & DETAIL OF RAILING |  | 2026-09-01 | 2026-09-07 |  | KARINA | 55 | JC090926 40204
|  | W314 | R0 - E11674.32100 - ARR'T & DETAIL OF MANHOLE |  | 2026-09-08 | 2026-09-17 |  |  | 90 | JC090926 40205
|  | M313 | R0 - E11674.32100 - ARR'T & DETAIL OF MANHOLE |  | 2026-09-18 | 2026-09-28 |  |  | 90 | JC090926 40206
|  |  | R0 - E11672.11100 - ARR'T OF STEEL & ALU DOOR |  | 2026-09-29 | 30/92026 |  |  | 14 | JC090926 40207
|  | M312 | R0 - E16032.33100 - TANK COMPARTMENT MARKING |  | 2026-09-01 | 2026-09-07 |  | IRENE | 50 | JC090926 40208
|  |  | R0 - E96000.92101 - WEIGHT CONTROL (KB-03) |  | 2026-09-08 | 2026-09-14 |  |  | 55 | JC090926 40211
|  | W314 | R0 - E16031.33100 - DRAUGHT MARK |  | 2026-09-15 | 2026-09-21 |  |  | 50 | JC090926 40213
|  | W308 | R0 - E16000.01100 - PRINCIPAL PARTICULAR HULL PART |  | 2026-09-22 | 2026-09-26 |  |  | 45 | JC090926 40215
|  |  | R0 - E15710.01100 - LIST OF R.A.S. EQUIPMENT |  | 2026-09-28 | 2026-09-30 |  |  | 27 | JC090926 40216
|  | M312 | R0 - E13315.33100 - FITTING FOR DRESSING LIGHT |  | 2026-09-08 | 2026-09-12 |  | SUTAN | 42 | JC090926 40217
|  |  | R0 - E16032.33104 - IN WATER SURVEY |  | 2026-09-23 | 2026-09-30 |  |  | 58 | JC090926 40218
|  | M313 | R0 - E16232.33101 - ARR'T & DETAIL OF LADDER (EXPOSED AREA) |  | 2026-09-14 | 2026-09-22 |  |  | 65 | JC090926 40219
|  | W308 | R0 - E16742.33100 - ARR'T OF DOCK WELL |  | 2026-09-01 | 2026-09-07 |  |  | 52 | JC090926 40221
|  | M312 | R0 - E16221.33200 - ARR'T OF FLOOR & GRATING AND LADDER IN E/R |  | 2026-09-01 | 2026-09-07 |  | ANAM | 45 | JC090926 40222
|  |  | R0 - E16221.33201 - ARR'T OF FLOOR & GRATING IN FW GENERATOR ROOM |  | 2026-09-08 | 2026-09-14 |  |  | 45 | JC090926 40223
|  |  | R0 - E16221.33202 - ARR'T OF FLOOR & GRATING IN BOW THRUSTER |  | 2026-09-15 | 2026-09-21 |  |  | 45 | JC090926 40224
|  |  | R0 - E16111.32200 - EYE PLATE OF OVERHAULING FOR AUX. EQUIP. IN E/R |  | 2026-09-22 | 2026-09-25 |  |  | 34 | JC090926 40225
|  |  | R0 - E16111.32201 - EYE PLATE OF OVERHAULING FOR AUX. EQUIP. IN FWG ROOM |  | 2026-09-26 | 2026-09-30 |  |  | 34 | JC090926 40226
|  | W314 | R0 - E16221.33200 - ARR'T FLOOR & LADDER IN E/R |  | 2026-09-01 | 2026-09-07 |  | FARHAN | 50 | JC090926 40227
|  | A26AOP01 | R0 - EZ5811.33200 - FOUND OF HYDRAULIC ANCHOR WINCH |  | 2026-09-08 | 2026-09-12 |  |  | 42 | JC090926 40228
|  |  | R0 - EZ5560.33201 - FOUND OF HPU FOR DECK MACHINERY SYSTEM |  | 2026-09-14 | 2026-09-18 |  |  | 42 | JC090926 40229
|  |  | R0 - EZ5560.33200 - FOUND OF HPU FOR DECK STEERING GEAR SYSTEM |  | 2026-09-19 | 2026-09-24 |  |  | 42 | JC090926 40230
|  |  | R0 - EZ1800.33201 - FOUND OF BILGE PUMP NO.1 |  | 2026-09-25 | 2026-09-30 |  |  | 42 | JC090926 40231
|  | W306 | ACCOMODATION LADDER - EVATEK APPROVAL DRAWING |  | 2026-09-01 | 2026-09-07 |  | MASYHUDI | 35 | JC090926 40232
|  |  | AMMUNITION LIFT - EVATEK APPROVAL DRAWING |  | 2026-09-08 | 2026-09-14 |  |  | 35 | JC090926 40233
|  | W308 | AMMUNITION LIFT - EVATEK APPROVAL DRAWING |  | 2026-09-15 | 2026-09-21 |  |  | 35 | JC090926 40235
|  |  | TILTING RAMP & STERN DOOR TWS - EVATEK PENAWARAN |  | 2026-09-22 | 2026-09-30 |  |  | 50 | JC090926 40236

## Dept. SPL (AO)
... Diisi Desain ... Agar diperhatikan spy timesheet masing2 personil bisa continue/tidak terputus krn terkait KPI Personil | [9 empty] | Diisi Planner
No | Tanggal Permintaan JC ditulis | Project | Task Name | Work Center | Schedule Start date | Schedule End date | Total Personil yang mengerjakan | PIC | JO | Kode Job Card | Keterangan | Planner
| DD / MM / YYYY | KODE PROYEK | REVISI KE - NO DOC / DWG - DESC PEKERJAAN | KODE BIRO - DESC BIRO | DD / MM / YYYY | DD / MM / YYYY | (DALAM ANGKA) | (NAMA) | (ANGKA) | JC010624 0001 |  | 023066812-Hashfi Moch Adam
CONTOH
1 | 2024-06-20 | W006 | R2 - E11672.11100 - ARR'T OF STEEL DOOR | 1CK200 - Biro Desain Perlengkapan Lambung | 2024-06-03 | 2024-06-07 | 2 |  |  | JC040624 0374 |  | 023066812-Hashfi Moch Adam
2 | 3 Maret 2025 | W304-305 | E15825.33100 - DRUM FOR MOORING ROPE - R2 |  | 2025-03-03 | 2025-03-08 | 1 | Irene | 40 | JC060325 16105
3 |  |  | E15724.33200 - ARRT OF LIFT BEAM IN E/R - R3 |  | 2025-03-03 | 2025-03-05 | 1 | Farhan | 24 | JC060325 16106
4 |  |  | EZ212P.33200 - FOUND. OF EQUIPMENT ON BLOCK 212 (P) - R3 |  | 2025-03-06 | 2025-03-10 | 1 | Farhan | 24 | JC060325 16107
5 |  |  | EZ232S.33200 - FOUND. EQUIPMENT ON BLOCK 232 (S) - R2 |  | 2025-03-11 | 2025-03-13 | 1 | Farhan | 24 | JC060325 16108
6 |  |  | EZ241P.33200 - FOUND EQUIPMENT BLOCK 241 (P) - R3 |  | 2025-03-14 | 2025-03-18 | 1 | Farhan | 24 | JC060325 16109
7 |  |  | EZ131C.33200 - FOUND. EQUIPMENT BLOCK 131 (C) - R3 |  | 2025-03-19 | 2025-03-27 | 1 | Farhan | 56 | JC060325 16110
8 |  |  | E16222.33200 - ARRT & DETAIL OF MPFF |  | 2025-03-03 | 2025-03-08 | 1 | Bagus | 40 | JC060325 16111
9 |  |  | CEK GAMBAR, EVALUASI TEKNIS DAN KOORDINASI TEKNIS |  | 2025-03-17 | 2025-03-21 | 2 | Yudi, Wiwid | 40 | JC060325 16112
10 |  | W306-307 | E11674.11100 - ARRT OF MANHOLE - R3 |  | 2025-03-03 | 2025-03-05 | 1 | Karina | 24 | JC060325 16113
11 |  |  | E11674.33100 - DETAIL OF MANHOLE & VL - RA1 |  | 2025-03-06 | 2025-03-08 | 1 | Karina | 24 | JC060325 16114
12 |  |  | 3D MODEL VEHICLE LIFT |  | 2025-03-03 | 2025-03-05 | 1 | Sutan | 24 | JC060325 16115
13 |  |  | 3D MODEL TURN TABLE |  | 2025-03-06 | 2025-03-08 | 1 | Sutan | 24 | JC060325 16116
14 |  |  | CEK GAMBAR, EVALUASI TEKNIS DAN KOORDINASI TEKNIS |  | 2025-03-03 | 2025-03-07 | 2 | Yudi, Wiwid | 40 | JC060325 16117
15 |  |  | EZ221P.33200 - FOUND. EQUIPMENT BLOCK 221 (P) - RA1 |  | 2025-03-03 | 2025-03-05 | 1 | Indra | 24 | JC060325 16118
16 |  |  | EZ221S.33200 - FOUND. EQUIPMENT BLOCK 221 (S) - RA0 |  | 2025-03-06 | 2025-03-08 | 1 | Indra | 24 | JC060325 16119
17 |  |  | EZ231P.33200 - FOUND. EQUIPMENT BLOCK 231 (P) - R3 |  | 2025-03-10 | 2025-03-12 | 1 | Indra | 24 | JC060325 16120
18 |  |  | EZ231S.33200 - FOUND. EQUIPMENT BLOCK 231 (S) - R5 |  | 2025-03-13 | 2025-03-15 | 1 | Indra | 24 | JC060325 16121
19 |  |  | EZ622P.33200 - FOUND. EQUIPMENT ON BLOCK 622 (P) - R0 |  | 2025-03-17 | 2025-03-19 | 1 | Indra | 24 | JC060325 16123
20 |  |  | E10660.11400 - ACCOMM. ARRT OF MAIN DECK - R1 |  | 2025-03-03 | 2025-03-05 | 1 | Rizal | 24 | JC060325 16124
21 |  |  | E10660.11401 - ACCOMM. ARRT OF 01 DECK - R1 |  | 2025-03-06 | 2025-03-10 | 1 | Rizal | 24 | JC060325 16125
22 |  |  | E10660.11402 - ACCOMM. ARRT OF 02 DECK - R1 |  | 2025-03-11 | 2025-03-13 | 1 | Rizal | 24 | JC060325 16126
23 |  |  | E10660.11403 - ACCOMM. ARRT OF 03 DECK - R1 |  | 2025-03-14 | 2025-03-18 | 1 | Rizal | 24 | JC060325 16127
24 |  |  | E10660.11404 - ACCOMM. ARRT OF 04 DECK - R1 |  | 2025-03-19 | 2025-03-21 | 1 | Rizal | 24 | JC060325 16128
25 |  |  | E10660.11405 - ACCOMM. ARRT OF 05 DECK - R1 |  | 2025-03-24 | 2025-03-27 | 1 | Rizal | 24 | JC060325 16129
26 |  |  | CEK GAMBAR, EVALUASI TEKNIS DAN KOORDINASI TEKNIS |  | 2025-03-24 | 2025-03-27 | 2 | Yudi, Wiwid | 32 | JC060325 16130
27 |  | W308 | E16231.33403 - STAIRWAY IN ACCOMMODATION 03 DECK - R1 |  | 2025-03-03 | 2025-03-08 | 1 | Anam | 40 | JC060325 16131
28 |  |  | E16231.33404 - STAIRWAY IN ACCOMMODATION 04 DECK - R2 |  | 2025-03-10 | 2025-03-15 | 1 | Anam | 40 | JC060325 16132
29 |  |  | E16520.33505 - ARRT & DETAIL OF LEAD PLATE |  | 2025-03-10 | 2025-03-15 | 1 | Iyan | 40 | JC060325 16133
30 |  |  | CEK GAMBAR, EVALUASI TEKNIS DAN KOORDINASI TEKNIS |  | 2025-03-10 | 2025-03-14 | 2 | Yudi, Wiwid | 40 | JC060325 16134
31 |  | KPI | REVIEW GA & BUILD. SPEC FOR BRS UAE |  | 03 Mar 0202 | 2025-03-07 | 2 | Dinata, Iyan | 40 | JC060325 16135
|  | W304-305 | E11674,33100 - DETAIL OF MANHOLE & VL |  | 2025-03-10 | 2025-03-15 | 1 | Karina | 40 | JC110325 16442
|  |  | EZ6631,33108 - SEAT OF EQUIP. IN ELECT. EQUIP. ROOM NO. 8 |  | 2025-03-10 | 2025-03-19 | 1 | Irene | 64 | JC110325 16443
|  |  | E26631.33108 - ML FOR SEAT OF EQ. IN ELECT. EQ. ROOM NO. 8 |  | 2025-03-20 | 2025-03-22 | 1 | Irene | 24 | JC110325 16447
|  | W308 | E16032,33102 - TURN TABLE & VEHICLE MARK |  | 2025-03-10 | 2025-03-14 | 1 | Sutan | 40 | JC110325 16448
|  |  | E16221,33208 - ARRT OF FLOOR IN SHAFT TUNNEL - R1 |  | 2025-03-10 | 2025-03-15 | 1 | Bagus | 40 | JC110325 16449
|  | W304-305 | E16135.33300 - ARRT & DETAIL OF PORTABLE AWNING |  | 2025-03-10 | 2025-03-14 | 1 | Dinata | 40 | JC110325 16450
| 2025-03-18 | W304-305 | E16631,33113 - SEAT OF EQUIPMENT IN ELECT. EQUIP. ROOM NO. 13 |  | 2025-03-17 | 2025-03-25 | 1 | Karina | 56 | JC190325 16785
|  |  | E26631,33113 - MAT. LIST FOR SEAT OF EQUIPMENT IN ELECT. EQUIP. ROOM NO. 13 |  | 2025-03-26 | 2025-03-28 | 1 | Karina | 24 | JC190325 16788
|  |  | KAJIAN TEKNIS LIFERAFT< RAILING HALUAN & ANODE |  | 2025-03-17 | 2025-03-22 | 1 | Dinata | 40 | JC190325 16793
|  | W308 | E16231,33402 - STAIRWAY IN ACCOMM. 02 DECK - R2 |  | 2025-03-17 | 2025-03-23 | 1 | Anam | 40 | JC190325 16794 |  | JC240325 17009
|  |  | E16231,33401 - STAIRWAY IN ACCOMM. 01 DECK - R2 |  | 2025-03-24 | 2025-03-28 | 1 | Anam | 40 | JC190325 16795 |  | JC240325 17010
| 2023-03-21 | W304-305 | E16631,33110 - SEAT OF EQUIPMENT IN ELECT. EQUIP. ROOM NO. 10 |  | 2025-03-24 | 2025-03-28 | 1 | Irene | 40 | JC210325 16870
|  |  | E6315,01300 - PAINTING SCHEDULE - RA0 |  | 2025-03-20 | 2025-03-21 | 1 | Indra | 16 | JC210325 16871
|  |  | E16631,33104 - SEAT OF EQUIPMENT IN ELECT. EQUIP. ROO NO. 4 |  | 2025-03-24 | 2025-03-28 | 1 | Dinata | 40 | JC210325 16872
|  | W306-307 | EVATEK MEDICAL EQUIPMENT |  | 2025-03-24 | 2025-03-28 | 1 | Iyan | 40 | JC210325 16873
|  | W308 | EVATEK MEDICAL EQUIPMENT |  | 2025-03-17 | 2025-03-22 | 1 | Iyan | 40 | JC210325 16874
|  | A24OP01 | PAINTING SCHEDULE |  | 2025-03-24 | 2025-03-26 | 1 | Sutan | 24 | JC210325 16875
|  |  | MAT. LIST FOR PAINT |  | 2025-03-27 | 2025-03-28 | 1 | Sutan | 16 | JC210325 16876
| 2025-03-24 | W304-305 | E16724.33400 - DETAIL OF COVER PLATE IN DRY PROVISION STORE |  | 2025-03-17 | 2025-03-21 | 1 | Bagus | 40 | JC240325 16973
|  |  | 3D MODEL CIC ROOM & MACHINERY CONTROL ROOM |  | 2025-03-24 | 2025-03-28 | 1 | Bagus | 40 | JC240325 16974
|  | W306-307 | E22000.01200 - MAT. LIST FOR BOLT & NUT IN E/R |  | 2025-03-24 | 2025-03-26 | 1 | Indra | 24 | JC240325 16987
|  |  | EF433P.36100 - 433 (P) BLOCK PAINTING |  | 2025-03-27 | 2025-03-27 | 1 | Indra | 8 | JC240325 16988
|  |  | EF433S.36100 - 433 (S) BLOCK PAINTING |  | 2025-03-28 | 2025-03-28 | 1 | Indra | 8 | JC240325 16989
2025-04-01
| 2025-04-07 | W304-305 | E12590.32200 - ARRT & DETAIL OF SUPPORT EXHAUST GAS PIPE |  | 2025-04-07 | 2025-04-14 | 1 | Iyan | 48 | JC080425 17384
|  |  | EZ213P.33200 - FOUND. EQUIP. BLOCK 213P |  | 2025-04-07 | 2025-04-17 | 1 | Farhan | 80 | JC080425 17386
|  |  | E16631.33104 - SEAT OF EQUIPMENT IN ELECT. EQ. ROOM NO. 4 |  | 2025-04-07 | 2025-04-11 | 1 | Dinata | 40 | JC080425 17392
|  |  | E26631.33104 - ML FOR SEAT EQ. IN ELECT. EQ ROOM NO. 4 |  | 2025-04-14 | 2025-04-16 | 1 | Dinata | 24 | JC080425 17408
|  |  | E16110.33200 - DECK TRAY IN E/R |  | 2025-04-07 | 2025-04-12 | 1 | Indra | 40 | JC080425 17409
|  |  | E26110.33200 - ML FOR DECK TRAY IN E/R |  | 2025-04-14 | 2025-04-16 | 1 | Indra | 24 | JC080425 17414
|  |  | E16631.33103 - SEAT OF EQUIPMENT IN ELECT. EQ. ROOM NO. 3 |  | 2025-04-07 | 2025-04-19 | 1 | Irene | 80 | JC080425 17417
|  |  | E26631.33103 - ML FOR SEAT EQUIP. IN ELECT. EQ ROOM NO. 3 |  | 2025-04-21 | 2025-04-23 | 1 | Irene | 24 | JC080425 17419
|  |  | E16222,33400 - ARRT & DETAIL OF MPFF |  | 2025-04-07 | 2025-04-16 | 1 | Bagus | 64 | JC080425 17420
|  |  | E26222,33401 - ML FOR MPFF |  | 2025-04-17 | 2025-04-19 | 1 | Bagus | 24 | JC080425 17421
|  |  | E16222.33401 - ARRT & DETAIL OF RAISED FLOOR |  | 2025-04-21 | 2025-04-26 | 1 | Bagus | 40 | JC080425 17422
|  |  | E26222.33401 - ML FOR RAISED FLOOR |  | 2025-04-28 | 2025-04-30 | 1 | Bagus | 24 | JC080425 17423
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-04-14 | 2025-04-18 | 2 | Yudi, Wiwid | 32 | JC080425 17424
|  |  | E16020.33403 - LAMBANG GARUDA |  | 2025-04-07 | 2025-04-09 | 1 | Rizal | 24 | JC080425 17428
|  |  | E26020.33403 - ML FOR LAMBANG GARUDA |  | 2025-04-10 | 2025-04-11 | 1 | Rizal | 16 | JC080425 17429
|  |  | EZ233S.33200 - FOUND. EQUIP. BLOCK 233S |  | 2025-04-18 | 2025-04-30 | 1 | Farhan | 72 | JC080425 17431
|  |  | EZ5140.33200 - SEAT OF EQUIP. IN AHU ROOM NO. 4 (01LB1) |  | 2025-04-17 | 2025-04-30 | 1 | Indra | 80 | JC080425 17444 |  | PENDING, MENUNGGU DATA DARI MO
|  | W306-307 | E16011.33400 - ARRT OF MISCELLANEOUS JOINER FITTING & DETAIL |  | 2025-04-14 | 2025-04-18 | 1 | Rizal | 32 | JC080425 17449
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-04-21 | 2025-04-25 | 2 | Yudi, Wiwid | 40 | JC080425 17450
|  |  | E26000.37100 - ML FOR OTHER SUPPLIES (HULL PART) |  | 2025-04-23 | 2025-04-25 | 1 | Dinata | 24 | JC080425 17451
|  | W308 | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-04-07 | 2025-04-11 | 2 | Yudi, Wiwid | 40 | JC080425 17452
|  |  | E25724.33200 - ML FOR LIFT BEAM D/G IN AUXILIARY ROOM |  | 2025-04-07 | 2025-04-09 | 1 | Anam | 24 | JC080425 17453
|  |  | E25724.33202 - ML FOR LIFT BEAM MAIN ENGINE |  | 2025-04-10 | 2025-04-12 | 1 | Anam | 24 | JC080425 17454
|  |  | E11672.33104 - COVER INSPECTION HOLES - R1 |  | 2025-04-07 | 2025-04-12 | 1 | Karina | 40 | JC080425 17455
|  |  | E21672.33104 - ML FOR COVER INSPECTION HOLES - R1 |  | 2025-04-14 | 2025-04-16 | 1 | Karina | 24 | JC080425 17456
|  |  | E15724.33205 - LIFT BEAM FOR ELECTRIC PROPULSION |  | 2025-04-14 | 2025-04-19 | 1 | Anam | 40 | JC080425 17457
|  |  | E20770.02300 - ML FOR SAFETY EQUIPMENT |  | 2025-04-17 | 2025-04-22 | 1 | Dinata | 24 | JC080425 17458
|  |  | E16010.10100 - GENERAL OUTFITTING ARRT - R1 |  | 2025-04-24 | 2025-04-26 | 1 | Irene | 24 | JC080425 17459 |  | PENDING, MENUNGGU DATA DARI MO
|  |  | E16640.10100 - DAMAGE CONTROL PLAN - R1 |  | 2025-04-28 | 2025-04-30 | 1 | Irene | 24 | JC080425 17460
|  | A24OP01 | SHOP PRIMER & SAND BLASTING PAINTING CALCULATION |  | 2025-04-07 | 2025-04-09 | 1 | Sutan | 24 | JC080425 17463
|  |  | ML FOR SHOP PRIMER & SAND BLASTING PAINTING |  | 2025-04-10 | 2025-04-11 | 1 | Sutan | 16 | JC080425 17465
| 2025-04-17 | W304-305 | EZ4261.33100 - SEAT OF EQUIP. IN FWD GYRO ROOM |  | 2025-04-17 | 2025-04-18 | 1 | Karina | 16 | JC210425 18092
|  |  | E24261.33100 - MAT. LIST FOR SEAT OF EQUIP. IN FWD GYRO ROOM |  | 2025-04-19 | 2025-04-19 | 1 | Karina | 8 | JC210425 18093
|  |  | EZ4261.33101 - SEAT OF EQUIP. IN AFT GYRO ROOM |  | 2025-04-21 | 2025-04-22 | 1 | Karina | 16 | JC210425 18096
|  |  | E24261.33101 - MAT. LIST FOR SEAT OF EQUIP. IN AFT GYRO ROOM |  | 2025-04-23 | 2025-04-23 | 1 | Karina | 8 | JC210425 18103
|  |  | EZ5140.33205 - SEAT OF EQUIP. IN AHU ROOM NO. 5 (1CA1) |  | 2025-04-24 | 2025-04-26 | 1 | Karina | 24 | JC210425 18104
|  |  | E11672,33105 - STEEL LATICE DOOR - R2 |  | 2025-04-14 | 2025-04-17 | 1 | Sutan | 32 | JC210425 18105
|  |  | E17130,33101 - FITTING IN GUN BAY (1CA0) |  | 2025-04-28 | 2025-05-03 | 1 | Karina | 40 | JC210425 18137
|  | W306-307 | E16442,33401 - DETAIL OF UNIT TOILET (RAW MATERIAL) |  | 2025-04-21 | 2025-04-25 | 1 | Rizal | 40 | JC210425 18106
|  |  | E26442,33401 - MAT. LIST FOR DETAIL OF UNIT TOILET (RAW MATERIAL) |  | 2025-04-28 | 2025-04-30 | 1 | Rizal | 24 | JC210425 18108
|  | W308 | E25724.33205 - MAT. LIST FOR LIFT BEAM FOR TRANSFER ELECTRIC PROPULSION |  | 2025-04-21 | 2025-04-23 | 1 | Anam | 24 | JC210425 18110
|  |  | E15724.33206 - LIFT BEAM FOR E/R - R1 |  | 2025-04-24 | 2025-04-30 | 1 | Anam | 40 | JC210425 18111
|  |  | E16032.33104 - IN WATER SURVEY |  | 2025-04-21 | 2025-04-25 | 1 | Sutan | 40 | JC210425 18113
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-04-28 | 2025-05-02 | 2 | Yudi, Wiwid | 40 | JC210425 18214
| 2025-04-22 | W304-305 | EZ432P.33200 - FOUND. EQUIP. IN BLOCK 432 P - R4 |  | 2025-04-21 | 2025-04-23 | 1 | Iyan | 24 | JC230425 18280
|  |  | EZ432S.33200 - FOUND. EQUIP. IN BLOCK 432 S - R1 |  | 2025-04-24 | 2025-04-26 | 1 | Iyan | 24 | JC230425 18281
|  |  | E11503.33200 - ARRT & DETAIL OF EQUIP IN FUNNEL |  | 2025-04-28 | 2025-05-08 | 1 | Iyan | 64 | JC230425 18282
| 2025-04-25 | W304-305 | E11710.33100 - ARRT & DETAIL OF EQUIPMENT ON FORE MAST |  | 2025-04-24 | 2025-05-10 | 1 | Irene | 96 | JC250425 18369
|  |  | EZ4611.33100 - SEAT OF EQUIPMENT IN SONAR ROOM |  | 2025-04-22 | 2025-05-03 | 1 | Indra | 80 | JC250425 18370
|  | W308 | SHOP PRIMER & SAND BLASTING PAINTING CALCULATION |  | 2025-04-07 | 2025-04-09 | 1 | Sutan | 24 | JC250425 18371
|  |  | ML FOR SHOP PRIMER & SAND BLASTING PAINTING |  | 2025-04-10 | 2025-04-11 | 1 | Sutan | 16 | JC250425 18372
| 2025-04-28 | W304-305 | E16631.33104 - SEAT OF EQUIPMENT IN ELECT. EQ. ROOM NO. 4 |  | 2025-04-28 | 2025-04-30 | 1 | Dinata | 24 | JC280425 18562
|  | W306-307 | E16000.75100 - MAIN EQUIP LIST FOR HULL PART - RA4 |  | 2025-04-28 | 2025-04-28 | 1 | Sutan | 8 | JC280425 18563
|  | W308 | E16000.75100 - MAIN EQUIP LIST FOR HULL PART - RA1 |  | 2025-04-29 | 2025-04-30 | 1 | Sutan | 16 | JC280425 18564
2025-05-01
| 2025-04-30 | W304-305 | EZ6233,33101 - SEAT OF WHARFT LADDER - R2 |  | 2025-05-01 | 2025-05-03 | 1 | Anam | 16 | JC300425 18630
|  |  | E16020.33402 - TANDA KESATUAN |  | 2025-05-02 | 2025-05-06 | 1 | Rizal | 24 | JC300425 18631
|  |  | E26020.33402 - MAT. LIST FOR TANDA KESATUAN |  | 2025-05-07 | 2025-05-09 | 1 | Rizal | 24 | JC300425 18632
|  |  | E22000.01200 - MAT. LIST FOR BOLT & NUT IN E/R - R1 |  | 2025-05-09 | 2025-05-10 | 1 | Iyan | 16 | JC300425 18633
|  |  | EZ423P.33200 - FOUND. OF EQUIP IN BLOCK 423 P |  | 2025-05-01 | 2025-05-03 | 1 | Farhan | 24 | JC300425 18670
|  |  | EZ223P.33200 - FOUND. OF EQUIP. IN BLOCK 223 P |  | 2025-05-05 | 2025-05-10 | 1 | Farhan | 40 | JC300425 18705
|  |  | EZ223S.33200 - FOUND. OF EQUIP IN BLOCK 223 S |  | 2025-05-12 | 2025-05-17 | 1 | Farhan | 40 | JC020525 18721
|  |  | EZ243P.33200 - FOUND. OF EQUIP IN BLOCK 243 P |  | 2025-05-19 | 2025-05-24 | 1 | Farhan | 40 | JC020525 18722
|  |  | EZ243S.33200 - FOUND. OF EQUIP IN BLOCK 243 S |  | 2025-05-26 | 2025-05-31 | 1 | Farhan | 40 | JC020525 18723
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-05-05 | 2025-05-09 | 2 | Yudi, Wiwid | 40 | JC020525 18724
|  | W308 | E16311,33301 - FUNNEL PAINT MARKING |  | 2025-05-01 | 2025-05-06 | 1 | Sutan | 32 | JC300425 18634
|  |  | E26311,33301 - MAT. LIST FOR FUNNEL PAINT MARKING |  | 2025-05-07 | 2025-05-09 | 1 | Sutan | 24 | JC300425 18635
|  |  | E16370.11400 - ARRT OF JOINER WORK |  | 2025-05-02 | 2025-05-03 | 1 | Bagus | 16 | JC020525 18725
|  |  | E15724,33204 - LIFT BEAM FOR SHAFTING NO 1 & 2 - R1 |  | 2025-05-05 | 2025-05-07 | 1 | Anam | 24 | JC020525 18733
|  |  | E16221,33205 - ARRT OF FLOOR IN SHAFT ROOM - R1 |  | 2025-05-08 | 2025-05-10 | 1 | Anam | 24 | JC020525 18734
|  |  | E16231,33406 - ARRT & DETAIL OF STORMRAIL IN STAIRWAY - R2 |  | 2025-05-12 | 2025-05-17 | 1 | Anam | 40 | JC020525 18735
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-05-13 | 2025-05-16 | 2 | Yudi, Wiwid | 32 | JC020525 18736
|  | W304-305 | E17130,33101 - FITTING IN GUN BAY (1CA0) - R1 |  | 2025-05-05 | 2025-05-10 | 1 | Karina | 40 | JC050525 18929
|  |  | E17130,33101 - MAT. LIST FOR FITTING IN GUN BAY (1CA0) - R1 |  | 2025-05-12 | 2025-05-14 | 1 | Karina | 24 | JC050525 18931
|  |  | E1730,33102 - EQUIPMENT IN GUN BAY 1DA0 |  | 2025-05-15 | 2025-05-21 | 1 | Karina | 40 | JC050525 18932
|  |  | E27130,33102 - MAT. LIST FOR EQUIPMENT IN GUN BAY 1DA0 |  | 2025-05-22 | 2025-05-24 | 1 | Karina | 24 | JC050525 18933
|  |  | EZ4611.33100 - SEAT OF EQUIPMENT IN SONAR ROOM |  | 2025-05-05 | 2025-05-13 | 1 | Indra | 48 | JC050525 18934
|  |  | E24611.33100 - MAT. LIST FOR SEAT OF EQUIPMENT IN SONAR ROOM |  | 2025-05-14 | 2025-05-16 | 1 | Indra | 24 | JC050525 18935
|  |  | E16311,33301 - FUNNEL PAINT MARKING |  | 2025-05-19 | 2025-05-21 | 1 | Indra | 24 | JC050525 18936
|  |  | E26311,33301 - MAT. LIST FOR FUNNEL PAINT MARKING |  | 2025-05-22 | 2025-05-24 | 1 | Indra | 16 | JC050525 18942
|  |  | E16500,33400 - SECT. ROOM OF GALLEY, PANTRY & LAUNDRY |  | 2025-05-05 | 2025-05-10 | 1 | Bagus | 40 | JC050525 18943
|  |  | E16023,32300 - ARRT OF IMO SIGN |  | 2025-05-05 | 2025-05-09 | 1 | Dinata | 40 | JC050525 18944
|  |  | E16023,32301 - ARRT OF NBCD SIGN |  | 2025-05-19 | 2025-05-23 | 1 | Dinata | 40 | JC050525 18945
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-05-19 | 2025-05-23 | 2 | Yudi, Wiwid | 40 | JC050525 18946
|  | W306-307 | E16023,32300 - ARRT OF IMO SIGN |  | 2025-05-13 | 2025-05-16 | 1 | Dinata | 32 | JC050525 18947
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-05-26 | 2025-05-30 | 2 | Yudi, Wiwid | 32 | JC050525 18948
|  | W308 | E16311,33301 - FUNNEL PAINT MARKING |  | 2025-05-05 | 2025-05-07 | 1 | Sutan | 24 | JC050525 18949
|  |  | E26311,33301 - MAT. LIST FOR FUNNEL PAINT MARKING |  | 2025-05-08 | 2025-05-09 | 1 | Sutan | 16 | JC050525 18952
|  |  | EF643P.04300 - 643 P BLOCK PAINTING |  | 2025-05-12 | 2025-05-12 | 1 | Sutan | 8 | JC050525 18954
|  |  | EF643S.04300 - 643 S BLOCK PAINTING |  | 2025-05-13 | 2025-05-13 | 1 | Sutan | 8 | JC050525 18955
|  |  | EF614P.04300 - 614 P BLOCK PAINTING |  | 2025-05-14 | 2025-05-14 | 1 | Sutan | 8 | JC050525 18956
|  |  | EF614S.04300 - 614 S BLOCK PAINTING |  | 2025-05-15 | 2025-05-15 | 1 | Sutan | 8 | JC050525 18957
|  |  | E26023,33103 - MAT. LIST FOR TURN TABLE MARK & VEHICLE LIFT MARK |  | 2025-05-16 | 2025-05-16 | 1 | Sutan | 8 | JC050525 18958
|  |  | E16724,33400 - DETAIL OF COVER PLATE IN DRY PROV. STORE |  | 2025-05-12 | 2025-05-16 | 1 | Bagus | 32 | JC050525 18959
|  |  | E25724,33206 - MAT. LIST FOR LIFT BEAM IN E/R |  | 2025-05-19 | 2025-05-21 | 1 | Anam | 24 | JC050525 18965
|  |  | E26724,33400 - MAT. LIST FOR DETAIL OF COVER PLATE IN DRY PROV. STORE |  | 2025-05-19 | 2025-05-21 | 1 | Bagus | 24 | JC050525 18974
|  | W304-305 | E11710.33102 - ARRT & DET. OF EQUIPMENT ON AFT MAST |  | 2025-05-13 | 2025-05-24 | 1 | Irene | 72 | JC130525 19308
|  |  | E21710.33102 - MAT. LIST FOR DET. OF EQUIPMENT ON AFT MAST |  | 2025-05-26 | 2025-05-28 | 1 | Irene | 24 | JC130525 19311
|  |  | E25014.33200 - MAT. LIST FOR SCALE PLATE FOR TANK |  | 2025-05-13 | 2025-05-14 | 1 | Iyan | 16 | JC130525 19313
|  |  | E22590.33200 - MAT. LIST FOR SUPPORT EXHAUST GAS PIPE |  | 2025-05-15 | 2025-05-16 | 1 | Iyan | 16 | JC130525 19315
|  |  | E86332.51300 - ICCP SYSTEM |  | 2025-05-13 | 2025-05-14 | 1 | Rizal | 16 | JC130525 19316
|  |  | E86333.51300 - MGPS SYSTEM |  | 2025-05-15 | 2025-05-16 | 1 | Rizal | 16 | JC130525 19319
|  | KPI | E10770.02300 - SAFETY & FIRE CONTROL PLAN |  | 2025-05-26 | 2025-05-30 | 1 | Dinata | 32 | JC130525 19322
|  |  | E11674.11100 - ARRT & DETAIL OF MANHOLE & VERT. LADDER |  | 2025-05-19 | 2025-05-24 | 1 | Sutan | 40 | JC130525 19323
|  |  | E15824.11100 - ARRT OF MOORING |  | 2025-05-26 | 2025-05-31 | 1 | Sutan | 32 | JC130525 19324
|  | W304-305 | EZ6221,33200 - SEAT OF EQUIPMENT IN CASING TRUNK (2LA1) |  | 2025-05-19 | 2025-05-24 | 1 | Iyan | 40 | JC150525 19378
|  |  | EZ6221,33201 - SEAT OF EQUIPMENT IN CASING TRUNK (2MA5) |  | 2025-05-26 | 2025-05-31 | 1 | Iyan | 40 | JC150525 19379
|  |  | E16251,11400 - WINDOW PLAN - R2 |  | 2025-05-22 | 2025-05-24 | 1 | Bagus | 16 | JC150525 19381
|  |  | E16122,33400 - ARRT OF HANDRAIL IN ACCOMMODATION - R1 |  | 2025-05-19 | 2025-05-20 | 1 | Rizal | 16 | JC150525 19383
|  |  | E26122,33400 - MAT. LIST FOR HANDRAIL IN ACCOMMODATION - R1 |  | 2025-05-21 | 2025-05-22 | 1 | Rizal | 16 | JC150525 19389
|  |  | E26254,32400 - MAT. LIST FOR WINDOW WIPER, CVS & SUNSCREEN - R3 |  | 2025-05-23 | 2025-05-23 | 1 | Rizal | 8 | JC150525 19391
|  |  | EZ6631,33120 - SEAT OF EQUIP. IN ELECT. EQUIP. ROOM NO. 20 |  | 2025-05-26 | 2025-06-03 | 1 | Karina | 56 | JC150525 19392
|  |  | EZ6623,33101 - SEAT OF EQUIP. IN RADIO ROOM |  | 2025-05-29 | 2025-06-07 | 1 | Irene | 56 | JC150525 19394
|  |  | E16621,33400 - ARRT OF PILOT CHAIR - R2 |  | 2025-05-26 | 2025-05-28 | 1 | Rizal | 24 | JC150525 19396
|  |  | E26621,33400 - MAT. LIST FOR PILOT CHAIR - R1 |  | 2025-05-30 | 2025-05-30 | 1 | Rizal | 8 | JC150525 19397
| 2025-05-19 | W308 | E16233,33203 - ARRT & DETAIL OF LADDER IN E/R - R2 |  | 2025-05-22 | 2025-05-24 | 1 | Anam | 24 | JC190525 19574
|  |  | E16233,33201 - ARRT & DETAIL OF LADDER IN CHILLER & REFRIGERANT PLANT ROOM - R1 |  | 2025-05-26 | 2025-05-28 | 1 | Anam | 24 | JC190525 19575
|  |  | E16233,33201 - ARRT & DETAIL OF LADDER IN FRESH WATER GEN. ROOM - R1 |  | 2025-05-29 | 2025-05-31 | 1 | Anam | 24 | JC190525 19576
|  | KPI | PLATFORM SHIFT LIFT |  | 2025-05-02 | 2025-05-31 | 1 | Diva | 152 | JC190525 19577
| 2025-05-27 | W304-305 | EZ4611,33101 - SEAT OF EQUIPMENT IN SONAR WATER FILTER (2AA0) |  | 2025-05-26 | 2025-05-31 | 1 | Indra | 40 | JC270525 19940
|  |  | EZ1801,33108 - SEAT OF EQUIPMENT IN PASSAGE WAY (2LA3) |  | 2025-05-26 | 2025-05-28 | 1 | Bagus | 24 | JC270525 19941
|  |  | EZ1801,33109 - SEAT OF EQUIPMENT IN PASSAGE WAY (2LA4) |  | 2025-05-29 | 2025-05-31 | 1 | Bagus | 24 | JC270525 19942
| 2025-06-03 | W304-305 | EZ1801,33103 - SEAT OF EQUIPMENT IN PASSAGE WAY (2MBO) |  | 2025-06-04 | 2025-06-07 | 1 | Karina | 24 | JC030625 20340
|  |  | E96000,92101 - WEIGHT KONTROL (KB - 03) |  | 2025-06-02 | 2025-06-07 | 1 | Sutan | 32 | JC030625 20341
|  |  | EZ1801,33113 - SEAT OF EQUIP. IN DIESEL DRIVEN FIRE PUMP NO.1 (2BA1) |  | 2025-06-02 | 2025-06-04 | 1 | Farhan | 24 | JC030625 20342
|  |  | EZ1801,33114 - SEAT OF EQUIP. IN DIESEL DRIVEN FIRE PUMP NO.2 (2PA5) |  | 2025-06-05 | 2025-06-10 | 1 | Farhan | 24 | JC030625 20343
|  |  | E16023,32301 - ARRT OF NBCD SIGN |  | 2025-06-02 | 2025-06-05 | 1 | Dinata | 32 | JC030625 20344
|  |  | E26621,33400 - MAT. LIST FOR PILOT CHAIR - R1 |  | 2025-06-02 | 2025-06-02 | 1 | Rizal | 8 | JC030625 20345
|  |  | E16621,33400 - ARRT OF PILOT CHAIR - R2 |  | 2025-06-03 | 2025-06-05 | 1 | Rizal | 24 | JC030625 20347
|  |  | EZ1801,33115 - SEAT OF EQUIPMENT IN PASSAGE WAY (2HZ2) |  | 2025-06-02 | 2025-06-07 | 1 | Indra | 32 | JC030625 20348
|  |  | EZ1801,33118 - SEAT OF EQUIPMENT IN BAGGAGE STORE NO. 1 (2FA4) |  | 2025-06-02 | 2025-06-07 | 1 | Bagus | 32 | JC030625 20349
|  | W308 | E16231,33406 - ARRT & DETAIL OF STORMRAIL IN STAIRWAY - R2 |  | 2025-06-02 | 2025-06-07 | 1 | Anam | 32 | JC030625 20313
|  |  | EVATEK MEDICAL EQUIPMENT |  | 2025-06-02 | 2025-06-07 | 1 | Iyan | 32 | JC030625 20314
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-06-02 | 2025-06-05 | 2 | Yudi, Wiwid | 32 | JC030625 20346
| 2025-06-08 | W304-305 | EZ6631,33117 - SEAT OF EQUIP. IN ELECT. EQUIP. ROOM NO. 17 |  | 2025-06-09 | 2025-06-12 | 1 | Karina | 32 | JC090625 20493
|  |  | EZ6631.33119 - SEAT OF EQUIP. IN ELECT. EQUIP ROOM NO. 19 |  | 2025-06-13 | 2025-06-14 | 1 | Karina | 16 | JC090625 20494
|  |  | E11710.33101 - ARRT & DET. OF EQUIPMENT ON MIDDLE MAST |  | 2025-06-09 | 2025-06-14 | 1 | Irene | 40 | JC090625 20495
|  |  | 3D MODEL BLAST DOOR |  | 2025-06-09 | 2025-06-14 | 1 | Sutan | 40 | JC090625 20496
|  |  | EZ6221.33202 - FOUND. OF EQUIPMENT IN CASING TRUNK (2JZ2) |  | 2025-06-09 | 2025-06-14 | 1 | Iyan | 40 | JC090625 20497
|  |  | EZ1801.33114 - SEAT OF EQUIP IN DIESEL DRIVEN FIRE PUMP NO, 2 (2PA5) |  | 2025-06-09 | 2025-06-10 | 1 | Farhan | 16 | JC090625 20498
|  |  | EZ312C.33200 - FOUND. OF EQUIP. IN BLOCK 312 (C) - R1 |  | 2025-06-11 | 2025-06-17 | 1 | Farhan | 40 | JC090625 20499
|  |  | EZ241S.33200 - FOUND. OF EQUIP. IN BLOCK 241 (S) - R5 |  | 2025-06-18 | 2025-06-19 | 1 | Farhan | 16 | JC090625 20500
|  |  | EZ131C.33200 - FOUND. OF EQUIP. IN BLOCK 131 (C) - R4 |  | 2025-06-20 | 2025-06-21 | 1 | Farhan | 16 | JC090625 20521
|  |  | EZ222P.33200 - FOUND. OF EQUIP. IN BLOCK 222 (P) - R1 |  | 2025-06-23 | 2025-06-28 | 1 | Farhan | 40 | JC090625 20528
|  |  | EZ152P.33200 - FOUND. OF EQUIP. IN BLOCK 152 (P) - R0 |  | 2025-06-30 | 2025-07-02 | 1 | Farhan | 24 | JC090625 20530
|  |  | EZ432P.33200 - FOUND. OF EQUIP. IN BLOCK 432 (P) - RA0 |  | 2025-07-03 | 2025-07-05 | 1 | Farhan | 24 | JC090625 20546
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-06-09 | 2025-06-13 | 3 | Yudi, Wiwid, Dinata | 40 | JC090625 20547
|  |  | EZ1801,33115 - SEAT OF EQUIPMENT IN PASSAGE WAY (2HZ2) |  | 2025-06-09 | 2025-06-11 | 1 | Bagus | 24 | JC090625 20550
|  |  | EZ1801,33116 - SEAT OF EQUIPMENT IN PASSAGE WAY (2JZ4) |  | 2025-06-12 | 2025-06-14 | 1 | Bagus | 24 | JC090625 20551
|  |  | EZ1233,33100 - SEAT OF EQUIPMENT IN ESC. TRUNK (2/4LA4) |  | 2025-06-09 | 2025-06-11 | 1 | Indra | 24 | JC090625 20552
|  |  | E12590.33200 - ARRT & DET. OF SUPPORT EXH. GAS PIPE |  | 2025-06-16 | 2025-06-21 | 1 | Iyan | 40 | JC090625 20581
|  | W308 | E26231.33400 - MAT. LIST FOR STAITWAY IN ACCOMM. - R2 |  | 2025-06-09 | 2025-06-10 | 1 | Anam | 16 | JC090625 20589
|  |  | E15724,33206 - LIFT BEAM FOR ENG. ROOM - R2 |  | 2025-06-11 | 2025-06-14 | 1 | Anam | 24 | JC090625 20590
|  |  | E11672.11100 - ARRT OFF STEEL DOOR - R3 |  | 2025-06-16 | 2025-06-17 | 1 | Karina | 16 | JC090625 20591
|  |  | E21672.33100 - MAT. LIST FOR STEEL DOOR - R1 |  | 2025-06-18 | 2025-06-21 | 1 | Karina | 24 | JC090625 20592
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-06-16 | 20 June 1015 | 3 | Yudi, Wiwid, Dinata | 40 | JC090625 20593
|  |  | E26233,33203 - MAT. LIST FOR LADDER IN ENG. ROOM |  | 2025-06-16 | 2025-06-18 | 1 | Anam | 24 | JC090625 20594
|  |  | E26233,33202 - MAT. LIST FOR LADDER IN CHILLER & STP ROOM |  | 2025-06-19 | 2025-06-21 | 1 | Anam | 24 | JC090625 20595
|  |  | E26233,33201 - MAT. LIST FOR LADDER IN CHILLER & REFRIGERANT PLANT ROOM |  | 2025-06-23 | 2025-06-25 | 1 | Anam | 24 | JC090625 20596
|  |  | E26233,33200 - MAT. LIST FOR LADDER INFRESH WATER GENERATOR ROOM |  | 2025-06-26 | 2025-06-28 | 1 | Anam | 24 | JC090625 20599
|  |  | E16250.33400 - STEEL WALL OPENING FOR WINDOW - R3 |  | 2025-06-09 | 2025-06-10 | 1 | Rizal | 16 | JC090625 20602
|  | KPI | 3D MODEL PLATFORM SHIFT LIFT |  | 2025-06-02 | 2025-06-13 | 1 | Diva | 80 | JC090625 20603
|  |  | 3D MODEL PLTAL |  | 2025-06-16 | 2025-06-30 | 1 | Diva | 88 | JC090625 20604
|  | W306-307 | E16370.11400 - ARRT OF JOINER WORK - R2 |  | 2025-06-11 | 2025-06-13 | 1 | Rizal | 24 | JC090625 20548
| 2025-06-13 | W304-305 | E11672.33103 - DETAIL OF BLAST DOOR |  | 2025-06-16 | 2025-06-25 | 1 | Sutan | 64 | JC130625 20720
|  |  | E21672.33103 - MAT. LIST FOR DETAIL OF BLAST DOOR |  | 2025-06-26 | 2025-06-28 | 1 | Sutan | 24 | JC130625 20721
|  |  | EZ6623,33101 - SEAT OF EQUIP. IN RADIO ROOM |  | 2025-06-12 | 2025-06-21 | 1 | Indra | 56 | JC130625 20722
| 2025-06-16 | W304-305 | EZ6631.33101 - FOUND. OF EQUIP. IN ELECTRONIC EQUIP ROOM NO. 1 |  | 2025-06-16 | 2025-06-21 | 1 | Irene | 40 | JC170625 20972
|  |  | EZ5820.33100 - FOUND. OF EQUIP. IN AFT MOORING AREA |  | 2025-06-16 | 2025-06-17 | 1 | Bagus | 16 | JC170625 20973
|  |  | EZ1801.33119 - FOUND. OF EQUIP IN PASSAGE WAY (2KA1) |  | 2025-06-18 | 2025-06-19 | 1 | Bagus | 16 | JC170625 20975
|  |  | EZ1801.33120 - FOUND. OF EQUIP IN PASSAGE WAY (2KA2) |  | 2025-06-20 | 2025-06-21 | 1 | Bagus | 16 | JC170625 20976
|  |  | E16402.11403 - LIST OF GALLEY, PANTRY & LAUNDRY FURNITURE - R1 |  | 2025-06-16 | 2025-06-17 | 1 | Rizal | 16 | JC170625 20977
|  | W308 | E16402.11403 - LIST OF GALLEY, PANTRY & LAUNDRY FURNITURE - R1 |  | 2025-06-18 | 2025-06-20 | 1 | Rizal | 24 | JC170625 20998
| 2025-06-23 | W304-305 | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-06-23 | 2025-06-26 | 2 | Yudi, Wiwid | 32 | JC230625 21253
|  |  | EZ6632.33100 - FOUND. OF EQUIP. IN SWITCHBOARD ROOM FORE |  | 2025-06-23 | 2025-06-28 | 1 | Karina | 40 | JC230625 21247
|  |  | EZ6631.33102 - FOUND. OF EQUIP. IN ELECTRONIC EQUIP ROOM NO. 2 |  | 2025-06-23 | 2025-07-05 | 1 | Irene | 80 | JC230625 21248
|  |  | E16723.33301 - ARRT & DETAIL OF RACK FOR SPARE PORTABLE FIRE EXT'R |  | 2025-06-23 | 2025-06-26 | 1 | Dinata | 32 | JC230625 21250
|  |  | E16311,33302 - PAINT AREA COMPARTMENT |  | 2025-06-23 | 2025-07-05 | 1 | Indra | 80 | JC230625 21251
|  |  | E25820.33101 - ML FOR FOUND. OF EQUIP. IN AFT MOORING AREA |  | 2025-06-23 | 2025-06-24 | 1 | Bagus | 16 | JC230625 21254
|  |  | E21801.33119 - ML FOR FOUND. OF EQUIP IN PASSAGE WAY (2KA1) |  | 2025-06-25 | 2025-06-26 | 1 | Bagus | 16 | JC230625 21255
|  |  | E21801.33120 - ML FOR FOUND. OF EQUIP IN PASSAGE WAY (2KA2) |  | 2025-06-27 | 2025-06-28 | 1 | Bagus | 16 | JC230625 21256
|  |  | E26241.33400 - MAT. LIST FOR FOLDING FOOR |  | 2025-06-23 | 2025-06-24 | 1 | Rizal | 16 | JC230625 21257
|  |  | E26723.33301 - ML FOR RACK FOR SPARE PORTABLE FIRE EXT'R |  | 2025-06-30 | 2025-07-01 | 1 | Dinata | 16 | JC230625 21258
|  |  | EZ6632.33101 - FOUND. OF EQUIP. IN SWITCHBOARD ROOM AFT |  | 2025-06-30 | 2025-07-05 | 1 | Karina | 40 | JC240625 21263
|  |  | E11672.33103 - DETAIL OF BLAST DOOR |  | 2025-06-30 | 2025-07-05 | 1 | Sutan | 40 | JC240625 21264
|  |  | E10660.10403 - ACCOMM. ARRT OF 01 DECK - R1 |  | 2025-06-30 | 2025-07-04 | 1 | Rizal | 40 | JC240625 21265
|  |  | EZ7130. 33101 - FOUND. OF EQUIP. IN RIFLE STORE |  | 2025-06-26 | 2025-06-28 | 1 | Iyan | 24 | JC240625 21266
|  |  | EZ6631.33108 - FOUND. OF EQUIP. IN ELECTRONIC ROOM NO. 8 - R1 |  | 2025-06-30 | 2025-07-02 | 1 | Iyan | 24 | JC240625 21268
|  |  | EZ6720,33101 - FOUND. OF EQUIP. IN RATION PACK STOWAGE |  | 2025-07-03 | 2025-07-05 | 1 | Iyan | 24 | JC240625 21269
|  | W306-307 | E16221.33207 - ARRT OF PLATFORM IN ENG. CASING - R1 |  | 2025-06-30 | 2025-07-02 | 1 | Anam | 24 | JC240625 21271
|  | W308 | E26241.33400 - MAT. LIST FOR FOLDING FOOR |  | 2025-06-25 | 2025-06-26 | 1 | Rizal | 16 | JC230625 21260
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-06-30 | 2025-07-04 | 2 | Yudi, Wiwid | 40 | JC240625 21272
|  |  | E16233.33202 - ARRT OF LADDER IN CHILLER & STP ROOM - R1 |  | 2025-07-03 | 2025-07-05 | 1 | Anam | 24 | JC240625 21276
|  | KPI | REVIEW BRS UAE |  | 2025-06-23 | 2025-06-25 | 1 | Iyan | 24 | JC230625 21259
|  |  | REVIEW BRS UAE |  | 2025-07-02 | 2025-07-04 | 1 | Dinata | 24 | JC230625 21261
|  | W304-305 | E26631.33115 - ML FOR FOUND. OF EQUIP. IN PASSAGE WAY (2HZ2) |  | 2025-06-30 | 2025-07-01 | 1 | Bagus | 16 | JC300625 21513
|  |  | E21801,33118 - ML FOR FOUND. OF EQUIP. IN BAGGAGE STORE NO. 1 (2FA4) |  | 2025-07-02 | 2025-07-03 | 1 | Bagus | 16 | JC300625 21524
|  |  | E21801.33116 - ML FOR FOUND. OF EQUIP IN PASSAGE WAY (2JZ4) |  | 2025-07-04 | 2025-07-05 | 1 | Bagus | 16 | JC300625 21527
|  |  | EZ5820.33100 - FOUND. OF EQUIP. IN AFT MOORING AREA |  | 2025-07-07 | 2025-07-12 | 1 | Karina | 40 | JC300625 21532
|  |  | EZ5820.33102 - FOUND. OF EQUIP. IN FORE MOORING AREA (1AA0-E) |  | 2025-07-14 | 2025-07-17 | 1 | Karina | 32 | JC300625 21533
|  |  | EZ5820.33102 - ML FOR FOUND. OF EQUIP. IN FORE MOORING AREA (1AA0-E) |  | 2025-07-18 | 2025-07-19 | 1 | Karina | 16 | JC300625 21552
|  |  | EZ6631,33118 - FOUND. OF EQUIP. IN ELECT. EQUIP. ROOM NO. 16 |  | 2025-07-07 | 2025-07-12 | 1 | Iyan | 40 | JC300625 21553
|  |  | EZ4380,33100 - FOUND. OF EQUIP. IN MCR & DCHQ (2KA0) |  | 2025-07-14 | 2025-07-19 | 1 | Iyan | 40 | JC300625 21554
|  |  | EZ1801,33111 - FOUND. OF EQUIPMENT IN PASSAGE WAY (2JA3) |  | 2025-07-07 | 2025-07-10 | 1 | Bagus | 32 | JC010725 21605
|  |  | E21801,33111 - ML FOR FOUND. OF EQUIPMENT IN PASSAGE WAY (2JA3) |  | 2025-07-11 | 2025-07-12 | 1 | Bagus | 16 | JC010725 21606
|  |  | E16311,01301 - LIST OF PAINT FOR SPARE |  | 2025-07-07 | 2025-07-10 | 1 | Indra | 32 | JC010725 21607
|  |  | E26311.01301 - MAT. LIST FOR LIST OF PAINT FOR SPARE |  | 2025-07-11 | 2025-07-12 | 1 | Indra | 16 | JC010725 21608
|  |  | EVATEK RHIB |  | 2025-07-07 | 2025-07-08 | 1 | Dinata | 16 | JC010725 21609
|  |  | EZ1801,33107 - FOUND. OF EQUIP. IN STAIRWAY (2GA4) |  | 2025-07-14 | 2025-07-17 | 1 | Bagus | 32 | JC010725 21610
|  |  | E21801,33107 - ML FOR FOUND. OF EQUIP. IN STAIRWAY (2GA4) |  | 2025-07-18 | 2025-07-19 | 1 | Bagus | 16 | JC010725 21618
|  |  | E10660.10402 - ACCOMM. ARRT OF 1 DECK - R1 |  | 2025-07-07 | 2025-07-11 | 1 | Rizal | 40 | JC010725 21619
|  |  | E16500,33401 - FOUND. OF GALLEY, PANTRY & LAUNDRY EQUIPMENT |  | 2025-07-14 | 2025-07-17 | 1 | Rizal | 32 | JC010725 21620
|  |  | E16500.33401 - ML FOR FOUND. OF GALLEY, PANTRY & LAUNDRY EQUIPMENT |  | 2025-07-18 | 2025-07-18 | 1 | Rizal | 8 | JC010725 21621
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-07-07 | 2025-07-11 | 2 | Yudi, Wiwid | 40 | JC010725 21622
|  | W306-307 | EVATEK LCU |  | 2025-07-09 | 2025-07-11 | 1 | Dinata | 32 | JC010725 21623
|  | W304-305 | E16233,33200 - DET. OF VL IN COMPT. E.F,G,H ON 4 DECK - R2 |  | 2025-07-07 | 2025-07-12 | 1 | Farhan | 40 | JC020725 21700
|  |  | EZ433P.33200 - FOUND. OF EQUIP IN BLOCK 433 (P) |  | 2025-07-14 | 2025-07-17 | 1 | Farhan | 32 | JC020725 21701
|  |  | EZ223S.33200 - FOUND. OF EQUIP IN BLOCK 223 (S) - R1 |  | 2025-07-18 | 2025-07-26 | 1 | Farhan | 48 | JC020725 21702
|  |  | EZ243P.33200 - FOUND. OF EQUIP IN BLOCK 243 (P) - R1 |  | 2025-07-28 | 2025-07-30 | 1 | Farhan | 24 | JC020725 21703
|  |  | EZ233S.33200 - FOUND. OF EQUIP IN BLOCK 233 (S) - R1 |  | 2025-07-31 | 2025-08-02 | 1 | Farhan | 24 | JC020725 21704
|  |  | E11503,33200 - ARRT & DET. OF EQUIPMENT IN FUNNEL - R1 |  | 2025-07-07 | 2025-07-12 | 1 | Anam | 40 | JC020725 21705
|  |  | EZ7531,33100 - FOUND. OF EQUIP. IN TORPEDO & STORE (01JA3) |  | 2025-07-07 | 2025-07-12 | 1 | Irene | 40 | JC020725 21706
|  |  | EZ7531,33101 - FOUND. OF EQUIP. IN TORPEDO & STORE (01JA4) |  | 2025-07-14 | 2025-07-19 | 1 | Irene | 40 | JC020725 21708
|  |  | E16120,33100 - ARRT OF RAILING - R3 |  | 2025-07-21 | 2025-07-26 | 1 | Irene | 40 | JC020725 21709
|  |  | E16120,33101 - DETAIL OF RAILING - R4 |  | 2025-07-28 | 2025-07-31 | 1 | Irene | 32 | JC020725 21710
|  |  | E26120.33101 - MAT. LIST FOR DETAIL OF RAILING - R4 |  | 2025-08-01 | 2025-08-02 | 1 | Irene | 16 | JC020725 21711
|  |  | E16311,33102 - PAINT AREA COMPARTMENT |  | 2025-07-14 | 2025-07-19 | 1 | Indra | 40 | JC020725 21713
|  |  | E16332,33200 - ARRT OF ICCP ANODE |  | 2025-07-11 | 2025-07-15 | 1 | Sutan | 24 | JC020725 21714
|  |  | E10660,10401 - ACCOMM. ARRT OF 2 DECK - R1 |  | 2025-07-21 | 2025-07-25 | 1 | Rizal | 40 | JC020725 21715
|  |  | E10660,10400 - ACCOMM. ARRT OF 3 DECK - R1 |  | 2025-07-28 | 2025-08-01 | 1 | Rizal | 40 | JC020725 21716
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-07-21 | 2025-07-25 | 3 | Yudi, Wiwid, Dinata | 40 | JC020725 21717
|  | W308 | E16233,33203 - ARRT & DETAIL OF LADDER IN E/R - R2 |  | 2025-07-14 | 2025-07-19 | 1 | Anam | 40 | JC020725 21718
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-07-14 | 2025-07-18 | 3 | Yudi, Wiwid, Dinata | 40 | JC020725 21719
|  |  | EF232P.04300 - 232 P BLOCK PAINTING - R3 |  | 2025-07-07 | 2025-07-07 | 1 | Sutan | 8 | JC020725 21720
|  |  | EF232S.04300 - 232 S BLOCK PAINTING - R3 |  | 2025-07-08 | 2025-07-08 | 1 | Sutan | 8 | JC020725 21721
|  |  | EF132P.04300 - 232 P BLOCK PAINTING - R3 |  | 2025-07-09 | 2025-07-09 | 1 | Sutan | 8 | JC020725 21722
|  |  | EF132S.04300 - 132 S BLOCK PAINTING - R3 |  | 2025-07-10 | 2025-07-10 | 1 | Sutan | 8 | JC020725 21723
|  | KPI | 3D MODEL PIPING PLTAL |  | 2025-07-01 | 2025-08-01 | 1 | Diva | 192 | JC020725 21707
|  | W304-305 | E21672,33103 - ML FOR BLAST DOOR |  | 2025-07-16 | 2025-07-18 | 1 | Sutan | 24 | JC070725 21982
|  |  | E11672,33105 - STEEL LATICE DOOR - R2 |  | 2025-07-21 | 2025-07-23 | 1 | Sutan | 24 | JC070725 21983
|  |  | E21672,33105 - ML FOR STEEL LATICE DOOR - R2 |  | 2025-07-24 | 2025-07-25 | 1 | Sutan | 16 | JC070725 21984
|  |  | EZ6720,33100 - FOUND. OF EQUIP. IN DIVERS STORE (2PA2) |  | 2025-07-21 | 2025-07-23 | 1 | Karina | 24 | JC070725 21986
|  |  | EZ6741,33100 - FOUND. OF EQUIP. IN HANGAR (1LA0) |  | 2025-07-24 | 2025-07-26 | 1 | Karina | 24 | JC070725 21988
|  |  | E21801,33109 - SEAT OF EQUIPMENT IN PASSAGE WAY (2LA4) |  | 2025-07-21 | 2025-07-22 | 1 | Bagus | 16 | JC070725 21990
|  |  | E21801,33110 - SEAT OF EQUIPMENT IN PASSAGE WAY (2LA3) |  | 2025-07-23 | 2025-07-24 | 1 | Bagus | 16 | JC070725 21991
|  |  | EZ5820,33102 - FOUND. OF EQUIP IN FORE MOORING AREA (1AA0-E) |  | 2025-07-25 | 2025-07-29 | 1 | Bagus | 24 | JC080725 22014
|  |  | EZ6720,33100 - FOUND. OF EQUIP. IN DIVERS STORE (2PA4) |  | 2025-07-30 | 2025-08-01 | 1 | Bagus | 24 | JC080725 22015
|  |  | E26720,33100 - ML FOR FOUND. OF EQUIP. IN DIVERS STORE (2PA4) |  | 2025-08-02 | 2025-08-02 | 1 | Bagus | 8 | JC080725 22016
|  |  | EZ6721,33101 - FOUND. OF EQUIP. IN HAWSER STORE (2PA3) |  | 2025-07-28 | 2025-08-02 | 1 | Karina | 40 | JC080725 22017
|  |  | E16032,32301 - ARRT OF CBRN SIGN - R1 |  | 2025-07-28 | 2025-08-01 | 1 | Dinata | 40 | JC080725 22019
|  | W304-305 | E16221,33204 - ARRT & DETAIL OF GRATING IN ENGINE CASING - R1 |  | 2025-07-21 | 2025-07-29 | 1 | Iyan | 56 | JC180725 22405
|  |  | E16221,33204 - ML FOR DETAIL OF GRATING IN ENGINE CASING - R1 |  | 2025-07-30 | 2025-07-31 | 1 | Iyan | 16 | JC180725 22408
|  |  | E15710,33101 - DETAIL OF RAS EQUIPMENT |  | 2025-08-01 | 2025-08-16 | 1 | Iyan | 96 | JC180725 22409
|  |  | EZ6723,33100 - FOUND. OF EQUIP. IN FOAM ROOM (01MZ3) |  | 2025-08-18 | 2025-08-21 | 1 | Iyan | 32 | JC180725 22410
|  |  | E26723,33100 - ML FOR FOUND. OF EQUIP. IN FOAM ROOM (01MZ3) |  | 2025-08-22 | 2025-08-23 | 1 | Iyan | 16 | JC180725 22413
|  |  | E12590.33200 - ARRT & DET. OF SUPPORT EXH. GAS PIPE - R1 |  | 2025-08-25 | 6 Sept 2025 | 1 | Iyan | 80 | JC180725 22414
|  | W306-307 | E16221,33207 - ARRT OF PLATFORM IN ENGINE CASING - R1 |  | 2025-07-21 | 2025-07-26 | 1 | Anam | 40 | JC180725 22415
|  | W308 | E16231,33406 - ARRT & DETAIL OF STORMRAIL IN STAIRWAY - R2 |  | 2025-07-28 | 2025-08-02 | 1 | Anam | 40 | JC180725 22417
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-07-28 | 2025-08-01 | 2 | Yudi, Wiwid | 40 | JC180725 22418
| 2025-07-24 | W304-305 | EZ6624,33100 - FOUND. OF EQUIP. IN RADIO ROOM (02FA1) |  | 2025-07-21 | 2025-07-26 | 1 | Indra | 40 | JC240725 22630
|  |  | E86332.51300 - ICCP SYSTEM |  | 2025-08-04 | 2025-08-06 | 1 | Sutan | 24 | JC240725 22634
|  |  | E86333.51300 - MGPS SYSTEM |  | 2025-08-07 | 2025-08-08 | 1 | Sutan | 16 | JC240725 22635
|  |  | EZ4611,33100 - SEAT OF EQUIPMENT IN SONAR ROOM (3BA0) - R1 |  | 2025-07-28 | 2025-08-02 | 1 | Indra | 40 | JC240725 22638
|  |  | E16440.33400 - STEEL COAMING FOR WET AREA - R1 |  | 2025-08-04 | 2025-08-06 | 1 | Bagus | 24 | JC240725 22640
|  |  | E16400.33400 - STEEL COAMING FOR DRY AREA - R1 |  | 2025-08-07 | 2025-08-09 | 1 | Bagus | 24 | JC240725 22642
|  |  | EZ6721.33101 - FOUND. OF EQUIP. IN HAWSER & CBRN STORE (2BA0) |  | 2025-08-04 | 2025-08-09 | 1 | Karina | 40 | JC240725 22645
|  |  | E16021.33400 - IMO NUMBER |  | 2025-08-04 | 2025-08-08 | 1 | Rizal | 40 | JC240725 22646
|  |  | E16020.33403 - LAMBANG GARUDA |  | 2025-08-11 | 2025-08-12 | 1 | Rizal | 16 | JC240725 22647
|  | W306-307 | E25730,51104 - ML FOR CARGO LIFT |  | 2025-08-11 | 2025-08-13 | 1 | Sutan | 24 | JC240725 22648
|  |  | E25730,51105 - ML FOR RHIB DAVIT |  | 2025-08-14 | 2025-08-16 | 1 | Sutan | 24 | JC240725 22651
|  | W308 | E21672,33104 - ML FOR COVER INSPECTION HOLES (RM) - R2 |  | 2025-07-28 | 2025-07-30 | 1 | Sutan | 24 | JC240725 22652
|  |  | EF122P.04300 - 122 P BLOCK PAINTING - R2 |  | 2025-07-31 | 2025-07-31 | 1 | Sutan | 8 | JC240725 22654
|  |  | EF122S.04300 - 122 S BLOCK PAINTING - R2 |  | 2025-08-01 | 2025-08-01 | 1 | Sutan | 8 | JC240725 22655
|  | KPI | 3D MODEL PIPING SHIFLIFT |  | 2025-08-04 | 2025-08-29 | 1 | Diva | 160 | JC240725 22656
| 2025-08-04 | W304-305 | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-08-04 | 2025-08-08 | 2 | Yudi, Wiwid | 40 | JC040825 23199
|  |  | EZ5140,33204 - FOUND. OF EQUIP. IN AC ROOM NO 2 & 3 (1CA1) |  | 2025-08-04 | 2025-08-09 | 1 | Farhan | 40 | JC040825 23200
|  |  | EZ5140,33205 - FOUND. OF EQUIP. IN AC ROOM NO 6 (1JZ0) |  | 2025-08-11 | 2025-08-16 | 1 | Farhan | 40 | JC040825 23201
|  |  | EZ5140,33202 - FOUND. OF EQUIP. IN AC ROOM NO 4 & 5 (01GZ0) |  | 2025-08-18 | 2025-08-23 | 1 | Farhan | 40 | JC040825 23202
|  |  | EZ5140,33203 - FOUND. OF EQUIP. IN AC ROOM NO 7 (01LB1) |  | 2025-08-25 | 2025-08-30 | 1 | Farhan | 40 | JC040825 23203 | Permintaan extend sampai 6 Sept.
|  |  | E16023,32301 - ARRT OF NBCD SIGN - R1 |  | 2025-08-04 | 2025-08-08 | 1 | Dinata | 40 | JC040825 23205
|  |  | REVIEW COMMENT LR - SAFETY PLAN |  | 2025-08-11 | 2025-08-15 | 1 | Dinata | 40 | JC040825 23207
|  |  | REVIEW COMMENT LR - ESCAPE WAY PLAN |  | 2025-08-18 | 2025-08-22 | 1 | Dinata | 40 | JC040825 23223
|  |  | EF542C.36100 - 542 C BLOCK PAINTING |  | 2025-08-04 | 2025-08-04 | 1 | Indra | 8 | JC040825 23225
|  |  | EF155C.36100 - 155 C BLOCK PAINTING |  | 2025-08-05 | 2025-08-05 | 1 | Indra | 8 | JC040825 23235
|  |  | EF613C,36100 - 613 C BLOCK PAINTING - R2 |  | 2025-08-06 | 2025-08-06 | 1 | Indra | 8 | JC040825 23238
|  |  | EF515C.36100 - 515 C BLOCK PAINTING - R2 |  | 2025-08-07 | 2025-08-07 | 1 | Indra | 8 | JC040825 23240
|  |  | EF693C,36100 - 693 C BLOCK PAINTING - R2 |  | 2025-08-08 | 2025-08-08 | 1 | Indra | 8 | JC040825 23245
|  |  | EF612P.36100 - 612 P BLOCK PAINTING - R2 |  | 2025-08-09 | 2025-08-09 | 1 | Indra | 8 | JC040825 23246
|  |  | EF612S.36100 - 612 S BLOCK PAINTING - R2 |  | 2025-08-11 | 2025-08-11 | 1 | Indra | 8 | JC040825 23248
|  |  | EF513P,36100 - 513 P BLOCK PAINTING - R2 |  | 2025-08-12 | 2025-08-12 | 1 | Indra | 8 | JC040825 23249
|  |  | EF513S,36100 - 513 S BLOCK PAINTING - R2 |  | 2025-08-13 | 2025-08-13 | 1 | Indra | 8 | JC040825 23251
|  |  | EF514C.36100 - 514 C BLOCK PAINTING - R2 |  | 2025-08-14 | 2025-08-14 | 1 | Indra | 8 | JC040825 23253
|  |  | EF623C,36100 - 623 C BLOCK PAINTING - R2 |  | 2025-08-15 | 2025-08-15 | 1 | Indra | 8 | JC040825 23254
|  | W306-307 | E16640,11100 - DAMAGE CONTROL PLAN - R1 |  | 2025-08-04 | 2025-08-09 | 1 | Irene | 40 | JC040825 23255
|  |  | E16000,10100 - GENERAL OUTFITTING ARRT - R2 |  | 2025-08-11 | 2025-08-16 | 1 | Irene | 40 | JC040825 23256
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-08-18 | 2025-08-22 | 2 | Yudi, Wiwid | 40 | JC040825 23257
|  |  | EVALUATION & REVIEW CARGO HANDLING |  | 2025-08-18 | 2025-08-30 | 1 | Sutan | 80 | JC040825 23258
|  |  | E17118.33400 - ARRT & DETAIL OF RIFLE STORE - R1 |  | 2025-08-11 | 2025-08-16 | 1 | Bagus | 40 | JC040825 23259
|  | W308 | EVALUATION & UPDATE POSITION OF FOUND, LADDER & FLOOR IN E/R |  | 2025-08-04 | 2025-08-16 | 1 | Anam | 80 | JC040825 23260
|  |  | E11672,11100 - ARRT OF STEEL DOOR - R3 |  | 2025-08-11 | 2025-08-16 | 1 | Karina | 40 | JC040825 23261
|  |  | E21672,33100 - MAT. LIST FOR STEEL DOOR - R1 |  | 2025-08-18 | 2025-08-20 | 1 | Karina | 24 | JC040825 23262
|  |  | E16442,33401 - DETAIL OF UNIT TOILET |  | 2025-08-13 | 2025-08-19 | 1 | Rizal | 40 | JC040825 23263
|  |  | E26442,33401 - MAT. LIST FOR DETAIL OF UNIT TOILET (RAW MATERIAL) |  | 2025-08-20 | 2025-08-22 | 1 | Rizal | 24 | JC040825 23271
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-08-11 | 2025-08-15 | 2 | Yudi, Wiwid | 40 | JC040825 23272
| 18 Agust 2025 | W304-305 | E12590,32201 - ARRT OF EXHAUST GAS PIPE (S) |  | 18 Agust 2025 | 30 Agust 2025 |  | Anam | 80 | JC190825 23876 | Permintaan extend sampai 6 Sept.
|  |  | EZ1802,33104 - FOUND OF EQUIP ON EXTERNAL BRIDGE WING |  | 18 Agust 2025 | 23 Agust 2025 |  | Irene | 40 | JC190825 23878
|  |  | EZ1802,33103 - FOUND OF EQUIP ON EXPOSED 02 DECK |  | 21 Agust 2025 | 27 Agust 2025 |  | Karina | 40 | JC190825 23880
|  |  | UPDATING 3D CADMATIC FOR ACCOMODATION |  | 18 Agust 2025 | 30 Agust 2025 |  | Bagus | 80 | JC190825 23879
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 25 Agust 2025 | 29 Agust 2025 |  | Yudi, Wiwid | 40 | JC190825 23890
|  |  | E21802,33104 - MAT. LIST FOR FOUND OF EQUIP ON EXTERNAL BRIDGE WING |  | 25 Agust 2025 | 27 Agust 2025 |  | Irene | 24 | JC190825 23891
|  |  | E11300,33101 - PLATFORM FOR AUXILIARY GUN 03 DECK |  | 28 Agust 2025 | 3 Sept 2025 |  | Irene | 40 | JC190825 23892
|  |  | E21300,33101 - MAT. LIST FOR PLATFORM FOR AUXILIARY GUN 03 DECK |  | 4 Sept 2025 | 6 Sept 2025 |  | Irene | 24 | JC190825 23893
|  |  | EZ1802.33103 - MAT. LIST FOR FOUND OF EQUIP ON EXPOSED 02 DECK |  | 28 Agust 2025 | 3 Sept 2025 |  | Karina | 24 | JC190825 23896
|  |  | 3D MODEL RHIB DAVIT |  | 25 Agust 2025 | 30 Agust 2025 |  | Dinata | 40 | JC190825 23897
|  |  | E16024,02300 - HAZARDOUS ZONE - R2 |  | 1 Sept 2025 | 6 Sept 2025 |  | Dinata | 40 | JC190825 23898
|  |  | E16011,33400 - ARRT OF MISCELLANEOUS FITTING & DETAIL |  | 25 Agust 2025 | 29 Agust 2025 |  | Rizal | 40 | JC190825 23899
|  |  | E26011,33400 - MAT. LIST FOR MISCELLANEOUS FITTING & DETAIL |  | 1 Sept 2025 | 3 Sept 2025 |  | Rizal | 24 | JC190825 23900
| 27 Agust 2025 | W304-305 | E16311.33102 - PAINT AREA COMPARTMENT - R1 |  | 18 Agust 2025 | 30 Agust 2025 |  | Indra | 80 | JC270825 24179
| 03 Sept 2025 | W304-305 | E12590,32201 - ARRT OF EXHAUST GAS PIPE (S) |  | 1 Sept 2025 | 13 Sept 2025 |  | Anam | 80 | JC040925 24561
|  |  | EZ4611,33101 - SEAT OF EQUIPMENT IN SONAR WATER FILTER (2AA0) - R2 |  | 1 Sept 2025 | 4 Sept 2025 |  | Indra | 32 | JC040925 24562
|  |  | E24611,33101 - ML FOR SEAT OF EQUIPMENT IN SONAR WATER FILTER (2AA0) - R1 |  | 5 Sept 2025 | 6 Sept 2025 |  | Indra | 16 | JC040925 24563
|  |  | EZ1233,33108 - FOUND. OF EQUIPMENT IN TRUNK (02/3JZ3) |  | 1 Sept 2025 | 3 Sept 2025 |  | Farhan | 24 | JC040925 24564
|  |  | EZ1233,33107 - FOUND. OF EQUIPMENT IN TRUNK (02/3JY3) |  | 4 Sept 2025 | 6 Sept 2025 |  | Farhan | 24 | JC040925 24565
|  |  | EZ1233,33103 - FOUND. OF EQUIPMENT IN TRUNK (02/2LY4) |  | 8 Sept 2025 | 10 Sept 2025 |  | Farhan | 24 | JC040925 24566
|  |  | EZ1233,33106 - FOUND. OF EQUIPMENT IN TRUNK (02/3lb2) |  | 11 Sept 2025 | 13 Sept 2025 |  | Farhan | 24 | JC040925 24567
|  |  | EZ1233,33104 - FOUND. OF EQUIPMENT IN TRUNK (02/2JZ2) |  | 15 Sept 2025 | 20 Sept 2025 |  | Farhan | 40 | JC040925 24568
|  |  | EZ1233,33105 - FOUND. OF EQUIPMENT IN TRUNK (02/2LA1) |  | 22 Sept 2025 | 27 Sept 2025 |  | Farhan | 40 | JC040925 24569
|  |  | E21233,33105 - ML FOR FOUND. OF EQUIPMENT IN TRUNK (02/2LA1) |  | 29 Sept 2025 | 30 Sept 2025 |  | Farhan | 16 | JC040925 24570
|  |  | EZ1801,33135 - FOUND. OF EQUIP. IN AIR FILTER CLEANING (02LB1) |  | 1 Sept 2025 | 4 Sept 2025 |  | Karina | 32 | JC080925 24802
|  |  | E21801,33135 - ML FOR FOUND. OF EQUIP. IN AIR FILTER CLEANING (02LB1) |  | 5 Sept 2025 | 6 Sept 2025 |  | Karina | 16 | JC080925 24803
|  |  | EZ6631,33104 - FOUND. OF EQUIP. IN ELECT. EQUIP. ROOM NO. 4 - R1 |  | 8 Sept 2025 | 10 Sept 2025 |  | Karina | 24 | JC040925 24571
|  |  | EZ1801,33100 - FOUND. OF EQUIP. IN PASSAGEWAY (2NZ4) - R1 |  | 11 Sept 2025 | 13 Sept 2025 |  | Karina | 24 | JC040925 24572
|  |  | EZ6721,33100 - FOUND. OF EQUIP. IN HAWSER & CBRN STORE (2BA0) - R1 |  | 15 Sept 2025 | 24 Sept 2025 |  | Karina | 64 | JC040925 24573
|  |  | EZ6631,33119 - FOUND. OF EQUIP. IN ELECTRIC ROOM NO. 3 (2LZ1) - R1 |  | 25 Sept 2025 | 27 Sept 2025 |  | Karina | 24 | JC040925 24595
|  |  | E26721,33100 - ML FOR FOUND. OF EQUIP. IN HAWSER & CBRN STORE (2BA0) - R1 |  | 29 Sept 2025 | 30 Sept 2025 |  | Karina | 16 | JC040925 24596
|  |  | E11300,33102 - PLATFORM FOR AUXILIARY GUN 02 DECK |  | 8 Sept 2025 | 13 Sept 2025 |  | Irene | 40 | JC040925 24599
|  |  | E21300,33102 - MAT. LIST FOR PLATFORM FOR AUXILIARY GUN 02 DECK |  | 15 Sept 2025 | 17 Sept 2025 |  | Irene | 24 | JC040925 24600
|  |  | E11672,33104 - COVER INSPECTION HOLES - R2 |  | 18 Sept 2025 | 20 Sept 2025 |  | irene | 24 | JC040925 24602
|  |  | E21672,33104 - ML FOR COVER INSPECTION HOLES - R2 |  | 22 Sept 2025 | 22 Sept 2025 |  | irene | 8 | JC040925 24603
|  |  | EZ6631,33102 - FOUND. OF EQUIP. IN ELECT. EQUIP. ROOM NO. 2 - R2 |  | 23 Sept 2025 | 27 Sept 2025 |  | Irene | 32 | JC080925 24800
|  |  | E26631,33102 - ML FOR FOUND. OF EQUIP. IN ELECT. EQUIP. ROOM NO. 2 - R2 |  | 29 Sept 2025 | 30 Sept 2025 |  | Irene | 16 | JC080925 24801
|  |  | RISET BLAST DOOR |  | 1 Sept 2025 | 6 Sept 2025 |  | Sutan | 40 | JC040925 24597
|  |  | RISET RCS RHIB DAVIT & MONORAIL |  | 8 Sept 2025 | 20 Sept 2025 |  | Sutan | 80 | JC040925 24605
|  |  | 3D MODEL HANGAR DOOR |  | 22 Sept 2025 | 27 Sept 2025 |  | Sutan | 40 | JC040925 24606
|  |  | 3D MODEL ACC. LADDER |  | 29 Sept 2025 | 2025-10-04 |  | Sutan | 40 | JC040925 24607
|  |  | E16720,33300 - ARRT & DET. OF FIRE 7REPAIR PARTY POST |  | 8 Sept 2025 | 13 Sept 2025 |  | Dinata | 40 | JC040925 24608
|  |  | E10770,02300 - SAFETY PLAN - R2 |  | 15 Sept 2025 | 20 Sept 2025 |  | Dinata | 40 | JC040925 24609
|  |  | E14360,02300 - FIRE CONTROL PLAN - R1 |  | 22 Sept 2025 | 27 Sept 2025 |  | Dinata | 40 | JC040925 24610
|  |  | E26720,33300 - ML FOR DET. OF FIRE 7REPAIR PARTY POST |  | 29 Sept 2025 | 30 Sept 2025 |  | Dinata | 16 | JC040925 24611
|  |  | EZ3041,33100 - HANGER FOR CABLE |  | 17 Sept 2025 | 20 Sept 2025 |  | Indra | 32 | JC040925 24612
|  |  | E23041,33100 - MAT. LIST FOR HANGER FOR CABLE |  | 22 Sept 2025 | 23 Sept 2025 |  | Indra | 16 | JC040925 24613
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 8 Sept 2025 | 12 Sept 2025 |  | Yudi, Wiwid | 40 | JC040925 24614
|  |  | 3D MODEL FOOD LIFT & PROV. LIFT |  | 1 Sept 2025 | 10 Sept 2025 |  | Bagus | 64 | JC040925 24598
|  |  | E26370,11400 - ML FOR JOINER WORK - R2 |  | 11 Sept 2025 | 13 Sept 2025 |  | Bagus | 16 | JC040925 24618
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 29 Sept 2025 | 2025-10-03 |  | Yudi, Wiwid | 40 | JC040925 24619
|  |  | E16241,33400 - FOLDING DOOR |  | 4 Sept 2025 | 10 Sept 2025 |  | Rizal | 40 | JC040925 24615
|  |  | E16020,33402 - TANDA KESATUAN - R1 |  | 18 Sept 2025 | 19 Sept 2025 |  | Rizal | 16 | JC080925 24700
|  |  | E16442,33401 - DETAIL OF UNIT TOILET (RAW MATERIAL) - R2 |  | 22 Sept 2025 | 24 Sept 2025 |  | Rizal | 24 | JC080925 24707
|  |  | E21671,11100 - ML FOR HATCH & VERTICAL LADDER - R2 |  | 15 Sept 2025 | 17 Sept 2025 |  | Anam | 24 | JC080925 24708
|  |  | E15710,33101 - DETAIL OF RAS EQUIPMENT |  | 15 Sept 2025 | 27 Sept 2025 |  | Iyan | 80 | JC080925 24715
|  |  | E25710,33101 - MAT. LIST FOR DETAIL OF RAS EQUIPMENT |  | 29 Sept 2025 | 30 Sept 2025 |  | Iyan | 16 | JC080925 24719
|  | W306-307 | EZ3041,33100 - HANGER FOR CABLE |  | 24 Sept 2025 | 27 Sept 2025 |  | Indra | 32 | JC080925 24724
|  |  | E23041,33100 - MAT. LIST FOR HANGER FOR CABLE |  | 29 Sept 2025 | 30 Sept 2025 |  | Indra | 16 | JC080925 24736
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 15 Sept2025 | 19 Sept 2025 |  | Yudi, Wiwid | 40 | JC080925 24738
|  |  | 3D MODEL FOOD LIFT |  | 26 Sept 2025 | 30 Sept 2025 |  | Bagus | 32 | JC080925 24742
|  |  | E27118,33400 - MAT. LIST FOR RIFLE STORE - R3 |  | 25 Sept 2025 | 26 Sept 2025 |  | Rizal | 16 | JC080925 24750
|  |  | E16700,33400 - RACK FOR STORE & LOCKER - R3 |  | 29 Sept 2025 | 30 Sept 2025 |  | Rizal | 16 | JC080925 24751
|  | W308 | EZ3041,33100 - HANGER FOR CABLE |  | 8 Sept 2025 | 13 Sept 2025 |  | Indra | 40 | JC080925 24749
|  |  | E23041,33100 - MAT. LIST FOR HANGER FOR CABLE |  | 15 Sept 2025 | 16 Sept 2025 |  | Indra | 16 | JC080925 24752
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 1 Sept 2025 | 5 Sept 2025 |  | Yudi, Wiwid | 40 | JC040925 24616
|  |  | 3D MODEL FOOD LIFT & PASSENGER LIFT |  | 15 Sept 2025 | 20 Sept 2025 |  | Bagus | 40 | JC080925 24753
|  |  | E16221,33101 - ARRT FLOOR IN BOW THRUSTER - R1 |  | 22 Sept 2025 | 25 Sept 2025 |  | Bagus | 32 | JC080925 24754
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 22 Sept 2025 | 26 Sept 2025 |  | Yudi, Wiwid | 40 | JC080925 24756
|  |  | E16241,33400 - FOLDING DOOR |  | 11 Sept 2025 | 17 Sept 2025 |  | Rizal | 40 | JC080925 24757
|  |  | EZ231P,33200 - FOUND. OF EQUIPMENT IN BLOCK 231 (P) - R5 |  | 18 Sept 2025 | 24 Sept 2025 |  | Anam | 40 | JC080925 24758
|  |  | E2342C.33200 - ML FOR FOUND. OF EQUIP. ON BLOCK 342 (C) |  | 25 Sept 2025 | 27 Spet 2025 |  | Anam | 24 | JC080925 24759
|  |  | E2222P.33200 - ML FOR FOUND. OF EQUIP. ON BLOCK 222 (P) - R1 |  | 29 Sept 2025 | 30 Sept 2025 |  | Anam | 16 | JC080925 24762
|  |  | RISET RECOMPRESSION CHAMBER & MEDICAL EQUIPMENT |  | 8 Sept 2025 | 13 Sept 2025 |  | Iyan | 40 | JC040925 24617
|  | KPI | 3D MODEL OUTFITTING PLTAL |  | 1 Sept 2025 | 30 Sept 2025 |  | Diva | 176 | JC040925 24604
|  | W304-305 | EZ1802,33100 - FOUND. OF EQUIP. IN EXPOSED 02 DECK |  | 2025-10-01 | 2025-10-04 |  | Karina | 32 | JC011025 25764
|  |  | E11672,33104 - COVER INSPECTION HOLES - R5 |  | 2025-10-01 | 2025-10-04 |  | Irene | 32 | JC011025 25765
|  |  | E16315,01300 - PAINTING SCHEDULE - RA0 |  | 2025-10-01 | 2025-10-04 |  | Indra | 32 | JC011025 25770
|  |  | E16400.33400 - STEEL COAMING FOR DRY AREA - R1 |  | 2025-10-01 | 2025-10-04 |  | Bagus | 32 | JC011025 25772
|  | W304-305 | EZ241S,33200 - FOUND. OF EQUIP. BLOCK 241 (S) - RA1 |  | 2025-10-01 | 2025-10-04 |  | Farhan | 32 | JC071025 26020
|  |  | EZ131C,33200 - FOUND. OF EQUIP. BLOCK 131 (C) - R5 |  | 2025-10-06 | 2025-10-11 |  | Farhan | 40 | JC071025 26021
|  |  | EZ232S,33200 - FOUND. OF EQUIP. BLOCK 232 (S) - RA1 |  | 2025-10-13 | 2025-10-18 |  | Farhan | 40 | JC071025 26022
|  |  | EZ212P,33200 - FOUND. OF EQUIP. BLOCK 212 (P) - RA3 |  | 2025-10-20 | 2025-10-25 |  | Farhan | 40 | JC071025 26023
|  |  | EZ222S,33200 - FOUND. OF EQUIP. BLOCK 222 (S) - R2 |  | 2025-10-27 | 2025-10-29 |  | Farhan | 24 | JC071025 26024
|  |  | EZ433P,33200 - FOUND. OF EQUIP. BLOCK 433 (P) - R1 |  | 2025-10-30 | 2025-11-01 |  | Farhan | 24 | JC071025 26025
|  |  | E10770,02300 - SAFETY PLAN - R2 |  | 2025-10-01 | 2025-10-04 |  | Dinata | 32 | JC071025 26026
|  |  | E14360,02300 - FIRE CONTROL PLAN - R1 |  | 2025-10-06 | 2025-10-11 |  | Dinata | 40 | JC071025 26027
|  |  | E16024,02300 - HAZARDOUS ZONE - R2 |  | 2025-10-13 | 2025-10-18 |  | Dinata | 40 | JC071025 26028
|  |  | E10773,10300 - ESCAPE WAY PLAN - R2 |  | 2025-10-20 | 2025-10-25 |  | Dinata | 40 | JC071025 26029
|  |  | E16023,32300 - ARRT OF IMO SIGN |  | 2025-10-27 | 2025-10-30 |  | Dinata | 32 | JC071025 26030
|  |  | E26023,32300 - MAT. LIST FOR IMO SIGN |  | 2025-10-31 | 2025-11-01 |  | Dinata | 16 | JC071025 26031
|  |  | EZ6631,33107 - FOUND. OF EQUIP. IN ELECT. EQUIP. ROOM NO. 7 - R1 |  | 2025-10-01 | 2025-10-04 |  | Iyan | 32 | JC071025 26032
|  |  | E12590,32201 - ARRT OF EXHAUST GAS PIPE (S) |  | 2025-10-01 | 2025-10-04 |  | Anam | 32 | JC071025 26033
|  |  | CEK GAMBAR, EVALUASI & KOORINASI TEKNIS |  | 2025-10-20 | 2025-10-24 |  | Yudi, Wiwid | 40 | JC141025 26383 |  | jc baru
|  |  | E11672,33107 - ENCLOSURE ROOM FOR BLAST TEST OF BLAST DOOR |  | 2025-10-06 | 2025-10-10 |  | Sutan | 40 | JC071025 26036
|  |  | E21672,33107 - ML FOR ENCLOSURE ROOM FOR BLAST TEST OF BLAST DOOR |  | 2025-10-13 | 2025-10-15 |  | Sutan | 24 | JC071025 26037
|  |  | EZ1802,33104 - FOUND. OF EQUIP. IN FORE MAST 05 DECK |  | 2025-10-06 | 2025-10-11 |  | Karina | 40 | JC071025 26038
|  |  | EZ1802,33102 - FOUND. OF EQUIP. ON BRIDGE ROOF |  | 2025-10-13 | 2025-10-25 |  | Karina | 80 | JC071025 26039
|  |  | E21802,33100 - ML FOR FOUND. OF EQUIP. IN EXPOSED 02 DECK |  | 2025-10-27 | 2025-10-29 |  | Karina | 24 | JC071025 26040
|  |  | E21802,33102 - ML FOR FOUND. OF EQUIP. ON BRIDGE ROOF |  | 2025-10-30 | 2025-11-01 |  | Karina | 24 | JC071025 26042
|  |  | E21672,33104 - ML FOR COVER INSPECTION HOLE - R4 |  | 2025-10-06 | 2025-10-07 |  | Irene | 16 | JC071025 26047
|  |  | EZ6631,33102 - FOUND. OF EQUIP. IN ELECT. EQUIP. ROOM NO. 2 - R3 |  | 2025-10-08 | 2025-10-11 |  | Irene | 24 | JC071025 26049
|  |  | E16440.33400 - STEEL COAMING FOR WET AREA - R1 |  | 2025-10-06 | 2025-10-11 |  | Bagus | 40 | JC071025 26051
|  | W306-307 | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 2025-10-06 | 2025-10-10 |  | Yudi, WIwid | 40 | JC071025 26052
|  |  | EZ223P.33200 - FOUND. OF EQUIPMENT ON BLOCK 223 (P) |  | 2025-10-06 | 2025-10-08 |  | Indra | 24 | JC071025 26053
|  |  | EZ223S.33200 - FOUND. OF EQUIPMENT ON BLOCK 223 (S) |  | 2025-10-09 | 2025-10-11 |  | Indra | 24 | JC071025 26054
|  |  | EZ6500,33400 - FOUND. OF GALLEY, PANTRY & LAUNDRY EQUI[PMENT |  | 2025-10-06 | 2025-10-10 |  | Rizal | 40 | JC071025 26055
|  |  | E26500,33400 - MAT. LIST FOR FOUND. OF GALLEY, PANTRY & LAUNDRY EQUI[PMENT |  | 2025-10-13 | 2025-10-15 |  | Rizal | 24 | JC071025 26056
|  | W308 | REVIEW MEDICAL EQUIPMENT |  | 2025-10-06 | 2025-10-11 |  | Iyan | 40 | JC071025 26059
|  |  | E16221,33203 - ARRT OF FLOOR IN AUXILIARY ROOM - R1 |  | 2025-10-06 | 2025-10-11 |  | Anam | 40 | JC071025 26060
|  |  | E16221,33204 - ARRT OF FLOOR IN ENGINE ROOM - R1 |  | 2025-10-13 | 2025-10-18 |  | Anam | 40 | JC071025 26061
|  |  | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 2025-10-13 | 2025-10-17 |  | Yudi, Wiwid | 40 | JC071025 26062
|  |  | E10660,10404 - ACCOMMODATION ARRT 04 DECK - R2 |  | 2025-10-01 | 2025-10-03 |  | Rizal | 24 | JC071025 26063
|  |  | E26311,91301 - ML FOR PIPING SYSTEM PAINTING |  | 2025-10-16 | 2025-10-18 |  | Sutan | 24 | JC071025 26064
|  |  | E16311,91301 - PIPING SYSTEM PAINTING |  | 2025-10-20 | 2025-10-25 |  | Sutan | 40 | JC071025 26065
|  | KPI | 3D MODEL OUTFITTING PLTAL |  | 2025-10-06 | 2025-10-31 |  | Diva | 152 | JC091025 26164
|  | W304-305 | E11672,33104 - COVER INSPECTION HOLES - RA0 |  | 2025-10-13 | 2025-10-18 |  | Irene | 40 | JC141025 26384
|  |  | E21672,33400 - MAT. LIST FOR COVER INSPECTION HOLE - R5 |  | 2025-10-20 | 2025-10-21 |  | irene | 16 | JC141025 26385
|  |  | E16222,33401 - ARRT & DET. OF RAISED FLOOR - R1 |  | 2025-10-20 | 2025-10-23 |  | Bagus | 32 | JC141025 26386
|  |  | E26222,33401 - MAT. LIST FOR RAISED FLOOR - R1 |  | 2025-10-24 | 2025-10-25 |  | Bagus | 8 | JC141025 26387
|  |  | E15710,33101 - DETAIL OF RAS EQUIPMENT |  | 2025-10-13 | 2025-10-18 |  | Iyan | 40 | JC141025 26388
|  |  | E25710,33101 - MAT. LIST FOR DETAIL OF RAS EQUIPMENT |  | 2025-10-20 | 2025-10-22 |  | Iyan | 24 | JC141025 26389
|  | W306-307 | EZ221P.33200 - FOUND. OF EQUIP. IN BLOCK 221 (P) |  | 2025-10-13 | 2025-10-18 |  | Indra | 40 | JC141025 26390
|  |  | EZ221S.33200 - FOUND. OF EQUIP. IN BLOCK 221 (S) |  | 2025-10-20 | 2025-10-25 |  | Indra | 40 | JC141025 26391
|  |  | E2221P.33200 - MAT. LIST FOR FOUND. OF EQUIP. IN BLOCK 221 (P) |  | 2025-10-27 | 2025-10-29 |  | Indra | 24 | JC141025 26392
|  |  | E2221S.33200 - MAT. LIST FOR FOUND. OF EQUIP. IN BLOCK 221 (S) |  | 2025-10-30 | 2025-11-01 |  | Indra | 24 | JC141025 26393
|  |  | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 2025-10-27 | 2025-10-31 |  | Yudi, Wiwid | 40 | JC141025 26398
|  | W308 | E16221,33101 - ARRT FLOOR IN BOW THRUSTER - R2 |  | 2025-10-13 | 2025-10-18 |  | Bagus | 40 | JC141025 26394
|  |  | E16402,11400 - LIST OF ALU FURNITURE - R2 |  | 2025-10-16 | 2025-10-17 |  | Rizal | 16 | JC141025 26395
|  |  | E26402,11400 - MAT. LIST FOR ALU FURNITURE - R2 |  | 2025-10-20 | 2025-10-21 |  | Rizal | 16 | JC141025 26397
| 2025-10-21 | W304-305 | E16231,33405 - STAIRWAY IN ACCOMM. 02 DECK - R5 |  | 2025-10-22 | 2025-10-25 |  | Irene | 24 | JC211025 26691
|  |  | E16231,33403 - STAIRWAY IN ACCOMM. 1 DECK - R5 |  | 2025-10-27 | 2025-10-30 |  | Irene | 32 | JC211025 26692
|  |  | E16231,33404 - STAIRWAY IN ACCOMM. 01 DECK - R5 |  | 2025-10-31 | 2025-11-04 |  | Irene | 24 | JC211025 26693
|  |  | E22590,33200 - ML FOR SUPPORT EXHAUST - R2 |  | 2025-10-23 | 2025-10-25 |  | Iyan | 24 | JC211025 26694
|  |  | E15710,33101 - DETAIL OF RAS EQUIPMENT |  | 2025-10-27 | 2025-11-01 |  | Iyan | 40 | JC211025 26696
|  |  | E10660,10404 - ACCOMMODATION ARRT 03 DECK - R1 |  | 2025-10-22 | 2025-10-24 |  | Rizal | 24 | JC211025 26697
|  |  | E10660,10402 - ACCOMMODATION ARRT 1 DECK - R1 |  | 2025-10-27 | 2025-10-31 |  | Rizal | 40 | JC211025 26698
|  |  | E10660,10404 - ACCOMMODATION ARRT 02 DECK - R1 |  | 2025-10-27 | 2025-11-01 |  | Bagus | 40 | JC211025 26699
|  | W306-307 | E16640,11100 - DAMAGE CONTROL PLAN - R1 |  | 2025-10-27 | 2025-11-01 |  | Anam | 40 | JC211025 26705
|  |  | REVIEW RO-RO EQUIPMENT |  | 2025-10-27 | 2025-10-31 |  | Sutan | 40 | JC211025 26706
|  | W308 | EZ111S.33200 - FOUND. OF EQUIP IN BLOCK 111 (S) - RA3 |  | 2025-10-20 | 2025-10-25 |  | Anam | 40 | JC211025 26707
|  |  | E16221,33101 - ARRT FLOOR IN BOW THRUSTER - R2 |  | 2025-10-13 | 2025-10-18 |  | Bagus | 40 | JC211025 26708
| 5 Nop 2025 | W304-305 | 3D MODEL WINDOW WIPER |  | 3 Nop 2025 | 4 Nop 2025 |  | Bagus | 16 | JC051125 27270
|  |  | E16251,33400 - STEEL WALL OPENING FOR WINDOW - R2 |  | 5 Nop 2025 | 8 Nop 2025 |  | Bagus | 24 | JC051125 27271
|  |  | EZ6631,33110 - FOUND. OF EQUIP. IN ELECTRIC ROOM NO. 10 - R2 |  | 5 Nop 2025 | 8 Nop 2025 |  | Irene | 24 | JC051125 27272
|  |  | E11710,33100 - ARRT & DETAIL OF EQUIPMENT IN FORE MAST |  | 10 Nop 2025 | 15 Nop 2025 |  | Irene | 40 | JC051125 27273
|  |  | E14220,10100 - ARRT OF NAVIGATION & SIGNAL LIGHTS - R3 |  | 17 Nop 2025 | 22 Nop 2025 |  | Irene | 40 | JC051125 27274
|  |  | E21710,33100 - ML FOR DETAIL OF EQUIPMENT IN FORE MAST |  | 24 Nop 2025 | 26 Nop 2025 |  | Irene | 24 | JC051125 27275
|  |  | EZ3317,33100 - FOUND. OF SIDE LIGHT |  | 27 Nop 2025 | 2025-12-02 |  | Irene | 40 | JC051125 27276
|  |  | EZ6631,33104 - FOUND. OF EQUIP. IN ELECT. EQUIP. ROOM NO. 4 - R2 |  | 3 Nop 2025 | 4 Nop 2025 |  | Karina | 16 | JC051125 27277
|  |  | EZ6631,33120 - FOUND. OF EQUIP. IN ELECTRIC ROOM NO 4 - R3 |  | 5 Nop 2025 | 6 Nop 2025 |  | Karina | 16 | JC051125 27278
|  |  | EZ6631,33107 - FOUND. OF EQUIP. IN ELECT. EQUIP. ROOM NO. 7 - R3 |  | 7 Nop 2025 | 8 Nop 2025 |  | Karina | 16 | JC051125 27279
|  |  | EZ6632,33100 - FOUND. OF EQUIP. IN SWITCHBOARD ROOM FORE - R4 |  | 10 Nop 2025 | 11 Nop 2025 |  | Karina | 16 | JC051125 27280
|  |  | EZ6632,33101 - FOUND. OF EQUIP. IN SWITCHBOARD ROOM AFT - R3 |  | 12 Nop 2025 | 13 Nop 2025 |  | Karina | 16 | JC051125 27281
|  |  | EZ1801,33126 - ML FOR FOUND. OF EQUIP. IN STAIRWAY - R1 |  | 14 Nop 2025 | 15 Nop 2025 |  | Karina | 16 | JC051125 27282
|  |  | EZ6621,33100 - FOUND. OF EQUIP. IN BRIDGE |  | 17 Nop 2025 | 19 Nop 2025 |  | Karina | 24 | JC051125 27283
|  |  | EZ6626,33100 - FOUND. OF EQUIP. IN HELI CONTROL ROOM - R1 |  | 20 Nop 2025 | 22 Nop 2025 |  | Karina | 24 | JC051125 27284
|  |  | E41672,72103 - TP & TR OF BLAST DOOR |  | 3 Nop 2025 | 5 Nop 2025 |  | Sutan | 24 | JC051125 27285
|  |  | E11693,33100 - ARRT & DETAIL OF MONORAIL DOOR |  | 10 Nop 2025 | 15 Nop 2025 |  | Sutan | 24 | JC051125 27286
|  |  | E21693,33100 - ML FOR DETAIL OF MONORAIL DOOR |  | 17 Nop 2025 | 19 Nop 2025 |  | Sutan | 24 | JC051125 27287
|  |  | EZ5140,33201 - FOUND. OF EQUIP. IN AC ROOM NO 1 |  | 3 Nop 2025 | 5 Nop 2025 |  | Farhan | 24 | JC051125 27288
|  |  | EZ1801,33137 - FOUND. OF EQUIP. IN EXTINGUISHER ROOM |  | 6 Nop 2025 | 8 Nop 2025 |  | Farhan | 24 | JC051125 27291
|  |  | EZ241P,33200 - FOUND. OF EQUIP. BLOCK 241 (P) - RA1 |  | 10 Nop 2025 | 12 Nop 2025 |  | Farhan | 24 | JC061125 27296
|  |  | EZ211S,33200 - FOUND. OF EQUIP. BLOCK 211 (S) - R4 |  | 13 Nop 2025 | 15 Nop 2025 |  | Farhan | 24 | JC061125 27297
|  |  | EZ241S,33200 - FOUND. OF EQUIP. BLOCK 241 (S) - RA1 |  | 17 Nop 2025 | 19 Nop 2025 |  | Farhan | 24 | JC061125 27298
|  |  | EZ211P,33200 - FOUND. OF EQUIP. BLOCK 211 (P) - R5 |  | 20 Nop 2025 | 22 Nop 2025 |  | Farhan | 24 | JC061125 27299
|  |  | E15724,33201 - LIFT BEAM FOR DG IN E/R - R1 |  | 24 Nop 2025 | 26 Nop 2025 |  | Farhan | 24 | JC061125 27316
|  |  | E15724,33202 - LIFT BEAM 2T FOR M/E - R1 |  | 27 Nop 2025 | 29 Nop 2025 |  | Farhan | 24 | JC061125 27317
|  |  | E16032,32301 - ARRT OF CBRN SIGN - R1 |  | 3 Nop 2025 | 8 Nop 2025 |  | Dinata | 40 | JC061125 27318
|  |  | E16135,33300 - ARRT & DETAIL OF PORTABLE AWNING - R1 |  | 10 Nop 2025 | 13 Nop 2025 |  | Dinata | 24 | JC061125 27319
|  |  | E26135,33300 - ML FOR DETAIL OF PORTABLE AWNING - R1 |  | 14 Nop 2025 | 15 Nop 2025 |  | Dinata | 16 | JC061125 27320
|  |  | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 10 Nop 2025 | 14 Nop 2025 |  | Iyan, Yudi, Wiwid | 40 | JC061125 27321
|  |  | 3D WINDOW WIPER |  | 3 Nop 2025 | 5 Nop 2025 |  | Bagus | 24 | JC061125 27322
|  |  | E16251,33400 - STEEL WALL OPENING FOR WINDOW - R2 |  | 6 Nop 2025 | 8 Nop 2025 |  | Bagus | 24 | JC061125 27323
|  |  | E10660,10403 - ACCOMM. ARRT 01 DECK - R1 |  | 10 Nop 2025 | 15 Nop 2025 |  | Bagus | 40 | JC061125 27324
|  |  | E16251,11400 - WINDOW PLAN - R3 |  | 10 Nop 2025 | 12 Nop 2025 |  | Rizal | 24 | JC061125 27325
|  |  | E16440.33400 - STEEL COAMING FOR WET AREA - R1 |  | 17 Nop 2025 | 22 Nop 2025 |  | Rizal | 40 | JC061125 27327
|  | W306-307 | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 17 Nop 2025 | 22 Nop 2025 |  | Dinata, Iyan, Yudi, Wiwid | 40 | JC061125 27329
|  |  | EZ122S.33200 - FOUND. OF EQUIP. IN BLOCK 122 (S) - R2 |  | 3 Nop 2025 | 8 Nop 2025 |  | Anam | 40 | JC061125 27330
|  |  | 3D MODEL LCU |  | 3 Nop 2025 | 28 Nop 2025 |  | Diva | 160 | JC071125 27348
|  |  | EVATEK MEDICAL EQUIPMENT |  | 3 Nop 2025 | 4 Nop 2025 |  | Iyan | 16 | JC071125 27349
|  |  | E16000,75101 - MAIN EQUIPMENT LIST LCU FOR HULL PART |  | 5 Nop 2025 | 8 Nop 2025 |  | Iyan | 24 | JC071125 27353
|  |  | EZ611P.33200 - FOUND. OF EQUIP. IN BLOCK 611 (P) - R1 |  | 3 Nop 2025 | 5 Nop 2025 |  | Indra | 24 | JC071125 27354
|  |  | EZ611S.33200 - FOUND. OF EQUIP. IN BLOCK 611 (S) - R1 |  | 6 Nop 2025 | 8 Nop 2025 |  | Indra | 24 | JC071125 27355
|  |  | EZ612P.33200 - FOUND. OF EQUIP. IN BLOCK 612 (P) - R1 |  | 10 Nop 2025 | 15 Nop 2025 |  | Indra | 40 | JC071125 27361
|  |  | EZ612S.33200 - FOUND. OF EQUIP. IN BLOCK 612 (S) - R1 |  | 17 Nop 2025 | 22 Nop 2025 |  | Indra | 40 | JC071125 27362
|  |  | EZ231P.33200 - FOUND. OF EQUIP. IN BLOCK 231 (P) - R2 |  | 24 Nop 2025 | 29 Nop 2025 |  | Indra | 40 | JC071125 27363
|  |  | E16011,33400 - ARRT OF MISCELLANEOUS - R1 |  | 3 Nop 2025 | 7 Nop 2025 |  | Rizal | 40 | JC071125 27364
|  |  | E16221,33207 - ARRT OF PLATFORM IN ENG. CASING - R1 |  | 10 Nop 2025 | 22 Nop 2025 |  | Anam | 80 | JC071125 27437
|  | W308 | E11672,33100 - ARRT OF WTD SLIDING DOOR - R3 |  | 6 Nop 2025 | 8 Nop 2025 |  | Sutan | 24 | JC071125 27365
|  |  | CEK GAMBAR, EVALUASI TEKINS & KOORDINASI TEKNIS |  | 3 Nop 2025 | 7 Nop 2025 |  | Yudi, Wiwid | 40 | JC071125 27366
|  |  | E16311,91302 - SHOP PRIMER FOR GALV. PIPE (FOT 3 & FO SETL TK) CALC |  | 24 Nop 2025 | 26 Nop 2025 |  | Sutan | 24 | JC071125 27367
|  |  | E26311,91302 - ML FOR SHOP PRIMER FOR GALV. PIPE (FOT 3 & FO SETL TK) CALC |  | 27 Nop 2025 | 28 Nop 2025 |  | Sutan | 16 | JC071125 27368
|  |  | CEK GAMBAR, EVALUASI TEKINS & KOORDINASI TEKNIS |  | 24 Nop 2025 | 28 Nop 2025 |  | Dinata, Iyan, Yudi, Wiwid | 40 | JC071125 27369
|  |  | E16250,11400 - WINDOW PLAN - R5 |  | 17 Nop 2025 | 18 Nop 2025 |  | Bagus | 16 | JC071125 27370
|  |  | E16251,33400 - STEEL WALL OPENING FOR WINDOW - R3 |  | 19 Nop 2025 | 22 Nop 2025 |  | Bagus | 24 | JC071125 27371
|  |  | E26250,11400 - ML FOR WINDOW - R5 |  | 13 Nop 2025 | 14 Nop 2025 |  | Rizal | 16 | JC071125 27374
|  | E250N002 | E11674,11100 - ARRT & DETAIL OF MANHOLE & VL - R1 |  | 20 Nop 2025 | 22 Nop 2025 |  | Sutan | 24 | JC061125 27300 | proyek 304
|  | W304-305 | E13210,33100 - DRUM FOR SHORE CONNECTION - R4 |  | 24 Nop 2025 | 26 Nop 2025 |  | Anam | 24 | JC201125 27934
|  |  | E16222,33400 - ARRT & DET. OF MPFF - R1 |  | 24 Nop 2025 | 29 Nop 2025 |  | Bagus | 40 | JC201125 27935
|  |  | E16022,33401 - SHIP NAME BOARD |  | 24 Nop 2025 | 28 Nop 2025 |  | Rizal | 40 | JC201125 27936
|  |  | EZ6621,33100 - FOUND. OF EQUIP. IN BRIDGE (03EA0) - R1 |  | 24 Nop 2025 | 29 Nop 2025 |  | Karina | 40 | JC201125 27937
|  | W306-307 | EZ221S.33200 - FOUND. OF EQUIP. IN BLOCK 221 (S) - RA2 |  | 27 Nop 2025 | 29 Nop 2025 |  | Anam | 24 | JC201125 27938
| 2025-12-01 | W304-305 | E96000.92102 - WEIGHT CONTROL (KB04) |  | 2025-12-01 | 2025-12-06 |  | Karina | 40 | JC011225 28474
|  |  | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 2025-12-01 | 2025-12-06 |  | Iyan, Dinata | 40 | JC011225 28475
|  |  | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 2025-12-01 | 2025-12-05 |  | Yudi, Wiwid | 40 | JC021225 28506
|  | W306-307 | E16311,01301 - LIST OF PAINT FOR SPARE |  | 2025-12-01 | 2025-12-04 |  | Indra | 32 | JC011225 28494
|  |  | E26311,01301 - MAT. LIST FOR PAINT FOR SPARE |  | 2025-12-05 | 2025-12-06 |  | Indra | 18 | JC011225 28495
|  |  | EZ221P.33200 - FOUND. OF EQUIP. IN BLOCK 221 (P) - RA1 |  | 2025-12-01 | 2025-12-03 |  | Anam | 24 | JC021225 28507
|  |  | E96000,92101 - WEIGHT KONTROL (KB03) |  | 2025-12-08 | 2025-12-13 |  | Dinata | 40 | JC021225 28508
|  |  | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 2025-12-08 | 2025-12-13 |  | Iyan, Yudi, Wiwid | 40 | JC021225 28509
|  | W308 | EZ1802,33101 - FOUND. OF EQUIP. IN EXP. DECK (4C41) - 05 DECK |  | 2025-12-04 | 2025-12-10 |  | Anam | 40 | JC021225 28534
|  |  | E21802,33101 - ML FOR FOUND. OF EQUIP. IN EXP. DECK (4C41) - 05 DECK |  | 2025-12-11 | 2025-12-13 |  | Anam | 24 | JC021225 28537
|  |  | EZ1802,33102 - FOUND. OF EQUIP. IN EXP. DECK (4C32) - 05 DECK |  | 2025-12-15 | 2025-12-20 |  | Anam | 40 | JC021225 28538
|  |  | E21802,33102 - ML FOR FOUND. OF EQUIP. IN EXP. DECK (4C32) - 05 DECK |  | 2025-12-22 | 2025-12-24 |  | Anam | 24 | JC021225 28539 | extend tgl 25, extend JO (32)
|  |  | E16311,01301 - LIST OF PAINT FOR SPARE |  | 2025-12-01 | 2025-12-03 |  | Sutan | 24 | JC021225 28540
|  |  | E26311,01301 - ML FOR LIST OF PAINT FOR SPARE |  | 2025-12-04 | 2025-12-05 |  | Sutan | 16 | JC021225 28541
|  |  | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 2025-12-15 | 2025-12-20 |  | Dinata, Iyan, Yudi, Wiwid | 40 | JC021225 28542
| 2025-12-05 | W304-305 | 3D MODEL TEMPORARY COVER ON FORE MAST |  | 2025-12-03 | 2025-12-04 |  | Irene | 16 | JC051225 28624
|  |  | E11672,33104 - COVER INSPECTION HOLE - RA1 |  | 2025-12-05 | 2025-12-06 |  | Irene | 16 | JC051225 28625
|  |  | E21672,33104 - ML FOR COVER INSPECTION HOLE - RA0 |  | 2025-12-08 | 2025-12-08 |  | Irene | 8 | JC051225 28626
|  |  | E16221,33200 - ARRT OF FLOOR IN FWD E/R - R1 |  | 2025-12-01 | 2025-12-06 |  | Farhan | 40 | JC051225 28627
|  |  | E16221,33202 - ARRT OF FLOOR IN AFT LOWER E/R - R1 |  | 2025-12-08 | 2025-12-13 |  | Farhan | 40 | JC051225 28628
|  |  | EZ432P.33200 - FOUND. OF EQUIP. IN BLOCK 432 (P) - RA3 |  | 2025-12-15 | 2025-12-16 |  | Farhan | 16 | JC051225 28629
|  |  | EZ212P.33200 - FOUND. OF EQUIP. IN BLOCK 212 (P) - RA4 |  | 2025-12-17 | 2025-12-20 |  | Farhan | 24 | JC051225 28630
|  |  | EZ232S,33200 - FOUND. OF EQUIP. IN BLOCK 232 (S) - RA2 |  | 2025-12-22 | 2025-12-31 |  | Farhan | 56 | JC051225 28631
|  |  | 3D MODEL ACCOMMODATION FURNITURE ALL DECK |  | 2025-12-01 | 2025-12-20 |  | Bagus | 120 | JC051225 28632
|  |  | E16000,10400 - COMPARTMENT NUMBERING SYSTEM |  | 2025-12-01 | 2025-12-05 |  | Rizal | 40 | JC051225 28633
|  |  | E16022,33401 - SHIP NAME BOARD |  | 2025-12-08 | 2025-12-12 |  | Rizal | 40 | JC051225 28634
|  |  | E10660,10403 - ACCOMM. ARRT OF 01 DECK - R1 |  | 2025-12-15 | 2025-12-19 |  | Rizal | 40 | JC051225 28635
|  |  | E10660,10404 - ACCOMM. ARRT OF 02 DECK - R1 |  | 2025-12-22 | 2025-12-26 |  | Rizal | 32 | JC051225 28636
|  |  | E10660,10405 - ACCOMM. ARRT OF 03 DECK - R1 |  | 2025-12-29 | 2025-12-31 |  | Rizal | 24 | JC051225 28637
|  |  | E11693,33100 - ARRT & DETAIL OF MONORAIL DOOR - R1 |  | 2025-12-08 | 2025-12-12 |  | Sutan | 40 | JC051225 28638
|  |  | E11672,33107 - ENCLOSURE ROOM FOR BLAST TEST OF BLAST DOOR - R1 |  | 2025-12-15 | 2025-12-17 |  | Sutan | 24 | JC051225 28639
|  |  | E21672,33107 - ML FOR ENCLOSURE ROOM FOR BLAST TEST OF BLAST DOOR - R1 |  | 2025-12-18 | 2025-12-19 |  | Sutan | 16 | JC051225 28642
|  |  | E41672,72103 - TP & TR OF BLAST DOOR - R1 |  | 2025-12-22 | 2025-12-24 |  | Sutan | 24 | JC051225 28643 | extend tgl 26, extend JO (40)
|  | LCU | E11674,32100 - ARRT & DETAIL OF MANHOLE & VL |  | 2025-12-08 | 2025-12-11 |  | Karina | 32 | JC051225 28644
|  |  | E21674,32100 - ML FOR OF MANHOLE & VL |  | 2025-12-12 | 2025-12-13 |  | Karina | 16 | JC051225 28645
|  |  | E16132,32100 - ARRT & DETAIL OF CAR LASHING |  | 2025-12-15 | 2025-12-18 |  | Karina | 32 | JC051225 28646
|  |  | E26132,32100 - ML FOR CAR LASHING |  | 2025-12-19 | 2025-12-20 |  | Karina | 16 | JC051225 28647
|  |  | E16221,33200 - ARRT & DETAIL OF FLOOR IN E/R |  | 2025-12-22 | 2025-12-27 |  | Iyan | 32 | JC051225 28648
|  |  | E16233,33200 - ARRT & DETAIL OF LADDER IN E/R |  | 2025-12-29 | 2025-12-31 |  | Iyan | 24 | JC051225 28649
|  | W306-307 | EZ221P. 33200 - FOUND. OF EQUIP. IN BLOCK 221 (P) - RA1 |  | 2025-12-08 | 2025-12-13 |  | Indra | 40 | JC051225 28650
|  |  | EZ221S.33200 - FOUND. OF EQUIP. IN BLOCK 221 (S) - RA1 |  | 2025-12-15 | 2025-12-20 |  | Indra | 40 | JC051225 28651
|  |  | EZ231P.33200 - FOUND. OF EQUIP. IN BLOCK 231 (P) - R4 |  | 2025-12-22 | 2025-12-27 |  | Indra | 32 | JC051225 28652
|  |  | EZ231S,33200 - FOUND. OF EQUIP. IN BLOCK 231 (S) - RA1 |  | 2025-12-29 | 2025-12-31 |  | Indra | 24 | JC051225 28653
|  | W308 | EZ4200,33100 - FOUND. OF EQUIP. IN GYRO ROOM |  | 2025-12-09 | 2025-12-11 |  | Irene | 24 | JC051225 28654
|  |  | EZ6631,33108 - FOUND. OF EQUIP. IN ELECTRONIC ROOM NO. 8 |  | 2025-12-12 | 2025-12-13 |  | Irene | 16 | JC051225 28655
|  |  | EZ6631,33109 - FOUND. OF EQUIP. IN ELECTRONIC ROOM NO. 9 |  | 2025-12-15 | 2025-12-17 |  | Irene | 24 | JC051225 28656
|  |  | EZ6631,33103 - FOUND. OF EQUIP. IN ELECTRONIC ROOM NO. 3 |  | 2025-12-18 | 2025-12-20 |  | Irene | 24 | JC051225 28657
|  |  | EZ6631,33101 - FOUND. OF EQUIP. IN ELECTRONIC ROOM NO. 1 |  | 2025-12-22 | 2026-01-03 |  | Irene | 64 | JC081225 28758
| 2025-12-22 | W304-305 | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 2025-12-22 | 2025-12-24 |  | Yudi, Wiwid | 24 | JC221225 29318
|  | W304-305 | CEK GAMBAR, EVALUASI TEKNIS & KOORDINASI TEKNIS |  | 2025-12-29 | 2026-01-02 |  | Yudi, Wiwid | 32 | JC221225 29319
|  | LCU | E11672,32100 - ARRT & DETAIL OF ALUMINUM DOOR |  | 2025-12-22 | 2025-12-24 |  | Karina | 24 | JC221225 29320
|  |  | E21672,32100 - ML FOR ALUMINUM DOOR |  | 2025-12-25 | 2025-12-27 |  | Karina | 16 | JC221225 29321
|  |  | E16350,11301 - INSULATION PLAN |  | 2025-12-22 | 2025-12-24 |  | Dinata | 24 | JC221225 29322
|  |  | E16350,11300 - FIRE PROTECTION |  | 2025-12-29 | 2026-01-02 |  | Dinata | 32 | JC221225 29323
|  |  | E16250,11400 - WINDOW PLAN |  | 2025-12-22 | 2025-12-24 |  | Bagus | 24 | JC221225 29324
|  |  | E26250,11400 - ML FOR WINDOW |  | 2025-12-25 | 2025-12-27 |  | Bagus | 16 | JC221225 29325
|  | W311 | E11672,32100 - ARRT & DETAIL OF ALUMINUM DOOR |  | 2025-12-29 | 2026-01-02 |  | Karina | 32 | JC221225 29326
|  |  | E16250,11400 - WINDOW PLAN |  | 2025-12-29 | 2026-01-02 |  | Bagus | 32 | JC221225 29327
|  | W308 | E11693,33100 - ARRT & DETAIL OF MONORAIL DOOR |  | 2025-12-29 | 2026-01-02 |  | Sutan | 32 | JC221225 29347
|  |  | EZ222P,33200 - FOUND. OF EQUIP. BLOCK 222 (P) - R5 |  | 2025-12-26 | 2025-12-27 |  | Anam | 16 | JC221225 29420
|  |  | EZ112S.33200 - FOUND. OF EQUIP BLOCK 112 (S) - R2 |  | 2025-12-29 | 2026-01-02 |  | Anam | 32 | JC221225 29421
2026-01-01
| 2026-01-06 | W304-305 | Cek gambar, evaluasi teknis & koordinasi teknis |  | 2026-01-02 | 2026-01-31 |  | Yudi, Wiwid | 40 | JC060126 29983
|  |  | Menyelesaikan gambar pondasi Frigate |  | 2026-01-02 | 2026-01-31 |  | Karina, Irene, Farhan | 40 | JC060126 29984
|  |  | Menyelesaikan gambar yard plan & prod. drawing Frigate |  | 2026-01-02 | 2026-01-31 |  | Sutan | 56 | JC060126 30003
|  |  | Menyelesaikan gambar yard plan & prod. drawing Frigate |  | 2026-01-02 | 2026-01-31 |  | Dinata | 32 | JC060126 30004
|  | W306-307 | Cek gambar, evaluasi teknis & koordinasi teknis proyek LDP & LCU |  | 2026-01-02 | 2026-01-31 |  | Yudi, Wiwid | 40 | JC060126 30005
|  |  | Menyelesaikan gambar yard plan & production drawing LCU |  | 2026-01-02 | 2026-01-31 |  | Karina | 96 | JC060126 30006
|  |  | Menyelesaikan gambar yard plan & prod. drawing LDP & LCU |  | 2026-01-02 | 2026-01-31 |  | Dinata, Sutan | 64 | JC060126 30007
|  |  | Menyelesaikan gambar yard plan & prod. drawing LDP & LCU |  | 2026-01-02 | 2026-01-31 |  | Iyan | 128 | JC060126 30008
|  |  | Menyelesaikan gambar yard plan & prod. drawing LDP & LCU |  | 2026-01-02 | 2026-01-31 |  | Indra | 136 | JC060126 30009
|  |  | Menyelesaikan gambar yard plan & prod. drawing LCU |  | 2026-01-02 | 2026-01-31 |  | Farhan | 68 | JC060126 30010
|  |  | Menyelesaikan gambar yard plan & prod. drawing LCU |  | 2026-01-02 | 2026-01-31 |  | Bagus, Rizal | 88 | JC060126 30011
|  | W3008 | Cek gambar, evaluasi teknis & koordinasi teknis |  | 2026-01-02 | 2026-01-31 |  | Yudi, Wiwid, Dinata | 40 | JC060126 30012
|  |  | Menyelesaikan gambar pondasi Al Maryah |  | 2026-01-02 | 2026-01-31 |  | Anam | 176 | JC060126 30013
|  |  | Menyelesaikan gambar pondasi AL Maryah |  | 2026-01-02 | 2026-01-31 |  | Irene | 136 | JC060126 30014
|  |  | menyelesaikan gambar yard plan & prod. drawing AL Maryah |  | 2026-01-02 | 2026-01-31 |  | Sutan | 56 | JC060126 30015
|  |  | Menyelesaikan gambar yard plan & prod. drawing Al Maryah |  | 2026-01-02 | 2026-01-31 |  | Iyan | 48 | JC060126 30016
|  | CORP2026 | Menyelesaikan gambar yard plan & prod. drawing KSSR |  | 2026-01-02 | 2026-01-31 |  | Bagus, Rizal | 88 | JC060126 30026
|  |  | Cek gambar, evaluasi teknis & koordinasi teknis KSSR |  | 2026-01-02 | 2026-01-31 |  | Yudi, Wiwid | 40 | JC060126 30027
|  |  | Menyelesaikan gambar yard plan & prod. drawing KSSR |  | 2026-01-02 | 2026-01-31 |  | Karina, Dinata, Indra | 40 | JC060126 30028
|  |  | Menyelesaikan gambar yard plan & prod. drawing KSSR |  | 2026-01-02 | 2026-01-31 |  | Farhan | 68 | JC060126 30029 |  | NO JC RAMADHAN HOURS
2026-02-01
|  | W304-305 | Cek gambar, evaluasi teknis & koordinasi teknis |  | 1 Febr 2026 | 28 Febr 2026 |  | Yudi, Wiwid | 36 | JC070126 30057 | jc utk 1-18 februari 2026 jo sisa 14 jam | JC180226 31796 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar-gambar pondasi |  | 1 Febr 2026 | 28 Febr 2026 |  | Irene, Karina | 40 | JC070126 30058 | jc utk 1-18 februari 2026 jo sisa 16 jam | JC180226 31798 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar-gambar yard plan & prod. drawing |  | 1 Febr 2026 | 28 Febr 2026 |  | Farhan, Sutan | 56 | JC070126 30059 | jc utk 1-18 februari 2026 jo sisa 21 jam | JC180226 31799 | jc utk 19 - 28 februari 2026
|  | W306-307 | Cek gambar, evaluasi teknis & koordinasi teknis LDP & LCU |  | 1 Febr 2026 | 28 Febr 2026 |  | Yudi, Wiwid | 36 | JC070126 30060 | jc utk 1-18 februari 2026 jo sisa 14 jam | JC180226 31800 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  | 1 Febr 2026 | 28 Febr 2026 |  | Farhan, Sutan | 56 | JC070126 30066 | jc utk 1-18 februari 2026 jo sisa 21 jam | JC180226 31801 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing LDP & LCU |  | 1 Febr 2026 | 28 Febr 2026 |  | Dinata, Iyan | 96 | JC070126 30067 | jc utk 1-18 februari 2026 jo sisa 36 jam | JC180226 31803 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing LDP & LCU |  | 1 Febr 2026 | 28 Febr 2026 |  | Indra | 120 | JC090126 30112 | jc utk 1-18 februari 2026 jo sisa 40 jam | JC180226 31804 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing LCU |  | 1 Febr 2026 | 28 Febr 2026 |  | Rizal | 72 | JC090126 30113 | jc utk 1-18 februari 2026 jo sisa 28 jam | JC190226 31811 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing LCU |  | 1 Febr 2026 | 28 Febr 2026 |  | Bagus | 80 | JC090126 30114 | jc utk 1-18 februari 2026 jo sisa 25 jam | JC190226 31812 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing LCU |  | 1 Febr 2026 | 28 Febr 2026 |  | Karina | 60 | JC090126 30115 | jc utk 1-18 februari 2026 jo sisa 20 jam | JC190226 31813 | jc utk 19 - 28 februari 2026
|  | W308 | Cek gambar, evaluasi teknis & koordinasi teknis |  | 1 Febr 2026 | 28 Febr 2026 |  | Yudi, Wiwid | 36 | JC090126 30122 | jc utk 1-18 februari 2026 jo sisa 14 jam | JC190226 31823 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar-gambar pondasi |  | 1 Febr 2026 | 28 Febr 2026 |  | Anam | 160 | JC090226 31361 | jc utk 1-18 februari 2026 jo sisa 56 jam | JC190226 31824 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar-gambar pondasi |  | 1 Febr 2026 | 28 Febr 2026 |  | Irene | 120 | JC090226 31362 | jc utk 1-18 februari 2026 jo sisa 40 jam | JC190226 31825 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  | 1 Febr 2026 | 28 Febr 2026 |  | Dinata, Iyan | 32 | JC090226 31364 | jc utk 1-18 februari 2026 jo sisa 16 jam | JC190226 31828 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  | 1 Febr 2026 | 28 Febr 2026 |  | Sutan | 48 | JC090226 31365 | jc utk 1-18 februari 2026 jo sisa 16 jam | JC190226 31829 | jc utk 19 - 28 februari 2026
|  | W311 | Cek gambar, evaluasi teknis & koordinasi teknis |  | 1 Febr 2026 | 28 Febr 2026 |  | Yudi, Wiwid | 36 | JC020226 31095 | jc utk 1-18 februari 2026 jo sisa 14 jam | JC190226 31830 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing KSSR |  | 1 Febr 2026 | 28 Febr 2026 |  | Karina | 60 | JC020226 31096 | jc utk 1-18 februari 2026 jo sisa 15 jam | JC190226 31831 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing KSSR |  | 1 Febr 2026 | 28 Febr 2026 |  | Dinata, Iyan | 32 | JC020226 31097 | jc utk 1-18 februari 2026 jo sisa 16 jam | JC190226 31833 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing KSSR |  | 1 Febr 2026 | 28 Febr 2026 |  | Farhan | 48 | JC020226 31098 | jc utk 1-18 februari 2026 jo sisa 16 jam | JC190226 31834 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing KSSR |  | 1 Febr 2026 | 28 Febr 2026 |  | Indra | 40 | JC020226 31099 | jc utk 1-18 februari 2026 jo sisa 16 jam | JC190226 31835 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gambar yard plan & prod. drawing KSSR |  | 1 Febr 2026 | 28 Febr 2026 |  | Rizal | 72 | JC020226 31101 | jc utk 1-18 februari 2026 jo sisa 28 jam | JC190226 31836 | jc utk 19 - 28 februari 2026
|  |  | Menyelesaikan gamabr yard plan & prod. drawing KSSR |  | 1 Febr 2026 | 28 Febr 2026 |  | Bagus | 80 | JC020226 31102 | jc utk 1-18 februari 2026 jo sisa 25 jam | JC190226 31837 | jc utk 19 - 28 februari 2026
2026-03-01
| 2026-03-02 | W304-305 | Cek gambar, evaluasi teknis & koordinasi teknis |  | 2026-03-02 | 2026-03-17 |  | Yudi , Wiwid | 21 | JC020326 32284 | JC260326 33187
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Dinata, Sutan, Karin, Iyan, | 28 | JC020326 32286 | JC260326 33188
[8 empty] | Farhan, Rizal | 28 | JC020326 32287 | JC260326 33189
|  | W306-307 | Cek gambar, evaluasi teknis & koordinasi teknis LDP & LCU |  | 2026-03-02 | 2026-03-17 |  | Yudi, Wiwid | 28 | JC020326 32302 | JC260326 33190
|  |  | Menyelesaikan gambar yard plan & prod. drawing LDP & LCU |  |  |  |  | Dinata, Indra, Sutan , Karin | 28 | JC020326 32306 | JC260326 33191
[8 empty] | Iyan, Farhan, Rizal | 28 | JC020326 32308 | JC260326 33192
|  | W308 | Cek gambar, evaluasi teknis & koordinasi teknis |  | 2026-03-02 | 2026-03-17 |  | Yudi, Wiwid | 28 | JC020326 32312 | JC260326 33193
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Dinata, Indra, Sutan , Karin | 28 | JC020326 32318 | JC260326 33194
[8 empty] | Iyan, Farhan, Rizal | 28 | JC020326 32319 | JC260326 33195
[8 empty] | Irene, Anam | 84 | JC020326 32320 | JC260326 33196
[8 empty] | Bagus | 42 | JC020326 32321 | JC260326 33197
|  | W311 | Cek gambar, evaluasi teknis & koordinasi teknis |  | 2026-03-02 | 2026-03-17 |  | Yudi, Wiwid | 21 | JC020326 32324 | JC260326 33198
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Indra | 28 | JC020326 32329 | JC260326 33199
[8 empty] | Bagus | 42 | JC020326 32331 | JC260326 33200
2026-04-01
| 2026-04-01 | W304-305 | Menyelesaikan gambar yard plan & prod. drawing |  | 2026-04-01 | 2026-04-30 |  | Iyan, Dinata, Rizal, Farhan | 40 | JC010426 33505
[8 empty] | Karina, Sutan | 80 | JC010426 33506
|  |  | Cek gambar, evaluasi teknis & koordinasi teknis |  |  |  |  | Yudi, Wiwid | 40 | JC010426 33507
|  | W306-307 | Menyelesaikan gambar yard plan & prod. drawing |  | 2026-04-01 | 2026-04-30 |  | Karina, Dinata, Indra, Rizal, Iyan, Farhan | 80 | JC010426 33508
[8 empty] | Bagus | 40 | JC010426 33509
|  |  | Cek gambar, evaluasi teknis & koordinasi teknis |  |  |  |  | Yudi, Wiwid | 40 | JC010426 33512
|  | W308 | Menyelesaikan gambar yard plan & prod. drawing |  | 2026-04-01 | 2026-04-30 |  | Anam, Irene | 160 | JC010426 33513
[8 empty] | Iyan, Bagus, Sutan, Dinata, Rizal, Farhan | 40 | JC010426 33514
|  |  | Cek gambar, evaluasi teknis & koordinasi teknis |  |  |  |  | Yudi, Wiwid | 40 | JC010426 33515
|  | W311 | Menyelesaikan gambar yard plan &prod. drawing |  | 2026-04-01 | 2026-04-30 |  | Bagus | 80 | JC010426 33516
|  |  | Cek gambar, evaluasi teknis & koordinasi teknis |  |  |  |  | Yudi, Wiwid | 40 | JC010426 33517
| 2026-04-06 | W306-307 | Menyelesaikan gambar yard plan &prod. drawing |  | 2026-04-01 | 2026-04-30 |  | Sutan | 40 | JC060426 33662
|  | W308 | Menyelesaikan gambar yard plan &prod. drawing |  | 2026-04-01 | 2026-04-30 |  | Indra | 80 | JC060426 33661
|  | W306-307 | Menyelesaikan gambar yard plan &prod. drawing |  | 2026-04-01 | 2026-04-30 |  | Indra | 32 | JC290426 34554
2026-05-01
| 2026-05-01 | W304-305 | Menyelesaikan gambar yard plan & prod. drawing |  | 2026-05-01 | 2026-05-31 |  | Karina, Farhan, Sutan | 120 | JC300426 34617
|  | W306-307 | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Dinata, Indra | 80 | JC300426 34618
|  | W308 | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Iyan, Anam, Irene | 120 | JC300426 34619
[8 empty] | Karina, Sutan, Dinata | 40 | JC300426 34620
| 2026-05-11 | M312 | Cek gambar, evaluasi teknis & koordinasi teknis |  |  |  |  | Yudi, Wiwid | 30 | JC110526 34924
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Rizal, Bagus | 60 | JC110526 34925
[8 empty] | Indra | 50 | JC110526 34926
[8 empty] | Farhan, Dinata | 20 | JC110526 34927
|  | W304-305 | Cek gambar, evaluasi teknis & koordinasi teknis |  |  |  |  | Yudi, Wiwid | 30 | JC110526 34928
|  | W306-307 | Cek gambar, evaluasi teknis & koordinasi teknis |  |  |  |  | Yudi, Wiwid, Iyan | 30 | JC110526 34929
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Rizal, Bagus, Anam, Irene | 40 | JC110526 34930
|  | W308 | Cek gambar, evaluasi teknis & koordinasi teknis |  |  |  |  | Yudi, Wiwid | 40 | JC110526 34931
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Rizal, Bagus | 40 | JC110526 34932
2026-06-01
| 2026-06-01 | M312 | Cek gambar, evatek & koordinasi teknik |  | 2026-06-01 | 2026-06-30 |  | Yudi, Wiwid | 40 | JC020626 35745
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Iyan, Karina, Indra, Rizal, Bagus, Sutan | 60 | JC020626 35747
[8 empty] | Farhan, Irene, Dinata | 40 | JC020626 35746
|  | W304-305 | Cek gambar, evatek & koordinasi teknik |  |  |  |  | Yudi, Wiwid | 20 | JC020626 35748
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Karina | 60 | JC020626 35749
[8 empty] | Sutan | 30 | JC020626 35750
[8 empty] | Farhan, Dinata | 40 | JC020626 35751
|  | W306-307 | Cek gambar, evatek & koordinasi teknik |  |  |  |  | Yudi, Wiwid | 20 | JC020626 35754
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Farhan, Anam, Dinata | 40 | JC020626 35752
[8 empty] | Indra | 60 | JC020626 35753
|  | W308 | Cek gambat, evatek & koordinasi teknik |  |  |  |  | Yudi, Wiwid | 40 | JC020626 35755
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Iyan | 80 | JC020626 35757
[8 empty] | Bagus | 60 | JC020626 35758
[8 empty] | Sutan, Dinata, Rizal | 40 | JC020626 35760
[8 empty] | Anam, Irene | 160 | JC020626 35761
|  | Corp2026 | Cek gambar, evatek & koordinasi teknik |  |  |  |  | Yudi, Wiwid | 40 | JC020626 35762
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Iyan | 60 | JC020626 35764
[8 empty] | Karina, Sutan, Farhan, Rizal, Bagus, Indra | 80 | JC020626 35766
[8 empty] | Dinata | 40 | JC020626 35767
2026-07-01
| 2026-07-06 | M312 | Cek gambar, evatek dan koordinasi teknik |  | 2026-07-01 | 2026-07-31 |  | Dinata, Wiwid | 64 | JC070726 37284
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Bagus, Indra | 160 | JC070726 37285
[8 empty] | Rizal | 64 | JC070726 37286
|  | W306-307 | Cek gambar, evatek & koordinasi teknis |  |  |  |  | Wiwid Dinata | 40 | JC070726 37287
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Rizal | 40 | JC070726 37288
|  | W308 | Cek gambar, evatek & koordinasi teknis |  |  |  |  | Wiwid Dinata | 40 | JC070726 37292
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Rizal | 40 | JC070726 37293
|  | CORP2026 | Cek gambar, evatek & koordinasi teknis |  |  |  |  | Wiwid Dinata | 40 | JC070726 37294
|  |  | Menyelesaikan gambar yard plan & prod. drawing |  |  |  |  | Bagus, Indra | 88 | JC070726 37295
[8 empty] | Rizal | 40 | JC070726 37296
AGUST 2026
| 6 Agust 2026 | W304-305 | E16401.01400 - Textille Fixture - Evatek |  | 1 Agust 2026 | 31 Agust 2026 |  | Wiwid | 40 | JC110826 38784
|  | W306-307 | E86254.51400 - Window Wiper & CVS - Cek approval drawing | [5 empty] | 24 | JC110826 38785
|  | W308 | E16370.11400 - Joiner Work - Cek approval drawing | [5 empty] | 40 | JC110826 38786
|  |  | E16442.33401 - Detail of Unit Toilet - cek material | [5 empty] | 24 | JC110826 38787
|  | W304-305 | E16000.37100 - List of Inventory Hull Part - R3 |  |  |  |  | Dinata | 24 | JC110826 38788
|  |  | E26000.37100 - ML for Inventory - R2 | [5 empty] | 16 | JC110826 38793
|  | W308 | E26352.11301 - ML for Pin Insulation - R2 | [5 empty] | 8 | JC110826 38795
|  |  | E16000.37100 - List of Inventory Hull Part - R1 | [5 empty] | 40 | JC110826 38796
|  | M312 | E80770.50300 - LSA & Fire Fighting Equipment - Evatek | [5 empty] | 32 | JC110826 38797
|  | W304-305 | E16315.01300 - Painting Schedule - FP |  |  |  |  | Indra | 24 | JC110826 38798
|  | M312 | E16315.01300 - Painting Schedule - R1 | [5 empty] | 24 | JC110826 38799
|  |  | E26315.01300 - ML for Paint - R1 | [5 empty] | 6 | JC110826 38800
|  | M313 | E16331.33300 - Arrt of Alu Anode | [5 empty] | 24 | JC110826 38801
|  |  | E26331.33300 - ML for Alu Anode | [5 empty] | 8 | JC110826 38802
|  |  | E16315.01300 - Painting Schedule | [5 empty] | 40 | JC110826 38803
|  |  | E26315.01300 - ML for Paint | [5 empty] | 16 | JC110826 38804
|  |  | E96312.36300 - Shop Primer & Sand Blasting | [5 empty] | 24 | JC110826 38805
|  |  | E26312.36300 - ML for Shop Primer & Sand Blasting | [5 empty] | 16 | JC110826 38806
|  |  | E10660.11400 - Acc. Arrt of 02 Deck |  |  |  |  | Rizal | 32 | JC110826 38807
|  |  | E10660.11401 - Acc. Arrt of 01 Deck | [5 empty] | 32 | JC110826 38808
|  |  | E10660.11402 - Acc. Arrt of 1 Deck | [5 empty] | 32 | JC110826 38809
|  |  | E10660.11403 - Acc. Arrt of 2 Deck | [5 empty] | 24 | JC110826 38810
|  |  | E16250.11400 - Window Plan |  |  |  |  | Bagus | 40 | JC110826 38811
|  |  | E26250.11400 - ML for Window | [5 empty] | 16 | JC110826 38812
|  |  | E16370.11400 - Arrt of Joiner Work | [5 empty] | 32 | JC110826 38813
|  |  | E26370.11400 - ML for Joiner Work | [5 empty] | 16 | JC110826 38814
|  |  | E16242.11400 - Arrt of Fire Proof Door in Accomm. | [5 empty] | 32 | JC110826 38815
|  |  | E26242.11400 - ML for Fire Proof Door in Accomm. | [5 empty] | 8 | JC110826 38816
|  |  | E16341.11400 - Deck Covering Plan | [5 empty] | 40 | JC110826 38817
SEPT 2026
| 2 Sept 2026 | W308 | Review Approval Drawing Acc. Package |  |  |  |  | Wiwid | 24 | JC080926 40154
|  |  | E16400,11413 - 3D Sect. Room of VIP Meeting & VIP Lounge Room |  |  |  |  | Bagus | 32 | JC080926 40155
|  |  | E16400,11414 - 3D Sect. Room of Female Room | [5 empty] | 32 | JC080926 40157
|  |  | E16400,11415 - 3D Sect. Room of Bridge | [5 empty] | 32 | JC080926 40158
|  |  | E16400,11416 - 3D Sect. Room of Corridor 04 Deck | [5 empty] | 32 | JC080926 40159
|  | M312 | Evatek Acc. Package |  |  |  |  | Wiwid | 24 | JC080926 40160
|  |  | EF511C.36100 - 511C Block Painting |  |  |  |  | Indra | 16 | JC080926 40161
|  |  | EF522C.36100 - 522C Block Painting | [5 empty] | 16 | JC080926 40162
|  |  | EF532C.36100 - 532C Block Painting | [5 empty] | 16 | JC080926 40163
|  |  | EF611C.36100 - 611C Block Painting | [5 empty] | 16 | JC080926 40164
|  |  | EF621C.36100 - 621C Block Painting | [5 empty] | 16 | JC080926 40165
|  |  | E16311,33300 - Anti Slip Paint Area | [5 empty] | 32 | JC080926 40166
|  |  | E26311,33300 - Estimation Material for Anti Slip Paint Area | [5 empty] | 16 | JC080926 40167
|  |  | E16122,33400 - Arrt of Handrail in Accomm. - R1 |  |  |  |  | Afrizal | 24 | JC090926 40174
|  |  | E26122.33400 - Estimation Material for Handrail in Accomm. - R1 | [5 empty] | 8 | JC090926 40175
|  | M313 | E10660.11400 - Accomm. Arrt of 02 Deck - Check |  |  |  |  | Wiwid | 8 | JC090926 40176
|  |  | E10660.11401 - Accomm. Arrt of 01 Deck - Check | [5 empty] | 8 | JC090926 40177
|  |  | E10660.11402 - Accomm. Arrt of 1 Deck - Check | [5 empty] | 8 | JC090926 40178
|  |  | E10660.11403 - Accomm. Arrt of 2 Deck - Check | [5 empty] | 8 | JC090926 40179
|  |  | E16250.11400 - Window Plan - Check | [5 empty] | 8 | JC090926 40180
|  |  | E16370.11400 - Arrt of Joiner Work - Check | [5 empty] | 8 | JC090926 40181
|  |  | E16242.11400 - Arrt of Fire Door in Accomm. - Check | [5 empty] | 8 | JC090926 40182
|  |  | E16341.11400 - Deck Covering Plan - Check | [5 empty] | 8 | JC090926 40183
|  |  | Matrix Accomm. Package | [5 empty] | 24 | JC090926 40184
|  |  | E16402.01400 - List of Wooden Furniture |  |  |  |  | Afrizal | 32 | JC090926 40185
|  |  | E26402.01400 - Estimation Material for Wooden Furniture | [5 empty] | 8 | JC090926 40186
|  |  | E16402.01401 - List of Sofa & Chair | [5 empty] | 24 | JC090926 40187
|  |  | E26402.01401 - Estimation Material for Sofa & Chair | [5 empty] | 8 | JC090926 40188
|  |  | E16402.01402 - List of Stainless Furniture | [5 empty] | 24 | JC090926 40189
|  |  | E26402.01402 - Estimation Material for Stainless Furniture | [5 empty] | 8 | JC090926 40190
|  |  | E15559.02300 - Fire Control Plan |  |  |  |  | Dinata | 24 | JC090926 40191
|  |  | E15832.02300 - Safety Plan | [5 empty] | 24 | JC090926 40192
|  | W314 | E10773.10300 - Escape Way Plan | [5 empty] | 24 | JC090926 40193
|  |  | E15559.02300 - Fire Control Plan | [5 empty] | 24 | JC090926 40194
|  |  | E25559.02300 - Estimation Material for Fire Control Plan | [5 empty] | 8 | JC090926 40195
|  |  | E15832.02300 - Safety Plan | [5 empty] | 24 | JC090926 40196
|  |  | E25832.02300 - Estimation Material for Safety Plan | [5 empty] | 8 | JC090926 40197
|  |  | E16315.01300 - Painting Schedule |  |  |  |  | Indra | 40 | JC090926 40198
|  |  | E96312.36300 - Shop Primer & Sand Blasting | [5 empty] | 32 | JC090926 40199
|  |  | E16250.11400 - Window Plan |  |  |  |  | Bagus | 32 | JC090926 40200
|  |  | E26250.11400 - Estimation Material for Window | [5 empty] | 8 | JC090926 40201
|  |  | E16370.11400 - Arrt of Joiner Work | [5 empty] | 32 | JC090926 40202
|  |  | E26370.11400 - Est. Mat. for Joiner Work | [5 empty] | 8 | JC090926 40203
| 14 Sept 2026 | W306/307 | Review Approval Drawing Acc. Package |  |  |  |  | Wiwid | 24 | JC150926 40524
|  | M314 | Matrix Accomm. Package | [5 empty] | 16 | JC150926 40525
|  |  | E16000.75101 - Main Equiplist List for Hull Part |  |  |  |  | Dinata | 24 | JC150926 40526
|  |  | E16440.11400 - Arrt of |  |  |  |  | Afrizal | 24 | JC150926 40527
|  | M312 | E26224.33400 - Est. Material for Wooden Grating & detail | [5 empty] | 16 | JC150926 40528

## Dept. MO
``` | [9 empty] | Diisi Planner
No | Tanggal Permintaan JC ditulis | Project | Task Name | Work Center | Schedule Start date | Schedule End date | Total Personil yang mengerjakan | PIC | JO | Kode Job Card | Keterangan | Planner
| DD / MM / YYYY | KODE PROYEK | REVISI KE - NO DOC / DWG - DESC PEKERJAAN | KODE BIRO - DESC BIRO | DD / MM / YYYY | DD / MM / YYYY | (DALAM ANGKA) | (NAMA) | (ANGKA) | JC010624 0001 | JO Ramadhan : 7 | 023066812-Hashfi Moch Adam
CONTOH
1 | 14 May 2024 | W000308 | E15261.22100 - PIPING DIAGRAM OF SCUPPERS & DECK DRAINS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2024-06-07 | 2024-06-20 | 2 |  |  | JC040624 0374 |  | 023066812-Hashfi Moch Adam
2 | 2024-06-19 | W000306 | Pipe Modelling Block 122, 132, 222, DataBase, 221, Check Model 123, 223 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2024-06-03 | 2024-06-28 | 1 | Dimas |  | JC200624 2566 |  | 023066812-Hashfi Moch Adam
3 | 2024-06-19 | W000306 | Pipe Modelling Block 112, 113, 232 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2024-06-03 | 2024-06-28 | 1 | Syaiful |  | JC200624 2567 |  | 023066812-Hashfi Moch Adam
4 | 2024-06-19 | W000306 | Pipe Modelling Block 132, 133, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2024-06-03 | 2024-06-28 | 1 | Rizki |  | JC200624 2568 |  | 023066812-Hashfi Moch Adam
5 | 2024-06-19 | W000308 | Pipe Modelling Block 212, 222, 232 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2024-06-03 | 2024-06-28 | 1 | Yasin |  | JC200624 2581 |  | 023066812-Hashfi Moch Adam
6 | 2024-06-19 | W000304 | Pipe Modelling Block 213 P/S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2024-06-03 | 2024-06-28 | 1 | Dewi |  | JC200624 2582 |  | 023066812-Hashfi Moch Adam
7 | 2024-06-19 | W000304 | Pipe Modelling Block 254, 244, 234, 224 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2024-06-03 | 2024-07-05 | 1 | Erly |  | JC210624 2698 |  | 023066812-Hashfi Moch Adam
8 | 2024-06-19 | W000304 | Check Drawing Pipe Output Block | 1CJ200 - Biro Desain Pengaturan Permesinan | 2024-06-03 | 2024-06-28 | 1 | Asi |  | JC210624 2695 |  | 023066812-Hashfi Moch Adam
9 | 2024-06-19 | W000306 | Check Drawing Pipe Output Block | 1CJ200 - Biro Desain Pengaturan Permesinan | 2024-06-03 | 2024-06-28 | 1 | Haryanto |  | JC210624 2697 |  | 023066812-Hashfi Moch Adam
10 | 2025-03-04 | W000307 | E15412.17100 - Pipe Model FO SERVICE & PURIFYING System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-01 | 2025-03-31 | 1 | Dimas | 40 | JC050325 15997
11 | 2025-03-04 | W000307 | E15292.17100 - Pipe Model Ballast system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-01 | 2025-03-31 | 1 | Dimas | 40 | JC050325 15998
12 | 2025-03-04 | W000307 | E15291.17100 - Pipe Model Bilge system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-01 | 2025-03-31 | 1 | Dimas | 40 | JC050325 15999
13 | 2025-03-04 | W000307 | E15411.17100 - Pipe Model FO Transfer System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-01 | 2025-03-31 | 1 | Dimas | 40 | JC050325 16000
14 | 2025-03-04 | W000304 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-01 | 2025-03-31 | 1 | Dimas | 25 | JC050325 16001
15 | 2025-03-04 | W000306 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-01 | 2025-03-31 | 1 | Dimas | 25 | JC050325 16002
16 | 2025-03-04 | W000308 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-01 | 2025-03-31 | 1 | Dimas | 25 | JC050325 16003
17 | 2025-03-04 | W000308 | Pipe Model In Engine Room Blok 212, 222, 232, 112 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-01 | 2025-03-31 | 1 | Yasin | 40 | JC050325 16004
18 | 2025-03-04 | W000308 | Pipe Model In Auxilary Room Blok 111, 112, 121, 122 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-01 | 2025-03-31 | 1 | Yasin | 40 | JC050325 16005
19 | 2025-03-04 | W000308 | Check 3D Model Pipe (Fungsi, Operasional, n maintenance) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-01 | 2025-03-31 | 1 | Yasin | 40 | JC050325 16006
20 | 2025-03-04 | W000308 | Check Output Isometric & Spool | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-01 | 2025-03-31 | 1 | Yasin | 40 | JC050325 16007
21 | 2025-03-04 | KPI2024 | Persiapan Project BRS 3 - Machinery Arrangement | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-01 | 2025-03-31 | 1 | Yasin | 40 | JC050325 16008
22 | 2025-03-04 | W000308 | Check Output Piping Isometric & Pipe Sketch of Penetration in Block 221 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-03 | 2025-03-04 | 1 | Syaiful | 16 | JC050325 16009
23 | 2025-03-04 | W000308 | E1332U.27100 Pipe Modelling & Ready in Block 332 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-05 | 2025-03-11 | 1 | Syaiful | 50 | JC050325 16010
24 | 2025-03-04 | W000308 | E1223U.27100 Pipe Modelling & Ready in Block 223 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-12 | 2025-03-20 | 1 | Syaiful | 61 | JC050325 16011
25 | 2025-03-04 | W000308 | E1133U.27100 Pipe Modelling & Ready in Block 133 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-21 | 2025-03-28 | 1 | Syaiful | 54 | JC050325 16012
26 | 2025-03-04 | W000306 | E132P.27100 Pipe Modelling Block 132P ADD R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-01 | 2025-03-07 | 1 | Rizki R | 60 | JC050325 16013
27 | 2025-03-04 | W000306 | E132S.27100 Pipe Modelling Block 132S ADD R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-08 | 2025-03-14 | 1 | Rizki R | 60 | JC050325 16014
28 | 2025-03-04 | W000306 | E132P.27100 Pipe Modelling Support Block 132P ADD R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-15 | 2025-03-21 | 1 | Rizki R | 60 | JC050325 16015
29 | 2025-03-04 | W000306 | E132P.27100 Pipe Modelling Block Support 132P ADD R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-22 | 2025-03-31 | 1 | Rizki R | 60 | JC050325 16016
30 | 2025-03-04 | W000304 | E1132P.17100 - Pipe Modelling Block 132P (R1) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-03 | 2025-03-08 | 1 | Erly | 60 | JC050325 16017
31 | 2025-03-04 | W000304 | E1132S.17100 - Pipe Modelling Block 132S (R1) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-10 | 2025-03-15 | 1 | Erly | 60 | JC050325 16019
32 | 2025-03-04 | W000304 | E1133P.17100 - Pipe Modelling Block 133P (R1) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-17 | 2025-03-22 | 1 | Erly | 60 | JC050325 16020
33 | 2025-03-04 | W000304 | E1133S.17100 - Pipe Modelling Block 133S (R1) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-24 | 2025-03-31 | 1 | Erly | 60 | JC050325 16021
34 | 2025-03-04 | W000304 | E15412.17100 - pipe routing FO service systems | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-01 | 2025-03-31 | 1 | Dewi | 60 | JC050325 16022
35 | 2025-03-04 | W000304 | E12590.17100 - pipe routing exhaust gas & mist systems | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-01 | 2025-03-31 | 1 | Dewi | 60 | JC050325 16023
36 | 2025-03-04 | W000304 | E15512.17100 - pipe routing medium pressure systems | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-01 | 2025-03-31 | 1 | Dewi | 60 | JC050325 16024
37 | 2025-03-04 | W000307 | Check Drawing Output Piping BLOCK E1513C, EK124-S, EK521-P, ES112-P/S, ES133-P/S, ES223S, ES232P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-03 | 2025-03-28 | 1 | Haryanto | 160 | JC050325 16025
38 | 2025-03-06 | W000305 | E1413P.18100 - ARR'T OF VENTILATION IN STEERING GEAR ROOM BLOCK 413 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-03 | 2025-03-05 | 1 | Stevan | 20 | JC060325 16136
39 | 2025-03-06 | W000305 | E1413S.18100 - ARR'T OF VENTILATION IN STEERING GEAR ROOM BLOCK 413 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-05 | 2025-03-07 | 1 | Stevan | 20 | JC060325 16137
40 | 2025-03-06 | W000305 | E1423P.18100 - ARR'T OF VENTILATION IN BLOCK 423 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-10 | 2025-03-12 | 1 | Stevan | 20 | JC060325 16138
41 | 2025-03-06 | W000305 | E1423S.18100 - ARR'T OF VENTILATION IN BLOCK 423 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-12 | 2025-03-14 | 1 | Stevan | 20 | JC060325 16139
42 | 2025-03-06 | W000305 | E1433P.18100 - ARR'T OF VENTILATION IN BLOCK 433 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-17 | 2025-03-19 | 1 | Stevan | 20 | JC060325 16140
43 | 2025-03-06 | W000305 | E1433S.18100 - ARR'T OF VENTILATION IN BLOCK 433 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-19 | 2025-03-21 | 1 | Stevan | 20 | JC060325 16141
44 | 2025-03-06 | W000305 | E1213P.18100 - ARR'T OF VENTILATION IN BLOCK 213 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-24 | 2025-03-26 | 1 | Stevan | 20 | JC070325 16179
45 | 2025-03-06 | W000305 | E1213S.18100 - ARR'T OF VENTILATION IN BLOCK 213 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-26 | 2025-03-31 | 1 | Stevan | 20 | JC070325 16180
46 | 2025-03-06 | W000308 | EVALUASI TEKNIS HVAC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-03 | 2025-03-31 | 1 | Stevan | 20 | JC070325 16181
47 | 2025-03-06 | W000308 | EVALUASI TEKNIS HVAC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-03 | 2025-03-31 | 1 | Stevan | 20 | JC070325 16182
48 | 2025-03-06 | W000308 | E15231.22100 - ISOMETRIC PID PREWETTING SYSTEM - R2 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-03 | 2025-03-07 | 1 | Satrio | 36.5 | JC070325 16183
49 | 2025-03-06 | W000308 | E15211.22100 - ISOMETRIC PID FIRE MAIN AND WASH DECK - R2 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-10 | 2025-03-12 | 1 | Satrio | 2025-05-22 | JC070325 16184
50 | 2025-03-06 | W000305 | E15164.22100 - PID OF CHILLED WATER DRAIN SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-13 | 2025-03-21 | 1 | Satrio | 50.5 | JC070325 16185
51 | 2025-03-06 | W000305 | E25931.01100 - EST. QTY. MAT. FOR PID OF OILY BILGE SEPARATOR SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-24 | 2025-03-26 | 1 | Satrio | 22.5 | JC070325 16190
52 | 2025-03-06 | W000305 | E25930.01100 - EST. QTY. MAT. FOR PID OF SLUDGE AND DISPOSAL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-27 | 2025-03-31 | 1 | Satrio | 24 | JC070325 16195
53 | 2025-03-06 | A24AOP01 | 3D MODEL GEARBOX KAPAL PENGINDRAAN BAWAH/ATAS AIR 15 METER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-03 | 2025-03-03 | 1 | Ardan | 7.5 | JC100325 16336
54 | 2025-03-06 | A24AOP01 | SIMULASI SIDE LAUNCHING KAPAL PENGINDRAAN BAWAH/ATAS AIR 15 METER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-04 | 2025-03-11 | 1 | Ardan | 44 | JC070325 16212
55 | 2025-03-06 | A24AOP01 | SIMULASI END LAUNCHING KAPAL PENGINDRAAN BAWAH/ATAS AIR 15 METER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-12 | 2025-03-19 | 1 | Ardan | 44 | JC070325 16219
56 | 2025-03-06 | A24AOP01 | DESAIN CRADLE DAN FASILITAS PELUNCURAN KAPAL PENGINDRAAN BAWAH/ATAS AIR 15 METER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-20 | 2025-03-31 | 1 | Ardan | 50.5 | JC070325 16220
57 | 2025-03-07 | W00308 | R2 - E15211.22100 - Fire Main and wash deck System | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-03 | 2025-03-07 |  | Irfan | 40 | JC080325 16233
58 | 2025-03-07 | W00305 | R1- E25211.01100- Est. Material of High pressure sea water system | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-10 | 2025-03-26 |  | Irfan | 120 | JC080325 16234
59 | 2025-03-14 | A24AOP01 | MODELING & INPUT SPESIFIKASI PIPE & FITTING ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-10 | 2025-03-31 | 1 | Ahmad Khunaifi | 40 | JC190325 16780
60 | 2025-03-14 | W000305 | MODELING & UPDATE REDRAW CADMATIC PID ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-01 | 2025-03-31 | 1 | Ahmad Khunaifi | 40 | JC190325 16781
61 | 2025-03-14 | W000307 | MODELING & UPDATE REDRAW CADMATIC PID ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-01 | 2025-03-31 | 1 | Ahmad Khunaifi | 40 | JC190325 16789
62 | 2025-03-14 | W000308 | MODELING & UPDATE REDRAW CADMATIC PID ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-01 | 2025-03-31 | 1 | Ahmad Khunaifi | 40 | JC190325 16792
63 | 2025-03-21 | W000304 | E15331.22101_PID OF HOT WATER SYSTEM_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-03 | 2025-03-04 | 1 | Diar Ayu | 16 | JC210325 16882
64 | 2025-03-21 | W000304 | E25331.01100_ESTIMATED MATERIAL FOR PID OF HOT WATER SYSTEM_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-05 | 2025-03-11 | 1 | Diar Ayu | 40 | JC210325 16883
65 | 2025-03-21 | W000304 | E15281.22100_PID OF SEWAGE SYSTEM IN ACCOMMODATION_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-12 | 2025-03-14 | 1 | Diar Ayu | 24 | JC210325 16884
66 | 2025-03-21 | W000304 | E25281.01100_ESTIMATED MATERIAL FOR PID OF SEWAGE SYSTEM IN ACC._R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-17 | 2025-03-21 | 1 | Diar Ayu | 20 | JC210325 16885
67 | 2025-03-21 | W000304 | E15330.22100_PID OF FRESH WATER SANITARY_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-24 | 2025-03-25 | 1 | Diar Ayu | 16 | JC210325 16886
68 | 2025-03-21 | W000304 | E25330.01100_ESTIMATED MATERIAL FOR PID OF FRESH WATER SANITARY_R4 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-26 | 2025-03-28 | 1 | Diar Ayu | 24 | JC210325 16888
69 | 2025-03-24 | A24AOP01 | E11002.03113_RUDDER CONSTRUCTION_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-03 | 2025-03-05 | 1 | Amam | 24 | JC240325 16975
70 | 2025-03-24 | W000304 | E15411.22100_PIPING DIAGRAM OF FO. TRANSFER & OVERFLOW_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-06 | 2025-03-07 | 1 | Amam | 16 | JC240325 16976
71 | 2025-03-24 | W000304 | E15412.22100_PIPING DIAGRAM OF FO. SERVICE_R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-10 | 2025-03-12 | 1 | Amam | 24 | JC240325 16977
72 | 2025-03-24 | W000304 | E15410.22100_PIPING DIAGRAM OF FO. PURIFIYING_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-13 | 2025-03-14 | 1 | Amam | 16 | JC240325 16978
73 | 2025-03-24 | A24AOP01 | BATTERY RACK_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-17 | 2025-03-20 | 1 | Amam | 32 | JC240325 16979
74 | 2025-03-24 | A24AOP01 | E13131.33100_SEAT OF BATTERY_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-21 | 2025-03-21 | 1 | Amam | 8 | JC240325 16980
75 | 2025-03-24 | A24AOP01 | E13131.33100_SEAT OF BATTERY_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-24 | 2025-03-26 | 1 | Amam | 24 | JC240325 16981
76 | 2025-03-24 | A24AOP01 | E12422.33100_COUPLING FOR CONNECTION MOTOR TO GEARBOX_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-26 | 2025-03-27 | 1 | Amam | 16 | JC240325 16982
77 | 2025-03-24 | A24AOP01 | E11002.03113_RUDDER CONSTRUCTION_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-28 | 2025-03-28 | 1 | Amam | 8 | JC240325 16983
78 | 2025-03-24 | W000304 | Check Drawing Output Piping BLOCK EP312C-R1, EK312C-R1, EP313C-R1, EK313C-R1, EP314C-R1, EK314C-R1, EP154P-R1, EK154P-R1, EP154S-R1, EK154S-R1, E1223P-R0, E1223S-R0 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-03 | 2025-03-07 | 1 | Asi Supeni | 40 | JC240325 16984
79 | 2025-03-24 | W000304 | Check Drawing Output Piping BLOCK E1212P-R0, E1212S-R0, E1222P-R0, E1222S-R0, E1214P-R0, E1214S-R0, E1224P-R0, E1224S-R0, E1232P-R0, E1232S-R0, E1314C-R0, E1233P-R0, E1233S-R0, E1234P-R0, E1234S-R0 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-10 | 2025-03-14 | 1 | Asi Supeni | 40 | JC240325 16985
80 | 2025-03-24 | W000304 | Check Drawing Output Piping BLOCK EP113P-R1, EK113P-R1, EP113S-R1, EK113S-R1, E1244P-R0, E1244S-R0, E1243P-R0, E1243S-R0, E1242P-R0, E1242S-R0, E1113P-R0,E1113S-R0, E1254P-R0,E1254S-R0,E1154S-R0 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-17 | 2025-03-21 | 1 | Asi Supeni | 40 | JC240325 16986
81 | 2025-03-24 | W000304 | E15291.22100_PID OF DEWATERING SYSTEM -R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-03 | 2025-03-07 | 1 | Nizar | 48 | JC250325 17015
82 | 2025-03-24 | W000308 | COMPARE MATERIAL 3D MODEL VS IM4 ALL SYSTEM PIPING | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-10 | 2025-03-14 | 1 | Nizar | 48 | JC250325 17016
83 | 2025-03-24 | W000304 | EVATEK PIPE & FITTING BATCH 3 VENDOR SJ METAL & SEPCO KOREA | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-17 | 2025-03-21 | 1 | Nizar | 48 | JC250325 17018
84 | 2025-03-24 | W000304 | EVATEK PIPE & FITTING BATCH 3 VENDOR ELDIYA KOREA | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-24 | 2025-03-28 | 1 | Nizar | 48 | JC250325 17019
85 | 2025-03-25 | W000308 | Maker Review for Electric Propulsion | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-03 | 2025-03-04 | 1 | Syafril | 16 | JC270325 17081
86 | 2025-03-25 | W000308 | Equipment List review & revision – R6 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-05 | 2025-03-05 | 1 | Syafril | 8 | JC270325 17082
87 | 2025-03-25 | W000304 | E1.2430.33100_Shaft Arrangement (Update Intermediate Shaft) – R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-06 | 2025-03-07 | 1 | Syafril | 16 | JC270325 17083
88 | 2025-03-25 | B190N025 | Preliminary E/R layout | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-10 | 2025-03-28 | 1 | Syafril | 88 | JC270325 17084
89 | 2025-03-25 | B190N025 | Technical meeting BMPP3 ,PT PAL – PLN IP | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-12 | 2025-03-21 | 1 | Syafril | 32 | JC270325 17085
90 | 2025-03-25 | W000308 | E15072.37100_NAME PLATE OF VALVE_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-03 | 2025-03-21 | 1 | Agus Setyo | 128 | JC270325 17089
91 | 2025-03-25 | W000308 | E15292.22101_BALLAST & DOCKWELL SYSTEM_R4 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-04 | 2025-03-04 | 1 | Agus Setyo | 8 | JC270325 17088
92 | 2025-03-25 | W000307 | E15412.22100_FO, SERVICE_R3 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-05 | 2025-03-07 | 1 | Agus Setyo | 16 | JC270325 17090
93 | 2025-03-25 | W000308 | Preliminary Design of Funnel Dust Cover | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-03 | 2025-03-28 | 1 | Aditya Prayoga | 24 | JC270325 17091
94 | 2025-03-25 | W000304 | Update KB-03 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-03 | 2025-03-28 | 1 | Aditya Prayoga | 16 | JC270325 17092
95 | 2025-03-25 | W000304 | Structural Analysis of Propulsion Shaft | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-03 | 2025-03-28 | 1 | Aditya Prayoga | 32 | JC270325 17093
96 | 2025-03-25 | W000304 | Reanalyze Steering Gear Supporting Structure due to Construction Changes | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-03 | 2025-03-28 | 1 | Aditya Prayoga | 8 | JC270325 17094
97 | 2025-03-25 | W000308 | Evaluasi Air Compressor R6 & R7 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-03 | 2025-03-28 | 1 | Aditya Prayoga | 8 | JC270325 17095
98 | 2025-03-25 | W000306 | Shaft and Shaft Bearing Loads Calculation | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-03 | 2025-03-28 | 1 | Aditya Prayoga | 80 | JC270325 17126
99 | 2025-03-26 | W000308 | CREATE PROSES PENGADAAN VALVE & OTHER PART 2_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-03 | 2025-03-07 | 1 | Krisdiyantoro | 40 | JC270325 17127
100 | 2025-03-26 | W000308 | EVATEK BY DESCRIPTION PART 1 LIST VALVE AND OTHER MAKER CNJ KOREA_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-10 | 2025-03-14 | 1 | Krisdiyantoro | 40 | JC270325 17128
101 | 2025-03-26 | W000308 | EVATEK BY DESCRIPTION PART 1 LIST VALVE AND OTHER MAKER CNJ KOREA_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-17 | 2025-03-21 | 1 | Krisdiyantoro | 40 | JC270325 17129
102 | 2025-03-26 | W000304 | UPDATE LIST VALVE & OTHER PART 2_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-24 | 2025-03-28 | 1 | Krisdiyantoro | 40 | JC270325 17130
103 | 2025-03-27 | W000306 | E15280.22100-R1- PIPING DIAGRAM OF INSIDE SCUPPER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-03 | 2025-03-07 | 1 | Rafika |  | JC270325 17131
104 | 2025-03-27 | W000308 | E15161.22100-R3-PIPING OF CHILLED WATER SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-10 | 2025-03-14 | 1 | Rafika |  | JC270325 17132
105 | 2025-03-27 | A24AOP01 | 3D MODELING SEAT OF BATTERY | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-17 | 2025-03-19 | 1 | Rafika |  | JC270325 17133
106 | 2025-03-27 | A24AOP01 | E13131.32100-MODULE BATTERY SKID | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-20 | 2025-03-24 | 1 | Rafika |  | JC270325 17134
107 | 2025-03-27 | A24AOP01 | E23131.01101-MATERIAL LIST FOR MODULE BATTERY SKID | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-25 | 2025-03-26 | 1 | Rafika |  | JC270325 17135
108 | 2025-03-27 | A24AOP01 | 3D MODELING MOTOR ENGINE BED | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-03-27 | 2025-03-28 | 1 | Rafika |  | JC270325 17136
109 | 2025-03-27 | A24AOP01 | 3D MODELLING EQUIPMENT_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-03 | 2025-03-05 | 1 | Miekail | 24 | JC270325 17137
110 | 2025-03-27 | A24AOP01 | E15291.27100_PIPE MODELLING BILGE SYSTEM_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-06 | 2025-03-07 | 1 | Miekail | 16 | JC270325 17138
111 | 2025-03-27 | A24AOP01 | E15510.22100_PIPING DIAGRAM OF COMPRESS AIR SYSTEM_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-10 | 2025-03-10 | 1 | Miekail | 8 | JC270325 17139
112 | 2025-03-27 | A24AOP01 | E15240.27100_PIPE MODELLING SEA WATER COOLING SYSTEM_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-11 | 2025-03-13 | 1 | Miekail | 24 | JC270325 17140
113 | 2025-03-27 | A24AOP01 | E15510.27100_PIPE MODELLING COMPRESSED AIR SYSTEM_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-14 | 2025-03-19 | 1 | Miekail | 32 | JC270325 17141
114 | 2025-03-27 | A24AOP01 | E15510.22100_PIPING DIAGRAM OF COMPRESS AIR SYSTEM_R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-20 | 2025-03-20 | 1 | Miekail | 8 | JC270325 17142
115 | 2025-03-27 | A24AOP01 | E25510.01100_EST. QTY MATERIAL FOR PIPING DIAGRAM OF COMPRESS AIR SYSTEM_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-21 | 2025-03-21 | 1 | Miekail | 8 | JC270325 17143
116 | 2025-03-27 | A24AOP01 | PIPE READY & CHECK ALL SYSTEM_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-24 | 2025-03-28 | 1 | Miekail | 40 | JC270325 17144
117 | 2025-03-27 | W000304 | Check Drawing Output Piping BLOCK E1132P-R0, E1132S-R0,E1142C-R0, E1152C-R0, E1323C-R0, E1154P-R0, E1114P-R0,E1114S-R0, E1144P-R0, E1144S-R0, E1155S-R0,EP123S-R1, EK123P-R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-03-24 | 2025-03-28 | 1 | Asi Supeni | 40 | JC270325 17155
118 | 2025-03-28 | W000308 | E15072.37100_NAME PLATE OF VALVE_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-03-24 | 2025-03-28 | 1 | Agus Setyo | 40 | JC280325 17218
2025-04-01
1 | 2025-04-08 | W000307 | E1212P.17100 - Pipe Modeling Block 212P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-07 | 2025-04-11 | 1 | Dimas | 20 | JC100425 17606
2 | 2025-04-08 | W000307 | E1212S.17100 - Pipe Modeling Block 212S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-07 | 2025-04-11 | 1 | Dimas | 20 | JC160425 17959
3 | 2025-04-08 | W000307 | E1211P.17100 - Pipe Modeling Block 211P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-12 | 2025-04-21 | 1 | Dimas | 28 | JC100425 17611
4 | 2025-04-08 | W000307 | E1211S.17100 - Pipe Modeling Block 211S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-12 | 2025-04-21 | 1 | Dimas | 28 | JC160425 17960
5 | 2025-04-08 | W000307 | E1213P.17100 - Pipe Modeling Block 213P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-22 | 2025-04-30 | 1 | Dimas | 30 | JC100425 17613
6 | 2025-04-08 | W000307 | E1213S.17100 - Pipe Modeling Block 213S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-22 | 2025-04-30 | 1 | Dimas | 30 | JC160425 17962
7 | 2025-04-08 | W000304 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-07 | 2025-04-30 | 1 | Dimas | 25 | JC100425 17615
8 | 2025-04-08 | W000306 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-07 | 2025-04-30 | 1 | Dimas | 25 | JC100425 17616
9 | 2025-04-08 | W000308 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-07 | 2025-04-30 | 1 | Dimas | 25 | JC100425 17617
10 | 2025-04-08 | W000308 | Pipe Model In Engine Room Blok 221U, 222U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-07 | 2025-04-30 | 1 | Yasin | 40 | JC100425 17618
11 | 2025-04-08 | W000308 | Pipe Model In Auxilary Room Blok 111U, 112U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-07 | 2025-04-30 | 1 | Yasin | 40 | JC100425 17619
12 | 2025-04-08 | W000308 | Pipe Model In Engine Casing Blok 232U, 113U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-07 | 2025-04-30 | 1 | Yasin | 40 | JC100425 17620
13 | 2025-04-08 | W000308 | Check 3D Model Pipe (Fungsi, Operasional, n maintenance) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-07 | 2025-04-30 | 1 | Yasin | 40 | JC100425 17621
14 | 2025-04-08 | W000308 | Check Output Isometric & Spool | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-07 | 2025-04-30 | 1 | Yasin | 40 | JC100425 17622
15 | 2025-04-08 | W000306 | E16652.11100-R1-Arrt of Store and Workshop in E/R | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-07 | 2025-04-30 | 1 | Yasin | 40 | JC100425 17623
16 | 2025-04-08 | W000306 | E1323S.17100 Pipe Modelling Block 323S ADD R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-07 | 2025-04-12 | 1 | Rizki R | 48 | JC100425 17624
17 | 2025-04-08 | W000306 | ES323S.17100 Pipe Modelling Support 132S ADD R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-14 | 2025-04-19 | 1 | Rizki R | 48 | JC100425 17625
18 | 2025-04-08 | W000306 | E1313P.17100 Pipe Modelling Support Block 313P ADD R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-21 | 2025-04-26 | 1 | Rizki R | 48 | JC150425 17956
19 | 2025-04-08 | W000306 | E1313S.17100 Pipe Modelling Block Support 313S ADD R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-28 | 2025-04-30 | 1 | Rizki R | 24 | JC100425 17627
20 | 2025-04-08 | W000308 | Check Output Piping Isometric & Pipe Sketch of Penetration in Block 123 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-07 | 2025-04-08 | 1 | Syaiful | 16 | JC100425 17628
21 | 2025-04-08 | W000308 | Check Output Piping Isometric & Pipe Sketch of Penetration in Block 322 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-09 | 2025-04-10 | 1 | Syaiful | 16 | JC100425 17629
22 | 2025-04-08 | W000308 | E1133U.27100 Pipe Modelling & Ready in Block 133 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-11 | 2025-04-21 | 1 | Syaiful | 62 | JC100425 17630
23 | 2025-04-08 | W000308 | E1443U.27100 Pipe Modelling & Ready in Block 443 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-22 | 2025-04-30 | 1 | Syaiful | 66 | JC100425 17631
24 | 2025-04-09 | W000305 | E1133P.17100 - Pipe Modelling Block 133P (R1) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-07 | 2025-04-12 | 1 | Erly | 50 | JC100425 17632
25 | 2025-04-09 | W000305 | E1133S.17100 - Pipe Modelling Block 133S (R1) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-14 | 2025-04-19 | 1 | Erly | 50 | JC100425 17634
26 | 2025-04-09 | W000305 | E1123S.17100 - Pipe Modelling Block 123P (R1) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-21 | 2025-04-30 | 1 | Erly | 70 | JC100425 17635
27 | 2025-04-09 | W000305 | E15931.17100 - Pipe Routing Oily Bilge Separator Systems | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-07 | 2025-04-30 | 1 | Dewi | 90 | JC100425 17636
28 | 2025-04-09 | W000305 | E15261.17100 - Pipe Routing Scupper Systems - PID Rev | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-07 | 2025-04-30 | 1 | Dewi | 90 | JC100425 17637
29 | 2025-04-09 | W000307 | Check Drawing Output Piping BLOCK | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-07 | 2025-04-30 | 1 | Haryanto | 140 | JC100425 17638
30 | 2025-04-15 | W000304 | Check Drawing Output Piping BLOCK E1414P-R0, E1414S-R0,E1333C-R0, E1315P-R0, E1315S-R0, E1324C-R0, E1325P-R0,E1325S-R0, E1512P-R0, E1512S-R0, E1423P-R0,E1423S-R0, E1513P-R0,E1513S-R0,E1433P-R0, E1434P-R0,E1522P-R0,E1522S-R0,E1424P-R0,E1424S-R0,E1514C-R0 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-07 | 2025-04-11 | 1 | Asi Supeni | 40 | JC150425 17942
31 | 2025-04-10 | W000305 | E85100.51100 - HVAC System & Fan (M) Fan Coil Unit Rev B | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-07 | 2025-04-12 | 1 | Pratama Akbar | 40 | JC100425 17570
32 | 2025-04-10 | W000305 | E1223P.18100 - ARR'T OF VENTILATION IN BLOCK 223 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-07 | 2025-04-09 | 1 | Stevan | 20 | JC100425 17571
33 | 2025-04-10 | W000305 | E1223S.18100 - ARR'T OF VENTILATION IN BLOCK 223 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-09 | 2025-04-12 | 1 | Stevan | 20 | JC100425 17572
34 | 2025-04-10 | W000305 | E1233P.18100 - ARR'T OF VENTILATION IN BLOCK 233 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-14 | 2025-04-16 | 1 | Stevan | 20 | JC100425 17573
35 | 2025-04-10 | W000305 | E1233S.18100 - ARR'T OF VENTILATION IN BLOCK 233 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-16 | 2025-04-19 | 1 | Stevan | 20 | JC100425 17577
36 | 2025-04-10 | W000305 | E1243P.18100 - ARR'T OF VENTILATION IN BLOCK 243 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-21 | 2025-04-23 | 1 | Stevan | 20 | JC100425 17579
37 | 2025-04-10 | W000305 | E1243S.18100 - ARR'T OF VENTILATION IN BLOCK 243 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-23 | 2025-04-26 | 1 | Stevan | 20 | JC100425 17581
38 | 2025-04-10 | W000305 | E1113P.18100 - ARR'T OF VENTILATION IN BLOCK 113 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-28 | 2025-04-30 | 1 | Stevan | 20 | JC100425 17583
39 | 2025-04-10 | W000305 | E1113S.18100 - ARR'T OF VENTILATION IN BLOCK 113 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-30 | 2025-05-03 | 1 | Stevan | 20 | JC100425 17584
40 | 2025-04-10 | W000305 | EVALUASI TEKNIS APPROVAL DRAWING HVAC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-07 | 2025-04-30 | 1 | Stevan | 20 | JC100425 17585
41 | 2025-04-10 | W000305 | ANALISIS UNDER WATER NOISE (UWN) APPENDAGES PIPA OVERBOARD | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-07 | 2025-04-18 | 1 | Ardan | 80 | JC100425 17586
42 | 2025-04-14 | W000305 | E15164.22100 - PID OF CHILLED WATER DRAIN | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-07 | 2025-04-09 | 1 | Satrio |  | JC150425 17919
43 | 2025-04-14 | W000308 | E15231.22100 - PID OF PREWETTING SYSTEM -R2 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-09 | 2025-04-15 | 1 | Satrio |  | JC150425 17920
44 | 2025-04-14 | W000305 | E15930.22100 - PID OF OIL WASTE TREATMENT AND DISPOSAL SYSTEM - R2 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-16 | 2025-04-18 | 1 | Satrio |  | JC150425 17921
45 | 2025-04-14 | W000308 | E15211.22100 - PID OF FIRE MAIN AND WASH DECK - R2 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-07 | 2025-04-30 | 1 | Irfan |  | JC150425 17922
46 | 2025-04-14 | W000305 | MODELING & UPDATE REDRAW CADMATIC PID ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-07 | 2025-04-30 | 1 | Ahmad Khunaifi | 40 | JC150425 17914
47 | 2025-04-14 | W000307 | MODELING & UPDATE REDRAW CADMATIC PID ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-07 | 2025-04-30 | 1 | Ahmad Khunaifi | 40 | JC150425 17915
48 | 2025-04-14 | W000308 | MODELING & UPDATE REDRAW CADMATIC PID ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-07 | 2025-04-30 | 1 | Ahmad Khunaifi | 40 | JC150425 17916
49 | 2025-04-14 | A24AOP01 | MODELING & INPUT SPESIFIKASI PIPE & FITTING ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-07 | 2025-04-30 | 1 | Ahmad Khunaifi | 40 | JC150425 17918
50 | 2025-04-14 | W000307 | SHORTIR MATERIAL PIPE & FITTING PP-R ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-07 | 2025-04-10 | 1 | Ahmad Khunaifi | 24 | JC150425 17917
51 | 2025-04-14 | W000308 | E35130.50100 - EVALUASI TEKNIS PENAWARAN DUST & SAND FILTERS SUPPLIER VENDOR H&H | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-14 | 2025-04-30 | 1 | Pratama Akbar |  | JC280425 18453
52 | 2025-04-21 | W000304 | E15330.22100_PID OF FRESH WATER SANITARY_ R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-07 | 2025-04-11 | 1 | Diar Ayu | 40 | JC210425 18118
53 | 2025-04-21 | W000304 | E15282.22100_R1_PIPING DIAGRAM OF GREY WATER SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-14 | 2025-04-18 | 1 | Diar Ayu | 40 | JC210425 18119
54 | 2025-04-21 | W000304 | E25330.01100_R4_ESTIMATED MATERIAL FOR FRESH WATER SANITARY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-21 | 2025-04-24 | 1 | Diar Ayu | 32 | JC210425 18120
55 | 2025-04-21 | W000304 | E25282.01100_R2_ESTIMATED MATERIAL FOR GREY WATER | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-25 | 2025-04-30 | 1 | Diar Ayu | 32 | JC210425 18122
56 | 2025-04-21 | W000308 | E95550.01100 - HYDRAULIC CALCULATION AND PUMP PERFORMANCE -R0 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-07 | 2025-04-16 | 1 | Firman |  | JC210425 18189
57 | 2025-04-21 | W300305 | HYDRAULIC CALCULATION AND PUMP PERFORMANCE - R0 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-21 | 2025-04-30 | 1 | Firman |  | JC210425 18190
58 | 2025-04-22 | W000304 | Check Drawing Output Piping R0-BLOCK E1532P, E1532S, E1531P, E1531S, E1612P, E1612S, E1521P, E1521S, E1541P, E1541S, E1434S, E1621P, E1621S, E1622P, E1622S, E1631P, E1631S, E1523P, E1523S, E1124P, E1124S, E1542P, E1542S, E1143P, E1143S, E1641S, E1641S, E1524P, E1524S, E1632P, E1632S, EP673P, EK673P. | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-14 | 2025-04-18 | 1 | Asi Supeni | 40 | JC220425 18224
59 | 2025-04-22 | W000305 | EVATEK PIPE & FITTING TAHAP 3 VENDOR ELDIYA & SEPCO KOREA | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-07 | 2025-04-11 | 1 | Nizar | 48 | JC220425 18259
60 | 2025-04-22 | W000305 | EVATEK PIPE & FITTING TAHAP 3 VENDOR SJMETAL & DAIDUCK KOREA | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-14 | 2025-04-19 | 1 | Nizar | 52 | JC220425 18260
61 | 2025-04-22 | W000305 | E25513.01100_EST QTY MATERIAL OF LOW AIR PRESSURE SYSTEM - R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-21 | 2025-04-25 | 1 | Nizar | 52 | JC220425 18261
62 | 2025-04-22 | W000308 | EVATEK PIPE & FITTING TAHAP 2 VENDOR SJ METAL & DAIDUCK KOREA | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-28 | 2025-04-30 | 1 | Nizar | 30 | JC220425 18262
63 | 2025-04-22 | W000308 | EVATEK BY DESCRIPTION PART 1 LIST VALVE AND OTHER MAKER CNJ KOREA_R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-07 | 2025-04-11 | 1 | Krisdiyantoro | 40 | JC230425 18283
64 | 2025-04-22 | W000304 | EVATEK BY DESCRIPTION PART RCV PART 2 MAKER HANLA_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-14 | 2025-04-18 | 1 | Krisdiyantoro | 40 | JC230425 18284
65 | 2025-04-22 | W000308 | CREATE PROSES PENGADAAN VALVE & OTHER PART 2_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-21 | 2025-04-25 | 1 | Krisdiyantoro | 40 | JC230425 18285
66 | 2025-04-22 | W000308 | CREATE PROSES PENGADAAN VALVE & OTHER PART 2_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-28 | 2025-04-30 | 1 | Krisdiyantoro | 24 | JC230425 18286
67 | 2025-04-23 | W000305 | ANALISIS UNDER WATER NOISE (UWN) APPENDAGES PIPA OVERBOARD (VARIASI KECEPATAN) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-21 | 2025-04-30 | 1 | Ardan |  | JC230425 18287
68 | 2025-04-23 | W000308 | E15072.37100_R0_NAME PLATE OF VALVE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-01 | 2025-04-30 | 1 | Agus Setyo | 136 | JC230425 18288
69 | 2025-04-26 | A24AOP01 | E23131.01100_R0_EST. MATERIAL OF SEAT OF BATTERY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-07 | 2025-04-08 | 1 | Amam | 16 | JC280425 18464
70 | 2025-04-26 | A24AOP01 | E12430.33100_R0_SHAFT PENETRATION ARRANGEMENT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-09 | 2025-04-11 | 1 | Amam | 24 | JC280425 18465
71 | 2025-04-26 | A24AOP01 | E22430.01100_R0_EST. MATERIAL OF SHAFT PENETRATION ARANGEMENT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-14 | 2025-04-14 | 1 | Amam | 8 | JC280425 18487
72 | 2025-04-26 | A24AOP01 | E13131.33100_R1_SEAT OF BATTERY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-15 | 2025-04-15 | 1 | Amam | 8 | JC280425 18491
73 | 2025-04-26 | A24AOP01 | E23131.01100_R1_EST. MATERIAL OF SEAT OF BATTERY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-16 | 2025-04-16 | 1 | Amam | 8 | JC280425 18493
74 | 2025-04-26 | A24AOP01 | E13131.34101_R0_BATTERY CONTROL UNIT RACK | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-17 | 2025-04-22 | 1 | Amam | 24 | JC280425 18494
75 | 2025-04-26 | A24AOP01 | E23131.01101_R0_EST. MATE FOR BATTERY CONTROL UNIT RACK | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-23 | 2025-04-23 | 1 | Amam | 8 | JC280425 18495
76 | 2025-04-26 | A24AOP01 | E15240.34100_R0_SEAT OF STEERING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-24 | 2025-04-29 | 1 | Amam | 36 | JC280425 18496
77 | 2025-04-26 | A24AOP01 | E25240.01101_R0_EST. MATERIAL OF STEERING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-30 | 2025-04-30 | 1 | Amam | 8 | JC280425 18497
78 | 2025-04-28 | W000304 | Maker Main Engine, Gearbox and Shaft Propulsion | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-07 | 2025-04-30 | 1 | Syafril | 64 | JC280425 18467
79 | 2025-04-28 | W000304 | Maker Engine Room Pumps | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-10 | 2025-04-15 | 1 | Syafril | 32 | JC280425 18472
80 | 2025-04-28 | W000304 | Review Maker Workshop Equipment | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-16 | 2025-04-17 | 1 | Syafril | 16 | JC280425 18475
81 | 2025-04-28 | W000308 | Rev ATO Main Engine, Gearbox and Shaft Propulsion | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-21 | 2025-04-23 | 1 | Syafril | 24 | JC280425 18478
82 | 2025-04-28 | W000304 | Check Drawing Output Piping R0-BLOCK E1153P, E1153S, E1642P, E1642S, E1623C, E1611P, E1611S, E1651P, E1651S, E1652P, E1652S, E1633C, E1663S, E1673P, ES673P, E1134P, E1134S, EP324C-R1, EK324C-R1, E1511P, E1511S, E1121P, E1133P, E1133S, E1123S, E1533P, E1533S. | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-21 | 2025-04-25 | 1 | Asi Supeni | 40 | JC280425 18480
83 | 2025-04-28 | W000308 | Preliminary Design of Funnel Dust Cover | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-07 | 2025-04-30 | 1 | Aditya Prayoga | 32 | JC280425 18498
84 | 2025-04-28 | W000308 | Evaluasi Dokumen Milestone #5 IRIDIUM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-07 | 2025-04-30 | 1 | Aditya Prayoga | 16 | JC280425 18499
85 | 2025-04-28 | W000304 | E12591.34101_R0_Detail and Arrangement of Funnel Louvre fo IRSS System | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-07 | 2025-04-30 | 1 | Aditya Prayoga | 32 | JC280425 18500
86 | 2025-04-28 | W000304 | E22591.34101_R0_Est. Mat. of Funnel Louvre fo IRSS System | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-07 | 2025-04-30 | 1 | Aditya Prayoga | 8 | JC280425 18501
87 | 2025-04-28 | W000304 | E22330.01100_R0_Est. Mat. of Chocking Resin for Shaft Propulsion | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-07 | 2025-04-30 | 1 | Aditya Prayoga | 8 | JC280425 18503
88 | 2025-04-28 | W000304 | E95000.92101_R0_KB03 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-08 | 2025-05-01 | 1 | Aditya Prayoga | 24 | JC280425 18504
89 | 2025-04-28 | A24AOP01 | R0_KB03 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-08 | 2025-05-01 | 1 | Aditya Prayoga | 16 | JC280425 18505
90 | 2025-04-28 | A24AOP01 | 3D MODELING FLOOR | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-07 | 2025-04-10 | 1 | Rafika |  | JC280425 18574
91 | 2025-04-28 | A24AOP01 | 3D MODELING SEAT OF PUMPS | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-11 | 2025-04-14 | 1 | Rafika |  | JC280425 18575
92 | 2025-04-28 | A24AOP01 | 3D MODELING BCU RACK | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-15 | 2025-04-17 | 1 | Rafika |  | JC280425 18576
93 | 2025-04-28 | A24AOP01 | 3D MODELING SEAT OF BATTERY | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-21 | 2025-04-23 | 1 | Rafika |  | JC280425 18577
94 | 2025-04-28 | A24AOP01 | 3D MODELING SEAT OF AF 11 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-24 | 2025-04-25 | 1 | Rafika |  | JC280425 18578
95 | 2025-04-28 | A24AOP01 | 3D MODELING MODULE FOR TEMPORARY BATTERY | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-28 | 2025-04-30 | 1 | Rafika |  | JC280425 18579
96 | 2025-04-29 | W000305 | E15162.22100 - PID OF DECK SCUPPERS & DECK DRAINS - R1 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-21 | 2025-04-25 | 1 | Satrio |  | JC290425 18619
97 | 2025-04-29 | W000305 | E25162.22100 - EST. QTY. MAT. FOR PID OF DECK SCUPPERS & DECK DRAINS - R1 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-04-28 | 2025-04-30 | 1 | Satrio |  | JC290425 18620
98 | 2025-04-29 | A24AOP01 | 3D MODELLING FIRE FIGHTING SYSTEM & HVAC_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-07 | 2025-04-11 | 1 | Miekail | 40 | JC290425 18622
99 | 2025-04-29 | A24AOP01 | 3D MODELLING ELECTRICAL AND CONTROL EQUIPMENT_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-14 | 2025-04-18 | 1 | Miekail | 40 | JC290425 18623
100 | 2025-04-29 | A24AOP01 | E15291.22100_PIPING DIAGRAM OF BILGE SYSTEM_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-21 | 2025-04-22 | 1 | Miekail | 16 | JC290425 18624
101 | 2025-04-29 | A24AOP01 | E15240.22100_PIPING DIAGRAM OF SEA WATER COOLING SYSTEM_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-23 | 2025-04-24 | 1 | Miekail | 16 | JC290425 18625
102 | 2025-04-29 | A24AOP01 | E15510.22100_PIPING DIAGRAM OF COMPRESS AIR SYSTEM_R3 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-25 | 2025-04-25 | 1 | Miekail | 8 | JC290425 18626
103 | 2025-04-29 | A24AOP01 | E15291.22100_PIPING DIAGRAM OF BILGE SYSTEM_R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-28 | 2025-04-29 | 1 | Miekail | 8 | JC290425 18627
104 | 2025-04-29 | A24AOP01 | E25510.01100_EST. QTY MATERIAL FOR PIPING DIAGRAM OF COMPRESS AIR SYSTEM_R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-04-30 | 2025-04-30 | 1 | Miekail | 16 | JC290425 18628
105 | 2025-04-30 | W000304 | Check Drawing Output Piping BLOCK E1123P-R0, E11631-R1, EP123P-R1, EK123P-R1, EP322C-R1, EK322C-R1, EP323C-R1, EK323C-R1, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-04-28 | 2025-04-30 | 1 | Asi Supeni | 24 | JC300425 18672
2025-05-01
1 | 2025-04-28 | A24AOP01 | SADDLE DESIGN FOR FIRST TRIMMING | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-02 | 2025-05-05 | 1 | Ardan |  | JC280425 18580
2 | 2025-04-28 | W000307 | ANALISIS HAMBATAN LCU | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-06 | 2025-05-13 | 1 | Ardan |  | JC280425 18581
3 | 2025-04-29 | W000308 | E15211.22100 - PID OF FIRE MAIN AND WASH DECK - R2 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-01 | 2025-05-30 | 1 | Irfan | 60 | JC090525 19213
4 | 2025-04-30 | W000308 | MODELING & UPDATE REDRAW CADMATIC PID ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-02 | 2025-05-30 | 1 | AHMAD KHUNAIFI | 40 | JC300425 18671
5 | 2025-04-30 | W000307 | MODELING & UPDATE REDRAW CADMATIC PID ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-02 | 2025-05-30 | 1 | AHMAD KHUNAIFI | 40 | JC300425 18673
6 | 2025-04-30 | W000305 | MODELING & UPDATE REDRAW CADMATIC PID ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-02 | 2025-05-30 | 1 | AHMAD KHUNAIFI | 40 | JC300425 18674
7 | 2025-04-30 | W000306 | SHORTIR MATERIAL GASKET, PLATE & PROFILE ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-02 | 2025-05-07 | 1 | AHMAD KHUNAIFI | 32 | JC300425 18676
8 | 2025-05-02 | W000308 | Pipe Model In Auxilary Room Blok 111U, 112U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-01 | 2025-05-31 | 1 | Yasin | 40 | JC050525 18849
9 | 2025-05-02 | W000308 | Pipe Model In Engine Room Blok 221U, 222U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-01 | 2025-05-31 | 1 | Yasin | 40 | JC050525 18850
10 | 2025-05-02 | W000308 | Pipe Model In Service Machinery Space Block 231U, 232U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-01 | 2025-05-31 | 1 | Yasin | 40 | JC050525 18851
11 | 2025-05-02 | W000308 | Check 3D Model Pipe (Fungsi, Operasional, n maintenance) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-01 | 2025-05-31 | 1 | Yasin | 40 | JC050525 18852
12 | 2025-05-02 | W000308 | Paparan di SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-01 | 2025-05-31 | 1 | Yasin | 16 | JC050525 18854
13 | 2025-05-02 | W000305 | E15330.17100-Pipe Routing-Rev-FW Service Systems | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-01 | 2025-05-31 | 1 | Dewi | 60 | JC050525 18858
14 | 2025-05-02 | W000305 | E15931.17100-Pipe Routing-PID Rev-Oily Bilge Separator Systems | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-01 | 2025-05-31 | 1 | Dewi | 60 | JC050525 18861
15 | 2025-05-02 | W000305 | E15410.17100-Pipe Routing-Rev-FO Purif Systems | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-01 | 2025-05-31 | 1 | Dewi | 60 | JC050525 18862
16 | 2025-05-05 | W000305 | E1123S.17100 - Pipe Modelling Block 123S (R1) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-01 | 2025-05-09 | 1 | Erly | 56 | JC050525 18894
17 | 2025-05-05 | W000305 | E1123P.17100 - Pipe Modelling Block 123P (R1) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-12 | 2025-05-16 | 1 | Erly | 40 | JC050525 18898
18 | 2025-05-05 | W000305 | E1124P.17100 - Pipe Modelling Block 124P (R1) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-19 | 2025-05-23 | 1 | Erly | 40 | JC050525 18899
19 | 2025-05-05 | W000305 | E1124S.17100 - Pipe Modelling Block 124S (R1) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-26 | 2025-05-30 | 1 | Erly | 40 | JC130525 19300
20 | 2025-05-05 | W000307 | E1213P.17100 - Pipe Modeling block 213P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-01 | 2025-05-09 | 1 | Dimas | 31 | JC050525 18901
21 | 2025-05-05 | W000307 | E1213S.17100 - Pipe Modeling block 213S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-01 | 2025-05-09 | 1 | Dimas | 31 | JC050525 18902
22 | 2025-05-05 | W000307 | E1214P.17100 - Pipe Modeling block 214P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-10 | 2025-05-19 | 1 | Dimas | 31 | JC050525 18903
23 | 2025-05-05 | W000307 | E1214S.17100 - Pipe Modeling block 214S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-10 | 2025-05-19 | 1 | Dimas | 31 | JC050525 18906
24 | 2025-05-05 | W000307 | E1221P.17100 - Pipe Modeling block 221P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-20 | 2025-05-31 | 1 | Dimas | 31 | JC050525 18907
25 | 2025-05-05 | W000307 | E1221S.17100 - Pipe Modeling block 221S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-20 | 2025-05-31 | 1 | Dimas | 31 | JC050525 18909
26 | 2025-05-05 | W000304 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-01 | 2025-05-31 | 1 | Dimas | 8 | JC050525 18917
27 | 2025-05-05 | W000306 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-01 | 2025-05-31 | 1 | Dimas | 8 | JC050525 18921
28 | 2025-05-05 | W000308 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-01 | 2025-05-31 | 1 | Dimas | 8 | JC050525 18922
29 | 2025-05-05 | W000308 | Pipe Model in Aux Room block 111U, 112U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-01 | 2025-05-31 | 1 | Yasin | 56 | JC050525 18925
30 | 2025-05-05 | W000308 | Pipe Model in Electric motor room block 211U, 212U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-01 | 2025-05-31 | 1 | Yasin | 56 | JC050525 18926
31 | 2025-05-05 | W000308 | Pipe model in service machinery space block 231U, 232U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-01 | 2025-05-31 | 1 | Yasin | 56 | JC050525 18927
32 | 2025-05-05 | W000308 | Check 3D model (fungsi, operasional, maintenance) & Paparan di SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-01 | 2025-05-31 | 1 | Yasin | 40 | JC050525 18928
33 | 2025-05-05 | W000306 | E1413P.17100 - Pipe Modeling block ADD R1 413P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-01 | 2025-05-10 | 1 | Rizki R | 52 | JC050525 18938
34 | 2025-05-05 | W000306 | E1413S.17100 - Pipe Modeling block ADD R1 413S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-12 | 2025-05-17 | 1 | Rizki R | 52 | JC050525 18939
35 | 2025-05-05 | W000306 | E1412P.17100 - Pipe Modeling block ADD R1 412P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-19 | 2025-05-24 | 1 | Rizki R | 52 | JC050525 18940
36 | 2025-05-05 | W000306 | E1412S.17100 - Pipe Modeling block ADD R1 412S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-26 | 2025-05-31 | 1 | Rizki R | 52 | JC050525 18941
37 | 2025-05-05 | W000308 | E1323U.27100 Pipe Modelling & Ready in Block 323 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-02 | 2025-05-16 | 1 | Syaiful | 90 | JC050525 18963
38 | 2025-05-05 | W000308 | E1333U.27100 Pipe Modelling & Ready in Block 333 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-19 | 2025-05-30 | 1 | Syaiful | 90 | JC050525 18964
39 | 2025-05-05 | W000308 | Check 3D model (fungsi, operasional, maintenance) & Paparan di SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-02 | 2025-05-30 | 1 | Syaiful | 30 | JC050525 18973
40 | 2025-05-09 | W000304 | Check Drawing Output Piping BLOCK EP211P-R3, EP221S-R3, EK221S-R3, EP221P-R3, EK221P-R3, EP231P-R3, EP231S-R3, EK231S-R3, EP121P-R2,EK121P-R2,EP121S-R3, EK121S-R2, EP131C-R2, EK131C-R2, EP241S-R3, EK241S-R3, EP241P-R3, EK241P-R3 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-02 | 2025-05-09 | 1 | Asi Supeni | 48 | JC090525 19130
41 | 2025-05-09 | W000304 | REVIEW COMBAT COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-01 | 2025-05-31 | 1 | Stevan | 20 | JC130525 19277
42 | 2025-05-09 | W000304 | EVALUASI TEKNIS APPROVAL DRAWING HVAC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-01 | 2025-05-31 | 1 | Stevan | 20 | JC130525 19278
43 | 2025-05-09 | W000304 | E1123P.18100 - ARR'T OF VENTILATION IN BLOCK 123 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-05 | 2025-05-07 | 1 | Stevan | 20 | JC130525 19279
44 | 2025-05-09 | W000304 | E1123S.18100 - ARR'T OF VENTILATION IN BLOCK 123 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-07 | 2025-05-10 | 1 | Stevan | 20 | JC130525 19281
45 | 2025-05-09 | W000304 | E1133P.18100 - ARR'T OF VENTILATION IN BLOCK 133 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-12 | 2025-05-14 | 1 | Stevan | 20 | JC130525 19282
46 | 2025-05-09 | W000304 | E1133S.18100 - ARR'T OF VENTILATION IN BLOCK 133 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-14 | 2025-05-17 | 1 | Stevan | 20 | JC130525 19283
47 | 2025-05-09 | W000304 | E1143P.18100 - ARR'T OF VENTILATION IN BLOCK 143 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-19 | 2025-05-21 | 1 | Stevan | 20 | JC130525 19284
48 | 2025-05-09 | W000304 | E1143S.18100 - ARR'T OF VENTILATION IN BLOCK 143 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-21 | 2025-05-24 | 1 | Stevan | 20 | JC130525 19288
49 | 2025-05-09 | W000304 | E1153P.18100 - ARR'T OF VENTILATION IN BLOCK 153 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-26 | 2025-05-28 | 1 | Stevan | 20 | JC130525 19289
50 | 2025-05-09 | W000304 | E1153S.18100 - ARR'T OF VENTILATION IN BLOCK 153 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-28 | 2025-05-31 | 1 | Stevan | 20 | JC130525 19290
51 | 2025-05-09 | W000304 | E15164.22100 - PID OF CHILLED WATER DRAIN - R0 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-01 | 2025-05-09 | 1 | Satrio |  | JC130525 19293
52 | 2025-05-09 | W000304 | E25164.01100 - EST. QTY. MAT. FOR PID OF CHILLED WATER DRAIN - R0 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-12 | 2025-05-14 | 1 | Satrio |  | JC130525 19296
53 | 2025-05-09 | A24AOP01 | E19936.95029 - END LAUNCHING ARRANGEMENT & PROCEDURE - R1 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-07 | 2025-05-30 | 1 | Ardan | 80 | JC130525 19291
54 | 2025-05-09 | W000304 | E35130.50100 - ATO AC & MECHANICAL FANS | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-02 | 2025-05-31 | 1 | Pratama Akbar |  | JC130525 19299
54 | 2025-05-15 | W000308 | E15221.22100 - EST MATERIAL OF PID OF FIRE MAIN AND WASH DECK - R1 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-16 | 2025-05-30 | 1 | Irfan | 60 | JC150525 19407
55 | 2025-05-16 | W000304 | Check Drawing Output Piping BLOCK EP111P-R3, EP111S-R3, EK111S-R3, EP112P-R2, EP112S-R2, EP132P-R1, EK132P-R1, EP142C-R2, EP413P-R1, EK413P-R1, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-13 | 2025-05-16 | 1 | Asi Supeni | 32 | JC160525 19444
56 | 2025-05-21 | W000308 | ANNEX TO ORDER (ATO) Workshop Machinery | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-02 | 2025-05-06 | 1 | Syafril Riza | 24 | JC210525 19650
57 | 2025-05-21 | W000307 | MAIN EQUIPMENT LIST FOR LCU | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-07 | 2025-05-09 | 1 | Syafril Riza | 24 | JC210525 19651
58 | 2025-05-21 | W000308 | TECHNICAL EVALUATION OF GENERATOR FOR RADIO | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-13 | 2025-05-14 | 1 | Syafril Riza | 16 | JC210525 19653
59 | 2025-05-21 | W000307 | E/R LAYOUT FOR LCU | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-15 | 2025-05-23 | 1 | Syafril Riza | 56 | JC210525 19654
60 | 2025-05-21 | A24A0901 | E15210.34100-R0-SEAT OF AF 11 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-02 | 2025-05-05 | 1 | Amam B | 16 | JC210525 19655
61 | 2025-05-21 | A24A0901 | E25210.01100-R0-EST. MAT FOR SEAT OF AF11 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-06 | 2025-05-06 | 1 | Amam B | 8 | JC210525 19656
62 | 2025-05-21 | A24A0901 | E15240.34100-R0-SEAT OF SW PUMP | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-07 | 2025-05-09 | 1 | Amam B | 24 | JC210525 19657
63 | 2025-05-21 | A24A0901 | E25240.01101-R0-EST MAT FOR SEAT OFSW PUMP | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-13 | 2025-05-13 | 1 | Amam B | 8 | JC210525 19658
64 | 2025-05-21 | A24A0901 | E15291.34100-R0-SEAT OF BILGE PUMP | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-14 | 2025-05-15 | 1 | Amam B | 16 | JC210525 19660
65 | 2025-05-21 | A24A0901 | E25291.01101-R0-EST MAT FOR SEAT OF BILGE PUMP | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-16 | 2025-05-16 | 1 | Amam B | 8 | JC210525 19661
66 | 2025-05-21 | A24A0901 | E25610.01100-R1-EST. MAT FOR SEAT OF STEERING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-19 | 2025-05-19 | 1 | Amam B | 8 | JC210525 19662
67 | 2025-05-21 | A24A0901 | E15210.34100-R1-SEAT OF AF11 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-20 | 2025-05-22 | 1 | Amam B | 24 | JC210525 19665
68 | 2025-05-21 | A24A0901 | E25210.01100-R1-EST. MAT FOR SEAT OF AF11 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-23 | 2025-05-23 | 1 | Amam B | 8 | JC210525 19666
69 | 2025-05-21 | A24A0901 | E25610.01100-R2-EST. MAT FOR SEAT OF STEERING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-26 | 2025-05-26 | 1 | Amam B | 8 | JC210525 19667
70 | 2025-05-21 | A24A0901 | E13131.33100-R2-SEAT OF BATTERY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-27 | 2025-05-28 | 1 | Amam B | 16 | JC210525 19668
71 | 2025-05-21 | A24A0901 | E23131.01100-R2-EST. MATERIAL OF SEAT OF BATTERY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-30 | 2025-05-30 | 1 | Amam B | 8 | JC210525 19672
72 | 2025-05-21 | W305 | E25515.01101-EST.MAT. FOR AIR RESERVOIR AND CONTROL | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-01 | 2025-05-02 | 1 | Nizar Z | 16 | JC210525 19673
73 | 2025-05-21 | W305 | E25410.01100-INPUT PDM IM4 REV.2 EST. MAT. OF FO PURIFYING | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-05 | 2025-05-06 | 1 | Nizar Z | 16 | JC210525 19674
74 | 2025-05-21 | W305 | E25551.01100-INPUT PDM IM4 REV.1 EST. MAT. OF FOAM FIRE EXTINGUISHING LINE (HULL) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-07 | 2025-05-09 | 1 | Nizar Z | 24 | JC210525 19675
75 | 2025-05-21 | W305 | COMPARE MATERIAL PDM VS PENGADAAN MATERIAL PIPE & FITTING | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-12 | 2025-05-16 | 1 | Nizar Z | 48 | JC210525 19676
76 | 2025-05-21 | W305 | E15515.22101- DETAIL DRAWING OF AIR RESERVOIR AND CONTROL VALVE CABINET FOR EMERGENCY SHUT-OFF VALVE (PNEU. OPER) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-19 | 2025-05-23 | 1 | Nizar Z | 48 | JC210525 19677
77 | 2025-05-21 | W305 | E15515.22102-DETAIL DRAWING OF REMOTE SHUT-OFF DEVICE FOR FO. EMERGENCY SHUT-OFF VALVE (WIRE OPERATION) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-26 | 2025-05-30 | 1 | Nizar Z | 48 | JC210525 19679
78 | 2025-05-21 | - | Administrasi Kesekretariatan Divisi Desain | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-01 | 2025-05-31 | 1 | Diar | 168 | JC220525 19701
79 | 2025-05-21 | W000305 | E15331.22101_R2_HOT WATER SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-29 | 2025-05-29 | 1 | Diar | 4 | JC220525 19699
80 | 2025-05-21 | W000308 | E25280.01100_ R1_ESTIMATED MATERIAL FOR INSIDE SCUPPER & DRAINAGE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-30 | 2025-05-30 | 1 | Diar | 4 | JC220525 19703
81 | 2025-05-22 | W000308 | E15072.37100-R0-NAME PLATE OF VALVE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-02 | 2025-05-21 | 1 | Agus | 104 | JC220525 19706
82 | 2025-05-22 | W000304 | E15072.37100-R0-NAME PLATE OF VALVE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-22 | 2025-05-30 | 1 | Agus | 48 | JC220525 19707
83 | 2025-05-22 | W000306 | Shaft and Bearing Loads Calculation | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-01 | 2025-05-31 | 1 | Aditya Prayoga | 40 | JC220525 19708
84 | 2025-05-22 | W000304 | E91002.97119 - Anchor Winch Supporting Structure Analysis Report | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-01 | 2025-05-31 | 1 | Aditya Prayoga | 120 | JC220525 19709
85 | 2025-05-22 | W000304 | REVIEW PACKING LIST & EST. VALVE SW. COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-26 | 2025-05-27 | 1 | Ahmad Khunaifi | 16 | JC220525 19711
86 | 2025-05-22 | W000306 | INPUT ITEM & PART NUMBER MAT. PP-R PIPE & FITTING FOR INQUIRY LIST | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-22 | 2025-05-23 | 1 | Ahmad Khunaifi | 16 | JC220525 19712
87 | 2025-05-22 | W000304 | PROPELLER CAVITATION ANALYSIS | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-26 | 2025-05-30 | 1 | Ardan |  | JC230525 19729
88 | 2025-05-22 | W000304 | E14860.22100-PID OF TRACKING RADAR COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-15 | 2025-05-23 | 1 | Satrio |  | JC230525 19730
89 | 2025-05-22 | W000304 | E14560.22100-PID OF MULTIFUNCTION RADAR COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-26 | 2025-06-06 | 1 | Satrio |  | JC230525 19731
90 | 2025-05-22 | W000304 | E14551.22100-PID OF IFF ANTENNA COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-09 | 2025-06-16 | 1 | Satrio |  | JC230525 19732
91 | 2025-05-26 | A24AOP01 | 3D MODELLING SEAT OF AF11 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-02 | 2025-05-06 | 1 | Rafika |  | JC260525 19878
92 | 2025-05-26 | A24AOP01 | 3D MODELLING VERTICAL LADDER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-07 | 2025-05-09 | 1 | Rafika |  | JC260525 19881
93 | 2025-05-26 | W000308 | E15292.22101 - R4 PIPING DIAGRAM OF WATER BALLAS AND DOCKWELL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-13 | 2025-05-19 | 1 | Rafika |  | JC260525 19885
94 | 2025-05-26 | W000308 | E25292.01101 - R4 EST QTY MAT FOR PIPING DIAGRAM OF WATER BALLAST AND DOCKWELL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-20 | 2025-05-26 | 1 | Rafika |  | JC260525 19890
95 | 2025-05-26 | W000306 | E15280.22100 - R1 PIPING DIAGRAM OF INSIDE SCUPPER AND DRAINAGE | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-05-27 | 2025-05-30 | 1 | Rafika |  | JC260525 19892
96 | 2025-05-26 | W000304 | Check Drawing Output Piping BLOCK EP413S-R1, EK413S-R1, EP122P-R2, EK122P-R2, EP132S-R1, EK132S-R1, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-19 | 2025-05-23 | 1 | Asi Supeni | 40 | JC270525 19954
97 | 2025-05-28 | W000304 | EVATEK BY DESCRIPTION PART RCV PART 2 MAKER HANLA-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-02 | 2025-05-06 | 1 | Kridiyantoro | 24 | JC280525 19990
98 | 2025-05-28 | W308 | CREATE PROSES PENGADAAN VALVE & OTHER PART 2-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-07 | 2025-05-09 | 1 | Kridiyantoro | 24 | JC280525 19991
99 | 2025-05-28 | W308 | EVATEK BY DESCRIPTION PART 1 LIST VALVE AND OTHER MAKER CNJ KOREA-R3 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-13 | 2025-05-16 | 1 | Kridiyantoro | 32 | JC280525 19992
100 | 2025-05-28 | W308 | EVATEK BY DESCRIPTION PART 1 LIST VALVE AND OTHER MAKER CNJ KOREA-R4 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-19 | 2025-05-23 | 1 | Kridiyantoro | 40 | JC280525 19993
101 | 2025-05-28 | W308 | EVATEK BY DESCRIPTION PART 1 LIST VALVE AND OTHER MAKER CNJ KOREA-R5 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-26 | 2025-05-30 | 1 | Kridiyantoro | 32 | JC280525 19994
102 | 2025-05-28 | A24AOP01 | E25510.01100-EST. QTY MATERIAL FOR PIPING DIAGRAM OF COMPRESS AIR SYSTEM-R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-01 | 2025-05-02 | 1 | Miekail | 16 | JC300525 20058
103 | 2025-05-28 | A24AOP01 | REV. 1 PIPE MODELLING, PIPE READY, CHECK PROD. DRAWING AND PIPING ARRANGEMENT BILGE SYSTEM-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-05 | 2025-05-09 | 1 | Miekail | 40 | JC300525 20059
104 | 2025-05-28 | A24AOP01 | REV. 1 PIPE MODELLING, PIPE READY, CHECK PROD. DRAWING AND PIPING ARRANGEMENT SEA WATER COOLING SYSTEM-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-12 | 2025-05-16 | 1 | Miekail | 40 | JC300525 20060
105 | 2025-05-28 | A24AOP01 | REV. 1 PIPE MODELLING, PIPE READY, CHECK PROD. DRAWING AND PIPING ARRANGEMENT COMPRESSED AIR SYSTEM-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-19 | 2025-05-23 | 1 | Miekail | 40 | JC300525 20061
106 | 2025-05-28 | W000308 | E25411.01100-EST. QTY MATERIAL FOR PIPING DIAGRAM OF FO TRANSFER SYSTEM-R3 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-05-26 | 2025-05-30 | 1 | Miekail | 40 | JC300525 20062
107 | 2025-05-30 | W000304 | Check Drawing Output Piping BLOCK EP432P-R2, EK433S-R2, EP432S-R2, EK432S-R2, EP232P-R2, EP122S-R2, EK122S-R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-05-26 | 2025-05-30 | 1 | Asi Supeni | 40 | JC300525 20079
2025-06-09
108 | 2025-06-02 | W000308 | E15221.22100 - EST MATERIAL OF PID OF FIRE MAIN AND WASH DECK - R1 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-02 | 2025-06-30 | 1 | Irfan | 160 | JC040625 20365
1 | 2025-06-02 | W000307 | E1222P.17100 - Pipe Modeling block 222P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-09 | 1 | Dimas | 24 | JC020625 20255
2 | 2025-06-02 | W000307 | E1222S.17100 - Pipe Modeling block 222S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-09 | 1 | Dimas | 24 | JC020625 20257
3 | 2025-06-02 | W000307 | E1223P.17100 - Pipe Modeling block 223P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-10 | 2025-06-19 | 1 | Dimas | 34 | JC030625 20287
4 | 2025-06-02 | W000307 | E1223S.17100 - Pipe Modeling block 223S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-10 | 2025-06-19 | 1 | Dimas | 34 | JC030625 20288
5 | 2025-06-02 | W000307 | E1224P.17100 - Pipe Modeling block 224P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-20 | 2025-06-30 | 1 | Dimas | 28 | JC030625 20289
6 | 2025-06-02 | W000307 | E1224S.17100 - Pipe Modeling block 224S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-20 | 2025-06-30 | 1 | Dimas | 28 | JC030625 20290
7 | 2025-06-02 | W000304 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-30 | 1 | Dimas | 8 | JC030625 20291
8 | 2025-06-02 | W000306 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-30 | 1 | Dimas | 8 | JC030625 20292
9 | 2025-06-02 | W000308 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-30 | 1 | Dimas | 8 | JC030625 20293
10 | 2025-06-02 | W000308 | E1111U.27100 - Pipe Model block 111U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-30 | 1 | Yasin | 40 | JC030625 20294
11 | 2025-06-02 | W000308 | E1112U.27100 - Pipe Model Block 112U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-30 | 1 | Yasin | 40 | JC030625 20295
12 | 2025-06-02 | W000308 | E1211U.27100 - Pipe Model block 211U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-30 | 1 | Yasin | 40 | JC030625 20296
13 | 2025-06-02 | W000308 | Check 3D model (fungsi, operasional, maintenance) & Paparan di SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-30 | 1 | Yasin | 18 | JC030625 20297
14 | 2025-06-02 | W000308 | E12000.10100 - Machinery Arrangement (comment owner) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-30 | 1 | Yasin | 18 | JC030625 20298
15 | 2025-06-02 | W000308 | E11631.10100 - Detail Piping & Seachest Arrangement (comment owner) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-30 | 1 | Yasin | 18 | JC030625 20299
13 | 2025-06-02 | W000305 | E1621S.17100 - Pipe Modeling block 621S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-30 | 1 | Dewi | 48 | JC030625 20300
14 | 2025-06-02 | W000305 | E1622S.17100 - Pipe Modeling block 622S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-30 | 1 | Dewi | 48 | JC030625 20301
15 | 2025-06-02 | W000305 | E1224S.17100 - Pipe Modeling block 224S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-30 | 1 | Dewi | 48 | JC030625 20302
16 | 2025-06-02 | W000305 | E1223S.17100 - Pipe Modeling block 223S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-30 | 1 | Dewi | 48 | JC030625 20303
17 | 2025-06-02 | W000306 | E1123P.17100 - Pipe Modeling block 123P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-07 | 1 | Rizki R | 55 | JC030625 20305
18 | 2025-06-02 | W000306 | E1123S.17100 - Pipe Modeling block 123S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-09 | 2025-06-14 | 1 | Rizki R | 55 | JC030625 20306
19 | 2025-06-02 | W000306 | ES123P.17100 - Pipe Modeling Support block 123P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-16 | 2025-06-21 | 1 | Rizki R | 55 | JC030625 20307
20 | 2025-06-02 | W000306 | ES123S.17100 - Pipe Modeling Support block 123S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-23 | 2025-06-30 | 1 | Rizki R | 55 | JC030625 20308
21 | 2025-06-02 | W000305 | E1312C.17100 - Pipe Modelling Block 312C | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-05 | 1 | Erly | 32 | JC030625 20310
22 | 2025-06-02 | W000305 | E1322C.17100 - Pipe Modelling Block 322C | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-06 | 2025-06-10 | 1 | Erly | 32 | JC030625 20311
23 | 2025-06-02 | W000305 | E1333C.17100 - Pipe Modelling Block 333C | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-11 | 2025-06-14 | 1 | Erly | 32 | JC030625 20316
24 | 2025-06-02 | W000305 | E1124S.17100 - Pipe Modelling Block 124S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-16 | 2025-06-21 | 1 | Erly | 48 | JC030625 20317
25 | 2025-06-02 | W000305 | E1134S.17100 - Pipe Modelling Block 134S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-23 | 2025-06-30 | 1 | Erly | 56 | JC030625 20318
26 | 2025-06-02 | W000308 | E1114U.27100 - Pipe Modelling & Ready in Block 114 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-30 | 1 | Syaiful | 40 | JC030625 20319
27 | 2025-06-02 | W000308 | E1233U.27100 - Pipe Modelling & Ready in Block 233 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-30 | 1 | Syaiful | 40 | JC030625 20320
28 | 2025-06-02 | W000308 | E1234U.27100 - Pipe Modelling & Ready in Block 234 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-30 | 1 | Syaiful | 40 | JC030625 20322
29 | 2025-06-02 | W000308 | Check 3D model (fungsi, operasional, maintenance) & Paparan di SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-30 | 1 | Syaiful | 24 | JC030625 20325
30 | 2025-06-03 | W000305 | EVATEK VALVE TAHAP 2 VENDOR SUN KOREA | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-02 | 2025-06-06 | 1 | Nizar | 40 | JC030625 20326
31 | 2025-06-03 | W000305 | EVATEK VALVE TAHAP 2 VENDOR ILSIN KOREA | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-09 | 2025-06-20 | 1 | Nizar | 80 | JC030625 20327
32 | 2025-06-03 | W000305 | CABINET FOR EMERG. SHUT OFF VALVE PIPE-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-23 | 2025-06-30 | 1 | Nizar | 48 | JC030625 20328
33 | 2025-06-03 | W000308 | MODELING & UPDATE REDRAW CADMATIC PID ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-01 | 2025-06-30 | 1 | AHMAD KHUNAIFI | 60 | JC030625 20329
34 | 2025-06-03 | W000307 | MODELING & UPDATE REDRAW CADMATIC PID ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-01 | 2025-06-30 | 1 | AHMAD KHUNAIFI | 60 | JC030625 20330
35 | 2025-06-03 | W000305 | MODELING & UPDATE REDRAW CADMATIC PID ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-01 | 2025-06-30 | 1 | AHMAD KHUNAIFI | 60 | JC030625 20331
36 | 2025-06-03 | W000304 | E15240.22100 PID OF SEA WATER COOLING SYSTEM REV. 2 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-02 | 2025-06-04 | 1 | AHMAD KHUNAIFI | 24 | JC030625 20332
37 | 2025-06-03 | W000306 | EVATEK PENAWARAN PIPE & FITTING BATCH II (DAIDUCK) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-05 | 2025-06-06 | 1 | AHMAD KHUNAIFI | 16 | JC030625 20333
38 | 2025-06-03 | W000304 | E91002.97121 - Forward Chain Stopper Supporting Structure Analysis Report | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-02 | 2025-06-28 | 1 | Aditya Prayoga | 120 | JC030625 20334
39 | 2025-06-03 | W000304 | E12000.90100 - RECOMMENDABLE OF OIL BRAND TABLE (MACHINERY PART) PCP & CWP | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-02 | 2025-06-07 | 1 | Pratama Akbar |  | JC030625 20361
40 | 2025-06-03 | W000304 | E14560.22100 - PID OF MULTIFUNCTION RADAR COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-02 | 2025-06-06 | 1 | Satrio |  | JC030625 20360
41 | 2025-06-03 | W000304 | EVALUASI TEKNIS APPROVAL DRAWING HVAC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-02 | 2025-06-30 | 1 | Stevan | 20 | JC030625 20350
42 | 2025-06-03 | W000304 | E1414P.18100 - ARR'T OF VENTILATION IN BLOCK 414 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-02 | 2025-06-04 | 1 | Stevan | 20 | JC030625 20351
43 | 2025-06-03 | W000304 | E1414S.18100 - ARR'T OF VENTILATION IN BLOCK 414 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-04 | 2025-06-07 | 1 | Stevan | 20 | JC030625 20352
44 | 2025-06-03 | W000304 | E1424P.18100 - ARR'T OF VENTILATION IN BLOCK 424 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-09 | 2025-06-11 | 1 | Stevan | 20 | JC030625 20353
45 | 2025-06-03 | W000304 | E1424S.18100 - ARR'T OF VENTILATION IN BLOCK 424 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-11 | 2025-06-14 | 1 | Stevan | 20 | JC030625 20354
46 | 2025-06-03 | W000304 | E1434P.18100 - ARR'T OF VENTILATION IN BLOCK 434 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-16 | 2025-06-18 | 1 | Stevan | 20 | JC030625 20355
47 | 2025-06-03 | W000304 | E1434S.18100 - ARR'T OF VENTILATION IN BLOCK 434 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-18 | 2025-06-21 | 1 | Stevan | 20 | JC030625 20356
48 | 2025-06-03 | W000304 | E1214P.18100 - ARR'T OF VENTILATION IN BLOCK 214 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-23 | 2025-06-26 | 1 | Stevan | 20 | JC030625 20357
49 | 2025-06-03 | W000304 | E1214S.18100 - ARR'T OF VENTILATION IN BLOCK 214 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-26 | 2025-06-30 | 1 | Stevan | 20 | JC030625 20358
50 | 2025-06-03 | W000304 | PROPELLER CAVITATION ANALYSIS (COMBINATOR MODE) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-02 | 2025-06-13 | 1 | Ardan |  | JC030625 20359
51 | 2025-06-09 | W000304 | Check Drawing Output Piping BLOCK EP242P-R2, EK242P-R2, EP242S-R2, EK242S-R2, EP232S-R2, EK232S-R2, EP433P-R1, EK433P-R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-02 | 2025-06-05 | 1 | Asi Supeni | 32 | JC090625 20605
52 | 2025-06-10 | W000304 | E15071.37100 - NAME PLATE FOR VENTILATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-09 | 2025-06-21 | 1 | Pratama Akbar |  | JC100625 20609
53 | 2025-06-10 | W000304 | E14511.22100 - PID of Surveillance Radar Cooling System | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-17 | 2025-06-24 | 1 | Satrio |  | JC130625 20713
54 | 2025-06-10 | W000304 | E14560.22100 - PID of Multi Function Radar Cooling System | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-25 | 2025-06-30 | 1 | Satrio |  | JC130625 20714
55 | 2025-06-13 | W000304 | Check Drawing Output Piping BLOCK EP433S-R1, EK433S-R1, EP212S-R2, EK212S-R2, EP212P-R2, EK212P-R2, EP113P-R2, EP402C-R1, EK402C-R1, EP213P-R1, EK213P--R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-09 | 2025-06-13 | 1 | Asi Supeni | 40 | JC130625 20711
56 | 2025-06-13 | W000308 | E15261.22100_R2_PID OF OUTSIDE DECK SCUPPER | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-02 | 2025-06-05 | 1 | Diar Ayu | 32 | JC160625 20846
57 | 2025-06-13 | W000308 | E15280.22100_PID OF INSIDE SCUPPER & DRAINAGE_R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-09 | 2025-06-11 | 1 | Diar Ayu | 24 | JC160625 20847
58 | 2025-06-13 | W000304 | E25312.01100_R1_ESTIMATED MATERIAL FOR FRESH WATER PRODUCTION SYSTEM (REVERSE OSMOSIS) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-12 | 2025-06-13 | 1 | Diar Ayu | 16 | JC160625 20849
59 | 2025-06-13 | W000304 | E15281.22100_R2_PID OF SEWAGE SYSTEM IN ACCOMMODATION | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-16 | 2025-06-18 | 1 | Diar Ayu | 24 | JC160625 20852
60 | 2025-06-13 | W000304 | E15282.22100_R2_PIPING DIAGRAM OF GREY WATER SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-19 | 2025-06-20 | 1 | Diar Ayu | 16 | JC160625 20854
61 | 2025-06-13 | W000304 | E15000.01100_R0_PRINCIPAL PARTICULAR MACHINERY PART | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-23 | 2025-06-30 | 1 | Diar Ayu | 40 | JC160625 20855
62 | 2025-06-13 | W000304 | E1114P.18100_R0_ARR'T OF VENT IN BLOCK 114 TR 1 S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-12 | 2025-06-17 | 1 | AHMAD KHUNAIFI | 32 | JC130625 20767
63 | 2025-06-13 | W308 | E15059.34101-DETAIL DRAWING OF PIPE BAND (CLAMP) FOR GRE PIPE SUPPORT-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-02 | 2025-06-06 | 1 | Amam | 40 | JC130625 20768
64 | 2025-06-13 | A24AOP01 | E13131.33101-BATTERY TRAY-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-09 | 2025-06-12 | 1 | Amam | 32 | JC130625 20769
65 | 2025-06-13 | A24AOP01 | E23131.01101-EST. MATERIAL FOR BATTERY TRAY-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-13 | 2025-06-13 | 1 | Amam | 8 | JC130625 20770
66 | 2025-06-13 | A24AOP01 | E15320.25100-BATTERY CONTROL UNIT RACK-R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-16 | 2025-06-17 | 1 | Amam | 16 | JC130625 20771
67 | 2025-06-13 | W304-305 | E15320.25100-RECOMMENDABLE OF COOLANT-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-18 | 2025-06-23 | 1 | Amam | 32 | JC130625 20772
68 | 2025-06-13 | A24AOP01 | 3D MODELLING BATTERY COVER & ELECTRICAL EQUIPMENT RE ARRANGEMENT POSSITION-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-02 | 2025-06-06 | 1 | Miekail | 40 | JC130625 20773
69 | 2025-06-13 | A24AOP01 | E13043.27100-3D MODELLING CABLE & SENSOR PENETRATION-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-09 | 2025-06-10 | 1 | Miekail | 16 | JC130625 20774
70 | 2025-06-13 | A24AOP01 | E13043.33100-ARRANGEMENT OF CABLE & SENSOR PENETRATION-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-11 | 2025-06-13 | 1 | Miekail | 24 | JC130625 20775
71 | 2025-06-13 | W000304 | E15072.37100-R0-NAME PLATE OF VALVE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-02 | 2025-06-30 | 1 | Agus | 168 | JC130625 20776
72 | 2025-06-13 | W000308 | Technical evaluation of Generator For Radio | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-02 | 2025-06-03 | 1 | Syafril Riza | 16 | JC130625 20777
73 | 2025-06-13 | W000308 | Revision of Equipment List -A0- | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-04 | 2025-06-05 | 1 | Syafril Riza | 16 | JC130625 20778
74 | 2025-06-13 | W000308 | Main equipment list Machinery Part | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-09 | 2025-06-10 | 1 | Syafril Riza | 16 | JC130625 20779
75 | 2025-06-13 | W000304 | Shaft Arrangement – R2 - | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-11 | 2025-06-11 | 1 | Syafril Riza | 8 | JC130625 20780
76 | 2025-06-13 | W000308 | Technical Evaluation for Workshop Machinery | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-12 | 2025-06-13 | 1 | Syafril Riza | 16 | JC130625 20781
77 | 2025-06-16 | A24AOP01 | E19936.95029 - END LAUNCHING ARRANGEMENT & PROCEDURE - R2 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-16 | 2025-06-30 | 1 | Ardan |  | JC160625 20887
78 | 2025-06-19 | A24AOP01 | UPDATE 3D MODELLING BCU RACK LADDER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-02 | 2025-06-03 | 1 | Rafika | 16 | JC190625 21043
79 | 2025-06-19 | A24AOP01 | 3D MODELLING BATTERY TRAY | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-04 | 2025-06-06 | 1 | Rafika | 24 | JC190625 21044
80 | 2025-06-19 | W000304 | E1144P,18100_R0_ARRT. OF VEN IN BLOCK 114 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-09 | 2025-06-13 | 1 | Rafika | 40 | JC190625 21045
81 | 2025-06-19 | W000304 | E1254S.018100_R0_ARR'T. OF VENT IN BLOCK 254 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-19 | 2025-06-23 | 1 | AHMAD KHUNAIFI | 40 | JC190625 21046
82 | 2025-06-19 | W000304 | Check Drawing Output Piping BLOCK EP213P-R1, EK213P-R1, EP213S-R1, EK213S-R1, EP123P-R1, EK123P-R1, EP233P-R1, EK233P-R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-16 | 2025-06-20 | 1 | Asi Supeni | 40 | JC190625 21049
83 | 2025-06-23 | W000304 | E25071.01100 - ESTIMATION MATERIAL FOR NAME PLATE VENTILATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-23 | 2025-06-30 | 1 | Pratama Akbar |  | JC230625 21246
84 | 2025-06-25 | W000304 | E1521S.018100_R0_ARR'T. OF VENT IN BLOCK 521 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-25 | 2025-06-30 | 1 | AHMAD KHUNAIFI | 32 | JC250625 21318
85 | 2025-06-25 | W000304 | REVIEW MAIN ENGINE (MAKER DWG) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-16 | 2025-06-20 | 1 | Syafril Riza | 40 | JC250625 21319
86 | 2025-06-25 | W000304 | REVIEW SHAFT PROPULSION (MAKER DWG) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-23 | 2025-06-30 | 1 | Syafril Riza | 40 | JC250625 21320
87 | 2025-06-25 | W000304 | BLAST DOOR PLRELIMINARY STRENGTH ANALYSIS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-02 | 2025-06-30 | 1 | Aditya Prayoga | 40 | JC250625 21321
88 | 2025-06-25 | W000304 | TOOLS AND INVENTORY R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-02 | 2025-06-30 | 1 | Kridiyantoro | 120 | JC250625 21324
89 | 2025-06-25 | W308 | EVATEK BY DESCRIPTION PART 1 VALVE AND OTHER MAKER CNJ KOREA R6 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-02 | 2025-06-30 | 1 | Kridiyantoro | 48 | JC250625 21325
90 | 2025-06-26 | W000304 | Check Drawing Output Piping BLOCK EP233S-R1, EK233S-R1, EP423P-R1, EK423P-R1, EP113S-R2, EK113S-R2 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-23 | 2025-06-26 | 1 | Asi Supeni | 32 | JC260625 21345
91 | 2025-06-26 | W000304 | E25320.01101-EST. QTY. MAT. FOR RECOMMENDABLE OF WATER COOLANT-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-24 | 2025-06-24 | 1 | Amam | 8 | JC260625 21383
92 | 2025-06-26 | W00308 | E25062.01100-EVALUASI TEKNIS MAKER GRE-R3 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-25 | 2025-06-27 | 1 | Amam | 24 | JC260625 21384
93 | 2025-06-26 | W00304 | E1521P.18100-ARRT. OF VENTILATION IN ACCOM. BLOCK 521 (B07)(P)-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-30 | 2025-06-30 | 1 | Amam | 8 | JC260625 21385
94 | 2025-06-26 | W000304 | Check Drawing Output Piping BLOCK EP423S-R1, EK423S-R1, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-06-30 | 2025-06-30 | 1 | Asi Supeni | 8 | JC300625 21471
95 | 2025-06-30 | A24AOP01 | E13043.33100-ARRANGEMENT OF CABLE & SENSOR PENETRATION-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-11 | 2025-06-13 |  | Miekail | 24 | JC300625 21520
96 | 2025-06-30 | W000304 | E15431.90100-RECOMMENDABLE OF OIL BRAND (MACHINERY PART)-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-16 | 2025-06-20 |  | Miekail | 40 | JC300625 21521
97 | 2025-06-30 | W000304 | E25431.90100-EST. Q'TY MAT. FOR RECOMMENDABLE OF OIL BRAND (MACHINERY PART)-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-23 | 2025-06-24 |  | Miekail | 16 | JC300625 21522
98 | 2025-06-30 | W000306 | E15431.90100-RECOMMENDABLE OF OIL BRAND (MACHINERY PART)-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-06-25 | 2025-06-30 |  | Miekail | 32 | JC300625 21523
2025-07-09
1 | 2025-06-30 | W000304 | E11631.10100 Check drawing Arr't and Detail Sea Chest | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-04 | 1 | Dimas | 32 | JC300625 21502
2 | 2025-06-30 | W000308 | EP123U.42100 Check Drawing Piping Isometrik Block 132 P/S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-05 | 2025-07-08 | 1 | Dimas | 24 | JC300625 21504
3 | 2025-06-30 | W000308 | EP322U.42100 Check Drawing Piping Isometrik Block 322 P/S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-09 | 2025-07-11 | 1 | Dimas | 24 | JC300625 21511
4 | 2025-06-30 | W000308 | E15281.17100 Check Model Black Water system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-12 | 2025-07-17 | 1 | Dimas | 40 | JC300625 21515
5 | 2025-06-30 | W000307 | E15412.17100 Pipe Model Fo Service system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-18 | 2025-07-31 | 1 | Dimas | 98 | JC300625 21516
6 | 2025-06-30 | W000304 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-31 | 1 | Dimas | 8 | JC300625 21517
7 | 2025-06-30 | W000306 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-31 | 1 | Dimas | 8 | JC300625 21518
8 | 2025-06-30 | W000308 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-31 | 1 | Dimas | 8 | JC300625 21534
9 | 2025-06-30 | W000308 | E15292.27100 - Pipe Modelling & Ready Revisi Air Pipe Material GRE | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-31 | 1 | Syaiful | 98 | JC300625 21542
10 | 2025-06-30 | W000308 | E1223U.27100 - Pipe Modelling & Ready in Block 223 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-31 | 1 | Syaiful | 98 | JC300625 21544
11 | 2025-06-30 | W000308 | Check 3D model (fungsi, operasional, maintenance) & Paparan di SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-31 | 1 | Syaiful | 24 | JC300625 21547
12 | 2025-06-30 | W000305 | E1133S.17100 - Pipe Modelling Block 133S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-16 | 1 | Erly | 108 | JC010725 21568
13 | 2025-06-30 | W000305 | E1114S.17100 - Pipe Modelling Block 114S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-17 | 2025-07-31 | 1 | Erly | 100 | JC010725 21569
14 | 2025-06-30 | W000307 | E1113S.17100 - Pipe Modeling block 113S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-13 | 1 | Rizki R | 96 | JC010725 21570
15 | 2025-06-30 | W000307 | E1113P.17100 - Pipe Modeling block 113P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-14 | 2025-07-27 | 1 | Rizki R | 96 | JC010725 21571
16 | 2025-06-30 | W000307 | ES113S.17100 - Pipe Modeling Support block 113S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-28 | 2025-07-31 | 1 | Rizki R | 38 | JC010725 21572
17 | 2025-06-30 | W000308 | E15292.27100 - Pipe model & ready system ballast & dockwell material GRE (stress analisys support & revisi change maker ballast water treatment) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-31 | 1 | Yasin | 80 | JC010725 21573
18 | 2025-06-30 | W000308 | E1311U.27100 - Pipe model block 311 P/S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-31 | 1 | Yasin | 60 | JC010725 21574
19 | 2025-06-30 | W000308 | E1312U.27100 - Pipe model block 312 P/S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-31 | 1 | Yasin | 60 | JC010725 21575
20 | 2025-06-30 | W000308 | Check 3D model (fungsi, operasional, maintenance) & Paparan di SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-31 | 1 | Yasin | 18 | JC010725 21581
21 | 2025-06-30 | W000308 | E15012.33100 - Revisi & ADD Detail of strainer | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-31 | 1 | Yasin | 10 | JC010725 21582
22 | 2025-06-30 | W000308 | E12000.10100 - Machinery Arrangement (comment owner) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-31 | 1 | Yasin | 10 | JC010725 21583
23 | 2025-06-30 | W000308 | E11631.10100 - Detail Piping & Seachest Arrangement (comment owner) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-31 | 1 | Yasin | 10 | JC010725 21584
24 | 2025-06-30 | W000305 | E1234S.17100 - Pipe Modelling Block 234S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-31 | 1 | Dewi | 70 | JC010725 21585
25 | 2025-06-30 | W000305 | E1234P.17100 - Pipe Modelling Block 234P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-31 | 1 | Dewi | 70 | JC010725 21586
26 | 2025-06-30 | W000305 | E1224S.17100 - Pipe Modelling Block 224S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-31 | 1 | Dewi | 70 | JC010725 21587
27 | 2025-06-30 | W000308 | MODELING & UPDATE REDRAW CADMATIC PID ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-01 | 2025-07-31 | 1 | AHMAD KHUNAIFI | 60 | JC010725 21565
28 | 2025-06-30 | W000307 | MODELING & UPDATE REDRAW CADMATIC PID ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-01 | 2025-07-31 | 1 | AHMAD KHUNAIFI | 60 | JC010725 21566
29 | 2025-06-30 | W000305 | MODELING & UPDATE REDRAW CADMATIC PID ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-01 | 2025-07-31 | 1 | AHMAD KHUNAIFI | 60 | JC010725 21567
30 | 2025-06-30 | W000304 | E1244P,18100_R0_ARRT. OF VENT IN BLOCK 224 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-16 | 2025-06-19 | 1 | Rafika | 32 | JC300625 21555
31 | 2025-06-30 | W000304 | E1244S,18100_R0_ARRT. OF VENT IN BLOCK 224 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-20 | 2025-06-25 | 1 | Rafika | 32 | JC300625 21556
32 | 2025-06-30 | W000304 | E1234P,18100_R0_ARRT. OF VENT IN BLOCK 234 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-06-26 | 2025-06-30 | 1 | Rafika | 24 | JC300625 21557
33 | 2025-07-03 | W000304 | E24511.01100 - EST. QTY. MAT. FOR PID OF SURVEILLANCE RADAR COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-01 | 2025-07-03 | 1 | Satrio |  | JC030725 21735
34 | 2025-07-03 | W000304 | E24560.01100 - EST. QTY. MAT. FOR PID OF MULTI FUNCTION RADAR COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-04 | 2025-07-08 | 1 | Satrio |  | JC030725 21736
35 | 2025-07-03 | W000304 | E24551.01100 - EST. QTY. MAT. FOR PID OF HAN IFF ANTENNA COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-09 | 2025-07-11 | 1 | Satrio |  | JC030725 21737
36 | 2025-07-03 | W000304 | E24860.01100 - EST. QTY. MAT. FOR PID OF TRACKING RADAR COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-14 | 2025-07-16 | 1 | Satrio |  | JC030725 21738
37 | 2025-07-03 | W000304 | E1541S.18100 - ARRT. OF VENT IN BLOCK 541 (S) - R0 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-01 | 2025-07-18 | 1 | Irfan |  | JC030725 21739
38 | 2025-07-03 | W000304 | E1531S.18100 - ARRT. OF VENT IN BLOCK 531 (S) - R0 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-21 | 2025-07-31 | 1 | Irfan |  | JC030725 21740
39 | 2025-07-03 | W000304 | EVALUASI TEKNIS APPROVAL DRAWING HVAC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-01 | 2025-07-31 | 1 | Stevan | 20 | JC030725 21741
40 | 2025-07-03 | W000304 | E15142.18100 - ARR'T & DETAIL OF VENTILATOR HEAD FOR AFT & FORE PART | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-01 | 2025-08-09 | 1 | Stevan | 56 | JC030725 21742
41 | 2025-07-03 | W000304 | E15142.18101 - ARR'T & DETAIL OF VENTILATOR HEAD FOR ACCOMODATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-10 | 2025-08-25 | 1 | Stevan | 96 | JC030725 21743
42 | 2025-07-03 | W000304 | SKETCHES FOR MIST ELIMINATOR BOX | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-10 | 2025-08-01 | 1 | Stevan | 40 | JC030725 21745
43 | 2025-07-03 | W000304 | PRELIMINARY BLAST DOOR STRENGTH ANALYSIS (TRANCIENT ANSYS) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-01 | 2025-07-15 | 1 | Ardan |  | JC030725 21746
44 | 2025-07-03 | A24AOP01 | PROPELLER ANALYSIS | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-16 | 2025-07-31 | 1 | Ardan |  | JC030725 21753
45 | 2025-07-03 | W000304 | E1512S.018100_R0_ARR'T. OF VENT IN BLOCK 512 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-02 | 2025-07-03 | 1 | AHMAD KHUNAIFI | 16 | JC030725 21747
46 | 2025-07-03 | W000304 | E1512P.018100_R0_ARR'T. OF VENT IN BLOCK 512 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-04 | 2025-07-05 | 1 | AHMAD KHUNAIFI | 16 | JC030725 21748
47 | 2025-07-03 | W000304 | E15072.37100-R0-NAME PLATE OF VALVE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-01 | 2025-07-31 | 1 | Agus | 184 | JC030725 21749
48 | 2025-07-03 | W000304 | EVATEK VALVE TAHAP 2 VENDOR CNJ -R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-01 | 2025-07-04 | 1 | Nizar Z | 32 | JC030725 21750
49 | 2025-07-03 | W000306 | P&ID of Bilge, Ballast & Fire System for LCU | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-01 | 2025-07-04 | 1 | Syafril Riza | 32 | JC030725 21751
50 | 2025-07-03 | W000304 | E91002.97122 - Starboard Chain Stopper Supporting Structure Analysis Report | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-01 | 2025-07-31 | 1 | Aditya Prayoga | 120 | JC030725 21752
51 | 2025-07-04 | W000304 | E85100,51100 - HVAC SYSTEM & FAN (M) EXPLOSION PROOF FAN REV.C | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-01 | 2025-07-05 | 1 | Pratama Akbar |  | JC040725 21784
52 | 2025-07-04 | W000304 | Check Drawing Output Piping BLOCK EP223P-R1, EK223P-R1, EP123S-R2, EK123S-R2, EP233S-R1, EK233S-R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-01 | 2025-07-04 | 1 | Asi Supeni | 32 | JC040725 21785
53 | 2025-07-07 | W000304 | E1523S.018100_R0_ARR'T. OF VENT IN BLOCK 523 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-04 | 2025-07-05 | 1 | AHMAD KHUNAIFI | 16 | JC070725 21900
54 | 2025-07-07 | W000304 | E1513P.018100_R0_ARR'T. OF VENT IN BLOCK 513 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-07 | 2025-07-09 | 1 | AHMAD KHUNAIFI | 16 | JC070725 21964
55 | 2025-07-07 | W000304 | E1234S.18100_R0 ARRT OF VENT IN BLOCK 234 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-01 | 2025-07-03 | 1 | Rafika |  | JC070725 21962
56 | 2025-07-07 | W000304 | E1652S.18100_R0 ARRT OF VENT IN BLOCK 652 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-04 | 2025-07-08 | 1 | Rafika |  | JC070725 21967
57 | 2025-07-07 | W000304 | E1533S.18100_R0 ARRT OF VENT IN BLOCK 533 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-09 | 2025-07-11 | 1 | Rafika |  | JC070725 21973
58 | 2025-07-07 | W000304 | E11675.10100-R4 ARRANGEMENT AND DET. OF BOTTOM PLUG | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-04 | 2025-07-11 | 1 | Faris | 48 | JC070725 21974
59 | 2025-07-09 | W000304 | E11675.10100-R4 ARRANGEMENT AND DET. OF BOTTOM PLUG | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-04 | 2025-07-11 | 1 | Faris | 48 | JC100725 22077
60 | 2025-07-10 | W000304 | EVATEK VALVE TAHAP 2 VENDOR SUN KOREA R3 & ILSHIN R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-07 | 2025-07-11 | 1 | Nizar Z | 48 | JC100725 22084
61 | 2025-07-11 | W000304 | Check Drawing Output Piping BLOCK EP222P-R2, EK222P-R2, EP222S-R2, EK222S-R2, EP153P-R1, EK153P-R1, EP243S-R1, EK243S-R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-07 | 2025-07-11 | 1 | Asi Supeni | 40 | JC110725 22118
62 | 2025-07-14 | W000304 | E15000.01100_R0_PRINCIPAL PARTICULAR MACHINERY PART | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-01 | 2025-07-31 | 1 | Diar Ayu | 72 | JC140725 22206
63 | 2025-07-14 | W000304 | E25330.01100_R3_ESTIMATED MATERIAL FOR FRESH WATER SANITARY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-08 | 2025-07-11 | 1 | Diar Ayu | 32 | JC140725 22211
64 | 2025-07-14 | W000304 | E25282.01100_R3_ESTIMATED MATERIAL FOR GREY WATER | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-14 | 2025-07-17 | 1 | Diar Ayu | 32 | JC140725 22215
65 | 2025-07-14 | W000304 | E15282.22100_R2_PIPING DIAGRAM OF GREY WATER SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-18 | 2025-07-23 | 1 | Diar Ayu | 32 | JC140725 22227
66 | 2025-07-14 | W000304 | E15281.22100_R2_PIPING DIAGRAM OF SEWAGE SYSTEM IN ACCOMMODATION | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-24 | 2025-07-25 | 1 | Diar Ayu | 16 | JC140725 22240
67 | 2025-07-14 | W000304 | E85100.51100 - HVAC System & Fan (M) Air Handling Unit Rev.B | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-07 | 2025-07-12 | 1 | Pratama Akbar |  | JC140725 22259
68 | 2025-07-14 | W000304 | E85100.51100 - HVAC System & Fan (M) Exhaust Fan Rev.D | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-14 | 2025-07-19 | 1 | Pratama Akbar |  | JC140725 22270
69 | 2025-07-14 | W000308 | E15261.34200_R0_ROSE PLATE FOR DECK SCUPPER | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-14 | 2025-07-18 | 1 | Diar Ayu | 40 | JC140725 22249
70 | 2025-07-15 | W000306 | P&ID of Fuel Oil System for LCU | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-07 | 2025-07-11 | 1 | Syafril Riza | 40 | JC150725 22333
71 | 2025-07-15 | W000306 | P&ID of Cooling System for LCU | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-14 | 2025-07-18 | 1 | Syafril Riza | 40 | JC150725 22334
72 | 2025-07-16 | W000304 | E24511.01100 - Est. Qty. Mat. for PID of Surveillance Radar Cooling System | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-01 | 2025-07-31 | 1 | Satrio | 9 | JC170725 22354
73 | 2025-07-16 | W000304 | E24560.01100 - Est. Qty. Mat. for PID of Multi Function Radar Cooling System | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-01 | 2025-07-31 | 1 | Satrio | 9 | JC170725 22355
74 | 2025-07-16 | W000304 | E24551.01100 - Est. Qty. Mat. for PID of Han IFF Antenna Cooling System | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-01 | 2025-07-31 | 1 | Satrio | 12 | JC170725 22356
75 | 2025-07-16 | W000304 | E24860.01100 - Est. Qty. Mat. for PID of Tracking Radar Cooling System | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-14 | 2025-07-16 | 1 | Satrio | 9 | JC170725 22362
76 | 2025-07-16 | W000304 | E25164.01100 - R1 - Est. Qty. Mat. for PID of Chilled Water Drain | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-17 | 2025-07-18 | 1 | Satrio | 24 | JC170725 22364
77 | 2025-07-16 | W000304 | E15164.22100 - R1 - PID of Chilled Water Drain | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-21 | 2025-07-25 | 1 | Satrio | 46 | JC170725 22365
78 | 2025-07-18 | W000304 | Check Drawing Output Piping BLOCK EP243P-R1, EK243P-R1, EP153S-R1, EK153S-R1, EP643C-R0, EK643C-R0, EP234P-R1, EK234P-R1,EP234S-R1, EK234S-R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-14 | 2025-07-18 | 1 | Asi Supeni | 40 | JC180725 22386
79 | 2025-07-18 | W000304 | EVATEK PIPE & FITTING TAHAP 3 VENDOR SJ METAL & SEPCO KOREA R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-14 | 2025-07-18 | 1 | Nizar Z | 48 | JC180725 22401
80 | 2025-07-18 |  | SHIP POWERING FPB 37 METER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-21 | 2025-07-23 |  | Ardan |  | JC210725 22491
81 | 2025-07-19 | W000306 | EVATEK PENAWARAN PIPE & FITTING BATCH II (SEPCO-KOREA) LD PHILIPPINES #1 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-10 | 2025-07-14 | 1 | AHMAD KHUNAIFI | 32 | JC210725 22487
82 | 2025-07-19 | W000306 | EVATEK PENAWARAN PIPE & FITTING BATCH II (SJ METAL-KOREA) LD PHILIPPINES #1 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-21 | 2025-07-22 | 1 | AHMAD KHUNAIFI | 16 | JC210725 22494
83 | 2025-07-19 | W000308 | EVATEK PIPE & FITTING TAHAP 3 VENDOR SJ METAL & SEPCO KOREA R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-21 | 2025-07-25 | 1 | Nizar Z | 48 | JC210725 22499
84 | 2025-07-21 | W000304 | E85100.51100 - HVAC System & Fan (M) Engine Room Fan Rev.B | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-21 | 2025-07-26 | 1 | Pratama Akbar |  | JC220725 22572
85 | 2025-07-21 | W304 | E1521P.18100-ARRT. OF VENTILATION IN ACCOM. BLOCK 521 (B07)(P)-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-01 | 2025-07-05 | 1 | Amam | 32 | JC220725 22577
86 | 2025-07-21 | W304 | E1512P.18100-ARRT. OF VENTILATION IN ACCOM. BLOCK 512 (BR6)(P)-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-07 | 2025-07-11 | 1 | Amam | 40 | JC220725 22578
87 | 2025-07-21 | A24AOP01 | E11002.03113-RUDDER CONSTRUCTION-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-14 | 2025-07-15 | 1 | Amam | 16 | JC220725 22579
88 | 2025-07-21 | W304 | E25320.01101-EST. QTY. MAT. FOR RECOMMENDABLE OF WATER COOLANT-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-16 | 2025-07-18 | 1 | Amam | 24 | JC220725 22581
89 | 2025-07-21 | W308 | E15312.22100-EST. QTY. MAT. FOR PID OF FRESH WATER PRODUCTION (REVERSE OSMOSIS)-R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-21 | 2025-07-25 | 1 | Amam | 40 | JC220725 22583
90 | 2025-07-21 | W000304 | EP134P/S, EP144P/S, Pipe Modelling Isometric Blok 134P/S, EP144P/S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-14 | 2025-07-18 | 1 | Faris | 40 | JC220725 22587
91 | 2025-07-22 | A24AOP01 | 3D Modelling Jet Pump | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-01 | 2025-07-07 | 1 | Firman |  | JC220725 22588
92 | 2025-07-22 | W000304 | Calculation for Fire Pump Configuration | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-08 | 2025-07-18 | 1 | Firman |  | JC220725 22590
93 | 2025-07-22 | W000308 | Calculation for Fire Extinguishing System-R1 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-21 | 2025-07-31 | 1 | Firman |  | JC220725 22591
94 | 2025-07-22 | W000304 | E1524P.18100_R0_ARRT OF VEN IN BLOCK 524 (CO2) (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-14 | 2025-07-16 | 1 | Rafika |  | JC220725 22592
95 | 2025-07-22 | W000304 | E1514C.18100_R0_ARRT OF VEN IN BLOCK 514(CO1) (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-17 | 2025-07-21 | 1 | Rafika |  | JC220725 22593
96 | 2025-07-24 | W000304 | Rev. 4-PID of Grey Water System- E15282.22100 (Update Galley) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-28 | 2025-08-08 | 1 | Satrio | 40 | JC280725 22862
97 | 2025-07-25 | W000306 | P&ID of Exhaust Gas System for LCU | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-21 | 2025-07-25 | 1 | Syafril Riza | 40 | JC250725 22677
98 | 2025-07-25 | W000306 | P&ID of F.W & Sewage System for LCU | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-28 | 2025-07-31 | 1 | Syafril Riza | 40 | JC250725 22680
99 | 2025-07-25 | W000304 | E91002.97119 - Anchor Winch Supporting Structure Analysis Report - R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-21 | 2025-07-31 | 1 | Aditya Prayoga | 56 | JC250725 22681
100 | 2025-07-25 | W000304 | Check Drawing Output Piping BLOCK EP653C-R0, EK653C-R0, EP254S-R1, EK254S-R1, EP254P-R1, EK254P-R1, EP224P-R1, EK224P-R1,EP224S-R1, EK224S-R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-21 | 2025-07-25 | 1 | Asi Supeni | 40 | JC250725 22688
101 | 2025-07-28 | W000304 | Check Drawing Output Piping BLOCK EP313C-R2, EK313C-R2, EP434S-R1, EK434S-R1, EP434P-R1, EK434P-R1, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-07-28 | 2025-07-31 | 1 | Asi Supeni | 32 | JC280725 22859
102 | 2025-07-28 | W000304 | Check Drawing Output Piping BLOCK EP114S-R1, EK114S-R1, EP114P-R1, EK114P-R1, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-01 | 2025-08-01 | 1 | Asi Supeni | 8 | JC280725 22860
103 | 2025-07-28 | W308 | E15312.27100-PIPE MODELING SYSTEM FRESH WATERPRODUCTION (REVERSE OSMOSIS)-R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-28 | 2025-07-31 | 1 | Amam | 32 | JC280725 22861
104 | 2025-07-28 | W308 | CREATE PROSES PENGADAAN VALVE & OTHER PART 2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-01 | 2025-07-31 | 1 | Krisdiyantoro | 184 | JC290725 22890
105 | 2025-07-28 | W000304 | E1531S.18100_R0_Arrangements Of Vent Block 531 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-01 | 2025-08-08 | 1 | Irfan |  | JC290725 22891
106 | 2025-07-28 | W000304 | E1652P.18100_R0_Arrangements Of Vent Block 652 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-11 | 2025-08-22 | 1 | Irfan |  | JC290725 22892
107 | 2025-07-28 | W000304 | E1523P.18100_R0_Arrangements Of Vent Block 523 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-25 | 2025-08-29 | 1 | Irfan |  | JC290725 22897
108 | 2025-07-28 | W000304 | E85100.51100_HVAC System & Fan (M) Fan Coil Unit Rev.C | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-28 | 2025-07-31 | 1 | Pratama Akbar |  | JC290725 22898
109 | 2025-07-28 | W000304 | EP134S.42100_R0_Piping Isometric in "2" Deck Block : 134(S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-14 | 2025-07-17 | 1 | Faris |  | JC290725 22899
110 | 2025-07-28 | W000304 | EP134P.42100_R0_Piping Isometric in "2" Deck Block : 134(P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-18 | 2025-07-24 | 1 | Faris |  | JC290725 22900
111 | 2025-07-28 | W000304 | E11675.10.100_R5_Bottom plug Frigate 140 M | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-23 | 2025-07-25 | 1 | Faris |  | JC290725 22904
112 | 2025-07-28 | W000304 | EP144S.42100_Piping Isometric in "2" Deck Block : 144(S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-28 | 2025-07-30 | 1 | Faris |  | JC290725 22905
113 | 2025-07-28 | W000304 | EP144P.42100_Piping Isometric in "2" Deck Block : 144(P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-28 | 2025-07-30 | 1 | Faris |  | JC290725 22906
114 | 2025-07-29 | W000304 | EVATEK VALVE TAHAP 2 VENDOR CNJ -R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-28 | 2025-07-31 | 1 | Nizar Z | 40 | JC290725 22907
115 | 2025-07-30 | W000304 | E1612S.18100-Arrt of Vent. in Block 612 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-01 | 2025-07-31 | 1 | Satrio | 12 | JC300725 22951
116 | 2025-07-30 | W308 | E1511S.18100-ARR'T OF VENT. IN ACCOM. BLOCK 511 (BO6) (S) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-01 | 2025-07-04 | 1 | Miekail |  | JC300725 22957
117 | 2025-07-30 | A24AOP01 | MENGAWAL DAN MEMBANTU PROSES HAT DAN SAT KSOT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-07 | 2025-07-11 | 1 | Miekail |  | JC300725 22958
118 | 2025-07-30 | W308 | E1511P.18100-ARR'T OF VENT. IN ACCOM. BLOCK 511 (BO6) (P) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-14 | 2025-07-17 | 1 | Miekail |  | JC300725 22959
119 | 2025-07-30 | W308 | E1532P.18100-ARR'T OF VENT. IN ACCOM. BLOCK 532 (BR8) (P) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-18 | 2025-07-22 | 1 | Miekail |  | JC300725 22960
120 | 2025-07-30 | W308 | E1532S.18100-ARR'T OF VENT. IN ACCOM. BLOCK 532 (BR8) (S) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-23 | 2025-07-25 | 1 | Miekail |  | JC300725 22961
121 | 2025-07-30 | A24AOP01 | E25510.01100-EST. QTY MATERIAL FOR PIPING DIAGRAM OF COMPRESS AIR SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-07-28 | 2025-07-31 | 1 | Miekail |  | JC300725 22962
122 | 2025-07-30 | W306 | E15280.22100-R2-PIPING DIAGRAM OF INSIDE SCUPPER AND DRAINAGE | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-22 | 2025-07-25 | 1 | Rafika |  | JC300725 22963
123 | 2025-07-30 | W308 | E15161.22100-R3-PIPING DIAGRAM CHILLED WATER SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-28 | 2025-07-31 | 1 | Rafika |  | JC300725 22964
27 | 2025-07-31 | W000304 | E11675.10.100-RA1 Bottom plug Frigate 140M | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-07-29 | 2025-07-31 | 1 | Faris |  | JC010825 23095
2025-08-09
1 | 2025-07-31 | W000306 | FINAL REVIEW DRAFT ANNEX BOLT-NUT & GASKET PROJECT LD PHILIPPINES #1 ALL SYSTEM FOR | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-01 | 2025-08-05 | 1 | AHMAD KHUNAIFI | 24 | JC310725 22970
2 | 2025-07-31 | W000308 | UPDATE MODEL & SPECIFICATION PID CADMATIC ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-01 | 2025-08-30 | 1 | AHMAD KHUNAIFI | 80 | JC310725 22971
3 | 2025-07-31 | W000307 | UPDATE MODEL & SPECIFICATION PID CADMATIC ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-01 | 2025-08-30 | 1 | AHMAD KHUNAIFI | 80 | JC310725 22972
4 | 2025-07-31 | W000305 | UPDATE MODEL & SPECIFICATION PID CADMATIC ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-01 | 2025-08-30 | 1 | AHMAD KHUNAIFI | 80 | JC310725 22973
5 | 2025-07-31 | W000307 | E15412.17100 Pipe Model Fo Service system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-01 | 2025-08-15 | 1 | Dimas | 100 | JC010825 23016
6 | 2025-07-31 | W000307 | E14372.17100 Pipe Model Tank Level system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-16 | 2025-08-31 | 1 | Dimas | 100 | JC010825 23018
7 | 2025-07-31 | W000304 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-01 | 2025-08-31 | 1 | Dimas | 8 | JC010825 23019
8 | 2025-07-31 | W000306 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-01 | 2025-08-31 | 1 | Dimas | 8 | JC010825 23020
9 | 2025-07-31 | W000308 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-01 | 2025-08-31 | 1 | Dimas | 8 | JC010825 23021
10 | 2025-07-31 | W000308 | E15292.27100 - Pipe Modelling & Ready Revisi Fitting NOV ke FPI pada Air Pipe Material GRE | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-01 | 2025-08-31 | 1 | Syaiful | 98 | JC010825 23022
11 | 2025-07-31 | W000308 | E1114U.27100 - Pipe Modelling & Ready in Block 114 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-01 | 2025-08-31 | 1 | Syaiful | 98 | JC010825 23023
12 | 2025-07-31 | W000308 | Check 3D model (fungsi, operasional, maintenance) & Paparan di SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-01 | 2025-08-31 | 1 | Syaiful | 24 | JC010825 23024
13 | 2025-07-31 | W000307 | ES113S.17100 - Pipe Modeling Support block 113S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-01 | 2025-08-09 | 1 | Rizki R | 62 | JC010825 23025
14 | 2025-07-31 | W000307 | E1113S.17100 - Pipe Modeling block 113S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-10 | 2025-08-17 | 1 | Rizki R | 54 | JC010825 23032
15 | 2025-07-31 | W000307 | E1233S.17100 - Pipe Modeling block 233S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-18 | 2025-08-31 | 1 | Rizki R | 110 | JC010825 23033
16 | 2025-07-31 | W000308 | E1221U .27100 - Pipe Model block 221 P/S Engine Room | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-01 | 2025-08-31 | 1 | Yasin | 62 | JC010825 23034
17 | 2025-07-31 | W000308 | E1222U.27100 - Pipe Model block 222 P/S Engine Room | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-01 | 2025-08-31 | 1 | Yasin | 62 | JC010825 23035
18 | 2025-07-31 | W000308 | Preparation and Presentation at SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-01 | 2025-08-31 | 1 | Yasin | 18 | JC010825 23036
19 | 2025-07-31 | W000308 | Evatek GRE Pipe Ballast Custom | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-01 | 2025-08-31 | 1 | Yasin | 46 | JC010825 23051
20 | 2025-07-31 | W000305 | E1114P.17100 - Pipe Modelling Block 114P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-01 | 2025-08-16 | 1 | Erly | 92 | JC010825 23053
21 | 2025-07-31 | W000305 | E1124P.17100 - Pipe Modelling Block 124P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-18 | 2025-08-31 | 1 | Erly | 92 | JC010825 23054
22 | 2025-07-31 | W000305 | E1433S.17100 - Pipe Modeling block 433S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-01 | 2025-08-31 | 1 | Dewi | 48 | JC010825 23056
23 | 2025-07-31 | W000305 | E1213S.17100 - Pipe Modeling block 213S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-01 | 2025-08-31 | 1 | Dewi | 48 | JC010825 23060
24 | 2025-07-31 | W000305 | E1213P.17100 - Pipe Modeling block 213P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-01 | 2025-08-31 | 1 | Dewi | 48 | JC010825 23063
25 | 2025-07-31 | W000305 | E1223S.17100 - Pipe Modeling block 223S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-01 | 2025-08-31 | 1 | Dewi | 48 | JC010825 23066
26 | 2025-07-31 | W000304 | Check Drawing Output Piping BLOCK EP214P-R1, EK214P-R1, EP214S-R1, EK214S-R1, EP134P-R1, EK134P-R1, EP313C-R2, EK312C-R2, EP244S-R1, EK244S-R1, EP531S-R1, EK531S-R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-04 | 2025-08-08 | 1 | Asi Supeni | 40 | JC050825 23279
27 | 2025-07-31 | W000304 | EVALUASI TEKNIS APPROVAL DRAWING HVAC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-01 | 2025-08-29 | 1 | Stevan | 20 | JC010825 23069
28 | 2025-07-31 | W000304 | E15142.33200 - SKETCHES FOR MIST ELIMINATOR BOX | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-01 | 2025-08-08 | 1 | Stevan | 40 | JC010825 23071
29 | 2025-07-31 | W000308 | E25141.01100 - EST. MAT. FOR AIR CONDITION SYSTEM (HULL PART) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-11 | 2025-08-15 | 1 | Stevan | 40 | JC010825 23072
30 | 2025-07-31 | W000308 | E15141.28100 - DIAGRAM OF AIR CONDITIONING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-18 | 2025-08-30 | 1 | Stevan | 80 | JC010825 23073
31 | 2025-08-04 | W000308 | E15280.22100_R2_PID OF INSIDE SCUPPER & DRAINAGE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-01 | 2025-08-06 | 1 | Diar | 32 | JC040825 23168
32 | 2025-08-04 | W000308 | E15261.34200_R0_ROSE PLATE FOR DECK SCUPPER | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-07 | 2025-08-13 | 1 | Diar | 40 | JC040825 23186
33 | 2025-08-04 | W000306 | E15000.01100_R0_PRINCIPAL PARTICULAR MACHINERY PART | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-14 | 2025-08-22 | 1 | Diar | 56 | JC040825 23187
34 | 2025-08-04 | W000304 | E15000.01100_R0_PRINCIPAL PARTICULAR MACHINERY PART | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-25 | 2025-08-29 | 1 | Diar | 40 | JC040825 23188
35 | 2025-08-04 | W000304 | E15162.25100_Piping Diagram Refrigeration Provision Store (M) Review Rev. H | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-01 | 2025-08-08 | 1 | Pratama Akbar |  | JC040825 23206
36 | 2025-08-05 | A24AOP01 | KAJIAN TEKNIS KOMPARASI MESIN DAN LAMBUNG | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-01 | 2025-08-08 |  | Ardan |  | JC050825 23301
37 | 2025-08-05 | A24AOP01 | DESAIN JIG LIGHT WEIGHT TORPEDO | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-11 | 2025-08-15 |  | Ardan |  | JC050825 23302
38 | 2025-08-05 | W308 | E15282.22100 - PID of Grey Water System - Rev.4 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-01 | 2025-08-15 | 1 | Satrio | 57 | JC050825 23319
39 | 2025-08-05 | W304 | E15261.22100 - PID of Scupper and Deck Drains - Rev.2 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-01 | 2025-08-22 | 1 | Satrio | 60 | JC050825 23320
40 | 2025-08-07 | W304 | EVATEK VALVE & INSTRUMENT TAHAP 2 VENDOR CNJ | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-01 | 2025-08-08 | 1 | NIZAR | 55 | JC070825 23371
41 | 2025-08-07 | W304 | E15072.37100-R0-NAME PLATE OF VALVE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-01 | 2025-08-08 | 1 | TEO | 48 | JC070825 23376
42 | 2025-08-07 | W304 | E11675.10100 - Rev A1. Bottom plug Frigate 140 M | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-01 | 2025-08-04 |  | Faris |  | JC070825 23379
43 | 2025-08-07 | W304 | E1213P.12100 - Piping Isometric in 3-Deck Block : EP213 (P) System 5512 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-05 | 2025-08-05 |  | Faris |  | JC070825 23380
44 | 2025-08-07 | W304 | E1114P.12100 - Pipinh Isometric in 2-Deck Block : EP114 (P) System 5331 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-06 | 2025-08-06 |  | Faris |  | JC070825 23381
45 | 2025-08-07 | W304 | E1213P/S.12100 - E1234P/S.12100 - Piping Isometric in Baseline Deck until 02_Deck | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-07 | 2025-08-08 |  | Faris |  | JC070825 23383
46 | 2025-08-07 | W304 | E1651P/S.12100 - Piping Isometric in 01-Deck Block : EP651 (P/S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-11 | 2025-08-13 |  | Faris |  | JC070825 23384
47 | 2025-08-11 | W306 | E1213P/S.12100 - E1234P/S.12100 - Piping Isometric in Baseline Deck until 02_Deck | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-07 | 2025-08-08 |  | Faris |  | JC110825 23586
48 | 2025-08-11 | W304 | E85100.51100 - HVAC System & Fan (M) Supply Fan for Decontamination Room Station Rev.B | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-11 | 2025-08-15 |  | Pratama Akbar |  | JC110825 23587
49 | 2025-08-14 | W304 | EVATEK VALVE & INSTRUMENT TAHAP 2 VENDOR CNJ | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-11 | 2025-08-15 | 1 | NIZAR | 50 | JC140825 23655
50 | 2025-08-14 | W304 | E15072.37100-R0-NAME PLATE OF VALVE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-11 | 2025-08-29 | 1 | TEO | 120 | JC140825 23656
51 | 2025-08-15 | W000304 | Check Drawing Output Piping BLOCK EP244P-R1, EK244P-R1, EP143P-R1, EK143P-R1, EP143S-R1, EK143S-R1, EP511P-R1, EK511P-R1, EP511S-R1, EK511S-R1, EP521P-R1, EK521P-R1, EP521S-R1, EK521S-R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-11 | 2025-08-15 | 1 | Asi Supeni | 40 | JC150825 23678
52 | 2025-08-18 | W306 | E1111P.12100 - Piping Isometric in Double Bottom Block : EP111 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-14 | 2025-08-14 |  | Faris |  | JC190825 23858
53 | 2025-08-18 | W306 | E1111S.12100 - Piping Isometric in Double Bottom Block : EP111 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-15 | 2025-08-15 |  | Faris |  | JC190825 23859
54 | 2025-08-18 | W306 | E1113P/S.12100 - Piping Isometric in 02_Deck | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-18 | 2025-08-20 |  | Faris |  | JC190825 23860
55 | 2025-08-18 | W304 | E15071.37100 - Name Plate for Ventilation R2 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-18 | 2025-08-29 |  | Pratama Akbar |  | JC190825 23861
56 | 2025-08-18 | A24AOP01 | E17521.33101 - Torpedo Saddle Jig - R0 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-18 | 2025-08-22 |  | Ardan |  | JC190825 23864
57 | 2025-08-18 | A24AOP01 | E17521.33101 - Torpedo Tube - R0 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-25 | 2025-08-29 |  | Ardan |  | JC190825 23866
58 | 2025-08-19 | W304 | E15072.37200-R0-CAUTION PLATE FOR EQUIPMENT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-18 | 2025-08-29 | 1 | TEO | 85 | JC190825 23868
59 | 2025-08-19 | W304 | LIST PENGADAAN VALVE TAHAP 3 (SYSTEM FFBNW & INVENTORY) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-18 | 2025-08-22 | 1 | NIZAR | 50 | JC190825 23874
60 | 2025-08-21 | W000304 | Check Drawing Output Piping BLOCK EP531P-R1, EK531P-R1, EP223S-R1, EK223S-R1, EP414P-R1, EK414P-R1, EP414S-R1, EK414S-R1, EP124P-R1, EK124P-R1, EP515C-R1, EK515C-R1, EP683C-R1, EK683C-R1, EP124-R1,EK124S-R1,EP424P-R1,EK424P-R1,EP424S-R1,EK424S-R1,EP651P-R1,EK651P-R1,EP651S-R1,EK651S-R1,EP133P-R1,EK133P-R1,EP532P-R1. | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-17 | 2025-08-22 | 1 | Asi Supeni | 45 | JC210825 23936
61 | 2025-08-26 | W304 | LIST PENGADAAN VALVE TAHAP 3 (SYSTEM FFBNW & INVENTORY) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-25 | 2025-08-29 | 1 | NIZAR | 40 | JC270825 24144
62 | 2025-08-26 | W000304 | E91002.97119 - Anchor Winch Supporting Structure Analysis Report - R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-01 | 2025-08-31 | 1 | Aditya Prayoga | 48 | JC270825 24145
63 | 2025-08-26 | W000308 | ANALYSIS OF DUCTING PRESSURE LOSS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-01 | 2025-08-31 | 1 | Aditya Prayoga | 120 | JC270825 24146
64 | 2025-08-26 | W000308 | E15312.27100 - PIPE MODELING SYSTEM FRESH WATERPRODUCTION (REVERSE OSMOSIS) - R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-01 | 2025-08-01 | 1 | Amam Baharullah | 8 | JC270825 24153
65 | 2025-08-26 | W000308 | E25062.01100 - EST. QTY. MAT. FOR PID OF AIR PIPE - R4 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-04 | 2025-08-05 | 1 | Amam Baharullah | 16 | JC270825 24154
66 | 2025-08-26 | W000304 | E15515.22100 - PID OF CONTROL AIR FOR EMERGENCY SHUT OFF VALVE - R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-06 | 2025-08-07 | 1 | Amam Baharullah | 16 | JC270825 24155
67 | 2025-08-26 | W000304 | E15513.27100 - PIPE MODELING OF LAOW PRESSURE AIR SYSTEM - R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-08 | 2025-08-31 | 1 | Amam Baharullah | 128 | JC270825 24156
68 | 2025-08-27 | A24AOP01 | 3D Modelling Air Compressor Skid and Trolley | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-01 | 2025-08-08 | 1 | Firman |  | JC270825 24157
69 | 2025-08-27 | W308 | Calculation for Fire Extinguishing System-R1 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-08 | 2025-08-18 | 1 | Firman |  | JC270825 24165
70 | 2025-08-27 | W304 | Calculation for Fire Pump Configuration | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-19 | 2025-08-29 | 1 | Firman |  | JC270825 24166
71 | 2025-08-27 | W306 | E1112P/S.12100 - Piping Isometric in 02_Deck | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-21 | 2025-08-21 | 1 | Faris |  | JC270825 24167
72 | 2025-08-27 | W304 | EP134S.42100 - Piping Isometric in "2" Deck Block : 134(S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-22 | 2025-08-29 | 1 | Faris |  | JC270825 24168
73 | 2025-08-27 | W304 | E15164.22100 - PID of Chilled Water Drain - R1 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-25 | 2025-08-30 | 1 | Satrio | 46 | JC270825 24169
74 | 2025-08-27 | W000307 | Machinery Layout for LCU | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-01 | 2025-08-08 | 1 | Syafril Riza |  | JC270825 24170
75 | 2025-08-27 | W000307 | Technical Evaluation of Main Engine for LCU | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-11 | 2025-08-15 | 1 | Syafril Riza |  | JC270825 24171
76 | 2025-08-27 | W000307 | Technical Evaluation of Generator for LCU | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-18 | 2025-08-22 | 1 | Syafril Riza |  | JC270825 24172
77 | 2025-08-27 | W000307 | Technical Evaluation of Water Jet for LCU | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-25 | 2025-08-29 | 1 | Syafril Riza |  | JC270825 24173
78 | 2025-08-28 | W000308 | EVATEK RCV ELECTRICAL TYPE MAKER HANLA_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-01 | 2025-08-08 | 1 | Krisdiyantoro | 48 | JC280825 24188
79 | 2025-08-28 | W000308 | EVATEK RCV ELECTRICAL TYPE MAKER IMSI_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-11 | 2025-08-15 | 1 | Krisdiyantoro | 40 | JC280825 24192
80 | 2025-08-28 | W000306 | CREATE PROSES PENGADAAN VALVE & OTHER PART 2_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-18 | 2025-08-22 | 1 | Krisdiyantoro | 40 | JC280825 24196
81 | 2025-08-28 | W000306 | CREATE PROSES PENGADAAN VALVE & OTHER PART 2_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-25 | 2025-08-29 | 1 | Krisdiyantoro | 40 | JC280825 24197
82 | 2025-08-28 | W304 | E14530. 22100 - PIPING DIAGRAM OF MAR-D ANTENA DY AIR CIRCUIT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-01 | 2025-09-19 | 1 | Irfan | 117 | JC280825 24198
83 | 2025-08-28 | W304 | E24530. 01100 - EST. QTY. MAT FOR PIPING DIAGRAM OF MAR-D ANTENA DRY AIR CIRCUIT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-22 | 2025-09-30 | 1 | Irfan | 55 | JC280825 24203
84 | 2025-08-28 | W308 | REV2 - E15162.25100 - PIPING DIAGRAM OF REFRIGERATION AND PROVISION STORE | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-01 | 2025-08-05 | 1 | Rafika |  | JC280825 24204
85 | 2025-08-28 | W308 | REV1 - E25162.01101 - EST MAT PIPING DIAGRAM OF REFRIGERATION AND PROVISION STORE | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-06 | 2025-08-08 | 1 | Rafika |  | JC280825 24205
86 | 2025-08-28 | W308 | REV3 - E15161.22100 - PIPING DIAGRAM OF CHILLED WATER SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-11 | 2025-08-18 | 1 | Rafika |  | JC280825 24206
87 | 2025-08-28 | W308 | REV1 - E25161.01101 - EST MAT PIPING DIAGRAM OF CHILLED WATER SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-19 | 2025-08-22 | 1 | Rafika |  | JC280825 24207
88 | 2025-08-28 | W308 | REV1 - E15262.22101 - EST MAT PIPING DIAGRAM OF WATER BALLAST AND WATER DOCKWELL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-25 | 2025-08-29 | 1 | Rafika |  | JC280825 24208
89 | 2025-08-29 | W304 | Check Drawing Output Piping BLOCK EP632P-R1, EK632P-R1, EP632S-R1, EK632S-R1, EP693C-R0, EK693C-R0, EP133S-R1, EK133S-R1, EP621S-R1, EK621S-R0, EP532S-R1, EP611P-R1, EK611S-R1, EP611S-R1, EK611S-R1, EP612S-R1, EK612S-R1, EP623C-R1, EK623C-R1, EP673P-R1, EK673P-R1, EP154P-R2, EK154P-R2, EP314C-R2, EK314C-R2, EP663S-R1, EK663S-R1, EP621P-R1, EK621P-R1, EP134S-R1, EK134S-R1. | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-08-25 | 2025-08-29 | 1 | Asi Supeni | 30 | JC290825 24225
90 | 2025-08-29 | W304 | E1511S.18100-ARR'T OF VENT. IN ACCOM. BLOCK 511 (BO6) (S)-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-01 | 2025-08-01 | 1 | Miekail | 8 | JC290825 24226
91 | 2025-08-29 | W304 | E14511.27100-PIPE MODEL SURVEILANCE RADAR COOLING SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-04 | 2025-08-08 | 1 | Miekail | 40 | JC290825 24227
92 | 2025-08-29 | W304 | E14551.27100-PIPE MODEL HAN IFF ANTENA COOLING SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-11 | 2025-08-15 | 1 | Miekail | 40 | JC290825 24229
93 | 2025-08-29 | W304 | E14560.27100-PIPE MODEL MULTI FUCTION RADAR COOLING SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-18 | 2025-08-22 | 1 | Miekail | 40 | JC290825 24230
94 | 2025-08-29 | W304 | E14860.27100-PIPE MODEL TRACKING RADAR COOLING SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-08-25 | 2025-08-29 | 1 | Miekail | 40 | JC290825 24232
2025-09-09
1 | 2025-09-01 | W000304 | E13410.17100 Pipe Model FO LO Drain System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-01 | 2025-09-15 | 1 | Dimas | 100 | JC010925 24340
2 | 2025-09-01 | W000307 | E15412.17100 Pipe Model FO Service System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-16 | 2025-09-30 | 1 | Dimas | 100 | JC010925 24341
3 | 2025-09-01 | W000304 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-01 | 2025-09-30 | 1 | Dimas | 8 | JC010925 24342
4 | 2025-09-01 | W000306 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-01 | 2025-09-30 | 1 | Dimas | 8 | JC010925 24343
5 | 2025-09-01 | W000308 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-01 | 2025-09-30 | 1 | Dimas | 8 | JC010925 24366
6 | 2025-09-01 | W000308 | E15330.27100 - Pipe Modelling of Fresh Water Sanitary Service System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-01 | 2025-09-30 | 1 | Syaiful | 136 | JC010925 24371
7 | 2025-09-01 | W000308 | Check 3D model (fungsi, operasional, maintenance) & Paparan di SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-01 | 2025-09-30 | 1 | Syaiful | 24 | JC010925 24372
8 | 2025-09-01 | W000305 | E1134P.17100 - Pipe Modelling Block 134P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-01 | 2025-09-13 | 1 | Erly | 88 | JC010925 24373
9 | 2025-09-01 | W000305 | E1134S.17100 - Pipe Modelling Block 134S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-14 | 2025-09-20 | 1 | Erly | 48 | JC010925 24375
10 | 2025-09-01 | W000305 | E1144P.17100 - Pipe Modelling Block 144P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-21 | 2025-09-30 | 1 | Erly | 66 | JC010925 24379
11 | 2025-09-01 | W000307 | ES324P.17100 - Pipe Modeling Support block 324P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-01 | 2025-09-06 | 1 | Rizki R | 40 | JC010925 24386
12 | 2025-09-01 | W000307 | E1324S.17100 - Pipe Modeling block 324S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-07 | 2025-09-13 | 1 | Rizki R | 56 | JC010925 24389
13 | 2025-09-01 | W000307 | E1531P.17100 - Pipe Modeling block 531P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-14 | 2025-09-20 | 1 | Rizki R | 56 | JC010925 24393
14 | 2025-09-01 | W000307 | E1531S.17100 - Pipe Modeling block 531S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-21 | 2025-09-30 | 1 | Rizki R | 68 | JC010925 24395
15 | 2025-09-01 | W000305 | E1433S.17100 - Pipe Modeling block 433S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-01 | 2025-09-30 | 1 | Dewi | 40 | JC010925 24396
16 | 2025-09-01 | W000305 | E1213S.17100 - Pipe Modeling block 213S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-01 | 2025-09-30 | 1 | Dewi | 40 | JC010925 24398
17 | 2025-09-01 | W000305 | E1213P.17100 - Pipe Modeling block 213P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-01 | 2025-09-30 | 1 | Dewi | 40 | JC010925 24401
18 | 2025-09-01 | W000305 | E1223S.17100 - Pipe Modeling block 223S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-01 | 2025-09-30 | 1 | Dewi | 40 | JC010925 24403
19 | 2025-09-01 | W000305 | E1223S.17100 - Pipe Modeling block 223S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-01 | 2025-09-30 | 1 | Dewi | 40 | JC010925 24404
20 | 2025-09-02 | W304 | E25072.37100-EST. MAT. FOR NAME PLATE OF VALVE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-01 | 2025-09-03 | 1 | TEO | 24 | JC020925 24501
21 | 2025-09-02 | W304 | E25072.37200-EST. MAT. FOR NAME PLATE & CAUTION PLATE OF EQUIPMENT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-04 | 2025-09-05 | 1 | TEO | 16 | JC020925 24502
22 | 2025-09-03 | W306 | COMPARE MATERIAL VALVE IM4 VS VALVE BATCH 1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-01 | 2025-09-05 | 1 | NIZAR | 40 | JC030925 24533
23 | 2025-09-03 | W000308 | E1111U.27100 - Pipe Model block 111 P/S Engine Room | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-01 | 2025-09-30 | 1 | Yasin | 80 | JC030925 24534
24 | 2025-09-03 | W000308 | E1112U.27100 - Pipe Model block 112 P/S Engine Room | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-01 | 2025-09-30 | 1 | Yasin | 80 | JC030925 24535
25 | 2025-09-03 | W000308 | Preparation and Presentation at SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-01 | 2025-09-30 | 1 | Yasin | 18 | JC030925 24536
26 | 2025-09-03 | W000308 | E11631.10100 - Rev. Piping Detail and Arrangement of Seachest (valve changes according to maker drawing) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-01 | 2025-09-30 | 1 | Yasin | 18 | JC030925 24537
27 | 2025-09-03 | W000308 | E25012.01100 - Material List of Strainer For seachest (material changes according to PID which has been approved owner) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-01 | 2025-09-30 | 1 | Yasin | 18 | JC030925 24538
28 | 2025-09-04 | W000304 | Check Drawing Output Piping BLOCK EP641P-R1, EK641P-R1, EP641S-R1, EK641S-R1, EP612P-R1, EK612P-R1, EP622P-R1, EK622P-R1, EP622S-R1, EK622S-R1, EP513P-R1, EK513P-R1, EP513S-R1, EK513S-R1, EP514C-R1,EK514CS-R1, EP324C-R2, EK324C-R2, EP541P-R1, EK541P-R1, EP541S-R1, EK541S-R1, EP542S-R1, EK542S-R1, EP542P-R1, EK542P-R1, EP642P-R1, EK642P-R1, EP642S-R1, EK642S-R1, EP613C-R0, EK613C-R0, EP633C-R1,EK633C-R1, EP652P-R1, EK652P-R1, EP652S-R1, EK652S-R1,EP631P-R1, EK631P-R1, EP631S-R1, EK631S-R1. | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-01 | 2025-09-04 | 1 | Asi Supeni | 30 | JC040925 24601
29 | 2025-09-10 | W308 | REV.2 - E15162.25100 - PIPING DIAGRAM OF REFRIGERATION AND PROVISION STORE | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-01 | 2025-08-05 | 1 | RAFIKA
30 | 2025-09-10 | W308 | REV.1 - E25162.01101 - EST MAT PIPING DIAGRAM OF REFRIGERATION AND PROVISION STORE | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-06 | 2025-08-08 | 1 | RAFIKA
31 | 2025-09-10 | W308 | REV.3 - E15161.22100 - PIPING DIAGRAM OF CHILLED WATER SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-11 | 2025-08-18 | 1 | RAFIKA
32 | 2025-09-10 | W308 | REV.1 - E25161.01101 - EST MAT PIPING DIAGRAM OF CHILLED WATER SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-19 | 2025-08-22 | 1 | RAFIKA
33 | 2025-09-10 | W308 | REV.1 - E15262.22101 - EST MAT PIPING DIAGRAM OF WATER BALLAST AND WATER DOCKWELL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-08-25 | 2025-08-29 | 1 | RAFIKA
34 | 2025-09-10 | W308 | REV.1 - E95620.91100 - CALCULATION OF RUDDER STOCK | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-01 | 2025-09-01 | 1 | ARDAN |  | JC100925 24857
35 | 2025-09-10 | W308 | REV.1 - E15620.63100 - RUDDER STOCK & FITTINGS | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-02 | 2025-09-02 | 1 | ARDAN |  | JC100925 24858
36 | 2025-09-10 | W304 | REV.0 - EVALUASI TEKNIS APPROVAL DRAWING HVAC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-01 | 2025-09-30 | 1 | STEVAN | 20 | JC110925 24873
37 | 2025-09-10 | W308 | REV.0 - EVALUASI TEKNIS HVAC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-01 | 2025-09-30 | 1 | STEVAN | 20 | JC110925 24875
38 | 2025-09-10 | W308 | REV.2 - E15141.28100 - DIAGRAM OF AIR CONDITIONING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-08 | 2025-09-20 | 1 | STEVAN | 80 | JC110925 24876
39 | 2025-09-10 | W308 | REV.0 - ED334P.48100 - MODELLING DUCT IN 02 DECK - BLOCK 334P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-22 | 2025-09-30 | 1 | STEVAN | 40 | JC110925 24885
40 | 2025-09-10 | W308 | REV.0 - ED334S.48100 - MODELLING DUCT IN 02 DECK - BLOCK 334S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-22 | 2025-09-30 | 1 | STEVAN | 40 | JC110925 24888
41 | 2025-09-10 | W304 | REV.1 - E25071.01100 - EST. MAT. FOR NAME PLATE VENTILATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-01 | 2025-09-06 | 1 | PRATAMA |  | JC100925 24869
42 | 2025-09-10 | A24AOP01 | REV.0 - E17511.33101 - TORPEDO TUBE | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-03 | 2025-09-05 | 1 | ARDAN |  | JC110925 24880
43 | 2025-09-10 | W304 | UPDATE MODEL & SPESIFIKASI PID CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-01 | 2025-09-30 | 1 | AHMAD KHUNAIFI | 120 | JC100925 24867
44 | 2025-09-10 | W308 | UPDATE MODEL & SPESIFIKASI PID CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-01 | 2025-09-30 | 1 | AHMAD KHUNAIFI | 120 | JC100925 24868
45 | 2025-09-10 | W304 | REV.A0 - E25240.01100 - EST. QTY. MAT. FOR PID OF S.W. COOLING | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-01 | 2025-09-03 | 1 | AHMAD KHUNAIFI | 24 | JC110925 24889
46 | 2025-09-10 | W306 | REKAP UPDATE EST. MAT. PIPE & FITTING PROJECT LD PHILIPPINES #1 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-04 | 2025-09-09 | 1 | AHMAD KHUNAIFI | 32 | JC110925 24890
47 | 2025-09-10 | W306 | REV.1 - E1113P/S.12100 - SPOOLING BLOK EP113 P/S BESERTA PENETRASINYA | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-01 | 2025-09-03 | 1 | FARIS NOVARIANSYAH | 24 | JC110925 24891
48 | 2025-09-10 | W306 | REV.1 - E1122P/S.12100 - SPOOLING BLOK EP122 P/S BESERTA PENETRASINYA | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-04 | 2025-09-09 | 1 | FARIS NOVARIANSYAH | 24 | JC110925 24892
49 | 2025-09-10 | W304 | REV.C - E15160.22100 - PIPING DIAGRAM OF CHILLED WATER SYSTEM (M) REVIEW | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-08 | 2025-09-30 | 1 | PRATAMA |  | JC110925 24893
50 | 2025-09-10 | A24AOP01 | 3D MODEL TORPEDO NOSE | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-08 | 2025-09-10 | 1 | ARDAN |  | JC110925 24881
51 | 2025-09-10 | A24AOP01 | 3D MODEL TORPEDO BATTERY | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-11 | 2025-09-17 | 1 | ARDAN |  | JC110925 24882
52 | 2025-09-11 | W308 | E15072.37200-NAME PLATE & CAUTION PLATE OF EQUIPMENT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-08 | 2025-09-30 | 1 | TEO | 136 | JC110925 24894
53 | 2025-09-12 | W000304 | Check Drawing Output Piping BLOCK EP144P-R1, EK144P-R1, EP144S-R1, EK144S-R1, EP522P-R1, EK522P-R1, EP522S-R1, EK522S-R1, EP155P-R1, EK155P-R1, EP155S-R1, EK155S-R1, EP333C-R1, EP512S-R1, EK512S-R1, EP523P-R1, EK523P-R1, EP523S-R1, EK523S-R1, EP315P-R1, EP315S-R1, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-08 | 2025-09-12 | 1 | Asi Supeni | 40 | JC120925 24919
54 | 2025-09-17 | A24AOP01 | CUTTING PLAN FOR BATTERY PLATE | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-18 | 2025-09-18 | 1 | ARDAN |  | JC170925 25172
55 | 2025-09-17 | W304 | REV.2 - E15931.22100 - PIPING DIAGRAM OF OILY BILGE SEPARATOR SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-01 | 2025-09-05 | 1 | SATRIO | 55 | JC170925 25173
56 | 2025-09-17 | W304 | REV.1 - E13410.22100 - PIPING DIAGRAM OF FO, LO AND OILY WATER DRAIN SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-08 | 2025-09-12 | 1 | SATRIO | 55 | JC180925 25179
57 | 2025-09-17 | W304 | REV.4 - E15282.22100 - PIPING DIAGRAM OF GREY WATER SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-15 | 2025-09-19 | 1 | SATRIO | 46 | JC230925 25381
58 | 2025-09-17 | W304 | REV.1 - E25555.01100 - EST MAT QTY FOR PIPNG DIAGRAM OF LOCAL APPLICATION SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-01 | 2025-09-04 | 1 | RAFIKA |  | JC180925 25181
59 | 2025-09-17 | W304 | REV.2 - E25553.01100 - EST MAT QTY FOR PIPNG DIAGRAM OF FIXED GAS FIRE EXTINGUISHING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-05 | 2025-09-10 | 1 | RAFIKA |  | JC180925 25182
60 | 2025-09-17 | W304 | REV.0 - E25551.01101 - EST MAT QTY FOR PIPING DIAGRAM OF DEEP FAT FRYER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-11 | 2025-09-16 | 1 | RAFIKA |  | JC180925 25183
61 | 2025-09-17 | W308 | REV.1 - E25161.01100 - EST MAT QTY FOR PIPING DIAGRAM OF CHILLED WATER SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-17 | 2025-09-19 | 1 | RAFIKA |  | JC180925 25184
62 | 2025-09-17 | W308 | REV.3 - E15161.01100 - PIPING DIAGRAM OF CHILLED WATER SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-22 | 2025-09-24 | 1 | RAFIKA |  | JC180925 25185
63 | 2025-09-17 | W304 | REV.0 - E22510.01100 - EST MAT QTY MATERIAL FOR DIAGRAM OF AIR INTAKE SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-25 | 2025-09-30 | 1 | RAFIKA |  | JC180925 25186
64 | 2025-09-17 | A24AOP01 | 3D MODEL RAIL FOR TORPEDO COMPONENTS | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-19 | 2025-09-23 | 1 | ARDAN |  | JC180925 25187
65 | 2025-09-19 | W000304 | E25330.01100_R4_ESTIMATED MATERIAL FOR FRESH WATER SANITARY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-01 | 2025-09-05 | 1 | DIAR | 40 | JC190925 25240
66 | 2025-09-19 | W000304 | E25331.01100_R2_ESTIMATED MATERIAL FOR HOT WATER SANITARY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-08 | 2025-09-12 | 1 | DIAR | 40 | JC190925 25242
67 | 2025-09-19 | W000304 | E25312.01100_R1_ESTIMATED MATERIAL FOR FRESH WATER PRODUCTION SYSTEM (REVERSE OSMOSIS) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-15 | 2025-09-17 | 1 | DIAR | 24 | JC190925 25243
68 | 2025-09-19 | W000308 | E15261.22100_R2_PID OF OUTSIDE DECK SCUPPER | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-18 | 2025-09-22 | 1 | DIAR | 24 | JC190925 25244
69 | 2025-09-19 | W000308 | E25261.01100_R1_ESTIMATED MATERIAL FOR OUTSIDE DECK SCUPPER | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-23 | 2025-09-24 | 1 | DIAR | 16 | JC190925 25245
70 | 2025-09-19 | W000304 | E15281.22100_R2_PIPING DIAGRAM OF SEWAGE SYSTEM IN ACCOMMODATION | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-25 | 2025-09-26 | 1 | DIAR | 16 | JC190925 25246
71 | 2025-09-19 | W000306 | E25330.01100_R3_ESTIMATED MATERIAL FOR FRESH WATER SANITARY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-29 | 2025-09-30 | 1 | DIAR | 16 | JC190925 25247
72 | 2025-09-19 | W304 | Compare Pipe & Fitting Materials All Systems 3D Models & Material Lists | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-08 | 2025-09-26 | 1 | NIZAR | 150 | JC190925 25248
73 | 2025-09-19 | W000304 | Check Drawing Output Piping System E15610.22100 , E15512.22100 , E15555.22100 , E15164.22100 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-15 | 2025-09-19 | 1 | Asi Supeni | 40 | JC190925 25249
74 | 2025-09-23 | W304 | E15515.22100-R1-PID OF CONTROL AIR FOR EMERGENCY SHUT OFF VALVE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-01 | 2025-09-02 | 1 | Amam Baharullah | 16 | JC240925 25428
75 | 2025-09-23 | W304 | E25411.01100-R2-EST. QTY. MAT. FOR PID OF FO. TRANSFER & OVERFLOW | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-03 | 2025-09-05 | 1 | Amam Baharullah | 24 | JC240925 25429
76 | 2025-09-23 | W304 | E25412.01100-R3-EST. QTY. MAT. FOR PID OF FO. SERVICE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-08 | 2025-09-10 | 1 | Amam Baharullah | 24 | JC240925 25430
77 | 2025-09-23 | W304 | E25515.01100-R1-EST. QTY. MAT. FOR PID OF CONTROL AIR FOR EMERGENCY SHUT OFF VALVE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-11 | 2025-09-17 | 1 | Amam Baharullah | 40 | JC240925 25432
78 | 2025-09-23 | W304 | E25410.01100-R3-EST. QTY. MAT. FOR PID OF FO. PURIFYING | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-18 | 2025-09-19 | 1 | Amam Baharullah | 16 | JC240925 25433
79 | 2025-09-23 | W304 | E15515.27100-R0-PIPE MODELING OF CONTROL AIR FOR EMERGENCY SHUT OFF VALVE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-22 | 2025-09-26 | 1 | Amam Baharullah | 40 | JC240925 25434
80 | 2025-09-23 | W304 | E15515.27100-R0-PIPE MODELING OF CONTROL AIR FOR EMERGENCY SHUT OFF VALVE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-29 | 2025-09-30 | 1 | Amam Baharullah | 16 | JC240925 25435
81 | 2025-09-23 | W304 | E91002.97120 - Stores Monorail Supporting Structure Analysis Report - R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-01 | 2025-09-30 | 1 | Aditya Prayoga | 120 | JC240925 25452
82 | 2025-09-23 | W304 | E95000-92101 - Yard Plan Weight Calculation (KB03) - MOD - R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-01 | 2025-09-30 | 1 | Aditya Prayoga | 40 | JC240925 25453
83 | 2025-09-23 | W308 | ANALYSIS OF DUCTING PRESSURE LOSS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-01 | 2025-09-30 | 1 | Aditya Prayoga | 16 | JC240925 25454
84 | 2025-09-24 | W306 | R0 - E1114P/S.12100 - SPOOLING BLOK EP114 P/S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-10 | 2025-09-12 | 1 | FARIS NOVARIANSYAH |  | JC250925 25460
85 | 2025-09-24 | W308 | R0 - ED332P.48100 - DUCT READY AND ARRAGEMENT DRAWING BLOCK 332 P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-15 | 2025-09-17 | 1 | FARIS NOVARIANSYAH |  | JC250925 25464
86 | 2025-09-24 | W304 | R0 - E1244P/S.18101 - SPOOL AIR VENT DUCTING SYSTEM 2051 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-18 | 2025-09-19 | 1 | FARIS NOVARIANSYAH |  | JC250925 25465
87 | 2025-09-24 | W308 | R0 - ED343P.48100 - DUCT READY AND ARRAGEMENT DRAWING BLOCK 343 P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-22 | 2025-09-24 | 1 | FARIS NOVARIANSYAH |  | JC250925 25466
88 | 2025-09-24 | W308 | R0 - ED313P.48100 - DUCT READY AND ARRAGEMENT DRAWING BLOCK 313 P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-25 | 2025-09-30 | 1 | FARIS NOVARIANSYAH |  | JC250925 25467
89 | 2025-09-25 | W304 | R0-PUMPING PLAN FOR BALLAST,OILY BILGE SEPARATOR & BILGE (DEWATERING) SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-29 | 2025-09-30 | 1 | NIZAR | 16 | JC250925 25468
90 | 2025-09-26 | W000304 | Check Drawing Pipe Modelling: E14860,22100, E14560,22100, E14551,22100, E13410,22100, Check Piping Arr't & Support, Iso, Penet : E1643C-R0, E1653C-R0, ES643C-R0, ES653C-R0, ES641S-R0, EP322C-R2, EK322C-R2 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-22 | 2025-09-26 | 1 | Asi Supeni | 40 | JC260925 25513
91 | 2025-09-26 | A24AOP01 | REVISI 3D MODEL TORPEDO NOSE | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-24 | 2025-09-30 | 1 | ARDAN |  | JC260925 25529
92 | 2025-09-26 | W304 | R0 - E15030.02100 - PUMPING PLAN FOR FO, LO, FW FILLING | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-22 | 2025-09-30 | 1 | SATRIO |  | JC260925 25530
93 | 2025-09-29 | W000308 | EVATEK BY DESCRIPTION PART 1 LIST VALVE AND OTHER MAKER WK KOREA_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-01 | 2025-09-05 | 1 | Kridiyantoro | 40 | JC300925 25685
94 | 2025-09-29 | W000308 | EVATEK BY DESCRIPTION PART 1 LIST VALVE AND OTHER MAKER KEYSTONE_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-08 | 2025-09-12 | 1 | Kridiyantoro | 40 | JC300925 25686
95 | 2025-09-29 | W000308 | CREATE PROSES PENGADAAN VALVE & OTHER PART 2_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-15 | 2025-09-19 | 1 | Kridiyantoro | 40 | JC300925 25690
96 | 2025-09-29 | W000308 | CREATE PROSES PENGADAAN VALVE & OTHER PART 2_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-22 | 2025-09-26 | 1 | Kridiyantoro | 40 | JC300925 25702
97 | 2025-09-29 | W000304-305 | CREAT LIST TOOLS & INVENTORY (MACHINERY PART)_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-29 | 2025-09-30 | 1 | Kridiyantoro | 16 | JC300925 25703
98 | 2025-09-29 | W304 | E24511.01100-R1-EST. MAT. QTY FOR PID OF SURVEILANCE RADAR COOLING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-01 | 2025-09-02 | 1 | MIEKAIL | 16 | JC300925 25691
99 | 2025-09-29 | W304 | E24551.01100-R1-EST. MAT. QTY FOR PID OF HAN IFF ANTENA COOLING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-03 | 2025-09-04 | 1 | MIEKAIL | 16 | JC300925 25692
100 | 2025-09-29 | W304 | E24560.01100-R1-EST. MAT. QTY FOR PID OF MULTI FUCTION RADAR COOLING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-05 | 2025-09-08 | 1 | MIEKAIL | 16 | JC300925 25693
101 | 2025-09-29 | W304 | E24860.01100-R1-EST. MAT. QTY FOR PID OF TRACKING RADAR COOLING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-09 | 2025-09-10 | 1 | MIEKAIL | 16 | JC300925 25694
102 | 2025-09-29 | W304 | E25510.01100-R4-EST. MAT. QTY FOR PID OF COMPRESSED AIR SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-11 | 2025-09-11 | 1 | MIEKAIL | 8 | JC300925 25713
103 | 2025-09-29 | W304 | E125100.27100-R0-PIPE MODEL & READY COMBUSTION AIR INTAKE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-12 | 2025-09-17 | 1 | MIEKAIL | 32 | JC300925 25696
104 | 2025-09-29 | W304 | E15510.22100-R4-PID OF COMPRESSED AIR SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-18 | 2025-09-18 | 1 | MIEKAIL | 8 | JC300925 25715
105 | 2025-09-29 | W304 | E14511.27100-R0-PIPE READY SURVEILANCE RADAR COOLING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-19 | 2025-09-22 | 1 | MIEKAIL | 16 | JC300925 25698
106 | 2025-09-29 | W304 | E14551.27100-R0-PIPE READY HAN IFF ANTENA COOLING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-23 | 2025-09-24 | 1 | MIEKAIL | 16 | JC300925 25699
107 | 2025-09-29 | W304 | E14560.27100-R0-PIPE READY MULTI FUCTION RADAR COOLING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-25 | 2025-09-26 | 1 | MIEKAIL | 16 | JC300925 25700
108 | 2025-09-29 | W304 | E14860.27100-R0-PIPE READY TRACKING RADAR COOLING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-29 | 2025-09-30 | 1 | MIEKAIL | 16 | JC300925 25701
109 | 2025-09-30 | W000304 | Check Drawing Pipe Modelling: E14860,22100, E14560,22100, E14551,22100, E13410,22100, Check Piping Arr't & Support, Iso, Penet : E1643C-R0, E1653C-R0, ES643C-R0, ES653C-R0, ES641S-R0, EP322C-R2, EK322C-R2 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-09-27 | 2025-09-30 | 1 | Asi Supeni | 16 | JC300925 25689
110 | 2025-09-30 | W308 | R1 - E9555.01100 - TECHNICAL REPORT OF FIRE EXTINGUISHING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-01 | 2025-09-19 | 1 | FIRMAN |  | JC300925 25704
111 | 2025-09-30 | W304 | R0 - ED213P.48101 - VENT SKETCHES AIR INTAKE BLOCK 213 P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-20 | 2025-09-21 | 1 | FIRMAN
112 | 2025-09-30 | W304 | R0 - ED213S.48101 - VENT SKETCHES AIR INTAKE BLOCK 213 S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-21 | 2025-09-22 | 1 | FIRMAN |  | JC300925 25705
113 | 2025-09-30 | W304 | R0 - ED223S.48101 - VENT SKETCHES AIR INTAKE BLOCK 223 S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-22 | 2025-09-23 | 1 | FIRMAN |  | JC300925 25706
114 | 2025-09-30 | W304 | R0 - ED224S.48101 - VENT SKETCHES AIR INTAKE BLOCK 224 S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-23 | 2025-09-24 | 1 | FIRMAN |  | JC300925 25707
115 | 2025-09-30 | W304 | R0 - ED233P.48101 - VENT SKETCHES AIR INTAKE BLOCK 233 P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-24 | 2025-09-25 | 1 | FIRMAN |  | JC300925 25708
116 | 2025-09-30 | W304 | R0 - - - DETAIL OF ALL MITER BENDS FOR AIR COMBUSTION DUCT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-09-25 | 2025-09-30 | 1 | FIRMAN |  | JC300925 25709
117 | 2025-09-30 | W306 | Technical Evaluation of Water Jet for LCU | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-01 | 2025-09-05 | 1 | SYAFRIL | 40 | JC300925 25687
118 | 2025-09-30 | W306 | Machinery Layout for LCU | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-08 | 2025-09-12 | 1 | SYAFRIL | 40 | JC300925 25688
119 | 2025-09-30 | W308 | E12421.32100-Shaft Protection Cover | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-15 | 2025-09-19 | 1 | SYAFRIL | 40 | JC300925 25710
120 | 2025-09-30 | W308 | E1.2331.33100-Main Engine Installation | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-09-22 | 2025-09-30 | 1 | SYAFRIL | 56 | JC300925 25711
2025-10-01
1 | 2025-10-01 | W307 | E25072.37100-EST.MAT. FOR NAME PLATE OF VALVE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-01 | 2025-10-07 | 1 | TEO | 40 | JC011025 25756
2 | 2025-10-01 | W307 | EST. MAT. FOR NAME PLATE & CAUTION PLATE OF EQUIPMENT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-08 | 2025-10-10 | 1 | TEO | 24 | JC011025 25757
3 | 2025-10-01 | W308 | EST. MAT. FOR NAME PLATE & CAUTION PLATE OF EQUIPMENT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-13 | 2025-10-15 | 1 | TEO | 24 | JC011025 25758
4 | 2025-10-01 | W000307 | E15411.17100 Pipe Model Fo Transfer system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-15 | 1 | Dimas | 106 | JC011025 25759
5 | 2025-10-01 | W000307 | E15412.17100 Pipe Model FO Service system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-16 | 2025-10-31 | 1 | Dimas | 117 | JC011025 25760
6 | 2025-10-01 | W000304 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-31 | 1 | Dimas | 8 | JC011025 25761
7 | 2025-10-01 | W000306 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-31 | 1 | Dimas | 8 | JC011025 25763
8 | 2025-10-01 | W000308 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-31 | 1 | Dimas | 8 | JC011025 25762
9 | 2025-10-01 | W000308 | E1111U.27100 - Pipe Model block 111 P/S Engine Room | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-31 | 1 | Yasin | 40 | JC011025 25773
10 | 2025-10-01 | W000308 | E1112U.27100 - Pipe Model block 112 P/S Engine Room | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-31 | 1 | Yasin | 40 | JC011025 25774
11 | 2025-10-01 | W000308 | E1232U.27100 - Pipe Model block 232 P/S Engine Room | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-31 | 1 | Yasin | 40 | JC011025 25775
12 | 2025-10-01 | W000308 | E15292.27100 - Pipe Model system ballast from standard NOV to standard FPI | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-31 | 1 | Yasin | 40 | JC011025 25776
13 | 2025-10-01 | W000308 | E15292.27100 - Evatek GRE Pipe System Ballast Custom From FPI | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-31 | 1 | Yasin | 40 | JC011025 25780
14 | 2025-10-01 | W000308 | Check Model 3D, Preparation and Presentation at SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-31 | 1 | Yasin | 18 | JC011025 25781
15 | 2025-10-01 | W000307 | ES232P.17100 - Pipe Modeling Support block 232P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-12 | 1 | Rizki R | 81 | JC011025 25782
16 | 2025-10-01 | W000307 | E1232P.17100 - Pipe Modeling block 232P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-13 | 2025-10-19 | 1 | Rizki R | 57 | JC011025 25783
17 | 2025-10-01 | W000307 | ES232S.17100 - Pipe Modeling Support block 232S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-20 | 2025-10-26 | 1 | Rizki R | 57 | JC011025 25784
18 | 2025-10-01 | W000307 | E1232S.17100 - Pipe Modeling block 232S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-27 | 2025-10-31 | 1 | Rizki R | 49 | JC011025 25785
19 | 2025-10-01 | W000305 | E1621S.17100 - Pipe Modeling block 621S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-31 | 1 | Dewi | 40 | JC011025 25786
20 | 2025-10-01 | W000305 | E1224S.17100 - Pipe Modeling block 224S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-31 | 1 | Dewi | 40 | JC011025 25787
21 | 2025-10-01 | W000305 | E1234S.17100 - Pipe Modeling block 234S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-31 | 1 | Dewi | 40 | JC011025 25788
22 | 2025-10-01 | W000305 | E1244P.17100 - Pipe Modeling block 244P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-31 | 1 | Dewi | 40 | JC011025 25789
23 | 2025-10-01 | W000305 | E1651P.17100 - Pipe Modeling block 651P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-31 | 1 | Dewi | 40 | JC011025 25790
24 | 2025-10-01 | W000305 | E1434P.17100 - Pipe Modelling Block 434P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-07 | 1 | Erly | 48 | JC021025 25796
25 | 2025-10-01 | W000305 | E1434S.17100 - Pipe Modelling Block 434S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-08 | 2025-10-14 | 1 | Erly | 48 | JC021025 25797
26 | 2025-10-01 | W000305 | E1424P.17100 - Pipe Modelling Block 424P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-15 | 2025-10-21 | 1 | Erly | 24 | JC021025 25798
27 | 2025-10-01 | W000305 | E1424S.17100 - Pipe Modelling Block 424S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-15 | 2025-10-21 | 1 | Erly | 24 | JC021025 25799
28 | 2025-10-01 | W000305 | E1414P.17100 - Pipe Modelling Block 414P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-22 | 2025-10-31 | 1 | Erly | 70 | JC021025 25800
29 | 2025-10-01 | W000308 | E1214U.27100 - Pipe Modelling & Ready in Block 214 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-31 | 1 | Syaiful | 48 | JC021025 25805
30 | 2025-10-01 | W000308 | E1234U.27100 - Pipe Modelling & Ready in Block 234 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-31 | 1 | Syaiful | 48 | JC021025 25806
31 | 2025-10-01 | W000308 | E1224U.27100 - Pipe Modelling & Ready in Block 224 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-31 | 1 | Syaiful | 48 | JC021025 25807
32 | 2025-10-01 | W000308 | E15161.27100 - Pipe Modelling Chilled Water System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-31 | 1 | Syaiful | 48 | JC021025 25808
33 | 2025-10-01 | W000308 | Check 3D model (fungsi, operasional, maintenance) & Paparan di SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-31 | 1 | Syaiful | 18 | JC021025 25809
34 | 2025-10-03 | W000304 | Check Modelling Piping System E14511.22100 , E15511.22100 , E15515.22100 , E15553.22100 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-01 | 2025-10-03 | 1 | Asi Supeni | 24 | JC031025 25903
35 | 2025-10-07 | W304 | R0-PUMPING PLAN FOR BALLAST,OILY BILGE SEPARATOR & BILGE (DEWATERING) SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-07 | 2025-10-17 | 1 | NIZAR | 80 | JC071025 26073
36 | 2025-10-07 | W304 | EVATEK DRAWING VALVE TAHAP 2 FINAL VENDOR SUN KOREA - R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-01 | 2025-10-06 | 1 | NIZAR | 32 | JC071025 26075
37 | 2025-10-08 | W304 | R0 - E14711. 22100 - PIPING DIAGRAM OF JNU-LIQUID COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-01 | 2025-10-24 | 1 | IRFAN | 140 | JC081025 26096
38 | 2025-10-08 | W304 | R0 - E24711. 01100 - EST. QTY MAT. FOR PIPING DIAGRAM OF JNU-LIQUID COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-22 | 2025-10-30 | 1 | IRFAN | 60 | JC081025 26097
39 | 2025-10-08 | W304 | UPDATE MODEL & SPESIFIKASI PID CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-01 | 2025-10-31 | 1 | AHMAD KHUNAIFI | 120 | JC081025 26098
40 | 2025-10-08 | W308 | UPDATE MODEL & SPESIFIKASI PID CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-01 | 2025-10-31 | 1 | AHMAD KHUNAIFI | 120 | JC081025 26099
41 | 2025-10-08 | W308 | R0 - E35130.50100 - EVALUASI TEKNIS PENAWARAN NBC AIR FILTRATION UNITS (VAN HALTEREN) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-01 | 2025-10-04 | 1 | PRATAMA |  | JC081025 26100
42 | 2025-10-08 | W304 | COMPARE LIST OF VALVE & OTHERS ALL SYSTEM FOR PURCHASING | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-01 | 2025-10-08 | 1 | SATRIO | 55 | JC081025 26103
43 | 2025-10-08 | W304 | RD - E15160.22100 - PIPING DIAGRAM OF CHILLED WATER SYSTEM (M) REVIEW | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-06 | 2025-10-11 | 1 | PRATAMA |  | JC081025 26104
44 | 2025-10-08 | A24AOP01 | REVISI MODEL STEERING SYSTEM KSOT 15 METER (HYDRAULIC) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-01 | 2025-10-10 | 1 | ARDAN |  | JC081025 26105
45 | 2025-10-08 | A24AOP01 | MODELLING ENGINE USV 8 METER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-13 | 2025-10-17 | 1 | ARDAN |  | JC081025 26110
46 | 2025-10-10 | W304 | ANALISIS UNDERWATERNOISE & RESISTANCE PERUBAHAN BENTUK V BRACKET FRIGATE 140 METER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-20 | 2025-10-31 | 1 | ARDAN |  | JC141025 26360
47 | 2025-10-13 | W000304 | Check Modelling Piping System EP132P-R2 , EK132P-R2, EP231P-R4, EP132S-R2, EK132S-R2, EP231S-R4, EK231S-R4, Check Pipe Model: E15553,22100, E15330.22100 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-06 | 2025-10-17 | 1 | Asi Supeni | 80 | JC131025 26345
48 | 2025-10-14 | W304 | ANALISIS UNDERWATERNOISE & RESISTANCE PERUBAHAN BENTUK V BRACKET FRIGATE 140 METER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-20 | 2025-10-31 | 1 | ARDAN |  | JC151025 26411
49 | 2025-10-14 | W308 | REV 2 - E25211.0110 - REV 2 EST. MAT FIRE FIGHTING SYSTEM AL MARYAH | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-01 | 2025-10-03 | 1 | FARIS NOVARIANSYAH |  | JC151025 26412
50 | 2025-10-14 | W308 | EP234P/S.42100 - READY PIPE, PIPE SUPPORT, AND SPOOLING BLOCK 234 P-S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-06 | 2025-10-09 | 1 | FARIS NOVARIANSYAH |  | JC151025 26413
51 | 2025-10-14 | W306 | SPOOLING ISO DAN MERAPIKAN DOKUMEN SELURUH BLOCK DIV. MODULE 4 & 6 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-10 | 2025-10-21 | 1 | FARIS NOVARIANSYAH |  | JC151025 26416
52 | 2025-10-14 | W304 | RB - E15161.22100 - CHILLED WATER CIRCULATION DIAGRAM (M) REVIEW | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-13 | 2025-10-18 | 1 | PRATAMA |  | JC151025 26419
53 | 2025-10-15 | W304 | E15072.37100-NAME PLATE OF VALVE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-16 | 2025-10-24 | 1 | TEO | 56 | JC151025 26420
54 | 2025-10-15 | W304 | E15072.37200-NAME PLATE & CAUTION PLATE FOR EQUIPMENT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-27 | 2025-10-31 | 1 | TEO | 40 | JC151025 26426
55 | 2025-10-16 | W306 | PERHITUNGAN HVAC ENGINE ROOM LCU | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-13 | 2025-10-17 | 1 | ARDAN |  | JC161025 26450
56 | 2025-10-16 | W304 | R0 - E1213S.18101 - ARR'T OF AIR INTAKE VENT IN BLOCK 213 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-01 | 2025-10-02 | 1 | RAFIKA |  | JC161025 26451
57 | 2025-10-16 | W304 | R0 - E1213P.18101 - ARR'T OF AIR INTAKE VENT IN BLOCK 213 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-03 | 2025-10-06 | 1 | RAFIKA |  | JC161025 26452
58 | 2025-10-16 | W304 | R0 - E1223S.18101 - ARR'T OF AIR INTAKE VENT IN BLOCK 223 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-07 | 2025-10-08 | 1 | RAFIKA |  | JC161025 26453
59 | 2025-10-16 | W304 | R0 - E1233S.18101 - ARR'T OF AIR INTAKE VENT IN BLOCK 233 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-09 | 2025-10-10 | 1 | RAFIKA |  | JC161025 26454
60 | 2025-10-16 | W304 | R0 - E1233P.18101 - ARR'T OF AIR INTAKE VENT IN BLOCK 213 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-13 | 2025-10-14 | 1 | RAFIKA |  | JC161025 26455
61 | 2025-10-16 | W304 | R0 - E1224S.18101 - ARR'T OF AIR INTAKE VENT IN BLOCK 224 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-15 | 2025-10-16 | 1 | RAFIKA |  | JC161025 26456
62 | 2025-10-16 | W304 | R0 - E1244P.18101 - ARR'T OF AIR INTAKE VENT IN BLOCK 244 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-17 | 2025-10-20 | 1 | RAFIKA |  | JC161025 26457
63 | 2025-10-16 | W308 | REV.0 - ED324P.48100 - MODELLING DUCT IN 02 DECK - BLOCK 324P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-01 | 2025-10-04 | 1 | STEVAN |  | JC201025 26641
64 | 2025-10-16 | W308 | REV.0 - ED324S.48100 - MODELLING DUCT IN 02 DECK - BLOCK 324S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-06 | 2025-10-11 | 1 | STEVAN |  | JC201025 26645
65 | 2025-10-16 | W308 | REV.0 - ED314P.48100 - MODELLING DUCT IN 02 DECK - BLOCK 314P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-13 | 2025-10-18 | 1 | STEVAN |  | JC201025 26646
66 | 2025-10-16 | W308 | REV.0 - ED314S.48100 - MODELLING DUCT IN 02 DECK - BLOCK 314S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-20 | 2025-10-25 | 1 | STEVAN |  | JC201025 26647
67 | 2025-10-16 | W308 | REV.0 - ED134P.48100 - MODELLING DUCT IN 02 DECK - BLOCK 134P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-27 | 2025-10-31 | 1 | STEVAN |  | JC201025 26648
68 | 2025-10-16 | W304 | REV.0 - EVALUASI TEKNIS APPROVAL DRAWING HVAC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-01 | 2025-10-31 | 1 | STEVAN |  | JC201025 26656
69 | 2025-10-20 | W304 | E15000.01100_R0_PRINCIPAL PARTICULAR MACHINERY PART | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-01 | 2025-10-14 | 1 | DIAR | 80 | JC201025 26657
70 | 2025-10-20 | W308 | E15280.22100_PID OF INSIDE SCUPPER & DRAINAGE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-15 | 2025-10-17 | 1 | DIAR | 24 | JC201025 26658
71 | 2025-10-20 | W304 | E15282.22100_AKAN R2_PIPING DIAGRAM OF GREY WATER SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-20 | 2025-10-21 | 1 | DIAR | 16 | JC201025 26659
72 | 2025-10-20 | W304 | E15330.22100_AKAN R2_PIPING DIAGRAM OF FRESH WATER SANITARY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-22 | 2025-10-23 | 1 | DIAR | 16 | JC201025 26660
73 | 2025-10-20 | W308 | E15000.01100_R0_PRINCIPAL PARTICULAR MACHINERY PART | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-24 | 2025-10-31 | 1 | DIAR | 48 | JC201025 26661
74 | 2025-10-20 | W304 | COMPARE LIST OF VALVE & OTHERS ALL SYSTEM FOR PURCHASING | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 9 October 2025 | 15 October 2025 | 1 | SATRIO |  | JC211025 26674
75 | 2025-10-20 | W304 | R0 - E15030.02100 - PUMPING PLAN FOR FO, LO, FW FILLING | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 16 October 2025 | 22 October 2025 | 1 | SATRIO |  | JC211025 26675
76 | 2025-10-20 | W308 | R0 - E35130.50100 - EVALUASI TEKNIS PENAWARAN UAE LPD TECHNICAL PROPOSAL 250915 UPDATED BY CENTURY | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 20 October 2025 | 25 October 2025 | 1 | PRATAMA |  | JC211025 26676
77 | 2025-10-20 | A24AOP01 | INDEPENDENT TORPEDO FIRING TEST | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 20 October 2025 | 24 October 2025 | 1 | ARDAN |  | JC211025 26678
78 | 2025-10-21 | W304 | E15515.27100-PIPE MODELING OF CONTROL AIR FOR EMERGENCY SHUT OFF VALVE-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-01 | 2025-10-03 | 1 | AMAM | 24 | JC211025 26710
79 | 2025-10-21 | W304 | E15515.22100-PID OF CONTROL AIR FOR EMERGENCY SHUT OFF VALVE-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-06 | 2025-10-10 | 1 | AMAM | 40 | JC211025 26711
80 | 2025-10-21 | W304 | E12430.33100- SHAFTING ARRANGEMENT & ACTUAL CHECK | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-13 | 2025-10-15 | 1 | AMAM | 24 | JC211025 26712
81 | 2025-10-21 | W306 | E15330.22100-PIPING DIAGRAM OF FRESH WATER SANITARY & SEWAGE SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-16 | 2025-10-22 | 1 | AMAM | 40 | JC221025 26715
82 | 2025-10-21 | W308 | E25062.01100-EST. MAT FOR PID OF ARI PIPE (ADD. GRE FOR PROCUREMENT BATCH 2)-R5 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-23 | 2025-10-28 | 1 | AMAM | 32 | JC221025 26716
83 | 2025-10-21 | W306 | E25330.01100-EST. MAT FOR PID OF FRESH WATER SANITARY & SEWAGE SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-29 | 2025-10-31 | 1 | AMAM | 24 | JC221025 26721
84 | 2025-10-22 | W306 | COMPARE MATERIAL LIST WITH 3D MODEL ALL SYSTEM PIPING | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-20 | 2025-10-31 | 1 | NIZAR | 80 | JC221025 26722
85 | 2025-10-27 | W306 | R1 - E1123S.12100 - SPOOL ISO PIPING BLOCK 123 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-22 | 2025-10-23 | 1 | FARIS NOVARIANSYAH |  | JC271025 26920
86 | 2025-10-27 | W306 | R1 - E1123P.12100 - SPOOL ISO PIPING BLOCK 123 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-24 | 2025-10-25 | 1 | FARIS NOVARIANSYAH |  | JC291025 26949
87 | 2025-10-27 | W306 | R0 - E1112S.12100 - PIPING ARRAGEMENT BLOCK 112 & 113 S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-27 | 2025-10-31 | 1 | FARIS NOVARIANSYAH |  | JC271025 26923
88 | 2025-10-27 | W304 | RE - E85100.51100 - HVAC SYSTEM & FAN (M) FAN COIL UNIT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-27 | 2025-10-31 | 1 | PRATAMA |  | JC271025 26924
89 | 2025-10-27 | A24AOP01 | TORPEDO BOX DESIGN | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 27 October 2025 | 31 October 2025 | 1 | ARDAN |  | JC271025 26926
90 | 2025-10-28 | W000304 | EVATEK PENGADAAN VALVE UNTUK AIR RESERVOIR TANK MAKER EURONAVIG DAN GOSEA MARINE_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-01 | 2025-10-03 | 1 | KRISDIYANTORO | 24 | JC291025 26947
91 | 2025-10-28 | W000304 | EVATEK PENGADAAN VALVE UNTUK AIR RESERVOIR TANK MAKER EURONAVIG DAN GOSEA MARINE_R1,R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-06 | 2025-10-10 | 1 | KRISDIYANTORO | 40 | JC291025 26950
92 | 2025-10-28 | W000308 | CREATE PROSES PENGADAAN VALVE & OTHER PART 2_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-13 | 2025-10-17 | 1 | KRISDIYANTORO | 40 | JC291025 26953
93 | 2025-10-28 | W000306 | CREATE PROSES PENGADAAN VALVE & OTHER PART 2_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-20 | 2025-10-24 | 1 | KRISDIYANTORO | 40 | JC291025 26954
94 | 2025-10-28 | W000308 | CREATE DATA BASE PIPA UNTUK COMPARE MAT. LIST DENGAN CADMATIC_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-27 | 2025-10-31 | 1 | KRISDIYANTORO | 40 | JC291025 26955
95 | 2025-10-28 | W000308 | E15410.22100-PIPING DIAGRAM OF FUEL OIL PURIFYING SYSTEM-R4 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-01 | 2025-10-03 | 1 | MIEKAIL | 24 | JC291025 26974
96 | 2025-10-28 | W000308 | E15410.01100-EST. MAT. QTY FOR PIPING DIAGRAM OF FUEL OIL PURIFYING SYSTEM-R4 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-06 | 2025-10-10 | 1 | MIEKAIL | 40 | JC291025 26975
97 | 2025-10-28 | A24AOP01 | 3D MODELLING BUOY SECTION-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-13 | 2025-10-17 | 1 | MIEKAIL | 40 | JC291025 26980
98 | 2025-10-28 | A24AOP01 | 3D MODELLING BUOY WINCH SYSTEM -R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-20 | 2025-10-21 | 1 | MIEKAIL | 16 | JC291025 26981
99 | 2025-10-28 | A24AOP01 | ARRANGEMENT LEVEL TRANSMITTER OF BALLAST TANK-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-22 | 2025-10-23 | 1 | MIEKAIL | 16 | JC291025 26982
100 | 2025-10-28 | A24AOP01 | MENGAWAL PERSIAPAN UJI SELAM DAN UJI TEMBAK TORPEDO KSOT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-24 | 2025-10-24 | 1 | MIEKAIL | 8 | JC291025 26983
101 | 2025-10-28 | A24AOP01 | MENGAWAL PERSIAPAN UJI SELAM DAN UJI TEMBAK TORPEDO KSOT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-27 | 2025-10-31 | 1 | MIEKAIL | 40 | JC291025 26984
102 | 2025-10-29 | W308 | R1 - E95551.01100 - FIRE EXTINGUISHING SYSTEM CALCULATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-01 | 2025-10-10 | 1 | FIRMAN |  | JC291025 26985
103 | 2025-10-29 | W308 | R0 - - 3D MODELLING ACCOMMODATION ROOM FOR ROOM PRESSURIZATION ANALYSIS USING CFD | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-13 | 2025-10-20 | 1 | FIRMAN |  | JC291025 26986
104 | 2025-10-29 | W308 | R0 - - ROOM PRESSURIZATION ANALYSIS USING CFD | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-21 | 2025-10-31 | 1 | FIRMAN |  | JC291025 26987
105 | 2025-10-29 | W308 | R5 - E25292.01101 - EST MAT QTY FOR PIPING DIAGRAM OF WATER BALLAST SYSTEM AND WATER DOCKWEL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-21 | 2025-10-24 | 1 | RAFIKA |  | JC291025 26988
106 | 2025-10-29 | W306-307 | R3 - E15280.22100 - PIPING DIAGRAM OF INSIDE SCUPPER AND DECK DRAINAGE | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-27 | 2025-10-31 | 1 | RAFIKA |  | JC291025 26989
107 | 2025-10-29 | W308 | R1 - E25231.01100 - EST. QTY. MAT. FOR PID OF PREWETTING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-23 | 2025-10-27 | 1 | SATRIO |  | JC291025 26990
108 | 2025-10-29 | W308 | R3 - E15231.22100 - PID OF PREWETTING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-10-28 | 2025-10-31 | 1 | SATRIO |  | JC291025 26991
109 | 2025-10-30 | W308 | DUCTING PRESSURE LOSS CALCULATION (SUPPLY LINES) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-01 | 2025-10-31 | 1 | Aditya Prayoga | 24 | JC301025 27019
110 | 2025-10-30 | W304 | BLAST DOOR STRUCTURAL ANALYSIS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-01 | 2025-10-31 | 1 | Aditya Prayoga | 56 | JC301025 27020
111 | 2025-10-30 | W306 | E95000-92101 - Yard Plan Weight Calculation (KB03) - MOD - R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-01 | 2025-10-31 | 1 | Aditya Prayoga | 32 | JC301025 27021
112 | 2025-10-30 | W304 | E12430.33100- SHAFTING ARRANGEMENT - R3 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-01 | 2025-10-31 | 1 | Aditya Prayoga | 16 | JC301025 27024
113 | 2025-10-30 | KSSR | KSSR HULL RESISTANCE ANALYSIS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-01 | 2025-10-31 | 1 | Aditya Prayoga | 56 | JC301025 27025
114 | 2025-10-30 | W000304 | Check Modelling Piping System EP212P-R3 , EK212P-R3, EP213S-R3, EK213S-R3, Check Pipe Model: E15412,22100, E13410.22100 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-20 | 2025-10-31 | 1 | Asi Supeni | 60 | JC301025 27022
115 | 2025-10-31 | W000308 | Pelatihan Fabrikasi Pipa GRE (Glass Reinforce Epoxy)- System Ballast & Air Pipe - FPI Product | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-10-27 | 2025-11-04 | 1 | Yasin | 60 | JC311025 27040
116 | 2025-10-31 | W000308 | E1.2331.33100_Main Engine Installation | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-01 | 2025-10-04 | 1 | Syafril | 32 | JC311025 27060
117 | 2025-10-31 | W000308 | E1.2421.32100_Shaft Protection Cover | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-06 | 2025-10-11 | 1 | Syafril | 48 | JC311025 27061
118 | 2025-10-31 | JW1-JW2 307 | E3.2331.50100_Annex to Order Main Engine and Gearbox LCU | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-13 | 2025-10-18 | 1 | Syafril | 48 | JC311025 27062
119 | 2025-10-31 | JW1-JW2 307 | E3.3400.50100_Annex to Order Main Generator Set for LCU | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-20 | 2025-10-24 | 1 | Syafril | 40 | JC311025 27063
120 | 2025-10-31 | R22FPBXA | E1.2430.33100_Shafting Arrangement | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-10-27 | 2025-10-31 | 1 | Syafril | 40 | JC311025 27065
2025-11-01
1 | 2025-11-01 | W000307 | E12590.17100 Pipe Model Exhaust Gas system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-01 | 2025-11-09 | 1 | Dimas | 52 | JC071125 27441
2 | 2025-11-01 | W000307 | E13410.17100 Pipe Model FO LO Drain system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-10 | 2025-11-23 | 1 | Dimas | 104 | JC071125 27442
3 | 2025-11-01 | W000307 | E15292.17100 Pipe Model Water Ballast System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-24 | 2025-11-30 | 1 | Dimas | 52 | JC071125 27445
4 | 2025-11-01 | W000304 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-01 | 2025-11-30 | 1 | Dimas | 8 | JC071125 27446
5 | 2025-11-01 | W000306 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-01 | 2025-11-30 | 1 | Dimas | 8 | JC071125 27448
6 | 2025-11-01 | W000308 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-01 | 2025-11-30 | 1 | Dimas | 8 | JC071125 27449
7 | 2025-11-01 | W000305 | E1521P.17100 - Pipe Modelling Block 521P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-01 | 2025-11-09 | 1 | Erly | 52 | JC071125 27450
8 | 2025-11-01 | W000305 | E1521S.17100 - Pipe Modelling Block 521S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-10 | 2025-11-16 | 1 | Erly | 46 | JC071125 27451
9 | 2025-11-01 | W000305 | E1531P.17100 - Pipe Modelling Block 531P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-17 | 2025-11-23 | 1 | Erly | 46 | JC071125 27452
10 | 2025-11-01 | W000305 | E1531S.17100 - Pipe Modelling Block 531S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-24 | 2025-11-30 | 1 | Erly | 46 | JC071125 27453
11 | 2025-11-01 | W000307 | ES223P.17100 - Pipe Modeling Support block 223P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-01 | 2025-11-09 | 1 | Rizki R | 58 | JC071125 27456
12 | 2025-11-01 | W000307 | ES223P.17100 - Pipe Modeling block 223P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-10 | 2025-11-16 | 1 | Rizki R | 55 | JC071125 27457
13 | 2025-11-01 | W000307 | ES213P.17100 - Pipe Modeling Support block 213P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-17 | 2025-11-23 | 1 | Rizki R | 55 | JC071125 27458
14 | 2025-11-01 | W000307 | E1213P.17100 - Pipe Modeling block 213P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-24 | 2025-11-30 | 1 | Rizki R | 55 | JC071125 27459
15 | 2025-11-01 | W000305 | E1214P.17100 - Pipe Modelling Block 214P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-01 | 2025-11-30 | 1 | Dewi | 40 | JC071125 27460
16 | 2025-11-01 | W000305 | E1234P.17100 - Pipe Modelling Block 234P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-01 | 2025-11-30 | 1 | Dewi | 40 | JC071125 27461
17 | 2025-11-01 | W000305 | E1224P.17100 - Pipe Modelling Block 224P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-01 | 2025-11-30 | 1 | Dewi | 40 | JC071125 27462
18 | 2025-11-01 | W000305 | E1244P.17100 - Pipe Modelling Block 244P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-01 | 2025-11-30 | 1 | Dewi | 40 | JC071125 27463
19 | 2025-11-01 | W000305 | E1254P.17100 - Pipe Modelling Block 254P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-01 | 2025-11-30 | 1 | Dewi | 40 | JC071125 27455
20 | 2025-11-03 | W308 | UPDATE MODEL & SPESIFIKASI PID CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-03 | 2025-11-28 | 1 | AHMAD KHUNAIFI | 120 | JC071125 27454
21 | 2025-11-03 | W306 | UPDATE MODEL & SPESIFIKASI PID CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-03 | 2025-11-28 | 1 | AHMAD KHUNAIFI | 8 | JC071125 27447
22 | 2025-11-03 | W304 | R0 - E15550.02100 - PUMPING PLAN HIGH PRESSURE SEA WATER SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-03 | 2025-11-28 | 1 | IRFAN | 160 | JC071125 27444
23 | 2025-11-03 | A24AOP01 | PERHITUNGAN HIDROLIS STEERING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-03 | 2025-11-07 | 1 | ARDAN |  | JC071125 27443
24 | 2025-11-03 | W000308 | E1611U.27100 - Pipe Modelling & Ready in Block 611 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-03 | 2025-11-30 | 1 | Syaiful | 55 | JC071125 27400
25 | 2025-11-03 | W000308 | E1444U.27100 - Pipe Modelling & Ready in Block 444 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-03 | 2025-11-30 | 1 | Syaiful | 55 | JC071125 27403
26 | 2025-11-03 | W000308 | E1224U.27100 - Pipe Modelling & Ready in Block 454 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-03 | 2025-11-30 | 1 | Syaiful | 55 | JC071125 27404
27 | 2025-11-03 | W000308 | Check 3D Model (fungsi,operasional, maintenance)/paparan di SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-03 | 2025-11-30 | 1 | Syaiful | 18 | JC071125 27405
28 | 2025-11-05 | W000308 | E1231U.27100 - Pipe Model Blok 231 P/S Engine Room | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-03 | 2025-11-30 | 1 | Yasin | 40 | JC071125 27406
29 | 2025-11-05 | W000308 | E1222U.27100 - Pipe Model Blok 222 P/S Engine Room | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-03 | 2025-11-30 | 1 | Yasin | 40 | JC071125 27407
30 | 2025-11-05 | W000308 | E1211U.27100 - Pipe Model Blok 211 P/S Engine Room | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-03 | 2025-11-30 | 1 | Yasin | 40 | JC071125 27408
31 | 2025-11-05 | W000308 | E15292.27100 - Detail Support Gasket Ballast System GRE Pipe | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-03 | 2025-11-30 | 1 | Yasin | 30 | JC071125 27409
32 | 2025-11-05 | W000308 | Check 3D Model (fungsi,operasional, maintenance)/paparan di SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-03 | 2025-11-30 | 1 | Yasin | 30 | JC071125 27410
33 | 2025-11-05 | W000308 | E15292.27100 - Evatek GRE Pipe System Ballast Custom From FPI | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-03 | 2025-11-30 | 1 | Yasin | 30 | JC071125 27411
34 | 2025-11-11 | W000306 | E12000.01101-LIST OF TOOL & INVENTORY MACH. PART | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-03 | 2025-11-14 | 1 | TEO | 80 | JC121125 27624
35 | 2025-11-11 | W000306 | E22000.01101-EST. QTY OF MATERIAL FOR TOOL & INVENTORY MACH PART | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-17 | 2025-11-28 | 1 | TEO | 80 | JC121125 27625
36 | 2025-11-19 | W000308 | CALCULATION OF MINIMUM CAPACITY DRAIN | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-03 | 2025-11-07 | 1 | Diar | 40 | JC191125 27905
37 | 2025-11-19 | W000308 | E15280.22100_R3_PID OF INSIDE SCUPPER & DRAINAGE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-10 | 2025-11-14 | 1 | Diar | 40 | JC191125 27906
38 | 2025-11-19 | W000304 | E15330.22100_R2_PIPING DIAGRAM OF FRESH WATER SANITARY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-17 | 2025-11-19 | 1 | Diar | 24 | JC191125 27909
39 | 2025-11-19 | W000306 | E25312.01100_R1_EST MAT'L FOR FRESH WATER PRODUCTION | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-20 | 2025-11-20 | 1 | Diar | 8 | JC191125 27910
40 | 2025-11-19 | W000306 | E15331.22101_R2_PID OF HOT WATER SANITARY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-21 | 2025-11-21 | 1 | Diar | 8 | JC191125 27911
41 | 2025-11-19 | W000306 | E25331.01101_R2_EST MAT'L FOR HOT WATER SANITARY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-24 | 2025-11-24 | 1 | Diar | 8 | JC191125 27912
42 | 2025-11-19 | W000306 | E15330.22100_R3_PID OF FRESH WATER SANITARY SERVICE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-25 | 2025-11-26 | 1 | Diar | 16 | JC191125 27913
43 | 2025-11-19 | W000306 | E25330.01100_R4_ESTIMATED MATERIAL FOR FRESH WATER SANITARY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-27 | 2025-11-28 | 1 | Diar | 16 | JC191125 27914
44 | 2025-11-24 | W000304 | Check Modelling Piping System EP241P-R4 , EK241P-R4, EP241S-R4, EK241S-R4, EP211S-R3, EK211S-R3, EP211P-R4, EK211P-R2, EP222S-R3, EK222S-R3 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-03 | 2025-11-21 | 1 | Asi Supeni | 70 | JC241125 28095
45 | 2025-11-24 | W306JW1-307JW2 | E25330.01100-EST. MAT FOR PID OF FRESH WATER SANITARY & SEWAGE SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-03 | 2025-11-03 | 1 | Amam | 8 | JC251125 28117
46 | 2025-11-24 | W304-305 | ANALISIS ALIRAN AKIBAT MODIFIKASI PENAMBAHAN INSERT PLATE PADA SHAFT BRACKET | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-04 | 2025-11-07 | 1 | Amam | 32 | JC251125 28118
47 | 2025-11-24 | A24AOP01 | MENGAWAL PERSIAPAN UJI COBA PELUNCURAN TORPEDO KSOT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-10 | 2025-11-14 | 1 | Amam | 40 | JC251125 28119
48 | 2025-11-24 | W306JW1-307JW2 | E15280.22100-PIPING DIAGRAM OF SEWAGE SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-17 | 2025-11-20 | 1 | Amam | 32 | JC251125 28120
49 | 2025-11-24 | W306JW1-307JW2 | E15292.22100-PIPING DIAGRAM OF BALLAST SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-21 | 2025-11-27 | 1 | Amam | 32 | JC251125 28121
50 | 2025-11-24 | W306JW1-307JW2 | E15291.22100-PIPING DIAGRAM OF BILGE SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-28 | 2025-11-28 | 1 | Amam | 8 | JC251125 28122
51 | 2025-11-24 | W000306 | COMPARE MATERIAL PIPE FITTING EST MAT VS 3D MODEL UNTUK PENGADAAN TAHAP 3 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-03 | 2025-11-03 | 1 | Nizar | 8 | JC251125 28123
52 | 2025-11-24 | W000306 | E14372.22100-R3-PID OF TANK LEVEL AND DRAUGHT GAUGING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-04 | 2025-11-07 | 1 | Nizar | 32 | JC251125 28124
53 | 2025-11-24 | W000306 | CREATE A PURCHASE LIST OF PIPE & FITTING MATERIALS BATCH 3 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-10 | 2025-11-11 | 1 | Nizar | 16 | JC251125 28125
54 | 2025-11-24 | W000304 | EVATEK PIPE & FITTING TAHAP 5 VENDOR ELDIYA-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-12 | 2025-11-14 | 1 | Nizar | 24 | JC251125 28126
55 | 2025-11-24 | W000306 | E14372.22100-R3-PID OF TANK LEVEL AND DRAFT GAUGING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-17 | 2025-11-17 | 1 | Nizar | 8 | JC251125 28127
56 | 2025-11-24 | W000308 | EVATEK MAKER TANK LEVEL AND DRAFT GAUGING | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-18 | 2025-11-24 | 1 | Nizar | 40 | JC251125 28128
57 | 2025-11-24 | W000305 | Create a Purchase List for Batch 1 Valves | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-25 | 2025-11-28 | 1 | Nizar | 32 | JC251125 28129
58 | 2025-11-25 | W308 | R0 - E35130.50100 - EVALUASI TEKNIS PENAWARAN AHU & CWU MAKER SUPPLIER VENDOR JOSUN | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-03 | 2025-11-08 |  | PRATAMA |  | JC261125 28131
59 | 2025-11-25 | W308 | REV.0 - ED134S.48100 - MODELLING DUCT IN 02 DECK - BLOCK134S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-01 | 2025-11-08 |  | STEVAN | 40 | JC261125 28132
60 | 2025-11-25 | W308 | REV.0 - ED124P.48100 - MODELLING DUCT IN 02 DECK - BLOCK124P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-10 | 2025-11-15 |  | STEVAN | 40 | JC261125 28133
61 | 2025-11-25 | W308 | REV.0 - ED124S.48100 - MODELLING DUCT IN 02 DECK - BLOCK124S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-17 | 2025-11-22 |  | STEVAN | 40 | JC261125 28134
62 | 2025-11-25 | W308 | REV.0 - ED114P.48100 - MODELLING DUCT IN 02 DECK - BLOCK114P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-24 | 2025-11-29 |  | STEVAN | 40 | JC261125 28137
63 | 2025-11-25 | W308 | REV.0 - EVALUASI TEKNIS HVAC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-01 | 2025-11-30 |  | STEVAN | 20 | JC261125 28138
64 | 2025-11-25 | W304 | REV.0 - EVALUASI TEKNIS APPROVAL DRAWING HVAC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-01 | 2025-11-30 |  | STEVAN | 20 | JC261125 28139
65 | 2025-11-25 | W308 | REV.01 - E35130.50100 - EVALUASI TEKNIS PENAWARAN PT. PAL UAE NAVY NB - HVAC SUPPLIER VENDOR JOSUN | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-10 | 2025-11-15 |  | PRATAMA |  | JC261125 28140
66 | 2025-11-25 | W306 | R0 - E1434P.12100 - PIPING ARRAGEMENT BLOCK 434 P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-03 | 2025-11-05 |  | FARIS NOVARIANSYAH | 18 | JC261125 28143
67 | 2025-11-25 | W306 | R0 - E1434S.12100 - PIPING ARRAGEMENT BLOCK 434 S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-06 | 2025-11-10 |  | FARIS NOVARIANSYAH | 18 | JC261125 28144
68 | 2025-11-25 | W308 | R0 - E232P.48100 - VENT SKETCHES BLOCK 232 P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-11 | 2025-11-13 |  | FARIS NOVARIANSYAH | 18 | JC261125 28145
69 | 2025-11-25 | W306 | R0 - ROUTING AND READY PIPE BALLAST WATER & DOCKWELL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-14 | 2025-11-19 |  | FARIS NOVARIANSYAH | 18 | JC261125 28146
70 | 2025-11-25 | W308 | RB1 - E35130.50100 - EVALUASI TEKNIS PENAWARAN AHU & CWU MAKER SUPPLIER VENDOR JOSUN | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-17 | 2025-11-22 |  | PRATAMA |  | JC261125 28141
71 | 2025-11-25 | W304 | R16 - E15141.28100 - DIAGRAM OF AIR CONDITIONING SYSTEM (M) REVIEW | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-24 | 2025-11-30 |  | PRATAMA |  | JC261125 28142
72 | 2025-11-25 | W306 | R0 - E1222P.12100 - PIPING ARRAGEMENT BLOCK 222 P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-20 | 2025-11-24 |  | FARIS NOVARIANSYAH | 18 | JC261125 28147
73 | 2025-11-25 | W306 | R1 - EP124P.42100 - PIPE ISOMETRIC IN "03" DECK BLOCK 124 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-25 | 2025-11-26 |  | FARIS NOVARIANSYAH | 12 | JC261125 28148
74 | 2025-11-25 | W306 | R1 - EP124P.42100 - PIPE ISOMETRIC IN "03" DECK BLOCK 124 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-26 | 2025-11-27 |  | FARIS NOVARIANSYAH | 12 | JC261125 28149
75 | 2025-11-25 | A24AOP01 | TORPEDO PIRANHA DESIGN (MODELLING) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-10 | 2025-11-21 |  | ARDAN |  | JC261125 28135
76 | 2025-11-25 | W000304 | TORPEDO PIRANHA DESIGN (TRIM CALCULATION) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-24 | 2025-11-28 |  | ARDAN |  | JC261125 28136
77 | 2025-11-26 | W304 | UPDATE MODEL & SPESIFIKASI PID CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-03 | 2025-11-30 |  | AHMAD KHUNAIFI | 120 | JC261125 28155
78 | 2025-11-27 | KSSR | KSSR HULL RESISTANCE ANALYSIS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-01 | 2025-11-30 |  | Aditya Prayoga | 40 | JC281125 28199
79 | 2025-11-27 | W304 | E12430.33100 - SHAFT ARRANGEMENT - R3 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-01 | 2025-11-30 |  | Aditya Prayoga | 16 | JC281125 28203
80 | 2025-11-27 | W306 | EVATEK ENGINE ROOM PUMPS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-01 | 2025-11-30 |  | Aditya Prayoga | 24 | JC281125 28204
81 | 2025-11-27 | W306 | E95000.92101 - KB03 - R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-01 | 2025-11-30 |  | Aditya Prayoga | 32 | JC281125 28206
82 | 2025-11-27 | A24AOP01 | TORPEDO PIRANHA DESIGN (DETAIL DRAWING ELECTONICS SECTION) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-01 | 2025-11-30 |  | Aditya Prayoga | 8 | JC281125 28205
83 | 2025-11-27 | W308 | UPDATE KB03 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-01 | 2025-11-30 |  | Aditya Prayoga | 16 | JC281125 28207
84 | 2025-11-27 | W304 | UPDATE KB04 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-01 | 2025-11-30 |  | Aditya Prayoga | 16 | JC281125 28208
85 | 2025-11-27 | W000308 | CREATE SISTEM KOMPARASI MATERIAL CADAMTIC VS EST. MAT_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-03 | 2025-11-07 | 1 | Krisdiyantoro | 40 | JC281125 28209
86 | 2025-11-27 | W000308 | CREATE SISTEM KOMPARASI MATERIAL CADAMTIC VS EST. MAT_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-10 | 2025-11-14 | 1 | Krisdiyantoro | 40 | JC281125 28210
87 | 2025-11-27 | W000308 | EVATEK BY DESCRIPTION PART RCV MAKER KEYSTONE_R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-17 | 2025-11-21 | 1 | Krisdiyantoro | 40 | JC281125 28211
88 | 2025-11-27 | R25US1XA | E15240.22100_PIPING DIAGRAM OF SEA WATER COOLING_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-24 | 2025-11-28 | 1 | Krisdiyantoro | 40 |  | JC291125 28309
89 | 2025-11-28 | W306 | R1 - E15060.22100 - EST. QTY. MAT. FOR PIPING DIAGRAM OF AIR PIPE & SOUNDING (HULL) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-03 | 2025-11-05 |  | SATRIO | 24 | JC281125 28212
90 | 2025-11-28 | W308 | R3 - E15282.22100 - PIPING DIAGRAM OF GREY WATER SYSTEM (UPDATED MAKER GREASE TRAP) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-06 | 2025-11-07 |  | SATRIO | 16 | JC281125 28214
91 | 2025-11-28 | W305 | R1 - E25231.22100 - EST. QTY. MAT. FOR PIPING DIAGRAM OF PREWETTING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-10 | 2025-11-14 |  | SATRIO | 40 | JC281125 28215
92 | 2025-11-28 | W308 | R0 - E1122P.18100 - ARRT OF VENT IN BLOCK 122 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-17 | 2025-11-18 |  | SATRIO | 16 | JC281125 28220
93 | 2025-11-28 | W306 | - - - CALCULATION OF FIRE & BILGE PUMPS | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-19 | 2025-11-20 |  | SATRIO | 24 | JC281125 28221
94 | 2025-11-28 | W308 | R0 - E1122S.18100 - ARRT OF VENT IN BLOCK 122 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-21 | 2025-11-24 |  | SATRIO | 16 | JC281125 28222
95 | 2025-11-28 | W308 | R0 - E1132P.18100 - ARRT OF VENT IN BLOCK 132 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-25 | 2025-11-25 |  | SATRIO | 8 | JC281125 28223
96 | 2025-11-28 | W308 | R0 - E1453S.18100 - ARRT OF VENT IN ACCOM. BLOCK 453 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-26 | 2025-11-26 |  | SATRIO | 8 | JC281125 28224
97 | 2025-11-28 | W308 | R0 - E1453P.18100 - ARRT OF VENT IN ACCOM. BLOCK 453 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-27 | 2025-11-28 |  | SATRIO | 8 | JC281125 28225
98 | 2025-11-28 | W307 | R3 - E15280.22100 - PIPING DIAGRAM OF INSIDE SCUPPER AND DECK DRAINAGE (UPDATE CALCULATION) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-03 | 2025-11-05 |  | RAFIKA |  | JC281125 28227
99 | 2025-11-28 | W308 | R4 - E15292.22101 - PIPING DIAGRAM OF WATER BALLAST AND WATER DOCKWELL SYSTEM (UPDATE MAKER GRE) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-06 | 2025-11-07 |  | RAFIKA |  | JC281125 28230
100 | 2025-11-28 | W308 | R5 - E25292.01101 - EST MAT FOR PIPING DIAGRAM OF WATER BALLAST AND WATER DOCKWELL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-10 | 2025-11-13 |  | RAFIKA |  | JC281125 28231
101 | 2025-11-28 | W307 | A0 - E25292.01101 - EST MAT FOR PIPING DIAGRAM OF WATER BALLAST AND WATER DOCKWELL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-14 | 2025-11-19 |  | RAFIKA |  | JC281125 28242
102 | 2025-11-28 | W308 | R0 - E1322S.18100 - ARRT OF VENT IN BLOCK 322 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-20 | 2025-11-25 |  | RAFIKA |  | JC281125 28235
103 | 2025-11-28 | W308 | R0 - E1322P.18100 - ARRT OF VENT IN BLOCK 322 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-26 | 2025-11-28 |  | RAFIKA |  | JC281125 28239
104 | 2025-11-28 | R22FPBXA | Shafting Arrangement | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-03 | 2025-11-07 | 1 | Syafril | 40 | JC29112528307
105 | 2025-11-28 | JW1 -JW2 | Annex to Order Water Jet for LCU | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-10 | 2025-11-14 | 1 | Syafril | 40 | JC281125 28252
106 | 2025-11-28 | KSSR 18 m | Propulsion system | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-17 | 2025-11-28 | 1 | Syafril | 80 | JC281125 28254
107 | 2025-11-28 | W308 | CALCULATION ROOM PRESSURIZATION FOR NBC MODE | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-03 | 2025-11-17 |  | FIRMAN | 88 | JC281125 28256
108 | 2025-11-28 | A24AOP01 | 3D MODELLING AND 2D DRAFTING FOR TOPEDO POOL TEST AND CRADLE | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-18 | 2025-11-24 |  | FIRMAN | 40 | JC281125 28257
109 | 2025-11-28 | W308 | R0 - E1531.18100 - ARRT AND DETAIL OF VENT HEAD IN ENGINE ROOM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-11-25 | 2025-11-28 |  | FIRMAN | 32 | JC281125 28258
110 | 2025-11-28 | A24AOP01 | E15510.01100 - R5 - EST. MAT. QTY FOR PIPING DIAGRAM OF COMPRESSED AIR SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-03 | 2025-11-07 |  | MIEKAIL | 40 | JC281125 28283
111 | 2025-11-28 | A24AOP01 | BATTERY & EQUIPMENT ARRANGEMENT FOR NEW GENERATION KSOT - R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-10 | 2025-11-12 |  | MIEKAIL | 24 | JC281125 28284
112 | 2025-11-28 | A24AOP01 | ARRANGEMENT KOLAM UJI TORPEDO - R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-13 | 2025-11-14 |  | MIEKAIL | 16 | JC281125 28285
113 | 2025-11-28 | A24AOP01 | 3D SCAN PROPULTION SECTION TORPEDO - R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-17 | 2025-11-21 |  | MIEKAIL | 40 | JC281125 28286
114 | 2025-11-28 | R25USIXA | E15321.22100 - PID OF HT LT FW COOLING SYSTEM -R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-11-24 | 2025-11-28 |  | MIEKAIL | 40 | JC041225 28613 | JC291125 28309
115 | 2025-11-28 | W000304 | Check Modelling Piping Output EP232P-R3 , EK232P-R2, ES121P-R0, ES142C-R0, EP232S-R3, EK232S-R3, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-11-24 | 2025-11-28 | 1 | Asi Supeni | 40 | JC281125 28288
2025-12-01
1 | 2025-11-28 | W000307 | E15281.17100 Pipe Model Black Water system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-14 | 1 | Dimas | 102 | JC011225 28421
2 | 2025-11-28 | W000307 | E13410.17100 Pipe Model FO LO Drain system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-15 | 2025-12-21 | 1 | Dimas | 52 | JC011225 28423
3 | 2025-11-28 | W000307 | E13410.17100 Pipe Model SW Cooling system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-22 | 2025-12-28 | 1 | Dimas | 52 | JC011225 28424
3 | 2025-11-28 | W000307 | E12590.17100 Pipe Model Exhaust Gas system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-29 | 2025-12-31 | 1 | Dimas | 30 | JC011225 28426
4 | 2025-11-28 | W000304 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-31 | 1 | Dimas | 8 | JC011225 28430
5 | 2025-11-28 | W000306 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-31 | 1 | Dimas | 8 | JC011225 28438
6 | 2025-11-28 | W000308 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-31 | 1 | Dimas | 8 | JC011225 28439 | JC041225 28613
7 | 2025-11-28 | W000305 | E1112S.17100 - Pipe Modelling Block 112P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-31 | 1 | Dewi | 40 | JC011225 28431
8 | 2025-11-28 | W000305 | E1122S.17100 - Pipe Modelling Block 122S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-31 | 1 | Dewi | 40 | JC011225 28432
9 | 2025-11-28 | W000305 | E1413P.17100 - Pipe Modelling Block 413P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-31 | 1 | Dewi | 40 | JC011225 28433
10 | 2025-11-28 | W000305 | E1413S.17100 - Pipe Modelling Block 413S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-31 | 1 | Dewi | 40 | JC011225 28434
11 | 2025-11-28 | W000305 | E1432P.17100 - Pipe Modelling Block 432P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-31 | 1 | Dewi | 40 | JC011225 28435
12 | 2025-12-01 | W000305 | E15513.17100 - Pipe Modelling Low Air Pressure | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-15 | 1 | Erly | 98 | JC011225 28436
13 | 2025-12-01 | W000305 | E15512.17100 - Pipe Modelling Medium Air Pressure | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-16 | 2025-12-31 | 1 | Erly | 98 | JC011225 28437
14 | 2025-12-01 | W000308 | E15062U.27100 - Pipe Modelling & Ready Air Pipe System Material GRE | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-31 | 1 | Syaiful | 55 | JC011225 28440
15 | 2025-12-01 | W000308 | E15161. 27100 - Pipe Modelling & Ready Chilled Water System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-31 | 1 | Syaiful | 55 | JC011225 28441
16 | 2025-12-01 | W000308 | E15331.27100 - Pipe Modelling & Ready Hot Water System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-31 | 1 | Syaiful | 55 | JC011225 28442
17 | 2025-12-01 | W000308 | Check 3D Model (fungsi,operasional, maintenance)/paparan di SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-31 | 1 | Syaiful | 18 | JC011225 28443
18 | 2025-12-01 | W000307 | ES531P.17100 - Pipe Modeling Support block 531P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-07 | 1 | Rizki R | 58 | JC011225 28427
19 | 2025-12-01 | W000307 | ES531P.17100 - Pipe Modeling block 531P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-08 | 2025-12-21 | 1 | Rizki R | 98 | JC011225 28428
20 | 2025-12-01 | W000307 | ES511P.17100 - Pipe Modeling block 511P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-22 | 2025-12-31 | 1 | Rizki R | 55 | JC011225 28429
21 | 2025-12-02 | W000308 | E15411.27100 - Pipe Model system Fuel Oil | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-31 | 1 | Yasin | 40 | JC021225 28519
22 | 2025-12-02 | W000308 | E15931.27100 - Pipe Model system Bilge | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-31 | 1 | Yasin | 40 | JC021225 28520
23 | 2025-12-02 | W000308 | E13410.27100 - Pipe model system LO,FO, oily water drain | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-31 | 1 | Yasin | 40 | JC021225 28521
24 | 2025-12-02 | W000308 | E15292.27100 - Detail Support Gasket Ballast System GRE Pipe | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-31 | 1 | Yasin | 24 | JC021225 28522
25 | 2025-12-02 | W000308 | Check 3D Model (fungsi,operasional, maintenance)/paparan di SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-31 | 1 | Yasin | 24 | JC021225 28523
26 | 2025-12-02 | W000308 | E15292.27101 - Evatek GRE Pipe System Ballast Custom From FPI | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-31 | 1 | Yasin | 24 | JC021225 28524
27 | 2025-12-02 | W000308 | E15040.33100-Level Gauge For Fixed Tank | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-31 | 1 | Yasin | 24 | JC021225 28525
28 | 2025-12-03 | W000307 | E15513.17100 - Pipe Modelling Low Air Pressure | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-15 | 1 | Erly | 98 | JC031225 28556
29 | 2025-12-03 | W000307 | E15512.17100 - Pipe Modelling Medium Air Pressure | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-16 | 2025-12-31 | 1 | Erly | 98 | JC031225 28557
30 | 2025-12-03 | R25USIXA | E15510.22100-COMP. AIR PIPING DIAGRAM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-01 | 2025-12-03 | 1 | TEO | 24 | JC041225 28613
31 | 2025-12-03 | R25USIXA | E15412.22100-FO. SERV. PIPING DIAGRAM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-04 | 2025-12-08 | 1 | TEO | 24 | JC041225 28613
32 | 2025-12-03 | W000306 | INPUT SPESIFIKASI & MODEL PID CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-12-01 | 2025-12-31 | 1 | AHMAD KHUNAIFI | 120 | JC031225 28582
33 | 2025-12-03 | W000305 | UPDATE SPESIFIKASI & MODEL PID CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-12-01 | 2025-12-31 | 1 | AHMAD KHUNAIFI | 80 | JC031225 28584
34 | 2025-12-03 | W000308 | UPDATE SPESIFIKASI & MODEL PID CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-12-01 | 2025-12-31 | 1 | AHMAD KHUNAIFI | 80 | JC031225 28585
35 | 2025-12-03 | W000306 | UPDATE SPESIFIKASI & MODEL PID CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-12-01 | 2025-12-31 | 1 | AHMAD KHUNAIFI | 40 | JC031225 28583
36 | 2025-12-03 | - | MODELLING KAPAL KLINIK PAPUA | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-12-01 | 2025-12-05 | 1 | ARDAN |  | JC041225 28607
37 | 2025-12-03 | W308 | R0 - ED232S.48100 - VENT SKETCHES BLOCK 232 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-12-01 | 2025-12-19 | 1 | IRFAN | 120 | JC041225 28592
38 | 2025-12-03 | W308 | R0 - ED312S.48100 - VENT SKETCHES BLOCK 312 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-12-22 | 2025-12-31 | 1 | IRFAN | 60 | JC041225 28593
39 | 2025-12-03 | W304 | RC - E85100.51100 - HVAC SYSTEM & FAN (M) AIR HANDLING UNIT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-12-01 | 2025-12-06 | 1 | PRATAMA |  | JC041225 28594
40 | 2025-12-03 | W304 | R2 - E15140.75100 - EQUIPMENT LIST HVAC & FANS | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-12-01 | 2025-12-06 | 1 | STEVAN | 40 | JC041225 28595
41 | 2025-12-03 | W308 | R1 - E25141.01100 - EST. MAT. FOR AIR CONDITION SYSTEM (HULL PART) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-12-08 | 2025-12-13 | 1 | STEVAN | 40 | JC041225 28596
42 | 2025-12-03 | W308 | R2 - E15140.75100 - MAIN EQUIPMENT LIST AC & FAN | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-12-15 | 2025-12-20 | 1 | STEVAN | 40 | JC041225 28597
43 | 2025-12-03 | W308 | R0 - EVALUASI TEKNIS SPIRO DUCT & ACCESSORIES | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-12-01 | 2025-12-31 | 1 | STEVAN | 40 | JC041225 28598
44 | 2025-12-04 | W308 | R0 - EVALUASI TEKNIS NBC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2025-12-01 | 2025-12-31 | 1 | STEVAN | 40 | JC041225 28599
45 | 2025-12-04 | W000304 | Check Modelling Piping Output ES515C-R0 , ES613C-R0, EP222P-R3, EK222P-R3, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-01 | 2025-12-05 | 1 | Asi Supeni | 40 | JC041225 28608
46 | 2025-12-04 | R25US1XA | E12590.22100_PIPING DIAGRAM OF MIST PIPE & EXHAUST GAS_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-01 | 2025-12-05 | 1 | Krisdiyantoro | 24 | JC041225 28613
47 | 2025-12-04 | W000304 | E15000.01100_PRINCIPAL PARTICULAR MACHINERY PART_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-01 | 2025-12-05 | 1 | Diar | 40 | JC041225 28610 | Extend 31 des
48 | 2025-12-04 | W000305 | Create a Purchase List for Batch 1 Valves | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-01 | 2025-12-12 | 1 | NIZAR | 80 | JC041225 28612
49 | 2025-12-05 | W307 | R1 - E15292.22100 - PIPING DIAGRAM OF PNEUMATIC VALVES REMOTE CONTROL FOR BALLAST AND DOCKWELL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 December 2025 | 2 December 2025 |  | RAFIKA |  | JC051225 28687
50 | 2025-12-05 | W308 | R0 - E1232S.18100 - ARR'T OF VENT IN BLOCK 232S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 3 December 2025 | 4 December 2025 |  | RAFIKA |  | JC051225 28688
51 | 2025-12-05 | W308 | R0 - E1232P.18100 - ARR'T OF VENT IN BLOCK 232P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 5 December 2025 | 8 December 2025 |  | RAFIKA |  | JC051225 28689
52 | 2025-12-05 | W306 | R0 - E11434P.12100 - ARRAGEMENT BLOCK 434 P IN 02 DECK | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 December 2025 | 2 December 2025 |  | FARIS NOVARIANSYAH | 12 | JC051225 28690
53 | 2025-12-05 | W306 | R0 - E11434S.12100 - ARRAGEMENT BLOCK 434 S IN 02 DECK | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 3 December 2025 | 4 December 2025 |  | FARIS NOVARIANSYAH | 12 | JC051225 28691
54 | 2025-12-05 | W306 | R0 - EP133P.42100 - ISOMETRIC BLOCK 133 P IN 02 DECK | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 5 December 2025 | 9 December 2025 |  | FARIS NOVARIANSYAH | 18 | JC051225 28693
55 | 2025-12-05 | W306 | R0 - EP133S.42100 - ISOMETRIC BLOCK 133 S IN 02 DECK | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 10 December 2025 | 12 December 2025 |  | FARIS NOVARIANSYAH | 18 | JC051225 28694
56 | 2025-12-05 | W306 | R0 - EP134P.42100 - ISOMETRIC BLOCK 134 P IN 03 DECK | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 15 December 2025 | 17 December 2025 |  | FARIS NOVARIANSYAH | 18 | JC051225 28695
57 | 2025-12-05 | W306 | R0 - EP134S.42100 - ISOMETRIC BLOCK 134 S IN 03 DECK | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 18 December 2025 | 22 December 2025 |  | FARIS NOVARIANSYAH | 18 | JC051225 28696
58 | 2025-12-05 | W304 | ANALYSIS OF SHAFT BEARING SEAWATER FLOW | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-01 | 2025-12-05 |  | Aditya Prayoga | 40 | JC081225 28756
59 | 2025-12-08 | W000308 | E15000.01100_R0_PRINCIPAL PARTICULAR MACHINERY PART | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-08 | 2025-12-12 | 1 | Diar | 40 | JC081225 28769 | Extend 31 des
60 | 2025-12-08 | W000305 | EVATEK VALVE TAHAP 3-R1-VENDOR CNJ | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-08 | 2025-12-19 | 1 | NIZAR | 80 | JC091225 28882
61 | 2025-09-12 | W308 | R0 - ED333P.48100 - VENT SKETCHES IN ACCOM BLOCK 333 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 December 2025 | 2 December 2025 |  | SATRIO | 16 | JC091225 28883
62 | 2025-09-12 | W308 | R0 - ED333S.48100 - VENT SKETCHES IN ACCOM BLOCK 333 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 3 December 2025 | 4 December 2025 |  | SATRIO | 16 | JC091225 28884
63 | 2025-09-12 | W308 | R0 - ED133P.48100 - VENT SKETCHES IN ACCOM BLOCK 133 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 5 December 2025 | 8 December 2025 |  | SATRIO | 16 | JC091225 28885
64 | 2025-09-12 | W308 | R0 - ED313P.48100 - VENT SKETCHES IN ACCOM BLOCK 313 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 9 December 2025 | 10 December 2025 |  | SATRIO | 16 | JC091225 28887
65 | 2025-09-12 | W308 | R0 - ED313S.48100 - VENT SKETCHES IN ACCOM BLOCK 313 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 11 December 2025 | 12 December 2025 |  | SATRIO | 16 | JC091225 28886
66 | 2025-09-12 | W308 | R0 - ED323P.48100 - VENT SKETCHES IN ACCOM BLOCK 323 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 15 December 2025 | 16 December 2025 |  | SATRIO | 16 | JC091225 28888
67 | 2025-09-12 | W308 | R0 - ED323S.48100 - VENT SKETCHES IN ACCOM BLOCK 323 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 17 December 2025 | 18 December 2025 |  | SATRIO | 16 | JC091225 28889
68 | 2025-09-12 | W308 | R1 - E25231.22100 - EST. QTY. MAT. FOR PIPING DIAGRAM OF PREWETTING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 15 December 2025 | 31 December 2025 |  | SATRIO | 16 | JC091225 28890
69 | 2025-09-12 | W308 | R1 - E25931.22100 - EST. QTY. MAT. FOR PIPING DIAGRAM OF SLUDGE & OILY BILGE SEPARATOR SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 15 December 2025 | 31 December 2025 |  | SATRIO | 16 | JC091225 28891
70 | 2025-09-12 | W308 | R0 - ED343P.48100 - VENT SKETCHES IN ACCOM BLOCK 343 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 25 December 2025 | 30 December 2025 |  | SATRIO | 16 | JC091225 28892
71 | 2025-09-12 | W308 | R0 - ED343S.48100 - VENT SKETCHES IN ACCOM BLOCK 343 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 25 December 2025 | 30 December 2025 |  | SATRIO | 16 | JC091225 28893
72 | 2025-09-12 | W308 | R0 - ED353S.48100 - VENT SKETCHES IN ACCOM BLOCK 353 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 31 December 2025 | 1 January 2026 |  | SATRIO | 16
73 | 2025-09-12 | W308 | R0 - ED353P.48100 - VENT SKETCHES IN ACCOM BLOCK 353 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 January 2026 | 5 January 2026 |  | SATRIO | 16
74 | 2025-09-12 | W308 | R0 - ED611S.48100 - VENT SKETCHES IN ACCOM BLOCK 611 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 6 January 2026 | 7 January 2026 |  | SATRIO | 16
75 | 2025-09-12 | W308 | R0 - ED611P.48100 - VENT SKETCHES IN ACCOM BLOCK 611 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 8 January 2026 | 9 January 2026 |  | SATRIO | 16
76 | 2025-09-12 | W306 | RC2 - E85100.51100 - HVAC SYSTEM & FAN (M) CHILLED WATER AIR HANDLING UNIT DATASHEET AND GA | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 8 December 2025 | 13 December 2025 |  | PRATAMA |  | JC091225 28894
77 | 2025-09-12 | A24AOPO1 | REVERSE ENGINEERING 3D MODEL PROPULSI TORPEDO | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 8 December 2025 | 19 December 2025 |  | ARDAN |  | JC091225 28895
78 | 2025-12-09 | R25US1XA | FO. FILLING TRANSFER & OVERFLOW PIPING DIAGRAM-E15411.22100 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-09 | 2025-12-12 |  | TEO | 32 | JC041225 28613
79 | 2025-12-09 | W306 | E15072.37100-NAME PLATE OF VALVE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-15 | 2025-12-19 |  | TEO | 40 | JC091225 28908
80 | 2025-12-09 | W306 | NAME PLATE & CAUTION PLATE OF EQUIPMENT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-22 | 2025-12-24 |  | TEO | 24 | JC091225 28909
81 | 2025-12-09 | W000306 | E15000.01100_R0_PRINCIPAL PARTICULAR MACHINERY PART | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-09 | 2025-12-19 |  | Diar | 72 | JC091225 28912
82 | 10 December 2025 | W308 | R0 - E1312S.18100 - ARR'T OF VENT IN BLOCK 312S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 9 December 2025 | 10 December 2025 |  | RAFIKA |  | JC111225 28928
83 | 10 December 2025 | W308 | R0 - E1312P.18100 - ARR'T OF VENT IN BLOCK 312P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 11 December 2025 | 12 December 2025 |  | RAFIKA |  | JC111225 28929
84 | 2025-12-11 | W000308 | EVATEK VALVE BATCH 2-R0-VENDOR CNJ | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-10 | 2025-12-31 |  | Diar | 120 | JC111225 28931
85 | 2025-12-11 | R22FPBXA | Main Generator Set (M) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-01 | 2025-12-05 |  | Syafril | 40 | JC111225 28939
86 | 2025-12-11 | KSSR 18 m | Propulsion system | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-08 | 2025-12-12 |  | Syafril | 40 | JC111225 28932
86 | 2025-12-11 | KSSR 18 m | EVATEK MAIN ENGINE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-15 | 2025-12-31 |  | Syafril | 104 | JC111225 28933
87 | 2025-12-11 | W000304 | Check Modelling Piping Output EP432S-R3 , EK432S-R3, EP432P-R3, EK432P-R3, ES683C-R0, EP423P-R2, EK423P-R2, EP413S-R2, EK413S-R2 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-08 | 2025-12-12 | 1 | Asi Supeni | 40 | JC111225 28940
88 | 2025-12-12 | W304 | ANALYSIS OF SHAFT BEARING SEAWATER FLOW | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-08 | 2025-12-12 |  | Aditya Prayoga | 24 | JC121225 28949
89 | 2025-12-12 | W304 | DETAIL AND ARRANGEMENT OF SHAFT PROTECTION COVER | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-08 | 2025-12-12 |  | Aditya Prayoga | 8 | JC121225 28950
90 | 2025-12-12 | W307 | E25282.01100-EST. MAT. QTY FOR PIPING DIAGRAM OF GREY WATER SYSTEM-R5 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-01 | 2025-12-04 |  | MIEKAIL | 32 | JC121225 28986
91 | 2025-12-12 | W307 | E25281.01100-EST. MAT. QTY FOR PIPING DIAGRAM OF BLACK WATER SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-05 | 2025-12-09 |  | MIEKAIL | 24 | JC121225 28987
92 | 2025-12-12 | R25USIXA | E15431.22100-PID OF LO. FILLING, TRANSFER AND OVERFLOW SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-10 | 2025-12-12 |  | MIEKAIL | 24 | JC041225 28613
93 | 2025-12-15 | W306JW1-307JW2 | E15291.22100-PIPING DIAGRAM OF BILGE SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-01 | 2025-12-03 |  | AMAM | 24 | JC151225 29131
94 | 2025-12-15 | W306JW1-307JW2 | E15210.22100-PIPING DIAGRAM OF FIRE MAIN & DECK WASH SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-04 | 2025-12-05 |  | AMAM | 16 | JC151225 29132
95 | 2025-12-15 | W306JW1-307JW2 | E15410.22100-PIPING DIAGRAM OF FUEL OIL SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-08 | 2025-12-12 |  | AMAM | 40 | JC151225 29133
96 | 2025-12-15 | W306JW1-307JW2 | E15240.22100-PIPING DIAGRAM OF SEA WATER COOLING SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-15 | 2025-12-18 |  | AMAM | 32 | JC151225 29134
97 | 2025-12-15 | W306JW1-307JW2 | E12590.22100-PIPING DIAGRAM OF EXHAUST GAS SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-19 | 2025-12-24 |  | AMAM | 32 | JC151225 29135
98 | 2025-12-15 | W306JW1-307JW2 | E15060.22100-PIPING DIAGRAM OF AIR & SOUNDING PIPE-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-25 | 2025-12-31 |  | AMAM | 40 | JC151225 29136
99 | 2025-12-15 | W304 | ANALYSIS OF SHAFT BEARING SEAWATER FLOW | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-15 | 2025-12-19 |  | Aditya Prayoga | 40 | JC151225 29137
100 | 2025-12-15 | R25USIXA | E15431.22100-PID OF LO. FILLING, TRANSFER AND OVERFLOW SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-15 | 2025-12-15 |  | MIEKAIL | 8 | JC041225 28613
101 | 15 December 2025 | A24AOP01 | R0 - - 3D MODEL & DRAFTING OF PLATFORM FOR TORPEDO TEST POOL | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 December 2025 | 5 December 2025 |  | FIRMAN |  | JC161225 29176
102 | 15 December 2025 | A24AOP01 | R0 - - 3D MODEL & DRAFTING OF ROV THRUSTER MOUNT FOR TORPEDO TEST POOL | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 8 December 2025 | 12 December 2025 |  | FIRMAN |  | JC161225 29178
103 | 15 December 2025 | W308 | R0 - E1531.18100 - ARR'T & DETAIL OF VENTILATOR HEAD FOR ENGINE ROOM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 15 December 2025 | 19 December 2025 |  | FIRMAN |  | JC161225 29180
104 | 15 December 2025 | W308 | R0 - E1312S.18100 - ARR'T OF VENT IN BLOCK 312S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 15 December 2025 | 16 December 2025 |  | RAFIKA |  | JC161225 29182
105 | 15 December 2025 | W308 | R0 - E1312P.18100 - ARR'T OF VENT IN BLOCK 312P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 17 December 2025 | 19 December 2025 |  | RAFIKA |  | JC161225 29183
106 | 15 December 2025 | W304 | RE - E15160.22100 - PIPING DIAGRAM OF CHILLED WATER SYSTEM (M) REVIEW | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 15 December 2025 | 20 December 2025 |  | PRATAMA |  | JC161225 29184
107 | 2025-12-16 | W306 | EVATEK VALVE BATCH 2-R0-VENDOR CNJ | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-16 | 2025-12-26 |  | NIZAR | 80 | JC161225 29185
108 | 16 December 2025 | W308 | KAJIAN TEKNIS PENEMPATAN POSISI TORPEDO DETECTION SONAR (TDS) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 22 December 2025 | 24 December 2025 |  | ARDAN |  | JC161225 29189
109 | 2025-12-18 | W000304 | Check Modelling Piping Output EP413-R2 , EK413P-R2, EP234P-R2, EK234P-R2, EP234S-R2, EK234S-R2, EP433P-R2, EK433P-R2, EP433S-R2, EK433S-R2, EP212S-R4, EK212S-R4, EP434S-R2, EK434S-R2, EP434P-R2,EK434P-R2, EP213S-R2, EK213S-R2, EP213P-R2, EK213P-R2 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-15 | 2025-12-19 | 1 | Asi Supeni | 40 | JC191225 29248
110 | 2025-12-19 | W000304 | Check Modelling Piping Output EP424P-R2 , EK424P-R2, EP424S-R2, EK424S-R2, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-22 | 2025-12-26 | 1 | Asi Supeni | 40 | JC191225 29279
111 | 23 December 2025 | W304 | RC - E15161.22100 - CHILLED WATER CIRCULATION DIAGRAM (M) REVIEW | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 22 December 2025 | 27 December 2025 |  | PRATAMA |  | JC231225 29476
112 | 23 December 2025 | W000311 | INPUT SPEC. PIPE LINE PID & MODELING CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-01-01 | 2026-01-31 |  | AHMAD KHUNAIFI | 160 | JC311225 29700
113 | 23 December 2025 | A24AOPO1 | PERHITUNGAN RESISTANCE DAN POWER NEXT MODEL KSOT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 29 December 2025 | 31 December 2025 |  | ARDAN |  | JC231225 29477
114 | 23 December 2025 | W308 | R0 - EVALUASI TEKNIS NBC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 January 2026 | 31 January 2026 |  | STEVAN | 40 | JC311225 29701
115 | 23 December 2025 | W306 | R0 - EVALUASI TEKNIS APPROVAL DRAWING AIR COND. SYSTEM (HULL PART) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 January 2026 | 31 January 2026 |  | STEVAN | 40 | JC311225 29702
116 | 23 December 2025 | W306 | R1 - E1314P.18100 - MODELLING VENT IN BLOCK 314P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 5 January 2026 | 10 January 2026 |  | STEVAN | 40 | JC311225 29703
117 | 23 December 2025 | W306 | R1 - E1314S.18100 - MODELLING VENT IN BLOCK 314S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 12 January 2026 | 17 January 2026 |  | STEVAN | 40 | JC311225 29704
118 | 23 December 2025 | W306 | R1 - E1134P.18100 - MODELLING VENT IN BLOCK 134P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 19 January 2026 | 23 January 2026 |  | STEVAN | 40 | JC311225 29705
119 | 23 December 2025 | W306 | R1 - E1134S.18100 - MODELLING VENT IN BLOCK 134S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 19 January 2026 | 24 January 2026 |  | STEVAN | 40 | JC311225 29706
120 | 23 December 2025 | W304 | R1 - E15142.33200 - MODELLING STRUCTURAL DUCT & MIST ELIMINATOR BOX | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 26 January 2026 | 31 January 2026 |  | STEVAN | 40 | JC311225 29707
121 | 24 December 2025 | A24AOPO1 | FINISH PLAN-E15510.22100-PIPING DIAGRAM OF COMPRESSED AIR SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-16 | 2025-12-17 |  | MIEKAIL | 16 | JC241225 29506
122 | 24 December 2025 | A24AOPO1 | FINISH PLAN-E15240.22100-PIPING DIAGRAM OF SEA WATER COOLING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-18 | 2025-12-18 |  | MIEKAIL | 8 | JC241225 29507
123 | 24 December 2025 | A24AOPO1 | FINISH PLAN-E15291.22100-PIPING DIAGRAM OF BILGE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-19 | 2025-12-19 |  | MIEKAIL | 8 | JC241225 29508
124 | 24 December 2025 | W000304 | FINISH PLAN-E15321.22100-PIPING DIAGRAM OF FRESH WATER CENTRAL COOLING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-22 | 2025-12-22 |  | MIEKAIL | 8 | JC241225 29505
125 | 24 December 2025 | W000311 | 3D MODELLING MACHINERY EQUIPMENT AND PROPULSION | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-23 | 2025-12-26 |  | MIEKAIL | 32 | JC301225 29649
126 | 2025-12-29 | W304 | EVATEK VALVE BATCH 3-R2-VENDOR CNJ | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-29 | 2025-12-31 |  | NIZAR | 24 | JC291225 29562
127 | 2025-12-29 | W000308 | EVATEK BY DESCRIPTION PART RCV MAKER HANLA_R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-08 | 2025-12-12 |  | Krisdiyantoro | 40 | JC291225 29596
128 | 2025-12-29 | W000308 | E25290.01100_KOMPARASI MATERIAL CADMATIC VS EST. MAT SYSTEM EXH. GAS_R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-15 | 2025-12-26 |  | Krisdiyantoro | 64 | JC291225 29597
129 | 2025-12-29 | W000306-307 | CREATE LIST OF ELECTRIC REMOTE CONTROL VALVE_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-29 | 2025-12-31 |  | Krisdiyantoro | 24 | JC291225 29598
130 | 2025-12-29 | W306 | FINISH PLAN ALL PIPING DIAGRAM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-29 | 2025-12-31 |  | TEO | 24 | JC301225 29647
131 | 2025-12-30 | W311 | ANALYSIS OF SEA WATER INLET SCOOP STRAINER | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-22 | 2025-12-31 |  | Aditya Prayoga | 32 | JC301225 29694
132 | 2025-12-31 | W000304 | Check Modelling Piping Output EP242P-R3 , EK2424P-R3, EP242S-R3, EK242S-R3, EP414P-R2 , EK414P-R2, EP414S-R2, EK414S-R2, EP124P-R2 , EK124P-R2, EP124S-R2, EK124S-R2, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2025-12-29 | 2026-01-02 | 1 | Asi Supeni | 40 | JC311225 29698
133 | 31 December 2025 | W308 | R0 - E1212S.18100 - ARR'T OF VENT IN BLOCK 212S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 22 December 2025 | 24 December 2025 |  | RAFIKA |  | JC311225 29722
134 | 31 December 2025 | W308 | R0 - E1212P.18100 - ARR'T OF VENT IN BLOCK 212P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 25 December 2025 | 26 December 2025 |  | RAFIKA |  | JC311225 29723
135 | 31 December 2025 | W308 | ROUTING SYSTEM REFRIG. PROVISION STORE (5162) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 23 December 2025 | 31 December 2025 |  | FARIS NOVARIANSYAH | 30 | JC311225 29724
136 | 31 December 2025 | W304 | RE - E85100.51100 - HVAC SYSTEM & FAN (M) EXHAUST FAN & WATER DUCT COOLER CIRCULAR | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 29 December 2025 | 31 December 2025 |  | PRATAMA |  | JC311225 29729
137 | 31 December 2025 | W308 | R0 - E15131.18100 - ARR'T & DETAIL OF VENTILATOR HEAD FOR AFT & FORE PART | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 22 December 2025 | 31 December 2025 |  | FIRMAN | 48 | JC311225 29726
138 | 31 December 2025 | W308 | R0 - ED214P.48100 - VENT SKETCHES IN ACCOM. BLOCK 214 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 29 December 2025 | 30 December 2025 |  | RAFIKA |  | JC311225 29727
139 | 31 December 2025 | W308 | R0 - ED214S.48100 - VENT SKETCHES IN ACCOM. BLOCK 214 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 31 December 2025 | 2 January 2026 |  | RAFIKA |  | JC311225 29728
2026-01-01
1 | 2026-01-02 | W000311 | PIPE MODELING SEA WATER COOLING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2025-12-29 | 2025-12-31 |  | MIEKAIL | 24 | JC020126 29822
2 | 2026-01-02 | W000307 | E12590.17100 Pipe Model Exhaust Gas system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-05 | 2026-01-07 | 1 | Dimas | 30 | JC020126 29796
3 | 2026-01-02 | W000307 | E15281.17100 Pipe Model Black Water system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-08 | 2026-01-16 | 1 | Dimas | 60 | JC020126 29797
4 | 2026-01-02 | W000307 | E13410.17100 Pipe Model FO LO Drain system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-17 | 2026-01-20 | 1 | Dimas | 24 | JC020126 29798
5 | 2026-01-02 | W000307 | E13410.17100 Pipe Model SW Cooling system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-21 | 2026-01-24 | 1 | Dimas | 30 | JC020126 29799
6 | 2026-01-02 | W000307 | E15282.17100 Pipe Model Grey Water system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-25 | 2026-01-31 | 1 | Dimas | 30 | JC020126 29800
7 | 2026-01-02 | W000304 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-02 | 2026-01-31 | 1 | Dimas | 8 | JC020126 29801
8 | 2026-01-02 | W000306 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-02 | 2026-01-31 | 1 | Dimas | 8 | JC020126 29802
9 | 2026-01-02 | W000308 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-02 | 2026-01-31 | 1 | Dimas | 8 | JC020126 29803
10 | 2026-01-02 | W000308 | E15161.27100 - Revisi Pipe Modelling Chilled Water System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-02 | 2026-01-31 | 1 | Syaiful | 50 | JC020126 29804
11 | 2026-01-02 | W000308 | ⁠E15513.27100 - Pipe Modelling Low Air Pressure System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-02 | 2026-01-31 | 1 | Syaiful | 50 | JC020126 29805
12 | 2026-01-02 | W000308 | E15231.27100 - Revisi Pipe Modelling Prewetting System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-02 | 2026-01-31 | 1 | Syaiful | 50 | JC020126 29806
13 | 2026-01-02 | W000308 | E15211.27100 - Revisi Pipe Modelling Fire and Wash Deck System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-02 | 2026-01-31 | 1 | Syaiful | 50 | JC020126 29807
14 | 2026-01-02 | W000308 | Check 3D Model (fungsi,operasional, maintenance)/paparan di SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-02 | 2026-01-31 | 1 | Syaiful | 18 | JC020126 29808
15 | 2026-01-02 | W000305 | E1222P.17100 - Pipe Modelling Block 222P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-02 | 2026-01-31 | 1 | Dewi | 38 | JC020126 29809
16 | 2026-01-02 | W000305 | E1222S.17100 - Pipe Modelling Block 222S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-02 | 2026-01-31 | 1 | Dewi | 38 | JC020126 29810
17 | 2026-01-02 | W000305 | E1232S.17100 - Pipe Modelling Block 232S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-02 | 2026-01-31 | 1 | Dewi | 38 | JC020126 29811
18 | 2026-01-02 | W000305 | E1232P.17100 - Pipe Modelling Block 232P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-02 | 2026-01-31 | 1 | Dewi | 38 | JC020126 29812
19 | 2026-01-02 | W000307 | E15280.17100 - Pipe Modelling Block inside scupper | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-02 | 2026-01-31 | 1 | Dewi | 38 | JC020126 29813
20 | 2026-01-02 | W000307 | E15513.17100 - Pipe Modelling Low Air Pressure | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-01 | 2026-01-10 | 1 | Erly | 60 | JC020126 29814
21 | 2026-01-02 | W000307 | E15551.17100 - Pipe Modelling Foam Fire Extinguishing | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-11 | 2026-01-31 | 1 | Erly | 132 | JC020126 29815
22 | 2026-01-05 | W000308 | E15012.33105 - Detail bellmouth system bahan bakar | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-02 | 2026-01-31 | 1 | Yasin | 24 | JC050126 29869
23 | 2026-01-05 | W000308 | E15040.33100 - Level switch for fixed tank | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-02 | 2026-01-31 | 1 | Yasin | 24 | JC050126 29872
24 | 2026-01-05 | W000308 | E15412.27100 - Pipe model system FO service in engine room | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-02 | 2026-01-31 | 1 | Yasin | 40 | JC050126 29873
25 | 2026-01-05 | W000308 | ⁠E15056.10100 - Rev.Arrangement & Detail Overboard discharge | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-02 | 2026-01-31 | 1 | Yasin | 40 | JC050126 29877
26 | 2026-01-05 | W000308 | E15931.27100 - Pipe model system bilge in engine room | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-02 | 2026-01-31 | 1 | Yasin | 40 | JC050126 29879
27 | 2026-01-05 | W000306 | E15012.33100 - Rev.detail of strainer | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-02 | 2026-01-31 | 1 | Yasin | 24 | JC050126 29881
28 | 2026-01-05 | W000307 | E1424S.17100 - Pipe Modeling System Fresh Water Block 424S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-01 | 2026-01-11 | 1 | Rizki R | 58 | JC050126 29894
29 | 2026-01-05 | W000307 | E1434S.17100 - Pipe Modeling System Fresh Water block 434S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-12 | 2026-01-18 | 1 | Rizki R | 55 | JC050126 29895
30 | 2026-01-05 | W000307 | E1214S.17100 - Pipe Modeling System Fresh Water block 214S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-19 | 2026-01-25 | 1 | Rizki R | 55 | JC050126 29896
31 | 2026-01-05 | W000307 | E1224S.17100 - Pipe Modelling System Hot Water Block 224S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-26 | 2026-01-31 | 1 | Rizki R | 55 | JC050126 29897
32 | 5 January 2026 | W304 | R0 - E85100.51100 - HVAC SYSTEM & FAN (M) LAYOUT COMBAT COOLING PUMP SKID | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 January 2026 | 3 January 2026 |  | PRATAMA |  | JC050126 29954
33 | 5 January 2026 | W308 | R0 - ED312S.48100 - VENT SKETCHES BLOCK 312 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 5 January 2026 | 10 January 2026 |  | IRFAN | 50 | JC050126 29950
34 | 5 January 2026 | W308 | R0 - ED212P.48100 - VENT SKETCHES BLOCK 212 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 12 January 2026 | 31 January 2026 |  | IRFAN | 120 | JC050126 29951
35 | 5 January 2026 | A24AOP01 | KAJIAN TEKNIS MESIN JETSKI | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 January 2026 | 7 January 2026 |  | ARDAN |  | JC060126 30018
36 | 2026-01-06 | W000304 | FINISH PLAN-E14372.22100-PIPING DIAGRAM OF TANK LEVEL AND DRAFT GAUGING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-05 | 2026-01-08 |  | NIZAR | 32 | JC060126 30001
37 | 2026-01-06 | W000304 | FINISH PLAN-E15062.22100-PIPING DIAGRAM OF AIR PIPE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-09 | 2026-01-14 |  | NIZAR | 32 | JC060126 30002
38 | 2026-01-07 | W306 | FINISH PLAN ALL PIPING DIAGRAM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-02 | 2026-01-30 |  | TEO | 60 | JC070126 30052
39 | 2026-01-08 | W000304 | Check Drawing Piping Output EP233P-R2 , EK233P-R2, EP233S-R2, EK233S-R2, EP223P-R2 , EK223P-R2, EP223S-R2, EK223S-R2, EP213P-R2 , EK213P-R2, EP224P-R2, EK224P-R2, EP224S-R2, EK224S-R2 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-05 | 2026-01-09 | 1 | Asi Supeni | 40 | JC080126 30100
40 | 2026-01-09 | W305 | ANALYSIS OF SILENCER BACK PRESSURE AND NOISE ATTENUATION | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-01 | 2026-01-09 |  | Aditya Prayoga | 48 | JC090126 30110
41 | 2026-01-09 | W000304 | EVATEK INSTRUMENTATION VALVE BATCH 2-R7-VENDOR ILSHIN | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-12 | 2026-01-14 |  | NIZAR | 24 | JC120126 30194
42 | 2026-01-12 | W000304 | FINISH PLAN-E14372.22100-PIPING DIAGRAM OF TANK LEVEL AND DRAFT GAUGING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-02 | 2026-01-02 |  | NIZAR | 8 | JC120126 30216
43 | 2026-01-12 | W000306 | EVATEK MAKER TANK LEVEL DRAFT GAUGING SYSTEM-R2-VENDOR HANLA IMS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-15 | 2026-01-23 |  | NIZAR | 56 | JC120126 30227
44 | 13 January 2026 | W308 | R0 - E35130.50100 - EVALUASI TEKNIS PENAWARAN SCREW CHILLER UNIT & REF. PLANT CONDENSING UNIT CENTURY | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 5 January 2026 | 10 January 2026 |  | PRATAMA |  | JC130126 30332
45 | 13 January 2026 | A24AOPO1 | SIMULASI OPERASIONAL BUOY DAN TURBIN GENERATOR | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 8 January 2026 | 15 January 2026 |  | ARDAN |  | JC130126 30333
46 | 13 January 2026 | A24AOPO1 | EQUIPMENT LIST USV 3.5 METER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 16 January 2026 | 19 January 2026 |  | ARDAN |  | JC130126 30334
47 | 2026-01-14 | W000304 | Check Drawing Piping Output EP243S-R2 , EK243S-R2, EP254P-R2, EK254P-R2, EP254S-R2 , EK254S-R2, EP244P-R2, EK244P-R2, EP244S-R2 , EK244S-R2, E1613C-R0, EP611P-R2, EP611S-R2, EK611S-R2 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-12 | 2026-01-15 | 1 | Asi Supeni | 32 | JC140126 30366
48 | 2026-01-20 | W000308 | EVATEK VALVE BATCH 2-R0-VENDOR CNJ | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-01 | 2026-01-14 | 1 | DIAR | 80 | JC200126 30538
49 | 2026-01-20 | W000308 | E15280.22100_R3_PID OF INSIDE SCUPPER & DRAINAGE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-15 | 2026-01-19 | 1 | DIAR | 16 | JC200126 30539
50 | 2026-01-20 | W000308 | W308_E25280.01100_R2_ESTIMATED MATERIAL FOR INSIDE SCUPPER & DRAINAGE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-19 | 2026-01-19 | 1 | DIAR | 8 | JC200126 30540
51 | 2026-01-20 | W000304 | E15330.22100_FINISH PLAN_PIPING DIAGRAM OF FRESH WATER SANITARY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-20 | 2026-01-21 | 1 | DIAR | 16 | JC200126 30541
52 | 2026-01-20 | W000304 | E15312.22100_FINISH PLAN_PIPING DIAGRAM OF FRESH WATER PRODUCTION SYSTEM (REVERSE OSMOSIS) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-22 | 2026-01-22 | 1 | DIAR | 8 | JC200126 30542
53 | 2026-01-20 | W000304 | E15331.22101_FINISH PLAN_PIPING DIAGRAM OF HOT WATER SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-23 | 2026-01-26 | 1 | DIAR | 16 | JC200126 30543
54 | 2026-01-20 | W000304 | E15281.22100_FINISH PLAN_PIPING DIAGRAM OF SEWAGE SYSTEM IN ACCOMMODATION | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-27 | 2026-01-28 | 1 | DIAR | 16 | JC200126 30544
55 | 2026-01-20 | W000304 | E15282.22100_FINISH PLAN_PIPING DIAGRAM OF GREY WATER SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-29 | 2026-01-30 | 1 | DIAR | 16 | JC200126 30545
56 | 20 January 2026 | W311 | R0 - EVALUASI PENAWARAN MAIN GENERATOR DIESEL ENGINE | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 12 January 2026 | 31 January 2026 |  | PRATAMA |  | JC210126 30573
57 | 20 January 2026 | W308 | R0 - ED234S.48100 - VENT SKETCHES IN ACCOM. BLOCK 234 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 5 January 2026 | 6 January 2026 |  | RAFIKA |  | JC210126 30574
58 | 20 January 2026 | W308 | R0 - ED234P.48100 - VENT SKETCHES IN ACCOM. BLOCK 234 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 7 January 2026 | 7 January 2026 |  | RAFIKA |  | JC210126 30575
59 | 20 January 2026 | W308 | R0 - ED114S.48100 - VENT SKETCHES IN ACCOM. BLOCK 114 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 8 January 2026 | 8 January 2026 |  | RAFIKA |  | JC210126 30603
60 | 20 January 2026 | W308 | R0 - ED114P.48100 - VENT SKETCHES IN ACCOM. BLOCK 114 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 9 January 2026 | 9 January 2026 |  | RAFIKA |  | JC210126 30604
61 | 20 January 2026 | W308 | R0 - ED124S.48100 - VENT SKETCHES IN ACCOM. BLOCK 124 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 12 January 2026 | 12 January 2026 |  | RAFIKA |  | JC210126 30576
62 | 20 January 2026 | W308 | R0 - ED124P.48100 - VENT SKETCHES IN ACCOM. BLOCK 124 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 14 January 2026 | 14 January 2026 |  | RAFIKA |  | JC210126 30577
63 | 20 January 2026 | W308 | R0 - ED134S.48100 - VENT SKETCHES IN ACCOM. BLOCK 134 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 15 January 2026 | 15 January 2026 |  | RAFIKA |  | JC210126 30578
64 | 20 January 2026 | W308 | R0 - ED134P.48100 - VENT SKETCHES IN ACCOM. BLOCK 134 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 16 January 2026 | 16 January 2026 |  | RAFIKA |  | JC210126 30605
65 | 20 January 2026 | W000304 | MODELING MANUAL VALVE & INSTRUMENT BATCH II (MAKER CNJ) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 12 January 2026 | 31 January 2026 |  | AHMAD KHUNAIFI | 80 | JC210126 30579
66 | 20 January 2026 | A24AOP01 | UPDATE GENERAL ARRANGEMENT KSOT (MASS PRODUCT) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 8 January 2026 | 14 January 2026 |  | ARDAN |  | JC210126 30580
67 | 20 January 2026 | A24AOP01 | DESAIN SECTION TURBIN ARUS BAWAH LAUT KSOT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 15 January 2026 | 23 January 2026 |  | ARDAN |  | JC210126 30581
68 | 21 January 2026 | W304 | ANALISIS STRUKTUR SUPPORT SHAFT BRACKET DAN STERN TUBE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 12 January 2026 | 14 January 2026 |  | ADITYA PRAYOGA | 24 | JC210126 30582
69 | 21 January 2026 | W307 | EVATEK DECK MACHINERIES | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 15 January 2026 | 21 January 2026 |  | ADITYA PRAYOGA | 32 | JC210126 30583
70 | 21 January 2026 | KPI 2026 | PENYUSUNAN DRAFT CII | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 22 January 2026 | 23 January 2026 |  | ADITYA PRAYOGA | 16 | JC210126 30584
71 | 2026-01-21 | W304 | E12590.22100-R2-PID OF EXH GAS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-26 | 2026-01-30 |  | NIZAR | 40 | JC210126 30586
72 | 2026-01-23 | W000304 | Check Drawing Piping Output E1515C-R0, EP621P-R2, E621S-R2, EP651P-R2, EK651P-R2, EP112S-R3, EP131C-R3, EK131C-R3 , EP214S-R2, EK214S-R2, EP214P-R2, EK214P-R2, EP133P-R2, EK133P-R2, EP133S-R2, EK133S-R2, EP134P-R2,EK134P-R2,EP134S-R2, EK134S-R2, EP651S-R2, EK651S-R2, EP122S-R3, EK122S-R2, EP122P-R3, EK122P-R2 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-19 | 2026-01-23 | 1 | Asi Supeni | 40 | JC230126 30649
73 | 23 January 2026 | A24AOP01 | BATTERY INTEGRATION ARRANGEMET OPTION FOR VENDOR PROPOSAL (SEAT OF BATTERY, RACK MODULE BATTERY, FLOOR PLATFORM ARRANGEMENT) - MASS PRODUCT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 1 January 2026 | 9 January 2026 |  | Amam Baharullah | 56 | JC270126 30784
74 | 23 January 2026 | W311 | R0_PIPING DIAGRAM OF BILGE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 12 January 2026 | 15 January 2026 |  | Amam Baharullah | 32 | JC270126 30785
75 | 23 January 2026 | W311 | R0_PIPING DIAGRAM OF FIRE MAIN AND WASH DECK SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 16 January 2026 | 20 January 2026 |  | Amam Baharullah | 24 | JC270126 30786
76 | 23 January 2026 | W311 | R0_PIPING DIAGRAM OF FUEL OIL SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 21 January 2026 | 27 January 2026 |  | Amam Baharullah | 40 | JC270126 30787
77 | 23 January 2026 | W311 | R0_PIPING DIAGRAM OF SEA WATER COOLING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 28 January 2026 | 30 January 2026 |  | Amam Baharullah | 24 | JC270126 30788
78 | 2026-01-29 | W000308 | CREATE SISTEM KOMPARASI MATERIAL CADAMTIC VS EST. MAT_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-01 | 2026-01-02 | 1 | Krisdiyantoro | 16 | JC300126 30887
79 | 2026-01-29 | W000308 | EVATEK BY DESCRIPTION PART RCV MAKER KEYSTONE_R3 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-05 | 2026-01-09 | 1 | Krisdiyantoro | 40 | JC300126 30889
80 | 2026-01-29 | W000308 | EVATEK BY DESCRIPTION PART RCV MAKER HANLA_R3 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-12 | 2026-01-16 | 1 | Krisdiyantoro | 40 | JC300126 30890
81 | 2026-01-29 | W000306-307 | E15072-37100_LIST NAME PLATE OF VALVE_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-19 | 2026-01-23 | 1 | Krisdiyantoro | 40 | JC300126 30891
82 | 2026-01-29 | R25US1XA | E15291.22100_PIPING DIAGRAM OF BILGE & BALLAST LINES_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-26 | 2026-01-30 | 1 | Krisdiyantoro | 40
83 | 29 January 2026 | W308 | R0 - ED612P.48100 - VENT SKETCHES IN ACCOM. BLOCK 612 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 January 2026 | 5 January 2026 |  | FARIS NOVARIANSYAH | 14 | JC300126 30893
84 | 29 January 2026 | W308 | R0 - ED612S.48100 - VENT SKETCHES IN ACCOM. BLOCK 614 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 6 January 2026 | 7 January 2026 |  | FARIS NOVARIANSYAH | 14 | JC300126 30894
85 | 29 January 2026 | W308 | R0 - ED622P.48100 - VENT SKETCHES IN ACCOM. BLOCK 622 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 8 January 2026 | 9 January 2026 |  | FARIS NOVARIANSYAH | 14 | JC300126 30895
86 | 29 January 2026 | W308 | R0 - ED622S.48100 - VENT SKETCHES IN ACCOM. BLOCK 622 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 12 January 2026 | 13 January 2026 |  | FARIS NOVARIANSYAH | 14 | JC300126 30896
87 | 29 January 2026 | W308 | R0 - ED632P.48100 - VENT SKETCHES IN ACCOM. BLOCK 632 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 14 January 2026 | 15 January 2026 |  | FARIS NOVARIANSYAH | 14 | JC300126 30897
88 | 29 January 2026 | W308 | R0 - ED632S.48100 - VENT SKETCHES IN ACCOM. BLOCK 632 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 16 January 2026 | 19 January 2026 |  | FARIS NOVARIANSYAH | 14 | JC300126 30898
89 | 29 January 2026 | W308 | R0 - ED642P.48100 - VENT SKETCHES IN ACCOM. BLOCK 642 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 20 January 2026 | 21 January 2026 |  | FARIS NOVARIANSYAH | 14 | JC300126 30899
90 | 29 January 2026 | W308 | R0 - ED642S.48100 - VENT SKETCHES IN ACCOM. BLOCK 642 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 22 January 2026 | 23 January 2026 |  | FARIS NOVARIANSYAH | 14 | JC300126 30900
91 | 29 January 2026 | W308 | R0 - ED512P.48100 - VENT SKETCHES IN ACCOM. BLOCK 512 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 26 January 2026 | 27 January 2026 |  | FARIS NOVARIANSYAH | 14 | JC300126 30901
92 | 29 January 2026 | W308 | R0 - ED512S.48100 - VENT SKETCHES IN ACCOM. BLOCK 512 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 28 January 2026 | 30 January 2026 |  | FARIS NOVARIANSYAH | 14 | JC300126 30902
93 | 29 January 2026 | W308 | R0 - ED353P.48100 - VENT SKETCHES IN ACCOM BLOCK 353 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 January 2026 | 5 January 2026 |  | SATRIO | 16 | JC290126 30867
94 | 29 January 2026 | W308 | R0 - ED611S.48100 - VENT SKETCHES IN ACCOM BLOCK 611 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 6 January 2026 | 7 January 2026 |  | SATRIO | 16 | JC290126 30868
95 | 29 January 2026 | W308 | R0 - ED611P.48100 - VENT SKETCHES IN ACCOM BLOCK 611 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 8 January 2026 | 9 January 2026 |  | SATRIO | 16 | JC290126 30870
96 | 29 January 2026 | W304 | R1 - E14560.22100 - PIPING DIAGRAM OF MULTIFUNCTION RADAR COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 12 January 2026 | 16 January 2026 |  | SATRIO | 35 | JC290126 30877
97 | 29 January 2026 | W308 | R0 - ED631S.48100 - VENT SKETCHES IN ACCOM BLOCK 631 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 19 January 2026 | 20 January 2026 |  | SATRIO | 16 | JC290126 30871
98 | 29 January 2026 | W308 | R0 - ED641P.48100 - VENT SKETCHES IN ACCOM BLOCK 641 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 21 January 2026 | 23 January 2026 |  | SATRIO | 21 | JC290126 30872
99 | 29 January 2026 | W308 | R0 - ED631P.48100 - VENT SKETCHES IN ACCOM BLOCK 631 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 26 January 2026 | 28 January 2026 |  | SATRIO | 21 | JC290126 30874
100 | 29 January 2026 | W308 | R0 - ED641S.48100 - VENT SKETCHES IN ACCOM BLOCK 641 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 29 January 2026 | 31 January 2026 |  | SATRIO | 21 | JC290126 30875
105 | 29 January 2026 | A24AOP01 | REDESAIN PROPELLER KSOT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 26 January 2026 | 30 January 2026 |  | ARDAN |  | JC300126 30915
106 | 29 January 2026 | W311 | E15240.27100 - PIPE MODELING SEA WATER COOLING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-02 | 2026-01-07 |  | MIEKAIL | 40 | JC300126 30918
107 | 29 January 2026 | W311 | E15291.27100 - PIPE MODELING BILGE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-08 | 2026-01-13 |  | MIEKAIL | 32 | JC300126 30921
108 | 29 January 2026 | W311 | E15410.27100 - PIPE MODELLING FUEL OIL SERVICE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-14 | 2026-01-21 |  | MIEKAIL | 48 | JC300126 30923
109 | 29 January 2026 | W311 | E15230.27100 - PIPE MODELLING PREWETTING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-22 | 2026-01-23 |  | MIEKAIL | 16 | JC300126 30926
110 | 29 January 2026 | A24AOP01 | MACHINERY LAYOUT FOR GA KAPAL PINISI | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-26 | 2026-01-27 |  | MIEKAIL | 16 | JC300126 30929
111 | 29 January 2026 |  | SCHEMATIC DIAGRAM OF COMPRESSED AIR FOR BALLAST SYSTEM KSOT NEW GENERATION | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-28 | 2026-01-30 |  | MIEKAIL | 24 | JC300126 30942
112 | 29 January 2026 | W311 | - - INPUT SPEC. - PIPE LINE PID & MODELING CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 January 2026 | 31 January 2026 |  | AHMAD KHUNAIFI | 120 | JC300126 30931
113 | 2026-01-30 | W304 | DETAIL AND ARRANGEMENT OF SHAFT PROTECTION COVER | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-26 | 2026-01-30 |  | Aditya Prayoga | 40 | JC300126 30932
114 | 30 January 2026 | W308 | R0 - ED314P.48100 - VENT SKETCHES IN ACCOM. BLOCK 314 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 19 January 2026 | 21 January 2026 |  | RAFIKA |  | JC300126 30936
115 | 30 January 2026 | W308 | R0 - ED314S.48100 - VENT SKETCHES IN ACCOM. BLOCK 314 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 22 January 2026 | 23 January 2026 |  | RAFIKA |  | JC300126 30937
116 | 30 January 2026 | W308 | R0 - E1112P.48100 - ARRT OF VENT IN BLOCK 112 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 26 January 2026 | 28 January 2026 |  | RAFIKA |  | JC300126 30940
117 | 30 January 2026 | W308 | R0 - E1112S.48100 - ARRT OF VENT IN BLOCK 112 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 29 January 2026 | 30 January 2026 |  | RAFIKA |  | JC300126 30941
118 | 30 January 2026 | KSSR | EVATEK PROPULSION SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-05 | 2026-01-15 | 1 | Syafril | 72 | JC300126 30905
119 | 30 January 2026 | KSSR | EVATEK MAIN DG | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-19 | 2026-01-23 | 1 | Syafril | 40 | JC300126 30906
120 | 30 January 2026 | JW1-JW2 | PROPULSION ARRANGEMENT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-01-26 | 2026-01-30 | 1 | Syafril | 40 | JC300126 30907
121 | 2026-01-30 | W000304 | Check Drawing Piping Output EP112P-R3, EK112P-R2, EP613C-R1, EK613C-R1 , EP641P-R2, EK641P-R2, EP214P-R2, EP641S-R2, EK641S-R2, EP631P-R2, EK631P-R2, EK631S-R2, EP631S-R2, EK243P-R2, EP243P-R2, EP144S-R2, EK144S-R2, EP153S-R2, EK153S-R2, EP154S-R2, EK154S-R2, EP155P-R2, EK155P-R2, EP155SS-R2, EK155SS-R2, EP153P-R2, EK153P-R2, EP153S-R2, EK153S-R2, EP511P-R2, EK511P-R2, EP511S-R2, EK511S-R2, EP114P-R2, EK114P-R2, EP114S-R2, EK114S-R2, EP402C-R2, EK402C-R2, EP612P-R2, EP612P-R2, EP612S-R2, EK612S-R2. | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-01-26 | 2026-01-30 | 1 | Asi Supeni | 40 | JC300126 30904
124 | 31 January 2026 | W308 | R0 - E15142.18100 - ARR'T & DETAIL OF VENTILATOR HEAD FOR AFT & FORE PART | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 January 2026 | 14 January 2026 |  | FIRMAN | 72 | JC310126 30963
125 | 31 January 2026 | W308 | R0 - E15142.18101 - ARR'T & DETAIL OF VENTILATOR HEAD FOR ACCOMMODATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 15 January 2026 | 22 January 2026 |  | FIRMAN | 48 | JC310126 30964
126 | 31 January 2026 | W306 | - - HVAC ANALYSIS ON LCU ENGINE ROOM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 23 January 2026 | 31 January 2026 |  | FIRMAN | 48 | JC310126 30965
2026-02-01
1 | 29 January 2026 | W308 | R0 - E85100.51100 - EVALUASI TEKNIS APPROVAL DRAWING | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 02 Febuary 2026 | 28 Febuary 2026 |  | STEVAN | 40 | JC300126 30943
2 | 29 January 2026 | W304 | R0 - E85100.51100 - EVALUASI TEKNIS WORKING DRAWING | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 02 Febuary 2026 | 28 Febuary 2026 |  | STEVAN | 40 | JC300126 30946
3 | 29 January 2026 | W308 | R0 - EVALUASI TEKNIS PENAWARAN NBC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 02 Febuary 2026 | 28 Febuary 2026 |  | STEVAN | 40 | JC300126 30944
4 | 29 January 2026 | W308 | R2 - E15141.28100 - DIAGRAM OF AIR CONDITION SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 02 Febuary 2026 | 28 Febuary 2026 |  | STEVAN | 40 | JC300126 30945
5 | 31 January 2026 | W308 | - - MODELING RCV & CONTROL PANEL MAKER HANLA IMS | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-02-02 | 2026-02-05 |  | AHMAD KHUNAIFI | 32 | JC020226 30990
6 | 31 January 2026 | W304 | - - MODELING MANUAL VALVE BATCH II MAKER CNJ | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-02-06 | 2026-02-28 |  | AHMAD KHUNAIFI | 80 | JC020226 30991
7 | 2026-02-02 | W000306 | E15281.17100 Pipe Model Black Water system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-01-07 | 1 | Dimas | 52 | JC020226 31019
8 | 2026-02-02 | W000306 | E15282.17100 Pipe Model Grey Water system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-09 | 2026-02-14 | 1 | Dimas | 52 | JC020226 31020
9 | 2026-02-02 | W000306 | E13410.17100 Pipe Model SW Cooling system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-16 | 2026-02-19 | 1 | Dimas | 24 | JC020226 31021
10 | 2026-02-02 | W000306 | E13410.17100 Pipe Model FO LO Drain system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-20 | 2026-02-24 | 1 | Dimas | 35 |  | no jc sdh ditambahkan dibawah
11 | 2026-02-02 | W000306 | E12590.17100 Pipe Model Exhaust Gas system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-25 | 2026-02-28 | 1 | Dimas | 35
12 | 2026-02-02 | W000304 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-18 | 1 | Dimas | 8 | JC030226 31164 | jc utk tgl 2-18 feb 2026
13 | 2026-02-02 | W000306 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-18 | 1 | Dimas | 8 | JC030226 31165 | jc utk tgl 2-18 feb 2026
14 | 2026-02-02 | W000308 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-18 | 1 | Dimas | 8 | JC030226 31166 | jc utk tgl 2-18 feb 2026
15 | 2026-02-02 | W000307 | E1424S.17100 - Pipe Modeling & Ready System Fresh Water Potable | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-15 | 1 | Rizki R | 108 | JC020226 31110
16 | 2026-02-02 | W000307 | E1434S.17100 - Pipe Modeling & Ready System Hot Water block | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-16 | 2026-02-18 | 1 | Rizki R | 52 | JC030226 31168 | jc utk tgl 16-18 feb 2026, sisa 28 jam
17 | 2026-02-02 | W000307 | E1214S.17100 - Pipe Modeling System Hot Water block 214S & 224S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-23 | 2026-02-28 | 1 | Rizki R | 52
18 | 2026-02-02 | W000308 | E1344U.27100 - Pipe Modelling & Ready in Block 344 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-18 | 1 | Syaiful | 50 | JC020226 31120 | jc utk tgl 2-18 feb 2026, sisa 68/4
19 | 2026-02-02 | W000308 | E15056.27100 - Pipe Modelling Overboard Discharge | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-18 | 1 | Syaiful | 50 | JC020226 31121 | jc utk tgl 2-18 feb 2026, sisa 68/4
20 | 2026-02-02 | W000308 | ⁠E15161.27100 - Revisi Pipe Modelling Chilled Water System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-18 | 1 | Syaiful | 50 | JC020226 31122 | jc utk tgl 2-18 feb 2026, sisa 68/4
21 | 2026-02-02 | W000308 | Check 3D Model (fungsi,operasional, maintenance)/paparan di SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-18 | 1 | Syaiful | 18 | JC020226 31123 | jc utk tgl 2-18 feb 2026, sisa 68/4
22 | 2026-02-02 | W000307 | E1222P.17100 - Pipe Modelling Block 222P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-18 | 1 | Erly | 50 | JC020226 31116 | jc utk tgl 2-18 feb 2026, sisa 20 jam
23 | 2026-02-02 | W000307 | E1222S.17100 - Pipe Modelling Block 222S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-18 | 1 | Erly | 50 | JC020226 31117 | jc utk tgl 2-18 feb 2026, sisa 20 jam
24 | 2026-02-02 | W000307 | E1232S.17100 - Pipe Modelling Block 232S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-18 | 1 | Erly | 50 | JC020226 31118 | jc utk tgl 2-18 feb 2026, sisa 20 jam
25 | 2026-02-02 | W000307 | E1232P.17100 - Pipe Modelling Block 232P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-18 | 1 | Erly | 50 | JC020226 31119 | jc utk tgl 2-18 feb 2026, sisa 20 jam
26 | 2026-02-03 | W000306 | E15280.17100 - Pipe Modelling Inside scupper dan LCU | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-18 | 1 | Dewi | 60 | JC030226 31172 | jc utk tgl 2-18 feb 2026, sisa 72/3 jam
27 | 2026-02-03 | W000305 | E1222S.17100 - Pipe Modelling Block 222S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-18 | 1 | Dewi | 60 | JC030226 31173 | jc utk tgl 2-18 feb 2026, sisa 72/3 jam
28 | 2026-02-03 | W000305 | E1232P.17100 - Pipe Modelling Block 232P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-18 | 1 | Dewi | 60 | JC030226 31174 | jc utk tgl 2-18 feb 2026, sisa 72/3 jam
29 | 2026-02-04 | W000308 | E15240.27100 - ADD.Pipe model system SW Cooling Supply Chiller | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-18 | 1 | Yasin | 43 | JC040226 31199 | jc utk tgl 2-18 feb 2026, sisa 11 jam
30 | 2026-02-04 | W000308 | E15291.27100 - Rev&ADD Pipe Model system Bilge Dewatering | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-18 | 1 | Yasin | 43 | JC040226 31200 | jc utk tgl 2-18 feb 2026, sisa 11 jam
31 | 2026-02-04 | W000308 | E15321.27100 - ADD Pipe Model system HT.LT FW Cooling | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-18 | 1 | Yasin | 43 | JC040226 31201 | jc utk tgl 2-18 feb 2026, sisa 11 jam
32 | 2026-02-04 | W000308 | E15412.27100 - ADD Pipe model system FO Service | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-18 | 1 | Yasin | 43 | JC040226 31202 | jc utk tgl 2-18 feb 2026, sisa 11 jam
33 | 2026-02-04 | W000308 | E15931.27100 - ADD pipe model system bilge separator | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-18 | 1 | Yasin | 43 | JC040226 31203 | jc utk tgl 2-18 feb 2026, sisa 11 jam
34 | 2026-02-04 | W000304 | FINISH PLAN-E15291.22100-PID OF DEWATERING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-02 | 2026-02-06 | 1 | NIZAR | 40 | JC040226 31208
35 | 4 February 2026 | W308 | MODELING RCV & CONTROL PANEL MAKER HANLA IMS | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-02-02 | 2026-02-05 |  | AHMAD KHUNAIFI | 32 | JC050226 31224
36 | 4 February 2026 | W304 | MODELING MANUAL VALVE BATCH II MAKER CNJ | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-02-06 | 2026-02-28 |  | AHMAD KHUNAIFI | 80 | JC060226 31308 | jc utk tgl 06-18 feb 2026 sisa 20 jam | JC190226 31814 | jc utk tgl 19 - 28 feb 2026
37 | 4 February 2026 | W308 | R0 - E15142.18100 - ARR'T & DETAIL OF VENTILATOR HEAD FOR AFT & FORE PART | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 February 2026 | 14 February2026 |  | FIRMAN | 72 | JC050226 31225
38 | 4 February 2026 | W308 | R0 - E15142.18101 - ARR'T & DETAIL OF VENTILATOR HEAD FOR ACCOMMODATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 16 February 2026 | 28 February 2026 |  | FIRMAN | 48 | JC060226 31304 | jc utk tgl 16-18 feb 2026 sisa 28 jam | JC190226 31815 | jc utk tgl 19 - 28 feb 2026
39 | 4 February 2026 | W306 | HVAC ANALYSIS ON LCU ENGINE ROOM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 16 February 2026 | 28 February 2026 |  | FIRMAN | 48 | JC060226 31305 | jc utk tgl 16-18 feb 2026 sisa 28 jam | JC190226 31817 | jc utk tgl 19 - 28 feb 2026
40 | 4 February 2026 | W308 | R0 - ED212S. 48100 - VENT SKETCHES BLOCK 212 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 February 2026 | 14 February 2026 |  | IRFAN | 100 | JC050226 31226
41 | 4 February 2026 | W308 | R0 - ED312P. 48100 - VENT SKETCHES BLOCK 312 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 16 February 2026 | 28 February 2026 |  | IRFAN |  | JC050226 31232 | jc utk tgl 16-18 feb 2026 | JC190226 31818 | jc utk tgl 19 - 28 feb 2026
42 | 4 February 2026 | W308 | R0 - ED511S.48100 - VENT SKETCHES IN ACCOM BLOCK 511 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 February 2026 | 4 February 2026 |  | SATRIO | 24 | JC050226 31227
43 | 4 February 2026 | W308 | R0 - ED511P.48100 - VENT SKETCHES IN ACCOM BLOCK 511 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 5 February 2026 | 9 February 2026 |  | SATRIO | 24 | JC050226 31228
44 | 4 February 2026 | W308 | R0 - ED521P.48100 - VENT SKETCHES IN ACCOM BLOCK 521 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 10 February 2026 | 12 February 2026 |  | SATRIO | 24 | JC050226 31229
45 | 4 February 2026 | W308 | R0 - ED521S.48100 - VENT SKETCHES IN ACCOM BLOCK 521 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 13 February 2026 | 18 February 2026 |  | SATRIO | 24 | JC050226 31230
46 | 4 February 2026 | A24AOP01 | DESAIN SISTEM KEMUDI HIDROLIS (UPDATED DESIGN KSOT RND) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 February 2026 | 13 February 2026 |  | ARDAN |  | JC050226 31231
47 | 2026-02-06 | W000304 | Check Drawing Piping Output EP514C-R2, EK514C-R2, E1683C-R0, E1693C-R0, EP632P-R2, EP632S-R2, EK632S-R2, EP522P-R2, EK522P-R2, EP522S-R2, EK522S-R2, EP532P-R2, EK532P-R1, EP532S-R2, EK532S-R1, EP323C-R2, EK323C-R2, EP232S-R4, EP622P-R2, EK622P-R2, EP622S-R2, EK622S-R2, EP313C-R3, EK313C-R3, EP663S-R2, EK663S-R2, EP314C-R3, EK314C-R3, EP693C-R1, EK693C-R1, EP623C-R2, EK623C-R2, EP152C-R2, EP652P-R2, EK652P-R2, EP652S-R2, EK652S-R2, EP315S-R2, EP633C-R2, EK633C-R2, EP515C-R1, EK515C-R1. | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-02 | 2026-02-06 | 1 | Asi Supeni | 40 | JC060226 31307
48 | 9 February 2026 | W311 | R0 - E15240.22100 - PIPING DIAGRAM OF SEA WATER COOLING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2 February 2026 | 3 February 2026 |  | Amam Baharullah | 16 | JC090226 31444
49 | 9 February 2026 | W311 | R0 - E12590.22100 - PIPING DIAGRAM OF EXHAUST GAS SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 4 February 2026 | 6 February 2026 |  | Amam Baharullah | 24 | JC090226 31446
50 | 9 February 2026 | W311 | R0 - E15060.22100 - PIPING DIAGRAM OF AIR AND SOUNDING PIPE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 9 February 2026 | 10 February 2026 |  | Amam Baharullah | 16 | JC090226 31447
51 | 9 February 2026 | W311 | R0 - E25291.01100 - EST. MATERIAL FOR PIPING DIAGRAM OF BILGE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 11 February 2026 | 12 February 2026 |  | Amam Baharullah | 16 | JC090226 31448
52 | 9 February 2026 | W311 | R0 - E25210.01100 - EST. MATERIAL FOR PIPING DIAGRAM OF FIRE MAIN AND WASH DECK SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 13 February 2026 | 16 February 2026 |  | Amam Baharullah | 16 | JC090226 31449
53 | 9 February 2026 | W311 | R0 - E25410.01100 - EST. MATERIAL FOR PIPING DIAGRAM OF FUEL OIL SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 17 February 2026 | 19 February 2026 |  | Amam Baharullah | 24 | JC100226 31493 | jc utk tgl 17-18 feb 2026, sisa 8jam | JC190226 31819 | jc utk tgl 19 feb 2026
54 | 9 February 2026 | W311 | R0 - E25240.01100 - EST. MATERIAL FOR PIPING DIAGRAM OF SEA WATER COOLING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 20 February 2026 | 23 February 2026 |  | Amam Baharullah | 16 |  |  | JC190226 31820
55 | 9 February 2026 | W311 | R0 - E22590.01100 - EST. MATERIAL FOR PIPING DIAGRAM OF EXHAUST GAS SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 24 February 2026 | 25 February 2026 |  | Amam Baharullah | 16 |  |  | JC190226 31821
56 | 9 February 2026 | W311 | R0 - E25060.01100 - EST. MATERIAL FOR PIPING DIAGRAM OF SOUNDING AND AIR PIPE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 26 February 2026 | 27 February 2026 |  | Amam Baharullah | 16 |  |  | JC190226 31822
57 | 2026-02-10 | W000304 | FINISH PLAN-E15513.22100-PID OF LOW AIR PRESSURE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-09 | 2026-02-18 | 1 | NIZAR | 56 | JC100226 31477
58 | 2026-02-13 | W000304 | Check Drawing Piping Output EP521P-R2, EK521P-R2, EP521S-R2, EK521S-R2, EP523P-R2, EK523P-R2, EP523S-R2, EK523S-R2, EP533P-R1, EK533P-R1, EP533S-R1, EK533S-R1, EP642P-R2, EK642P-R2, EP642S-R2, EK642S-R2, EP531P-R2, EK531P-R2, EP531S-R2, EK531S-R2, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-09 | 2026-02-13 | 1 | Asi Supeni | 40 | JC130226 31609
59 | 2026-02-13 | W000304 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-19 | 2026-02-28 | 1 | Dimas | 8 | JC180226 31688
60 | 2026-02-13 | W000306 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-19 | 2026-02-28 | 1 | Dimas | 8 | JC180226 31692
61 | 2026-02-13 | W000308 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-19 | 2026-02-28 | 1 | Dimas | 8 | JC180226 31693
62 | 2026-02-13 | W000306 | E13410.17100 Pipe Model FO LO Drain system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-20 | 2026-02-24 | 1 | Dimas | 35 | JC180226 31704
63 | 2026-02-13 | W000306 | E12590.17100 Pipe Model Exhaust Gas system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-25 | 2026-02-28 | 1 | Dimas | 35 | JC180226 31705
64 | 2026-02-13 | W000307 | E1434S.17100 - Pipe Modeling & Ready System Hot Water block | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-19 | 2026-02-21 | 1 | Rizki R | 28 | JC180226 31706
65 | 2026-02-13 | W000307 | E1214S.17100 - Pipe Modeling System Hot Water block 214S & 224S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-23 | 2026-02-28 | 1 | Rizki R | 52 | JC180226 31708
66 | 2026-02-13 | W000308 | E1344U.27100 - Pipe Modelling & Ready in Block 344 (P/S) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-19 | 2026-02-28 | 1 | Syaiful | 20 | JC180226 31695
67 | 2026-02-13 | W000308 | E15056.27100 - Pipe Modelling Overboard Discharge | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-19 | 2026-02-28 | 1 | Syaiful | 20 | JC180226 31696
68 | 2026-02-13 | W000308 | ⁠E15161.27100 - Revisi Pipe Modelling Chilled Water System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-19 | 2026-02-28 | 1 | Syaiful | 20 | JC180226 31697
69 | 2026-02-13 | W000308 | Check 3D Model (fungsi,operasional, maintenance)/paparan di SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-19 | 2026-02-28 | 1 | Syaiful | 8 | JC180226 31698
70 | 2026-02-13 | W000307 | E1222P.17100 - Pipe Modelling Block 222P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-19 | 2026-02-28 | 1 | Erly | 20 | JC180226 31710
71 | 2026-02-13 | W000307 | E1222S.17100 - Pipe Modelling Block 222S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-19 | 2026-02-28 | 1 | Erly | 20 | JC180226 31711
72 | 2026-02-13 | W000307 | E1232S.17100 - Pipe Modelling Block 232S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-19 | 2026-02-28 | 1 | Erly | 20 | JC180226 31713
73 | 2026-02-13 | W000307 | E1232P.17100 - Pipe Modelling Block 232P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-19 | 2026-02-28 | 1 | Erly | 20 | JC180226 31714
74 | 2026-02-13 | W000308 | E15240.27100 - ADD.Pipe model system SW Cooling Supply Chiller | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-19 | 2026-02-28 | 1 | Yasin | 11 | JC180226 31699
75 | 2026-02-13 | W000308 | E15291.27100 - Rev&ADD Pipe Model system Bilge Dewatering | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-19 | 2026-02-28 | 1 | Yasin | 11 | JC180226 31700
76 | 2026-02-13 | W000308 | E15321.27100 - ADD Pipe Model system HT.LT FW Cooling | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-19 | 2026-02-28 | 1 | Yasin | 11 | JC180226 31701
77 | 2026-02-13 | W000308 | E15412.27100 - ADD Pipe model system FO Service | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-19 | 2026-02-28 | 1 | Yasin | 11 | JC180226 31702
78 | 2026-02-13 | W000308 | E15931.27100 - ADD pipe model system bilge separator | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-19 | 2026-02-28 | 1 | Yasin | 11 | JC180226 31703
79 | 2026-02-19 | W000304 | FINISH PLAN-E15512.22100-PID OF MEDIUM AIR PRESSURE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-19 | 2026-02-26 | 1 | NIZAR | 48 | JC190226 31842
80 | 23 February 2026 | W000308 | R0 - ED312S. 48100 - VENT SKETCHES BLOCK 312 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 18 February 2026 | 28 February 2026 |  | IRFAN | 100 | JC230226 31924 | jc utk tgl 18 feb 2026, sisa 92jam | JC230226 31926 | jc utk tgl 19 - 28 feb 2026
81 | 23 February 2026 | W000304 | FP - E15240.22100 - PID OF SEA WATER COOLING SYSTEM (FINISH PLAN) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 23 February 2026 | 28 February 2026 |  | AHMAD KHUNAIFI | 40 | JC230226 31927
82 | 23 February 2026 | W000306 | UPDATE SPEC. & MODEL CADMATIC ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-02-16 | 28 February 2026 |  | AHMAD KHUNAIFI | 48 | JC230226 31940 | jc utk tgl 16-18 feb 2026 sisa 28 jam | JC230226 31931 | jc utk tgl 19 - 28 feb 2026
83 | 23 February 2026 | W000308 | R0 - E17520.33101 - ARRANGEMENT & DETAIL OF GUIDE TORPEDO DETECTION SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-02-16 | 27 February 2026 |  | ARDAN |  | JC230226 31941 | jc utk tgl 16-18 feb 2026 | JC230226 31942 | jc utk tgl 19 - 28 feb 2026
81 | 23 February 2026 | W000308 | E15280.22100_PID OF INSIDE SCUPPER & DRAINAGE_R3 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-02 | 2026-02-02 |  | Diar | 8 | JC230226 32045
85 | 23 February 2026 | W000304 | E15282.22100_FINISHN PLAN_PIPING DIAGRAM OF GREY WATER SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-04 | 2026-02-04 |  | Diar | 8 | JC230226 32046
86 | 23 February 2026 | W000304 | E15331.22101_FINISH PLAN_PIPING DIAGRAM OF HOT WATER SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-05 | 2026-02-05 |  | Diar | 8 | JC230226 32049
87 | 23 February 2026 | W000304 | E15330.22100_FINISH PLAN_PIPING DIAGRAM OF FRESH WATER SANITARY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-06 | 2026-02-06 |  | Diar | 8 | JC230226 32051
88 | 23 February 2026 | W000306 | E15330.22100_PID OF FRESH WATER SANITARY SERVICE_R3 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-09 | 2026-02-10 |  | Diar | 16 | JC230226 32053
89 | 23 February 2026 | W000304 | E25330.01100_A0_ESTIMATED MATERIAL FOR FRESH WATER SANITARY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-11 | 2026-02-12 |  | Diar | 16 | JC230226 32052
90 | 23 February 2026 | W000304 | E15281.22100_FINISH PLAN_PIPING DIAGRAM OF SEWAGE SYSTEM IN ACCOMMODATION | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-13 | 2026-02-20 |  | Diar | 32 | JC230226 32054 | jc utk tgl 13-18 feb 2026 | JC230226 32055 | jc utk tgl 19 - 20 feb 2026
91 | 23 February 2026 | W000308 | EVATEK VALVE BATCH 2-R0-VENDOR WONKWANG | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-23 | 2026-02-27 |  | Diar | 40 | JC230226 32056
92 | 25 February 2026 | W000306 | E15330.22100_PID OF FRESH WATER SANITARY SERVICE_R3 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-03 | 2026-02-03 |  | Diar | 8 | JC250226 32107
93 | 25 February 2026 | W000306 | E95000.92101_R0_YARD PLAN WEIGHT CALCULATION (KB03) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-01 | 2026-02-28 |  | Aditya Prayoga | 24 | JC250226 32109 | jc utk tgl 1-18 feb 2026, sisa 8 jam | JC250226 32118 | jc utk tgl 19 - 28 feb 2026
94 | 25 February 2026 | W000304 | SEA WATER FLOW ANALYSIS DUE TO SHAFT COVER INSTALLATION | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-01 | 2026-02-28 |  | Aditya Prayoga | 40 | JC250226 32110 | jc utk tgl 1-18 feb 2026, sisa 8 jam | JC250226 32119 | jc utk tgl 19 - 28 feb 2026
95 | 25 February 2026 | W000304 | E12421.32100_R0_SHAFT COVER | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-01 | 2026-02-28 |  | Aditya Prayoga | 16 | JC250226 32111 | jc utk tgl 1-18 feb 2026, sisa 8 jam | JC250226 32120 | jc utk tgl 19 - 28 feb 2026
96 | 25 February 2026 | W000304 | E22421.01100_R0_EST. QTY. MAT. OF SHAFT COVER | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-01 | 2026-02-28 |  | Aditya Prayoga | 8 | JC250226 32112 | jc utk tgl 1-18 feb 2026, sisa 4 jam | JC250226 32121 | jc utk tgl 19 - 28 feb 2026
97 | 25 February 2026 | W000306 | E22330.01100_R0_EST MAT OF CHOCKING RESIN FOR MAIN ENGINE, GEARBOX AND SHAFT BEARING_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-01 | 2026-02-28 |  | Aditya Prayoga | 8 | JC250226 32113 | jc utk tgl 1-18 feb 2026, sisa 4 jam | JC250226 32122 | jc utk tgl 19 - 28 feb 2026
98 | 25 February 2026 | W000306 | E35723.50100_W000306-307_ATO HELI HANGAR HOIST, DOCK WELL HOIST AND PROVISION TELECOPIC CRANES | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-01 | 2026-02-28 |  | Aditya Prayoga | 8 | JC250226 32114 | jc utk tgl 1-18 feb 2026, sisa 4 jam | JC250226 32123 | jc utk tgl 19 - 28 feb 2026
99 | 25 February 2026 | W000308 | UPDATE-YARD PLAN WEIGHT CALCULATION (KB03) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-01 | 2026-02-28 |  | Aditya Prayoga | 8 | JC250226 32116 | jc utk tgl 1-18 feb 2026, sisa 4 jam | JC250226 32124 | jc utk tgl 19 - 28 feb 2026
100 | 25 February 2026 | W000306 | E15620.63100_R0_RUDDER STOCK & FITTINGS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-01 | 2026-02-28 |  | Aditya Prayoga | 8 | JC250226 32115 | jc utk tgl 1-18 feb 2026, sisa 4 jam | JC250226 32125 | jc utk tgl 19 - 28 feb 2026
101 | 25 February 2026 | W000308 | EVATEK DECK MACHINERIES | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-01 | 2026-02-28 |  | Aditya Prayoga | 24 | JC250226 32117 | jc utk tgl 1-18 feb 2026, sisa 8 jam | JC250226 32127 | jc utk tgl 19 - 28 feb 2026
102 | 25 February 2026 | W00308 | R0 - E1124P.18100 - ARR'T OF VENT IN ACCOM. BLOCK 124 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-02-02 | 2026-02-03 |  | FARIS NOVARIANSYAH | 14 | JC250226 32146
103 | 25 February 2026 | W00308 | R0 - E1124S.18100 - ARR'T OF VENT IN ACCOM. BLOCK 124 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-02-04 | 2026-02-05 |  | FARIS NOVARIANSYAH | 14 | JC250226 32147
104 | 25 February 2026 | W00308 | R0 - E1134P.18100 - ARR'T OF VENT IN ACCOM. BLOCK 134 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-02-06 | 2026-02-09 |  | FARIS NOVARIANSYAH | 14 | JC250226 32148
105 | 25 February 2026 | W00308 | R0 - E1134S.18100 - ARR'T OF VENT IN ACCOM. BLOCK 134 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-02-10 | 2026-02-11 |  | FARIS NOVARIANSYAH | 14 | JC250226 32149
106 | 25 February 2026 | W00308 | R0 - E1314P.18100 - ARR'T OF VENT IN ACCOM. BLOCK 314 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-02-12 | 2026-02-13 |  | FARIS NOVARIANSYAH | 14 | JC250226 32150
107 | 25 February 2026 | W00308 | R0 - E1314S.18100 - ARR'T OF VENT IN ACCOM. BLOCK 314 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-02-16 | 2026-02-17 |  | FARIS NOVARIANSYAH | 14 | JC250226 32151
108 | 25 February 2026 | W00308 | R0 - E1324P.18100 - ARR'T OF VENT IN ACCOM. BLOCK 324 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-02-18 | 2026-02-19 |  | FARIS NOVARIANSYAH | 14 | JC250226 32154 | jc utk tgl 18 feb 2026, | JC250226 32155 | jc utk tgl 19 feb 2026
109 | 25 February 2026 | W00308 | R0 - E1324S.18100 - ARR'T OF VENT IN ACCOM. BLOCK 324 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-02-20 | 2026-02-23 |  | FARIS NOVARIANSYAH | 14 | JC250226 32156
110 | 25 February 2026 | W00308 | R0 - E1334P.18100 - ARR'T OF VENT IN ACCOM. BLOCK 334 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-02-24 | 2026-02-25 |  | FARIS NOVARIANSYAH | 14 | JC250226 32157
111 | 25 February 2026 | W00308 | R0 - E1334S.18100 - ARR'T OF VENT IN ACCOM. BLOCK 334 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-02-26 | 2026-02-27 |  | FARIS NOVARIANSYAH | 14 | JC250226 32158
112 | 25 February 2026 | W00308 | R0 - ED324S.48100 - VENT SKETCHES IN ACCOM. BLOCK 324 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 February 2026 | 4 February 2026 |  | RAFIKA |  | JC250226 32160
113 | 25 February 2026 | W00308 | R0 - ED324P.48100 - VENT SKETCHES IN ACCOM. BLOCK 324 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 5 February 2026 | 6 February 2026 |  | RAFIKA |  | JC250226 32161
114 | 25 February 2026 | W00308 | R0 - ED334S.48100 - VENT SKETCHES IN ACCOM. BLOCK 334 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 9 February 2026 | 11 February 2026 |  | RAFIKA |  | JC250226 32162
115 | 25 February 2026 | W00308 | R0 - ED334P.48100 - VENT SKETCHES IN ACCOM. BLOCK 334 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 12 February 2026 | 13 February 2026 |  | RAFIKA |  | JC250226 32163
116 | 25 February 2026 | W00308 | R2 - E15292.22100 - PIPING DIAGRAM OF PNEUMATIC VALVES REMOTE CONTROL FOR BALLAST AND DOCKWELL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 18 February 2026 | 20 February 2026 |  | RAFIKA |  | JC250226 32164 | jc utk tgl 18 feb 2026, | JC250226 32165 | jc utk tgl 19 - 20feb 2026
117 | 25 February 2026 | W00308 | R0 - E1323P.18100 - ARR'T OF VENT IN ACCOM. BLOCK 323 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 23 February 2026 | 25 February 2026 |  | RAFIKA |  | JC250226 32167
118 | 25 February 2026 | W00308 | R0 - E1323S18100 - ARR'T OF VENT IN ACCOM. BLOCK 323 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 26 February 2026 | 27 February 2026 |  | RAFIKA |  | JC250226 32166
119 | 25 February 2026 | W308 | R0 - ED531S.48100 - VENT SKETCHES IN ACCOM BLOCK 531 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 19 February 2026 | 20 February 2026 |  | SATRIO | 15 | JC260226 32171
120 | 25 February 2026 | W308 | R0 - ED531P.48100 - VENT SKETCHES IN ACCOM BLOCK 531 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 23 February 2026 | 24 February 2026 |  | SATRIO | 15 | JC260226 32172
121 | 25 February 2026 | W308 | R0 - E1444S.18100 - ARR'T OF VENT IN ACCOM. BLOCK 444 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 25 February 2026 | 25 February 2026 |  | SATRIO | 8 | JC260226 32173
122 | 25 February 2026 | W308 | R0 - E1234S.18100 - ARR'T OF VENT IN ACCOM. BLOCK 234 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 26 February 2026 | 27 February 2026 |  | SATRIO | 15 | JC260226 32174
123 | 2026-02-26 | W00308 | EVATEK BY DESCRIPTION PART RCV MAKER WONKWANG_FINAL | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-02 | 2026-02-06 |  | Krisdiyantoro | 40 | JC260226 32192
124 | 2026-02-26 | W00308 | EVATEK BY DESCRIPTION PART RCV MAKER KEYSTONE_FINAL | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-09 | 2026-02-13 |  | Krisdiyantoro | 40 | JC260226 32193
125 | 2026-02-26 | W00308 | EVATEK BY DESCRIPTION PART RCV MAKER HANLA_FINAL | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-16 | 2026-02-20 |  | Krisdiyantoro | 40 | JC260226 32194 | jc utk tgl 16-18 feb 2026 | JC260226 32195 | jc utk tgl 19 - 20feb 2026
126 | 2026-02-26 | W00308 | CREATE SISTEM KOMPARASI MATERIAL CADAMTIC VS EST. MAT_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-23 | 2026-02-27 |  | Krisdiyantoro | 40 | JC260226 32196
127 | 2026-02-27 | W000304 | Check Drawing Piping Output EP541P-R2, EK541P-R2, EP541S-R2, EK541S-R2, EP512P-R1, EK512P-R1, EP512S-R2, EK512S-R2, EP124S-R3, EK124S-R3, EP114S-R3, EK114S-R3, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-02-23 | 2026-02-27 | 1 | Asi Supeni | 40 | JC270226 32200
128 | 2026-02-27 | R22FPBXA | E15410.22100_PID OF FUEL OIL SYSTEM_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-02 | 2026-02-06 |  | Miekail | 40 | JC270226 32204
129 | 2026-02-27 | W311 | PIPE READY ALL SYSTEM FOR PRODUCTION DRAWING_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-09 | 2026-02-20 |  | Miekail | 80 | JC270226 32202 | jc utk tgl 9-18 feb 2026 | JC270226 32203 | jc utk tgl 19 - 20feb 2026
130 | 2026-02-27 | E250N002 | E15291.2710_PIPE MODELLING & READY BILGE SYSTEM_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-23 | 2026-02-25 |  | Miekail | 40 | JC270226 32218
131 | 2026-02-27 | E250N002 | E15292.27100_PIPE MODELLING & READY BALLAST SYSTEM_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-26 | 2026-02-27 |  | Miekail | 40 | JC270226 32219
132 | 2026-02-27 | W301 – KSSR 18M | EVATEK MAIN DG | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-02 | 2026-02-13 |  | Syafril | 80 | JC270226 32211
133 | 2026-02-27 | W301 – KSSR 18M | ATO MAIN DG | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-18 | 2026-02-20 |  | Syafril | 24 | JC270226 32212 | jc utk tgl 18 feb 2026 | JC270226 32213 | jc utk tgl 19 - 20feb 2026
134 | 2026-02-27 | W301 – KSSR 18M | SHAFTING ARRANGEMENT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-02-23 | 2026-02-27 |  | Syafril | 40 | JC270226 32216
| 27 February 2026 | W311 | HVAC ANALYSIS OF ENGINE ROOM USING CFD | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 15 February 2026 | 18 February 2026 |  | FIRMAN | 32 | JC020326 32276
| 27 February 2026 | W311 | 3D MODEL ARRANGEMENT OF VENTILATOR FOR HVAC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 19 February 2026 | 24 February 2026 |  | FIRMAN | 32 | JC020326 32278
| 27 February 2026 | W311 | R0 - E15131.18100 - ARR'T & DETAIL OF VENTILATOR HEAD FOR ENGINE ROOM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 25 February 2026 | 27 February 2026 |  | FIRMAN | 18 | JC020326 32279
2026-03-26
1 | 25 February 2026 | W308 | R0 - E1234P.18100 - ARR'T OF VENT IN ACCOM. BLOCK 234 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 March 2026 | 3 March 2026 |  | SATRIO | 15 | JC020326 32366
2 | 25 February 2026 | W308 | R0 - E1114P.18100 - ARR'T OF VENT IN ACCOM. BLOCK 114 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 4 March 2026 | 5 March 2026 |  | SATRIO | 15 | JC020326 32368
3 | 26 February 2026 | W308 | R0 - E1114S.18100 - ARR'T OF VENT IN ACCOM. BLOCK 114 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 6 March 2026 | 9 March 2026 |  | SATRIO | 15 | JC020326 32369
4 | 27 February 2026 | W311 | R0 - E15131.18100 - ARR'T & DETAIL OF VENTILATOR HEAD FOR ENGINE ROOM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 March 2026 | 4 March 2026 |  | FIRMAN | 18 | JC020326 32280
5 | 27 February 2026 | W311 | R0 - E15131.18101 - ARR'T & DETAIL OF VENTILATOR HEAD FOR GENERATOR ROOM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 5 March 2026 | 11 March 2026 |  | FIRMAN | 40 | JC020326 32281
6 | 27 February 2026 | W308 | EVALUASI TEKNIS PENAWARAN NBC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 March 2026 | 31 March 2026 |  | STEVAN | 40 | JC020326 32372 | jc utk 2-19 Maret 2026 | JC260326 33185 | utk tgl 25-31 maret 2026
7 | 27 February 2026 | W308 | EVALUASI TEKNIS APPROVAL DRAWING CHILLER SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 March 2026 | 7 March 2026 |  | STEVAN | 40 | JC020326 32374
8 | 27 February 2026 | W308 | EVALUASI TEKNIS APPROVAL DRAWING PROVISION REFRIGERATION SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 9 March 2026 | 14 March 2026 |  | STEVAN | 40 | JC020326 32377
9 | 27 February 2026 | W308 | EVALUASI TEKNIS APPROVAL DRAWING MECHANICAL FANS SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 16 March 2026 | 21 March 2026 |  | STEVAN | 40 | JC020326 32378
10 | 27 February 2026 | W308 | EVALUASI TEKNIS APPROVAL DRAWING AC PACKAGED & FAN COIL UNIT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 23 March 2026 | 31 March 2026 |  | STEVAN | 50 | JC020326 32384
11 | 27 February 2026 | W308 | CHECK OUTPUT DRAWING ARRANGEMENT & VENT SKETCHES | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 March 2026 | 31 March 2026 |  | STEVAN | 40 | JC020326 32385 | jc utk 2-19 Maret 2026 | JC260326 33174 | utk tgl 25-31 maret 2026
12 | 2026-03-02 | W000304 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-02 | 2026-03-18 | 1 | Dimas | 8 | JC020326 32403
13 | 2026-03-02 | W000306 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-02 | 2026-03-18 | 1 | Dimas | 8 | JC020326 32404
14 | 2026-03-02 | W000308 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-02 | 2026-03-18 | 1 | Dimas | 8 | JC020326 32405
15 | 2026-03-02 | W000306 | E12590.17100 Pipe Model Exhaust Gas system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-02 | 2026-03-07 | 1 | Dimas | 52 | JC020326 32417
16 | 2026-03-02 | W000306 | E15281.17100 Pipe Model Black Water system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-09 | 2026-03-14 | 1 | Dimas | 52 | JC020326 32418
17 | 2026-03-02 | W000306 | E13410.17100 Pipe Model FO LO Drain system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-16 | 2026-03-18 | 1 | Dimas | 24 | JC020326 32419
18 | 2026-03-02 | W000308 | E15161.27100 - Revisi Pipe Modelling Chilled Water System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-02 | 2026-03-18 | 1 | Syaiful | 52 | JC020326 32414
19 | 2026-03-02 | W000308 | E15330.27100 - Revisi Pipe Modelling FW Sanitary Service System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-02 | 2026-03-18 | 1 | Syaiful | 52 | JC020326 32415
20 | 2026-03-02 | W000308 | Check 3D Model (fungsi,operasional, maintenance)/paparan di SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-02 | 2026-03-18 | 1 | Syaiful | 8 | JC020326 32416
21 | 2026-03-02 | W000307 | E15421.17100 - Pipe Modeling System FO Service For Helicopter Block 434S, 214S & 224S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-02 | 2026-03-18 | 1 | Rizki R | 60 | JC030326 32430
22 | 2026-03-02 | W000307 | E15421.17100 - Pipe Modeling System FO Service For Helicopter Block 213S , 223S & 213P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-02 | 2026-03-18 | 1 | Rizki R | 60 | JC030326 32432
23 | 2026-03-03 | W000308 | E1211U.27100 - ADD. Pipe model block 211U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-02 | 2026-03-18 | 1 | Yasin | 32 | JC030326 32433
24 | 2026-03-03 | W000308 | E1221U.27100 - ADD. Pipe model block 221U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-02 | 2026-03-18 | 1 | Yasin | 32 | JC030326 32434
25 | 2026-03-03 | W000308 | E1451U.27100 - ADD. Pipe Model block 451U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-02 | 2026-03-18 | 1 | Yasin | 32 | JC030326 32435
26 | 2026-03-03 | W000308 | Check 3D model (fungsi, operasional, maintenance) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-02 | 2026-03-18 | 1 | Yasin | 8 | JC030326 32436
27 | 2026-03-03 | W000305 | E15410.27100 - Revisi Pipe Modelling FO Purifying System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-02 | 2026-03-18 | 1 | Erly | 32 | JC030326 32438
28 | 2026-03-03 | W000305 | E13410.27100 - Revisi Pipe Modelling FO LO Oily Water Drain System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-02 | 2026-03-18 | 1 | Erly | 32 | JC030326 32439
29 | 2026-03-03 | W000308 | E15432.27100 - Pipe Modelling LO Service | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-02 | 2026-03-18 | 1 | Erly | 32 | JC030326 32437
30 | 2026-03-06 | W000306 JW1 | Check Drawing Piping Output E11631-R0, EP5292-R0, EP5210-R0, EP5330-R0, EP5291-R0, EP5060-R0, EP5280-R0, EP5240-R0, EP2590-R0, EP5410-R0, EP5261-R0, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-02 | 2026-03-06 | 1 | Asi Supeni | 40 | JC060326 32553
31 | 2026-03-13 | W000308 | Check Modelling Piping E15291-22100, E15292-22101, Check Isometic EP342C-42100, EK342C-42100 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-09 | 2026-03-13 | 1 | Asi Supeni | 40 | JC130326 32841
32 | 2026-03-13 | W000306 | EVATEK PIPE & FITTING TAHAP 2 VENDOR SJMI-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-02 | 2026-03-06 | 1 | NIZAR | 40 | JC160326 32879
33 | 2026-03-13 | W000305 | EVATEK PIPE & FITTING TAHAP 1 VENDOR SJMI-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-09 | 2026-03-20 | 1 | NIZAR | 40 | JC160326 32882
34 | 2026-03-13 | W000304 | FINISH PLAN-E15512.22100-PID OF MEDIUM AIR PRESSURE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-16 | 2026-03-20 | 1 | NIZAR | 40 | JC160326 32883
35 | 2026-03-16 | A24AOP01 | E10500.00003_GENERAL ARRANGEMENT (MASS PRODUCT)_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-02 | 2026-03-03 | 1 | Amam | 16 | JC170326 33028
36 | 2026-03-16 | A24AOP01 | E11002.03113_RUDDER & HYDROPLANE CONSTRUCTION (DESIGN MODIFICATION AND REFINEMENT)_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-04 | 2026-03-06 | 1 | Amam | 24 | JC170326 33029
37 | 2026-03-16 | A24AOP01 | E25620.63102_MATERIAL LIST FOR HYDRAULIC STEERING SYSTEM CONFIGURATION (UPDATED DESIGN)_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-09 | 2026-03-10 | 1 | Amam | 16 | JC170326 33030
38 | 2026-03-16 | W000304 | E15412.22100_PIPING DIAGRAM OF FUEL OIL SYSTEM_FINISH PLAN | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-11 | 2026-03-12 | 1 | Amam | 16 | JC170326 33031
39 | 2026-03-16 | W000304 | E15410.22100_PIPING DIAGRAM OF FUEL OIL PURIFIYING_FINISH PLAN | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-13 | 2026-03-13 | 1 | Amam | 8 | JC170326 33032
40 | 2026-03-16 | W000304 | E15411.22100_PIPING DIAGRAM OF FUEL OIL TRANSFER & OVERFLOW_FINISH PLAN | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-16 | 2026-03-16 | 1 | Amam | 8 | JC170326 33033
41 | 2026-03-16 | W000304 | E15515.22100_PIPING DIAGRAM OF CONTROL AIR FOR EMERGENCY SHUT OFF VALVE_FINISH PLAN | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-17 | 2026-03-17 | 1 | Amam | 8 | JC170326 33034
42 | 2026-03-16 | A24AOP01 | E15620.22100_HYDRAULIC STEERING SYSTEM CONFIGURATION (UPDATED DESIGN)_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-25 | 2026-03-27 | 1 | Amam | 24 | JC250326 33089
43 | 2026-03-16 | W000308 | E25330.01100_EST. MATERIAL FOR PIPING DIAGRAM OF FRESH WATER SANITARY SERVICE_R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-30 | 2026-03-31 | 1 | Amam | 16 | JC250326 33103
44 | 17 March 2026 | W308 | RO - ED342C.48100 - VENT SKETCHES BLOCK 342 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 March 2026 | 11 March 2026 |  | IRFAN | 60 | JC170326 33035
45 | 17 March 2026 | W308 | ISOMETRIC DRAWING MODULE 2 BLOCK 232,231,222 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 March 2026 | 5 March 2026 |  | FARIS NOVARIANSYAH | 28 | JC170326 33036
46 | 17 March 2026 | W308 | ISOMETRIC DRAWING MODULE 1 BLOCK 111,121,122,112 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 6 March 2026 | 10 March 2026 |  | FARIS NOVARIANSYAH | 28 | JC170326 33037
47 | 17 March 2026 | W308 | R0 - E1344P.18100 - ARRT OF VENT IN BLOCK 344 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 11 March 2026 | 13 March 2026 |  | FARIS NOVARIANSYAH | 21 | JC170326 33038
48 | 17 March 2026 | W308 | R0 - E1344S.18100 - ARRT OF VENT IN BLOCK 344 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 16 March 2026 | 17 March 2026 |  | FARIS NOVARIANSYAH | 14 | JC260326 33184
49 | 17 March 2026 | W308 | ISOMETRIC DRAWING MODULE 3 BLOCK 322,342,341 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 25 March 2026 | 27 March 2026 |  | FARIS NOVARIANSYAH | 21 | JC250326 33065
50 | 17 March 2026 | W308 | ISOMETRIC DRAWING MODULE 6 BLOCK 621,622 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 30 March 2026 | 31 March 2026 |  | FARIS NOVARIANSYAH | 14 | JC250326 33066
51 | 17 March 2026 | W000306 | UPDATE SPEC. & MODEL CADMATIC ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 March 2026 | 31 March 2026 |  | AHMAD KHUNAIFI | 96 | JC170326 33040 | dipakai 50 jam | JC250326 33145 | utk tgl 25-31 maret 2026
52 | 17 March 2026 | W000308 | UPDATE SPEC. & MODEL CADMATIC ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 March 2026 | 31 March 2026 |  | AHMAD KHUNAIFI | 96 | JC170326 33041 | dipakai 50 jam | JC250326 33146 | utk tgl 25-31 maret 2026
53 | 17 March 2026 | W000304 | UPDATE SPEC. & MODEL CADMATIC ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 March 2026 | 31 March 2026 |  | AHMAD KHUNAIFI | 32 | JC170326 33042 | dipakai 50 jam | JC250326 33147 | utk tgl 25-31 maret 2026
54 | 17 March 2026 | A24AOP01 | R0 - E25620.01102 - MATERIAL LIST FOR HYDRAULIC STEERING SYSTEM CONFIGURATION (UPDATED DESIGN) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 March 2026 | 5 March 2026 |  | ARDAN |  | JC170326 33043
55 | 17 March 2026 | A24AOP01 | R0 - E27500.01101 - MATERIAL LIST FOR TORPEDO PIRANHA CASING | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 6 March 2026 | 10 March 2026 |  | ARDAN |  | JC170326 33044
56 | 17 March 2026 | A24AOP01 | R0 - E17500.33101 - TORPEDO PIRANHA - V3 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 11 March 2026 | 13 March 2026 |  | ARDAN |  | JC170326 33045
57 | 17 March 2026 | A24AOP01 | R0 - E15620.21103 - HYDRAULIC STEERING SYSTEM CONFIGURATION (MODIFICATION & UPDATED DESIGN) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 15 March 2026 | 17 March 2026 |  | ARDAN |  | JC170326 33046
58 | 2026-03-17 | W000304 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-25 | 2026-03-31 | 1 | Dimas | 5 | JC250326 33127
59 | 2026-03-17 | W000306 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-25 | 2026-03-31 | 1 | Dimas | 5 | JC250326 33128
60 | 2026-03-17 | W000308 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-25 | 2026-03-31 | 1 | Dimas | 5 | JC250326 33129
61 | 2026-03-17 | W000306 | E12590.17100 Pipe Model Exhaust Gas system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-25 | 2026-03-31 | 1 | Dimas | 20 | JC250326 33130
62 | 2026-03-17 | W000306 | E15281.17100 Pipe Model Black Water system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-25 | 2026-03-31 | 1 | Dimas | 20 | JC250326 33131
63 | 2026-03-17 | W000306 | E13410.17100 Pipe Model FO LO Drain system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-25 | 2026-03-31 | 1 | Dimas | 20 | JC250326 33132
64 | 2026-03-17 | W000308 | E15161.27100 - Revisi Pipe Modelling Chilled Water System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-25 | 2026-03-31 | 1 | Syaiful | 40 | JC250326 33133
65 | 2026-03-17 | W000308 | E15330.27100 - Revisi Pipe Modelling FW Sanitary Service System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-25 | 2026-03-31 | 1 | Syaiful | 40 | JC250326 33134
66 | 2026-03-17 | W000308 | Check 3D Model (fungsi,operasional, maintenance)/paparan di SVG PMT Almaryah | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-25 | 2026-03-31 | 1 | Syaiful | 5 | JC250326 33135
67 | 2026-03-17 | W000307 | E15421.17100 - Pipe Modeling System FO Service For Helicopter Block 434S, 214S & 224S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-25 | 2026-03-31 | 1 | Rizki R | 30 | JC250326 33141
68 | 2026-03-17 | W000307 | E15421.17100 - Pipe Modeling System FO Service For Helicopter Block 213S , 223S & 213P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-25 | 2026-03-31 | 1 | Rizki R | 30 | JC250326 33142
69 | 2026-03-17 | W000308 | E1211U.27100 - ADD. Pipe model block 211U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-25 | 2026-03-31 | 1 | Yasin | 25 | JC250326 33136
70 | 2026-03-17 | W000308 | E1221U.27100 - ADD. Pipe model block 221U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-25 | 2026-03-31 | 1 | Yasin | 25 | JC250326 33137
71 | 2026-03-17 | W000308 | E1451U.27100 - ADD. Pipe Model block 451U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-25 | 2026-03-31 | 1 | Yasin | 25 | JC250326 33138
72 | 2026-03-17 | W000308 | Check 3D model (fungsi, operasional, maintenance) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-25 | 2026-03-31 | 1 | Yasin | 5 | JC250326 33139
73 | 2026-03-17 | W000305 | E15410.27100 - Revisi Pipe Modelling FO Purifying System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-25 | 2026-03-31 | 1 | Erly | 15 | JC250326 33143
74 | 2026-03-17 | W000305 | E13410.27100 - Revisi Pipe Modelling FO LO Oily Water Drain System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-25 | 2026-03-31 | 1 | Erly | 15 | JC250326 33144
75 | 2026-03-17 | W000308 | E15432.27100 - Pipe Modelling LO Service | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-25 | 2026-03-31 | 1 | Erly | 20 | JC250326 33140
76 | 2026-03-17 | W000308 | Check Piping Output EP332U-42100-R2, EK332U-42100-R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-16 | 2026-03-17 | 1 | Asi Supeni | 16 | JC170326 33049
77 | 26 March 2026 | A24AOP01 | PEMBUATAN PRESENTASI PROGRESS DESAIN TORPEDO PIRANHA | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 25 March 2026 | 25 March 2026 |  | ARDAN | 4 | JC260326 33201
78 | 26 March 2026 | A24AOP01 | DESAIN GENERATOR LISTRIK UNTUK KSOT MASS PRODUCT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 25 March 2026 | 31 March 2026 |  | ARDAN |  | JC260326 33202
79 | 26 March 2026 | W000308 | R0 - ED342C.48100 - VENT SKETCHES BLOCK 342 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 26 March 2026 | 31 March 2026 |  | IRFAN | 40 | JC260326 33203
80 | 2026-03-26 | W000305 | EVATEK PIPE & FITTING TAHAP 1 VENDOR SJMI-R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-23 | 2026-03-31 | 1 | NIZAR | 56 | JC260326 33213
81 | 26 March 2026 | W000308 | R0 - ED412P.48100 - VENT SKETCHES BLOCK 412 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 9 March 2026 | 11 March 2026 |  | IRFAN | 24 | JC260326 33214
82 | 2026-03-27 | W000308 | EVATEK VALVE BATCH 2-R0-VENDOR WONKWANG | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-02 | 2026-03-27 | 1 | Diar | 120 | JC270326 33245 | JC270326 33246
83 | 2026-03-27 | W000304 | E15281.22100_FINISH PLAN_PIPING DIAGRAM OF SEWAGE SYSTEM IN ACCOMMODATION | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-30 | 2026-03-31 | 1 | Diar | 16 | JC270326 33247
84 | 2026-03-27 | W000308 | PAPARAN HELICOPTER TRAVERSING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-02 | 2026-03-02 | 1 | Aditya Prayoga | 8 | JC270326 33262
85 | 2026-03-27 | W000304 | E12591.33100_R1_ARRANGEMENT AND DETAIL OF FUNNEL LOUVRE FOR IRSS SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-03 | 2026-03-03 | 1 | Aditya Prayoga | 8 | JC270326 33263
86 | 2026-03-27 | W000308 | CHECKING ILS (IRIDIUM) DOCUMENT_SHIP HANDBOOK | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-04 | 2026-03-05 | 1 | Aditya Prayoga | 16 | JC270326 33264
87 | 2026-03-27 | W000306 | E15620.63100_R2_RUDDER STOCK & FITTINGS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-06 | 2026-03-06 | 1 | Aditya Prayoga | 8 | JC270326 33265
88 | 2026-03-27 | W000308 | EVATEK DECK CRANES - ATHIRA | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-09 | 2026-03-09 | 1 | Aditya Prayoga | 8 | JC270326 33267
89 | 2026-03-27 | W000306 | E12000.90100_R0_RECOMMENDED LUBRICATING OIL BRANDS (MACHINERY PARTS) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-10 | 2026-03-11 | 1 | Aditya Prayoga | 16 | JC270326 33266
90 | 2026-03-27 | W000308 | E12000.90100_R0_RECOMMENDED LUBRICATING OIL BRANDS (MACHINERY PARTS) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-12 | 2026-03-13 | 1 | Aditya Prayoga | 16 | JC270326 33268
91 | 2026-03-27 | W000308 | VEHICLE HANDLING SCENARIO USING SNATCH WINCH | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-16 | 2026-03-17 | 1 | Aditya Prayoga | 16 | JC270326 33269
92 | 2026-03-27 | W000308 | VEHICLE HANDLING SCENARIO USING SNATCH WINCH | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-25 | 2026-03-31 | 1 | Aditya Prayoga | 32 | JC270326 33270
93 | 30 March 2026 | W000308 | R0 - ED412P.48100 - VENT SKETCHES BLOCK 412 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 26 March 2026 | 31 March 2026 |  | IRFAN | 80 | JC300326 33399
94 | 30 March 2026 | W000308 | R0 - ED412P.48100 - VENT SKETCHES BLOCK 412 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 9 March 2026 | 11 March 2026 |  | IRFAN | 24 | JC300326 33400
95 | 30 March 2026 | W000304 | CHECK OUTPUT REVISI DRAWING ARRANGEMENT OF VENTILATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-01 | 2026-04-30 |  | STEVAN | 40 | JC010426 33480
96 | 30 March 2026 | W000308 | CHECK OUTPUT DRAWING ARRANGEMENT & VENT SKETCHES | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-01 | 2026-04-30 |  | STEVAN | 40 | JC010426 33481
97 | 30 March 2026 | W000308 | R0 - E15141.28100 - REV. DIAGRAM OF AIR CONDITIONING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-06 | 2026-04-18 |  | STEVAN | 80 | JC010426 33484
98 | 30 March 2026 | W000308 | EVALUASI TEKNIS APPROVAL DRAWING AC PACKAGED & FAN COIL UNIT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-20 | 2026-04-25 |  | STEVAN | 40 | JC010426 33486
99 | 30 March 2026 | W000308 | EVALUASI TEKNIS APPROVAL DRAWING AIR HANDLING UNIT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-27 | 2026-04-30 |  | STEVAN | 40 | JC010426 33487
100 | 30 March 2026 | W000308 | R0 - E1613C.18100 - ARR'T OF VENT IN BLOCK 613 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 10 March 2026 | 11 March 2026 |  | SATRIO | 15 | JC300326 33401
101 | 30 March 2026 | W000308 | R0 - E1623C.18100 - ARR'T OF VENT IN BLOCK 623 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 12 March 2026 | 13 March 2026 |  | SATRIO | 15 | JC300326 33402
102 | 30 March 2026 | W000308 | R0 - E1633C.18100 - ARR'T OF VENT IN BLOCK 633 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 16 March 2026 | 17 March 2026 |  | SATRIO | 15 | JC300326 33403
103 | 30 March 2026 | W000308 | R0 - E1624P.18100 - ARR'T OF VENT IN BLOCK 624 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 25 March 2026 | 26 March 2026 |  | SATRIO | 15 | JC300326 33405
104 | 30 March 2026 | W000308 | R0 - E1624S.18100 - ARR'T OF VENT IN BLOCK 624 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 27 March 2026 | 30 March 2026 |  | SATRIO | 15 | JC300326 33406
105 | 30 March 2026 | W000308 | R0 - E1634C.18100 - ARR'T OF VENT IN BLOCK 634 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 31 March 2026 | 2026-04-01 |  | SATRIO | 15 | JC300326 33407
106 | 30 March 2026 | W000308 | R0 - E1525C.18100 - ARR'T OF VENT IN BLOCK 525 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-02 | 2026-04-03 |  | SATRIO | 15 | JC010426 33491
107 | 30 March 2026 | W000308 | R0 - E1454P.18100 - ARR'T OF VENT IN BLOCK 454 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-06 | 2026-04-07 |  | SATRIO | 15 | JC010426 33492
108 | 30 March 2026 | W000308 | R0 - E1454S.18100 - ARR'T OF VENT IN BLOCK 454 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-08 | 2026-04-09 |  | SATRIO | 15 | JC010426 33493
109 | 30 March 2026 | W000306-307 | R4 - E15241.22100 - PIPING DIAGRAM OF SEA WATER COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-10 | 2026-04-14 |  | SATRIO | 24 | JC010426 33494
110 | 30 March 2026 | W000306-307 | R3 - E15931.22100 - PIPING DIAGRAM OF SLUDGE & OILY BILGE SEPARATOR SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-15 | 2026-04-17 |  | SATRIO | 24 | JC010426 33495
111 | 30 March 2026 | W000308 | R0 - E1521S.18100 - ARR'T OF VENT IN ACCOM. BLOCK 521 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 March 2026 | 4 March 2026 |  | RAFIKA |  | JC300326 33410
112 | 30 March 2026 | W000308 | R2 - E95551.01100 - TECHNICAL REPORT OF FIRE EXTINGUISHING SYSTEM - R2 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 12 March 2026 | 17 March 2026 |  | FIRMAN | 32 | JC300326 33416
113 | 30 March 2026 | W000308 | R1 - E15131.18100 - ARR'T & DETAIL OF VENTILATOR HEAD FOR ENGINE ROOM - R1 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 23 March 2026 | 2026-03-27 |  | FIRMAN | 40 | JC300326 33417
114 | 30 March 2026 | W000308 | R0 - E1521P.18100 - ARR'T OF VENT IN ACCOM. BLOCK 521 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 5 March 2026 | 11 March 2026 |  | RAFIKA |  | JC300326 33411
115 | 30 March 2026 | W000308 | R0 - E1522S.18100 - ARR'T OF VENT IN ACCOM. BLOCK 522 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 12 March 2026 | 17 March 2026 |  | RAFIKA |  | JC300326 33412
116 | 30 March 2026 | W000308 | R0 - E1522P.18100 - ARR'T OF VENT IN ACCOM. BLOCK 522 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 25 March 2026 | 27 March 2026 |  | RAFIKA |  | JC300326 33414
117 | 30 March 2026 | W000308 | R0 - E1343S.18100 - ARR'T OF VENT IN ACCOM. BLOCK 343 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 30 March 2026 | 31 March 2026 |  | RAFIKA |  | JC300326 33415
118 | 30 March 2026 | A26AOP01 | GENERAL ARRANGEMENT (PRELIMINARY KSOT NEW GENERATION)-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-02 | 2026-03-06 | 1 | MIEKAIL | 40 | JC310326 33438
119 | 30 March 2026 | W311 | W311 E12300.75100 MAIN EQUIPMENT LIST (MACHINERY PART)-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-03 | 2026-03-10 | 1 | MIEKAIL | 16 | JC310326 33426
120 | 30 March 2026 | W308 | W308 E15423.22100 PID OF PETROL TRANSFER SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-11 | 2026-03-13 | 1 | MIEKAIL | 24 | JC310326 33431
121 | 30 March 2026 | W311 | W311 - HYDRAULIC CALCULATION AND EVALUTION FOR MISSILE LAUNCHER-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-16 | 2026-03-20 | 1 | MIEKAIL | 40 | JC310326 33427
122 | 30 March 2026 | W311 | W311 E15410.27100 PIPE MODELLING FUEL OIL SYSTEM-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-23 | 2026-03-24 | 1 | MIEKAIL | 16 | JC310326 33428
123 | 30 March 2026 | W311 | W311 E15292.27100 PIPE MODELLING EXHAUST GAS SYSTEM-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-25 | 2026-03-27 | 1 | MIEKAIL | 24 | JC310326 33429
124 | 30 March 2026 | W311 | W311 - 3D MODELLING OF BRACKET MOUNTING FOR MAIN ENGINE AND GEAR BOX INSTALLATION-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-30 | 2026-03-31 | 1 | MIEKAIL | 16 | JC310326 33430
125 | 2026-03-31 | W000308 | KOMPARASI MATERIAL PIPA (EST. MAT VS. CADMATIC) SISTEM EXH. GAS, AIR PIPE AND SOUNDING_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-02 | 2026-03-06 | 1 | Kridiyantoro | 40 | JC310326 33440
126 | 2026-03-31 | W000308 | KOMPARASI MATERIAL PIPA (EST. MAT VS. CADMATIC) SISTEM FIRE, SEA WATER AND FRESH WATER_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-09 | 2026-03-13 | 1 | Kridiyantoro | 40 | JC310326 33441
127 | 2026-03-31 | W000308 | KOMPARASI MATERIAL PIPA (EST. MAT VS. CADMATIC) SISTEM FO, LO, AND COMPRESS AIR_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-16 | 2026-03-31 | 1 | Kridiyantoro | 56 | JC310326 33442 | 16-17 MARET 26 | JC310326 33443 | 25-31 MARET 26
128 | 2026-03-31 | W301 – KSSR 18M | SHAFTING ARRANGEMENT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-02 | 2026-03-13 | 1 | Syafril | 72 | JC310326 33444
129 | 2026-03-31 | W301 – KSSR 18M | MAIN ENGINE (M) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-16 | 2026-03-31 | 1 | Syafril | 40 | JC310326 33445 | 16-17 MARET 26 | JC310326 33446 | 25-31 MARET 26
130 | 2026-03-31 | W000308 | Check Piping Output EP432C-R2, EK432C-R2, EP222U-R1, EK222U-R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-03-30 | 2026-03-31 | 1 | Asi Supeni | 16 | JC310326 33450
131 | 31 March 2026 | W000308 | R1 - E15131.18100 - ARR'T & DETAIL OF VENTILATOR HEAD FOR ENGINE ROOM - R1 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 30 March 2026 | 31 March 2026 |  | FIRMAN | 16 | JC310326 33465
132 | 2026-04-01 | W000308 | EVATEK VALVE BATCH 2-R0-VENDOR WONKWANG | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-09 | 2026-03-09 | 1 | Diar | 3 | JC010426 33544
133 | 2026-04-01 | W000304 | E15281.22100_FINISH PLAN_PIPING DIAGRAM OF SEWAGE SYSTEM IN ACCOMMODATION | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-03-16 | 2026-03-16 | 1 | Diar | 3 | JC010426 33545
| 2026-04-01 | W000308 | R2 - E95550.01100 - TECHNICAL REPORT OF FIRE EXTINGUISHING SYSTEM-R2 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 4 March 2026 | 4 March 2026 |  | FIRMAN | 3 | JC010426 33526
| 2026-04-01 | W000308 | R0 - E1224S.18100 - ARR'T OF VENT IN BLOCK 224 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 4 March 2026 | 4 March 2026 |  | SATRIO | 3 | JC010426 33527
| 2026-04-01 | W000308 | R0 - E1454P.18100 - ARR'T OF VENT IN BLOCK 454 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 6 March 2026 | 6 March 2026 |  | SATRIO | 3 | JC010426 33528
| 2026-04-01 | W000308 | R0 - E1454S.18100 - ARR'T OF VENT IN BLOCK 454 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 9 March 2026 | 9 March 2026 |  | SATRIO | 3 | JC010426 33529
| 2026-04-01 | W000308 | R1 - E15131.18100 - ARR'T & DETAIL DRAWING OF VENTILATOR HEAD FOR ENGINE ROOM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 10 March 2026 | 10 March 2026 |  | FIRMAN | 3 | JC010426 33530
| 2026-04-01 | W000308 | R0 - E1634C.18100 - ARR'T OF VENT IN BLOCK 634 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 10 March 2026 | 10 March 2026 |  | SATRIO | 3 | JC010426 33531
| 2026-04-01 | W000308 | R2 - E95550.01100 - TECHNICAL REPORT OF FIRE EXTINGUISHING SYSTEM-R2 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 14 March 2026 | 24 March 2026 |  | FIRMAN | 30 | JC010426 33532
| 2026-04-01 | W000308 | R0 - E1633C.18100 - ARR'T OF VENT IN BLOCK 633 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 14 March 2026 | 14 March 2026 |  | SATRIO | 6 | JC010426 33533
| 2026-04-01 | W000308 | R0 - E1623C.18100 - ARR'T OF VENT IN BLOCK 623 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 18 March 2026 | 18 March 2026 |  | SATRIO | 6 | JC010426 33534
| 2026-04-01 | W000306-307 | R4 - E15241.22100 - PIPING DIAGRAM OF SEA WATER COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 28 March 2026 | 28 March 2026 |  | SATRIO | 6 | JC010426 33535
| 2026-04-01 | W000308 | R0 - E15142.18101 - ARR'T & DETAIL OF VENTILATOR HEAD FOR ACCOMMODATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 30 March 2026 | 30 March 2026 |  | FIRMAN | 3 | JC010426 33536
| 2026-04-01 | R22FPBXA | R0 - E15240.22100 - R22FPBXA | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 17 March 2026 | 17 March 2026 |  | MIEKAIL | 3 | JC010426 33543
| 2026-04-01 | W000311 | R0 - E15240.27100 - PIPE MODELLING SW COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 18 March 2026 | 18 March 2026 |  | MIEKAIL | 8 | JC010426 33537
| 2026-04-01 | W000311 | R1 - E12590.27100 - PIPE MODELLING EXHAUST GAS SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 14 March 2026 | 14 March 2026 |  | MIEKAIL | 8 | JC010426 33538
| 2026-04-01 | W000308 | SCHEMATIC OF PETROL TRANSFER FOR VEHICLE SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 5 March 2026 | 5 March 2026 |  | MIEKAIL | 3 | JC010426 33540
| 2026-04-01 | W000311 | CALCULATION OF HYDRAULIC SYSTEM FOR MISSILE LAUNCHER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 3 March 2026 | 3 March 2026 |  | MIEKAIL | 3 | JC010426 33539
| 2026-04-01 | W000308 | R0 - ED412S.48100 - VENT SKETCHES BLOCK 412 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 March 2026 | 31 March 2026 |  | IRFAN | 40 | JC010426 33541 | 1-20 maret | JC010426 33542 | 25 - 31 maret
| 2026-04-01 | W000308 | R0 - E1532S.18100 - ARR'T OF VENT IN BLOCK 532 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 23 March 2026 | 24 March 2026 |  | RAFIKA | 16 | JC010426 33546
| 2026-04-01 | W000308 | R0 - E1532S.18100 - ARR'T OF VENT IN BLOCK 532 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 23 March 2026 | 24 March 2026
2026-04-26
1 | 2026-04-01 |  | ENGINE PROPELLER MATCHING PINISHI | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-01 | 2026-04-03 |  | ARDAN |  | JC020426 33623
2 | 2026-04-02 | W000307 | E15241.17100 Pipe Model SW Cooling system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-01 | 2026-04-04 | 1 | Dimas | 30 | JC020426 33589
3 | 2026-04-02 | W000307 | E15281.17100 Pipe Model Black Water system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-05 | 2026-04-11 | 1 | Dimas | 46 | JC020426 33590
4 | 2026-04-02 | W000307 | E15282.17100 Pipe Model Grey Water system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-12 | 2026-04-18 | 1 | Dimas | 46 | JC020426 33594
5 | 2026-04-02 | W000307 | E15161.17100 Pipe Model Chilled Water system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-19 | 2026-04-25 | 1 | Dimas | 46 | JC020426 33595
6 | 2026-04-02 | W000307 | E15931.17100 Pipe Model Sludge and Oily Bilge system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-26 | 2026-04-30 | 1 | Dimas | 36 | JC020426 33596
7 | 2026-04-02 | W000304 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-01 | 2026-04-30 | 1 | Dimas | 8 | JC020426 33597
8 | 2026-04-02 | W000306 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-01 | 2026-04-30 | 1 | Dimas | 8 | JC020426 33599
9 | 2026-04-02 | W000308 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-01 | 2026-04-30 | 1 | Dimas | 8 | JC020426 33600
10 | 2026-04-02 | W000305 | E15610.27100 - Revisi Pipe Modelling Hydraulic Of Steering Gear System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-01 | 2026-04-30 | 1 | Erly | 46 | JC020426 33604
11 | 2026-04-02 | W000308 | E15432.27100 - Pipe Modelling LO Service | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-01 | 2026-04-30 | 1 | Erly | 46 | JC020426 33601
12 | 2026-04-02 | W000308 | E15312.27100 - Pipe Modelling FW Production | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-01 | 2026-04-30 | 1 | Erly | 46 | JC020426 33602
13 | 2026-04-02 | W000308 | E15431.27100 - Pipe Modelling LO Filling and Transfer | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-01 | 2026-04-30 | 1 | Erly | 46 | JC020426 33603
14 | 2026-04-02 | W000308 | E15161.27100 - Revisi Pipe Modelling & Ready Chilled Water System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-01 | 2026-04-30 | 1 | Syaiful | 52 | JC020426 33605
15 | 2026-04-02 | W000308 | E15412.27100 - Pipe Modelling & Ready FO Service System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-01 | 2026-04-30 | 1 | Syaiful | 52 | JC020426 33606
16 | 2026-04-02 | W000308 | E15330.27100 - Revisi Pipe Modelling & Ready FW Sanitary Service System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-01 | 2026-04-30 | 1 | Syaiful | 52 | JC020426 33607
17 | 2026-04-02 | W000308 | Check 3D Model (fungsi,operasional, maintenance) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-01 | 2026-04-30 | 1 | Syaiful | 8 | JC020426 33608
18 | 2026-04-02 | W000307 | E15551.17100 - Pipe Modeling System Foam Fire Extingushing Line (Hull) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-01 | 2026-04-12 | 1 | Rizki R | 68 | JC060426 33654
19 | 2026-04-02 | W000307 | E15162.17100 - Pipe Modeling System Refrigeration Provision Store | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-13 | 2026-04-26 | 1 | Rizki R | 104 | JC060426 33655
20 | 2026-04-02 | W000307 | E15513.17100 - Pipe Modeling System Low Air Pressure | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-27 | 2026-04-30 | 1 | Rizki R | 38 | JC060426 33656
21 | 2026-04-02 | W000308 | E15412.27100 - ADD. pipe Model FO. Service Supply DG 1, DG 2, DG 3, DG 4, DG 5, ME 1, ME 2 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-01 | 2026-04-30 | 1 | Yasin | 46 | JC060426 33657
22 | 2026-04-02 | W000308 | E1222U.27100 - ADD pipe model block 222U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-01 | 2026-04-30 | 1 | Yasin | 46 | JC060426 33658
23 | 2026-04-02 | W000308 | E1111U.27100 - ADD pipe model block 111U | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-01 | 2026-04-30 | 1 | Yasin | 46 | JC060426 33659
24 | 2026-04-02 | W000308 | E15282.27100 - ADD pipe model Grey water in Engine room | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-01 | 2026-04-30 | 1 | Yasin | 46 | JC060426 33660
25 | 2026-04-08 | W000304 | R1 - E15142.33200 - REVISI MODELLING OF STRUCTURAL DUCT & MIST ELIMINATOR BOX | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-01 | 2026-04-04 | 1 | STEVAN | 20 | JC080426 33788
26 | 2026-04-08 | A26AOP01 | R0 - E12300.75100 - EQUIPMENT LIST | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-01 | 2026-04-02 | 1 | ARDAN |  | JC080426 33789
27 | 2026-04-08 |  | R0 - E12300.75100 - EQUIPMENT LIST PINISHI 50 METER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-03 | 2026-04-09 | 1 | ARDAN |  | JC080426 33790
28 | 2026-04-08 |  | PAPARAN TERKAIT ANEP 77 UNTUK KEMHAN | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-10 | 2026-04-13 | 1 | ARDAN |  | JC080426 33791
29 | 2026-04-10 | W000308 | Check Piping Output EP312U-R1, EK312U-R1, EP212U-R1, EK212U-R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-01 | 2026-04-02 | 1 | Asi Supeni | 16 | JC100426 33900
30 | 2026-04-10 | W000308 | Check Piping Output EP132U-R1, EK132U-R1, EP231U-R1, EK231U-R1, EP222U-R2, EK222U-R2, EP232U-R1, EK232U-R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-06 | 2026-04-10 | 1 | Asi Supeni | 40 | JC100426 33901
31 | 2026-04-13 | W000305 | EVATEK PIPE & FITTING TAHAP 1 VENDOR ELDIYA-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-01 | 2026-04-07 | 1 | NIZAR | 40 | JC140426 34015
32 | 2026-04-13 | W000306 | EVATEK PIPE & FITTING TAHAP 3 VENDOR ELDIYA-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-08 | 2026-04-14 | 1 | NIZAR | 40 | JC140426 34016
33 | 2026-04-13 | W000306 | CREAT PURCHASING LIST OF VALVE BATCH 2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-01 | 2026-04-17 | 1 | NIZAR | 40 | JC140426 34017
34 | 2026-04-14 | W000304 | SORT MATERIAL BASED ON 3D MODEL | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-01 | 2026-04-06 | 1 | Diar | 32 | JC140426 34018
35 | 2026-04-14 | W000304 | E25281.01100_R4_EST. MAT. FOR PIPING DIAGRAM OF SEWAGE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-07 | 2026-04-07 | 1 | Diar | 8 | JC140426 34019
36 | 2026-04-14 | W000304 | E25282.01100_A0_ESTIMATED MATERIAL FOR GREY WATER | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-08 | 2026-04-08 | 1 | Diar | 8 | JC140426 34020
37 | 2026-04-14 | W000308 | EVATEK VALVE BATCH 2-R0-VENDOR WONKWANG | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-08 | 2026-04-09 | 1 | Diar | 6 | JC140426 34022
38 | 2026-04-14 | W000304 | E15281.22100_FINISH PLAN_PIPING DIAGRAM OF SEWAGE SYSTEM IN ACCOMMODATION | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-09 | 2026-04-09 | 1 | Diar | 8 | JC140426 34021
39 | 2026-04-14 | W000308 | SORT VALVE SPECIFICATION BASED ON PDM BATCH 2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-10 | 2026-04-17 | 1 | Diar | 48 | JC140426 34023
40 |  | W000311 | UPDATE SPEC. & MODEL CADMATIC ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-01 | 2026-04-30 | 1 | AHMAD KHUNAIFI | 32 | JC210426 34254
41 |  | W000308 | UPDATE SPEC. & MODEL CADMATIC ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-01 | 2026-04-30 | 1 | AHMAD KHUNAIFI | 80 | JC210426 34255
42 |  | W000306 | UPDATE SPEC. & MODEL CADMATIC ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-01 | 2026-04-30 | 1 | AHMAD KHUNAIFI | 80 | JC210426 34256
43 |  | W000304 | UPDATE SPEC. & MODEL CADMATIC ALL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-01 | 2026-04-30 | 1 | AHMAD KHUNAIFI | 40 | JC210426 34257
44 |  | W000308 | E1634C.18100 - ARR'T OF VENT IN BLOCK 634 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-01 | 2026-04-01 | 1 | SATRIO | 8 | JC210426 34258
44 |  | W000304 | E15261.34200 - ROSE PLATE FOR DECK SCUPPER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-20 | 2026-04-22 | 1 | SATRIO | 30 | JC210426 34259
44 |  | W000304 | E14511.22100 - PIPING DIAGRAM OF SURVEILLANCE RADAR COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-23 | 2026-04-27 | 1 | SATRIO | 30 | JC210426 34260
44 |  |  | CALCULATION OF HVAC SYSTEM FOR ASDP ROPAX 1100 LANE METER (PRELIMINARY) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-13 | 2026-04-17 | 1 | STEVAN | 40 | JC210426 34261
44 |  | W000308 | ED513C.48100 - VENT SKETCHES BLOCK 513 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-01 | 2026-04-10 | 1 | IRFAN | 40 | JC210426 34262
44 |  | W000308 | ED523P.48100 - VENT SKETCHES BLOCK 523 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-14 | 2026-04-22 | 1 | IRFAN | 40 | JC210426 34263
44 |  | W000308 | ED523S.48100 - VENT SKETCHES BLOCK 523 (S) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-23 | 2026-04-30 | 1 | IRFAN | 40 | JC210426 34264
45 | 2026-04-17 | W000308 | Check Piping Output EP112U-R1, EK112U-R1, EP232U-R1, EK232U-R1, EP111U-R1, EK111U-R1, EP211U-R2, EK211U-R2 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-13 | 2026-04-17 | 1 | Asi Supeni | 40 | JC170426 34096
46 | 2026-04-17 | W000308 | R2 - E15292.22100 - PIPING DIAGRAM OF PNEUMATIC VALVES REMOTE CONTROL FOR BALLAST AND DOCKWELL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-01 | 2026-04-08 | 1 | RAFIKA |  | JC200426 34135
47 | 2026-04-17 | W000308 | R0 - PIPING DIAGRAM OF SURVEILANCE RADAR COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-09 | 2026-04-14 | 1 | RAFIKA |  | JC200426 34154
48 | 2026-04-17 | W000308 | R0 - PIPING DIAGRAM OF SONAR COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-15 | 2026-04-22 | 1 | RAFIKA |  | JC200426 34155
49 | 2026-04-17 | W000308 | R0 - PIPING DIAGRAM OF IRST COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-23 | 2026-04-28 | 1 | RAFIKA |  | JC200426 34157
50 | 2026-04-17 | W000308 | R0 - PIPING DIAGRAM OF MAIN CALIBER GUN 76MM COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-29 | 2026-04-30 | 1 | RAFIKA |  | JC200426 34158
51 | 2026-04-17 | W000308 | R0 - E15142.18101 - ARR'T & DETAIL OF VENTILATOR HEAD FOR ACCOMMODATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-01 | 2026-04-10 | 1 | FIRMAN |  | JC200426 34159
52 | 2026-04-17 | W000311 | 3D MODELLING AIR CONDITIONING DUCT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-13 | 2026-04-23 | 1 | FIRMAN |  | JC200426 34163
53 | 2026-04-17 | W000308 | R0 - E25142.18100 - EST. MAT. OF VENTILATOR HEAD FOR AFT & FORE PART | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-24 | 2026-04-28 | 1 | FIRMAN |  | JC200426 34161
54 | 2026-04-17 | W000308 | R0 - E25142.18101 - EST. MAT. OF VENTILATOR HEAD FOR ACCOMMODATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-29 | 2026-04-30 | 1 | FIRMAN |  | JC200426 34162
55 | 2026-04-17 | A26AOP01 | GENERAL ARRANGEMENT KSOT MASS PRODUCT TIPE SURVEILLANCE | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-13 | 2026-04-24 | 1 | ARDAN |  | JC200426 34164
56 | 2026-04-24 | W000306 | ARRGEMENT BALLAST SYSTEM AND WATER DOCKWELL | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-01 | 2026-04-03 | 1 | FARIS NOVARIANSYAH | 21 | JC240426 34355
57 | 2026-04-24 | W000306 | R0 - E1531P/S.12100 - ARRAGEMENT BLOCK 531 P & S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-06 | 2026-04-07 | 1 | FARIS NOVARIANSYAH | 14 | JC240426 34356
58 | 2026-04-24 | W000306 | R0 - E1633P/S.12100 - ARRAGEMENT BLOCK 633 P & S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-08 | 2026-04-09 | 1 | FARIS NOVARIANSYAH | 14 | JC240426 34357
59 | 2026-04-24 | W000306 | R0 - E1523P/S.12100 - ARRAGEMENT BLOCK 523 P & S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-10 | 2026-04-13 | 1 | FARIS NOVARIANSYAH | 14 | JC240426 34358
60 | 2026-04-24 | W000306 | R0 - E1112P/S.12100 - ARRAGEMENT BLOCK 112 P & S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-14 | 2026-04-15 | 1 | FARIS NOVARIANSYAH | 14 | JC240426 34360
61 | 2026-04-24 | W000306 | R0 - E1123P/S.12100 - ARRAGEMENT BLOCK 123 P & S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-16 | 2026-04-17 | 1 | FARIS NOVARIANSYAH | 14 | JC240426 34361
62 | 2026-04-24 | W000306 | MEMBUAT GDL PUMP SW FOR DECK MACHINERY | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-20 | 2026-04-21 | 1 | FARIS NOVARIANSYAH | 14 | JC240426 34363
63 | 2026-04-24 | W000306 | R0 - PIPING MODEL - READY PIPING SYSTEM 5330-5331 WATER SANITARY | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-22 | 2026-04-24 | 1 | FARIS NOVARIANSYAH | 21 | JC240426 34367
64 | 2026-04-24 | W000306 | R0 - PIPING MODEL - READY PIPING SYSTEM 5241 SEA WATER COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-27 | 2026-04-28 | 1 | FARIS NOVARIANSYAH | 21 | JC240426 34369
65 | 2026-04-24 | W000306 | R0 - PIPING MODEL - READY PIPING SYSTEM 5421 FUEL OIL SERVICE FOR HELICOPTER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-29 | 2026-04-30 | 1 | FARIS NOVARIANSYAH | 21 | JC240426 34370
66 | 2026-04-24 | A26AOP01 | DESAIN & ANALISIS TURBIN GENERATOR DENGAN DEFLEKTOR | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-27 | 2026-04-30 |  | ARDAN |  | JC240426 34372
67 | 2026-04-24 | W000308 | Check Piping Modelling & Output E15411-22100-R1, E15161-22100-R1, EP221U-R1, EK221U-R1, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-20 | 2026-04-24 | 1 | Asi Supeni | 40 | JC240426 34373
68 | 2026-04-25 | Kapal Pinisi Makassar | PID OF BILGE,BALLAST & FIRE WASH DECK SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-15 | 2026-04-30 | 1 | NIZAR | 104 | JC270426 34450
69 | 2026-04-25 | W305 | CREATE PURCHASING LIST VALVE BATCH 1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-24 | 2026-04-28 | 1 | NIZAR | 30 | JC270426 34452
70 | 2026-04-27 | W308 | E25330.01100-R2-EST. MATERIAL FOR PIPING DIAGRAM OF FRESH WATER SANITARY SERVICE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-01 | 2026-04-02 | 1 | AMAM | 16 | JC270426 34453
71 | 2026-04-27 | W308 | E25331.01100-R2-EST. MATERIAL FOR PIPING DIAGRAM OF HOT WATER SANITARY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-06 | 2026-04-09 | 1 | AMAM | 32 | JC270426 34454
72 | 2026-04-27 | A24AOP01 | E25620.63102-R1-MATERIAL LIST FOR HYDRAULIC STEERING SYSTEM CONFIGURATION (UPDATED DESIGN) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-10 | 2026-04-13 | 1 | AMAM | 16 | JC300426 34615
73 | 2026-04-27 | A24AOP01 | E27500.01101-R0-MATERIAL LIST FOR TORPEDO PIRANHA CASING | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-14 | 2026-04-15 | 1 | AMAM | 16 | JC270426 34486
74 | 2026-04-27 | W304-305 | E25412.01100-R5-EST. MATERIAL FOR PIPING DIAGRAM OF FO. SERVICE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-16 | 2026-04-16 | 1 | AMAM | 8 | JC270426 34488
75 | 2026-04-27 | W304-305 | E25411.01100-R3-EST. MATERIAL FOR PIPING DIAGRAM OF FO. TRANSFER & OVERFLOW | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-17 | 2026-04-17 | 1 | AMAM | 8 | JC300426 34616
76 | 2026-04-27 | W306JW1-W307JW2 | E15330.22100-R1-PIPING DIAGRAM OF FRESH WATER SERVICE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-20 | 2026-04-20 | 1 | AMAM | 8 | JC270426 34492
77 | 2026-04-27 | W306JW1-W307JW2 | E15280.22100-R1-PIPING DIAGRAM OF SEWAGE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-21 | 2026-04-21 | 1 | AMAM | 8 | JC270426 34493
78 | 2026-04-27 | W306JW1-W307JW2 | E15292.22100-R1-PIPING DIAGRAM OF BALLAST SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-22 | 2026-04-23 | 1 | AMAM | 8 | JC270426 34495
79 | 2026-04-27 | W306JW1-W307JW2 | E15261.22100-R1-PIPING DIAGRAM OF DECK SCUPPER | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-23 | 2026-04-23 | 1 | AMAM | 16 | JC270426 34496
80 | 2026-04-27 | W306JW1-W307JW2 | E15291.22100-R1-PIPING DIAGRAM OF BILGE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-27 | 2026-04-27 | 1 | AMAM | 8 | JC270426 34499
81 | 2026-04-27 | W306JW1-W307JW2 | E15410.22100-R1-PIPING DIAGRAM OF FUEL OIL SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-28 | 2026-04-29 | 1 | AMAM | 16 | JC270426 34500
82 | 2026-04-27 | W306JW1-W307JW2 | E15240.22100-R2-PIPING DIAGRAM OF SEA WATER COOLING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-30 | 2026-04-30 | 1 | AMAM | 8 | JC270426 34502
83 | 2026-04-28 | W301 – KSSR 18M | MAIN ENGINE (M) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-01 | 2026-04-02 | 1 | Syafril | 16 | JC280426 34533
84 | 2026-04-28 | R22FPBXA | Preliminary Design Review KRI Tipe FPB | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-06 | 2026-04-30 | 1 | Syafril | 152 | JC280426 34532
85 | 2026-04-29 | W000304 | E15000.01100_PRINCIPAL PARTICULAR MACHINERY PART _R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-27 | 2026-04-30 | 1 | Diar | 32 | JC290426 34553
86 | 2026-04-29 | W000306 | E12300.75100_R3_MAIN EQUIPMENT LIST (MACHINERY PART) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-01 | 2026-04-30 | 1 | Aditya Prayoga | 8 | JC290426 34555
87 | 2026-04-29 | W000308 | E12300.75100_RA1_MAIN EQUIPMENT LIST (MACHINERY PART) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2027-04-01 | 2026-04-30 | 1 | Aditya Prayoga | 8 | JC290426 34558
88 | 2026-04-29 | W000308 | E22000.90100_R0_EST. MAT. OF LUBRICATING OIL | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2028-04-01 | 2026-04-30 | 1 | Aditya Prayoga | 16 | JC290426 34559
89 | 2026-04-29 | W000306 | E22000.90100_R0_EST. MAT. OF LUBRICATING OIL | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2029-04-01 | 2026-04-30 | 1 | Aditya Prayoga | 16 | JC290426 34556
90 | 2026-04-29 | W000311 | E95000.92100_R0_KEY PLAN WEIGHT CALCULATION (KB-02) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2030-04-01 | 2026-04-30 | 1 | Aditya Prayoga | 16 | JC290426 34561
91 | 2026-04-29 | PINISI | RUDDER STOCK CALCULATION | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2031-04-01 | 2026-04-30 | 1 | Aditya Prayoga | 24 | JC300426 34565
92 | 2026-04-29 | W000304 | E92330.91100_CALCULATION OF CHOCKING RESIN FOR INTERMEDIATE SHAFT BEARING IN CASE OF SHOCK | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2032-04-01 | 2026-04-30 | 1 | Aditya Prayoga | 16 | JC290426 34560
93 | 2026-04-29 | GEOMARIN | MAIN EQUIPMENT LIST (MACHINERY PART) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2033-04-01 | 2026-04-30 | 1 | Aditya Prayoga | 16 | JC300426 34566
95 | 2026-04-30 | W000308 | KOMPARASI MATERIAL PIPA (EST. MAT VS. CADMATIC) ALL SYSTEM_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-01 | 2026-04-10 | 1 | Krisdiyantoro | 56 | JC300426 34569
96 | 2026-04-30 | W000306-307 | EVATEK RCVS, MAKER KEYSTONE & HANLA_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-13 | 2026-04-17 | 1 | Krisdiyantoro | 40 | JC300426 34570
97 | 2026-04-30 | PINISI | CREATE PID FO SYSTEM, EXH GAS, AND SW. COOLING_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-20 | 2026-04-30 | 1 | Krisdiyantoro | 72 | JC300426 34571
98 | 2026-04-30 | W311 | E15240.27100-R1-PIPE MODELLING SEA WATER COOLING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2034-04-01 | 2026-04-03 | 1 | MIEKAIL | 24 | JC300426 34588
99 | 2026-04-30 | W311 | R0-PIPE MODELLING OVERBOARD AND CUSTOMIZE PIPING PENETRATION FOR ALL SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2034-04-06 | 2026-04-10 | 1 | MIEKAIL | 40 | JC300426 34594
100 | 2026-04-30 | W308 | E15321.27100-R0-PIPE MODELLING HT & LT FW COOLING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2034-04-13 | 2026-04-17 | 1 | MIEKAIL | 60 | JC300426 34595
101 | 2026-04-30 | A26AOP01 | E15510.22100-R0-PID OF COMPRESSED AIR SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2034-04-20 | 2026-04-24 | 1 | MIEKAIL | 50 | JC300426 34596
102 | 2026-04-30 | A26AOP01 | E25510.01100-R1-EST. QTY. MATERIAL FOR PID OF COMPRESSED AIR SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2034-04-27 | 2026-04-30 | 1 | MIEKAIL | 32 | JC300426 34597
103 | 2026-04-30 | W000304 | E25330.01100_A1_ESTIMATED MATERIAL FOR FRESH WATER SANITARY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-16 | 2026-04-16 | 1 | Diar | 3 | JC300426 34593
104 | 2026-04-30 | W000308 | SORT VALVE SPECIFICATION BASED ON PDM BATCH | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-04-18 | 2026-04-18 | 1 | Diar | 6 | JC300426 34592
105 | 2026-04-30 | W000306 | - PIPE MODEL - ROUTING & READY ADDITIONAL PIPE SYSTEM 5421 FUEL OIL SERVICE FOR HELICOPTER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-25 | 2026-04-25 |  | FARIS NOVARIANSYAH | 8 | JC300426 34599
106 | 2026-04-30 | W000308 | R0 - E15142.18101 - ARR'T & DETAIL OF VENTILATOR HEAD FOR ACCOMMODATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-04-01 | 2026-04-11 |  | FIRMAN |  | JC300426 34598
107 | 2026-04-30 | W000308 | Check Piping Modelling E15330-22100, ES334U-R0, ES344U-R0, ES353U-R0, ES222U-R0 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-27 | 2026-04-30 | 1 | Asi Supeni | 32 | JC300426 34591
2026-05-26
1 | 2026-04-28 | W000307 | E15282.17100 Pipe Model Grey Water system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-04-28 | 2026-05-12 | 1 | Dimas | 96 | JC280426 34535
2 | 2026-04-28 | W000307 | E15161.17100 Pipe Model Chilled Water system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-13 | 2026-05-26 | 1 | Dimas | 96 | JC280426 34536
3 | 2026-04-28 | W000307 | E15931.17100 Pipe Model Sludge and Oily Bilge system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-27 | 2026-06-02 | 1 | Dimas | 22 | JC280426 34537
4 | 2026-04-28 | W000305 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-01 | 2026-05-31 | 1 | Dimas | 8 | JC280426 34539
5 | 2026-04-28 | W000307 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-01 | 2026-05-31 | 1 | Dimas | 8 | JC280426 34538
6 | 2026-04-28 | W000308 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-01 | 2026-05-31 | 1 | Dimas | 8 | JC280426 34540
7 | 2026-04-28 | W000311 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-01 | 2026-05-31 | 1 | Dimas | 8 | JC280426 34541
8 | 2026-04-30 | PINISI | R0 - E95140.91001 - CALCULATION OF HVAC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 May 2026 | 5 May 2026 | 1 | STEVAN |  | JC040526 34677
9 | 2026-04-30 | PINISI | R0 - E15140.75100 - MAIN EQUIPMENT LIST AC & FAN | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 6 May 2026 | 13 May 2026 | 1 | STEVAN |  | JC040526 34678
10 | 2026-04-30 | GEOMARIN | R0 - E95140.91001 - CALCULATION OF HVAC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 14 May 2026 | 16 May 2026 | 1 | STEVAN |  | JC040526 34688
11 | 2026-04-30 | GEOMARIN | R0 - E15140.75100 - MAIN EQUIPMENT LIST AC & FAN | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 18 May 2026 | 23 May 2026 | 1 | STEVAN |  | JC040526 34689
12 | 2026-04-30 | W000308 | R2 - E15141.28100 - REV. DIAGRAM OF AIR CONDITIONING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 25 May 2026 | 30 May 2026 | 1 | STEVAN | 80 | JC040526 34690
13 | 2026-04-30 | W000304 | CHECK OUTPUT REVISI DRAWING SKETCHES & ARRANGEMENT OF VENTILATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 May 2026 | 31 May 2026 | 1 | STEVAN | 40 | JC040526 34693
14 | 2026-04-30 | W000306 | CHECK OUTPUT REVISI DRAWING SKETCHES & ARRANGEMENT OF VENTILATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 May 2026 | 31 May 2026 | 1 | STEVAN | 40 | JC040526 34696
15 | 2026-04-30 | W000308 | CHECK OUTPUT REVISI DRAWING SKETCHES & ARRANGEMENT OF VENTILATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 May 2026 | 31 May 2026 | 1 | STEVAN | 40 | JC040526 34691
16 | 2026-04-30 | W000308 | ⁠E15282.27100 - Pipe Modelling & Ready Grey Water System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-01 | 2026-05-31 | 1 | Syaiful | 60 | JC040526 34703
17 | 2026-04-30 | W000308 | E15161.27100 - Revisi Pipe Modelling & Ready Chilled Water | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-01 | 2026-05-31 | 1 | Syaiful | 60 | JC040526 34704
18 | 2026-04-30 | W000308 | E15330.27100 - Revisi Pipe Modelling & Ready FW Sanitary Service System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-01 | 2026-05-31 | 1 | Syaiful | 60 | JC040526 34705
19 | 2026-05-04 | W000305 | E15412.27100 - Revisi Pipe Modelling FO Service. | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-01 | 2026-05-31 | 1 | Erly | 46 | JC040526 34720
20 | 2026-05-04 | W000308 | E15431.27100 - Pipe Modelling LO Filling and Transfer. | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-01 | 2026-05-31 | 1 | Erly | 46 | JC040526 34710
21 | 2026-05-04 | W000308 | E15330.27100 - Pipe Ready FW Sanitary. | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-01 | 2026-05-31 | 1 | Erly | 46 | JC040526 34711
22 | 2026-05-04 | W000308 | E15162.27100 - Pipe Modelling Refrigeration Provision Store. | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-01 | 2026-05-31 | 1 | Erly | 46 | JC040526 34712
23 | 2026-05-04 | W000307 | E15750.17100 - Pipe Modeling System Hydraulic Roro-Equipment | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-01 | 2026-05-10 | 1 | Rizki R | 52 | JC040526 34721
24 | 2026-05-04 | W000307 | E15810.17100 - Pipe Modelling System Hydraulic Deck Machinery | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-11 | 2026-05-20 | 1 | Rizki R | 70 | JC040526 34723
25 | 2026-05-04 | W000307 | E15162.17100 - Pipe Modeling System Refrigeration Provision Store | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-21 | 2026-05-31 | 1 | Rizki R | 52 | JC040526 34724
26 | 2026-05-04 | W000308 | E13410.27100 - Pipe model FO, LO, Oily drain | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-01 | 2026-05-31 | 1 | Yasin | 46 | JC040526 34706
27 | 2026-05-04 | W000308 | E15513.27100 - Pipe model Low Air Pressure | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-01 | 2026-05-31 | 1 | Yasin | 46 | JC040526 34707
28 | 2026-05-04 | W000308 | E15512.27100 - Pipe model Medium Air Pressure | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-01 | 2026-05-31 | 1 | Yasin | 46 | JC040526 34708
29 | 2026-05-04 | W000308 | E15331.27100 - Pipe Model Hot Water Sanitary | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-01 | 2026-05-31 | 1 | Yasin | 46 | JC040526 34709
30 | 7 May 2026 | W000306 | R4 - E25421.01100 - EST. QTY. MAT. FOR PIPING DIAGRAM OF SW COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 4 May 2026 | 9 May 2026 | 1 | SATRIO | 25 | JC080526 34899
31 | 7 May 2026 | W000308 | R4 - E25231.01100 - EST. QTY. MAT. FOR PIPING DIAGRAM OF PREWETTING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 4 May 2026 | 8 May 2026 | 1 | SATRIO | 25 | JC080526 34901
32 | 7 May 2026 | W000306 | R4 - E15421.22100 - PIPING DIAGRAM OF SW COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 11 May 2026 | 16 May 2026 | 1 | SATRIO | 20 | JC080526 34900
33 | 7 May 2026 | W000308 | R5 - E15282.22100 - PIPING DIAGRAM OF GREY WATER SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 11 May 2026 | 23 May 2026 | 1 | SATRIO | 50 | JC080526 34902
34 | 7 May 2026 | W000308 | R3 - E15231.22100 - PIPING DIAGRAM OF PREWETTING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 11 May 2026 | 23 May 2026 | 1 | SATRIO | 50 | JC080526 34903
35 | 7 May 2026 | W000304 | FP - E14860.22100 - PIPING DIAGRAM OF TRACKING RADAR COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 25 May 2026 | 26 May 2026 | 1 | SATRIO | 20 | JC080526 34907
36 | 7 May 2026 | W000304 | FP - E14860.22100 - PIPING DIAGRAM OF HAN IFF ANTENNA COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 27 May 2026 | 28 May 2026 | 1 | SATRIO | 20 | JC080526 34908
37 | 7 May 2026 | W000304 | FP - E14860.22100 - PIPING DIAGRAM OF SURVEILLANCE RADAR COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 29 May 2026 | 30 May 2026 | 1 | SATRIO | 15 | JC080526 34909
38 | 7 May 2026 | W000308 | R0 - ED525C.48100 - VENT SKETCHES BLOCK 525 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 May 2026 | 12 May 2026 | 1 | IRFAN | 50 | JC080526 34905
39 | 7 May 2026 | W000308 | R0 - ED624P.48100 - VENT SKETCHES BLOCK 624 (P) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 18 May 2026 | 27 May 2026 | 1 | IRFAN | 50 | JC080526 34906
40 | 2026-05-11 | W000308 | Check Piping Output: ES521U-R0, ES522U-R0, ES612U-R0, Check Piping Modelling E15330-22100, E15240-22100 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-04 | 2026-05-08 | 1 | Asi Supeni | 40 | JC110526 34935
41 | 11 May 2026 | W000304 | FP - E55240.22100 - FINISH PLAN PID OF SEA WATER COOLING | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 May 2026 | 30 May 2026 | 1 | AHMAD KHUNAIFI | 40 | JC120526 35037
42 | 11 May 2026 | W000311 | UPDATE MODEL EQUIPMENT, VALVE & INSTRUMENT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 May 2026 | 30 May 2026 | 1 | AHMAD KHUNAIFI | 40 | JC120526 35039
43 | 11 May 2026 | W000308 | R3 - E15211.22100 - PIPING DIAGRAM OF FIRE MAIN & WASH DECK | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 May 2026 | 30 May 2026 | 1 | IRFAN | 50 | JC120526 35038
44 | 11 May 2026 | A26AOP01 | INPUT SPEC. - PIPE LINE PID & MODELING CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 May 2026 | 30 May 2026 | 1 | AHMAD KHUNAIFI | 48 | JC120526 35040
45 | 2026-05-13 | W000308 | Check Piping Output: ES523U-R0, Check Piping Modelling E15281-22100, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-11 | 2026-05-13 | 1 | Asi Supeni | 24 | JC130526 35079
46 | 2026-05-16 | W000304 | E15000.01100_R0_PRINCIPAL PARTICULAR MACHINERY PART | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-01 | 2026-05-31 | 1 | Diar | 8 | JC180526 35128
47 | 2026-05-16 | M000312 | SCHEMATIC DIAGRAM OF FRESH WATER SANITARY SERVICE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-01 | 2026-05-31 | 1 | Diar | 32 | JC180526 35135
48 | 2026-05-16 | M000312 | SCHEMATIC DIAGRAM OF SEA WATER SANITARY SERVICE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-01 | 2026-05-31 | 1 | Diar | 32 | JC180526 35136
49 | 2026-05-16 | M000312 | SCHEMATIC DIAGRAM OF SEWAGE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-01 | 2026-05-31 | 1 | Diar | 32 | JC180526 35139
50 | 2026-05-16 | M000312 | SCHEMATIC DIAGRAM OF DECK SCUPPER | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-01 | 2026-05-31 | 1 | Diar | 32 | JC180526 35140
51 | 19 May 2026 | W000308 | R4 - E15161.22100 - PIPING DIAGRAM CHILLED WATER SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 May 2026 | 8 May 2026 | 1 | RAFIKA |  | JC200526 35380
52 | 19 May 2026 | W000308 | R0 - PIPING DIAGRAM OF INFRARED SEARCH AND TRACK COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 11 May 2026 | 15 May 2026 | 1 | RAFIKA |  | JC200526 35381
53 | 19 May 2026 | W000306 | R1 - E25280.01100 - EST MATERIAL FOR PIPING DIAGRAM OF INSIDE SCUPPER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 18 May 2026 | 22 May 2026 | 1 | RAFIKA |  | JC200526 35382
54 | 19 May 2026 | W000306 | R2 - E25261.01100 - EST MATERIAL FOR PIPING DIAGRAM OF OUTSIDE SCUPPER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 25 May 2026 | 30 May 2026 | 1 | RAFIKA |  | JC200526 35383
55 | 19 May 2026 | W000306 | EVATEK VALVE BATCH 2 VENDOR EURONAVIG & CNJ -R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-11 | 2026-05-15 | 1 | NIZAR | 24 | JC200526 35388
56 | 19 May 2026 | M000312 | PID OF BILGE & BALLAST SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-04 | 2026-05-30 | 1 | NIZAR | 40 | JC200526 35384
57 | 19 May 2026 | M000312 | PID OF FIRE & WASH DECK SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-04 | 2026-05-30 | 1 | NIZAR | 40 | JC200526 35385
58 | 19 May 2026 | M000312 | PID OF AIR & SOUNDING PIPE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-04 | 2026-05-30 | 1 | NIZAR | 40 | JC200526 35386
59 | 19 May 2026 | M000312 | PID OF LOW AIR PRESSURE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-04 | 2026-05-30 | 1 | NIZAR | 40 | JC200526 35387
60 | 19 May 2026 | W000308 | E25513.01100-R2-EST QTY MATERIAL OF LOW AIR PRESSURE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-11 | 2026-05-11 | 1 | NIZAR | 8 | JC200526 35389
61 | 2026-05-22 | W000304 | Check Piping Output: EP532P-R3, EK532P-R2, EP532S-R3, EK532S-R2, EP652P-R3, EK652P-R3, EP652S-R3, EK652S-R3, EP523P-R3, EK523P-R3, EP523S-R3, EK523S-R3, EP514C-R3, EK514C-R3, EP522P-R3, EK522P-R3, EP522S-R3, EK522S-R3, EP642P-R3, EK642P-R3, EP642S-R3, EK642S-R3, EP622P-R3, EK622P-R3, EP622S-R3, EK622S-R3 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-18 | 2026-05-22 | 1 | Asi Supeni | 40 | JC220526 35448
62 | 2026-05-23 | M000312 | INPUT SPEC. - PIPE LINE PID & MODELING CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 20 May 2026 | 30 May 2026 | 1 | AHMAD KHUNAIFI | 40 | JC250526 35540
63 | 2026-05-23 | W000308 | UPDATE SPEC., MODEL EQUIPMENT, VALVE & INSTRUMENT CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 May 2026 | 30 May 2026 | 1 | AHMAD KHUNAIFI | 32 | JC250526 35534
64 | 2026-05-23 | W000306 | UPDATE SPEC., MODEL EQUIPMENT, VALVE & INSTRUMENT CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 May 2026 | 30 May 2026 | 1 | AHMAD KHUNAIFI | 32 | JC250526 35538
65 | 25 May 2026 | W306JW1-W307JW2 | E12590.22100-PIPING DIAGRAM OF EXHAUST GAS SYSTEM-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-04 | 2026-05-04 | 1 | AMAM | 8 | JC250526 35542
66 | 25 May 2026 | W306JW1-W307JW2 | E15060.22100-PIPING DIAGRAM OF AIR AND SOUNDING PIPE-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-05 | 2026-05-05 | 1 | AMAM | 8 | JC250526 35543
67 | 25 May 2026 | W304-305 | E25410.01100-EST. MATERIAL FOR PIPING DIAGRAM OF FUEL OIL PURIFIYING-R4 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-06 | 2026-05-06 | 1 | AMAM | 8 | JC250526 35544
68 | 25 May 2026 | W311 | E15291.22100-PIPING DIAGRAM OF BILGE SYSTEM-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-07 | 2026-05-08 | 1 | AMAM | 16 | JC250526 35546
69 | 25 May 2026 | W311 | E15210.22100-PIPING DIAGRAM OF FIRE MAIN AND WASH DECK SYSTEM-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-11 | 2026-05-12 | 1 | AMAM | 16 | JC250526 35547
70 | 25 May 2026 | W311 | E15410.22100-PIPING DIAGRAM OF FUEL OIL SYSTEM-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-13 | 2026-05-19 | 1 | AMAM | 24 | JC250526 35548
71 | 25 May 2026 | W311 | E15240.22100-PIPING DIAGRAM OF SEA WATER COOLING SYSTEM-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-20 | 2026-05-22 | 1 | AMAM | 24 | JC250526 35549
72 | 25 May 2026 | W311 | E12590.22100-PIPING DIAGRAM OF EXHAUST GAS SYSTEM-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-25 | 2026-05-26 | 1 | AMAM | 16 | JC250526 35550
73 | 25 May 2026 | W311 | E15060.22100-PIPING DIAGRAM OF AIR AND SOUNDING PIPE-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-29 | 2026-05-29 | 1 | AMAM | 8 | JC250526 35552
74 | 2026-05-26 | W000304 | Check Piping Output: EP612P-R3, EK612P-R2, EP612S-R3, EK612S-R3, EP542P-R2, EK542P-R2, EP542S-R2, EK542S-R2, EP632P-R3, EK632P-R2, EP632S-R3, EK632S-R3 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-05-25 | 2026-05-26 | 1 | Asi Supeni | 16 | JC260526 35588
75 | 2026-05-26 | R22FPBXA | Preliminary Design Review KRI Tipe FPB | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-01 | 2026-05-31 | 1 | Syafril | 128
76 | 2026-05-28 | A26AOP01 | E25420.01100-EST. QTY. MATERIAL FOR PID OF SEA WATER COOLING SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-04 | 2026-05-08 | 1 | MIEKAIL | 40 | JC280526 35605
77 | 2026-05-28 | A26AOP01 | E15291.22100-PID OF BILGE SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-11 | 2026-05-13 | 1 | MIEKAIL | 16 | JC280526 35606
78 | 2026-05-28 | A26AOP01 | E15293.22100-PID OF COMPENSATING AND EMERGENCY BLOWING SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-18 | 2026-05-20 | 1 | MIEKAIL | 24 | JC280526 35607
79 | 2026-05-28 | A26AOP01 | E25293.01100-EST. QTY. MATERIAL FOR PID OF COMPENSATING AND EMERGENCY BLOWING SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-21 | 2026-05-22 | 1 | MIEKAIL | 16 | JC280526 35608
80 | 2026-05-28 | A26AOP01 | E15420.27100-PIPE MODELING OF SEA WATER COOLING SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-25 | 2026-05-29 | 1 | MIEKAIL | 40 | JC280526 35609
81 | 2026-05-28 | A26AOP01 | E15420.22100-PID OF SEA WATER COOLING SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-01 | 2026-05-14 | 1 | MIEKAIL | 30 | JC280526 35610
82 | 2026-05-28 | W304 | E25291.01100-PID OF BILGE SYSTEM- | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-15 | 2026-05-15 | 1 | MIEKAIL | 8 | JC280526 35611
83 | 2026-05-28 | W304 | E25291.01100-EST. QTY. MATERIAL FOR PID OF BILGE SYSTEM- | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-16 | 2026-05-16 | 1 | MIEKAIL | 8 | JC280526 35612
84 | 2026-05-28 | A26AOP01 | E25420.01100-EST. QTY. MATERIAL FOR PID OF SEA WATER COOLING SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-18 | 2026-05-18 | 1 | MIEKAIL | 8 | JC280526 35613
85 | 2026-05-28 | A26AOP01 | E15420.27100-PIPE MODELING OF SEA WATER COOLING SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-23 | 2026-05-23 | 1 | MIEKAIL | 8 | JC280526 35614
86 | 2026-05-28 | A26AOP01 | E15510.27100-PIPE MODELING OF COMPRESSED AIR SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-28 | 2026-05-28 | 1 | MIEKAIL | 8 | JC280526 35615
87 | 29 May 2026 | W000311 | R1 - E15131.18100 - ARR'T & DETAIL OF VENTILATOR HEAD FOR ENGINE ROOM - R1 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 May 2026 | 6 May 2026 | 1 | FIRMAN | 32 | JC290526 35625
88 | 29 May 2026 | W000311 | R1 - E15131.18101 - ARR'T & DETAIL OF VENTILATOR HEAD FOR GENERATOR ROOM - R1 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 7 May 2026 | 12 May 2026 | 1 | FIRMAN | 32 | JC290526 35626
89 | 29 May 2026 | W000311 | R1 - E25131.01100 - EST. MAT. OF VENTILATOR HEAD FOR ENGINE ROOM - R1 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 13 May 2026 | 15 May 2026 | 1 | FIRMAN | 24 | JC290526 35627
90 | 29 May 2026 | W000311 | R1 - E25131.01101 - EST. MAT. OF VENTILATOR HEAD FOR GENERATOR ROOM - R1 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 18 May 2026 | 20 May 2026 | 1 | FIRMAN | 24 | JC290526 35628
91 | 29 May 2026 | W000306 | R1 - E15134.18100 - DAMPER OF VENTILATION FOR AUXILLIARY ENGINE ROOM - R1 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 21 May 2026 | 26 May 2026 | 1 | FIRMAN | 32 | JC290526 35629
92 | 29 May 2026 | W000306 | R1 - E25134.01100 - EST. MAT OF VENTILATION DAMPER FOR AUXILLIARY ENGINE ROOM - R1 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 27 May 2026 | 31 May 2026 | 1 | FIRMAN | 16 | JC290526 35630
93 | 29 May 2026 | W000306 | - MODELLING - ROUTING & READY PIPING PORTABLE WATER DARI FRESH WATER SYSTEM (5330) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 4 May 2026 | 5 May 2026 | 1 | FARIS NOVARIANSYAH | 16 | JC290526 35631
94 | 29 May 2026 | W000306 | - MODELLING - ROUTING & READY PIPING BLACK WATER SYSTEM (5281) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 6 May 2026 | 12 May 2026 | 1 | FARIS NOVARIANSYAH | 38 | JC290526 35632
95 | 29 May 2026 | W000304 | - E15161.12214 - PIPING ARRAGEMENT COOLING WATER SYSTEM BLOCK 214 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 13 May 2026 | 13 May 2026 | 1 | FARIS NOVARIANSYAH | 8 | JC290526 35636
96 | 29 May 2026 | W000304 | - E15161.12224 - PIPING ARRAGEMENT COOLING WATER SYSTEM BLOCK 224 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 18 May 2026 | 19 May 2026 | 1 | FARIS NOVARIANSYAH | 16 | JC290526 35638
97 | 29 May 2026 | W000306 | - MODELLING - ROUTING & READY PIPING GREY WATER SYSTEM (5281) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 20 May 2026 | 26 May 2026 | 1 | FARIS NOVARIANSYAH | 38 | JC290526 35633
98 | 29 May 2026 | W000306 | - MODELLING - ROUTING & READY PIPING GREY WATER SYSTEM (5281) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 28 May 2026 | 29 May 2026 | 1 | FARIS NOVARIANSYAH | 16 | JC290526 35635
99 | 2026-05-29 | M000312 | CREATE PIPING SCHEMATIC OF EXH. GAS, FO TRANSFER & SERVICE, LO TRANSFER & SERVICE, SEA WATER COOLING, AND FO, LO, & OILY WATER DRAIN_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-04 | 2026-05-29 | 1 | Krisdiyantoro | 128 | JC290526 35646
99 | 2026-05-29 | M000312 | E95620.91100_R0_CALCULATION OF RUDDER STOCK | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-04 | 2026-05-29 | 1 | Aditya Prayoga | 16 | JC290526 35647
99 | 2026-05-29 | M000312 | E95610.91100_R0_CALCULATION OF STEERING GEAR | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-04 | 2026-05-29 | 1 | Aditya Prayoga | 8 | JC290526 35648
99 | 2026-05-29 | M000312 | E15620.63100_R0_RUDDER STOCK AND FITTINGS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-04 | 2026-05-29 | 1 | Aditya Prayoga | 32 | JC290526 35649
99 | 2026-05-29 | A24AOP01 | HULL RESISTANCE ANALYSIS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-04 | 2026-05-29 | 1 | Aditya Prayoga | 24 | JC290526 35651
99 | 2026-05-29 | M000312 | E1230075100_R0_MAIN EQUIPMENT LIST MACHINERY PART | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-04 | 2026-05-29 | 1 | Aditya Prayoga | 8 | JC290526 35650
99 | 2026-05-29 | W000308 | UPDATE DATA BERAT EQUIPMENT CADMATIC | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-04 | 2026-05-29 | 1 | Aditya Prayoga | 16 | JC290526 35653
99 | 2026-05-29 | M000312 | EVATEK E/R PUMPS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-04 | 2026-05-29 | 1 | Aditya Prayoga | 8 | JC290526 35654
99 | 2026-05-29 | M000312 | E1230075100_R1_MAIN EQUIPMENT LIST MACHINERY PART | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-04 | 2026-05-29 | 1 | Aditya Prayoga | 8 | JC290526 35655
100 | 2026-05-30 | A26A0P01 | Perhitungan, Desain, Modelling & Output Sistem Propulsi KSOT 20 Meter | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-05-01 | 2026-05-30 | 1 | Ardan Nagra Coutsar |  | JC010626 35728
2026-06-26
1 | 2026-05-25 | W000307 | E15432.17100 LO SERVICE & PURIFYING SYSTEM | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-10 | 1 | Dimas | 71 | JC020626 35769
2 | 2026-05-25 | W000307 | E15321.17100 HT LT FW COOLING SYSTEM | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-11 | 2026-06-12 | 1 | Dimas | 19 | JC020626 35770
3 | 2026-05-25 | W000307 | E15555.17100 LOCAL APPLICATION SYSTEM | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-13 | 2026-06-20 | 1 | Dimas | 49 | JC020626 35771
3 | 2026-05-25 | W000307 | E15551.17100 FIRE EXTINGUISHER DEEP FAT FRYER SYSTEM | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-21 | 2026-06-30 | 1 | Dimas | 68 | JC020626 35773
4 | 2026-05-25 | W000305 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-30 | 1 | Dimas | 8 | JC020626 35782
5 | 2026-05-25 | W000307 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-30 | 1 | Dimas | 8 | JC020626 35776
6 | 2026-05-25 | W000308 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-30 | 1 | Dimas | 8 | JC020626 35786
7 | 2026-05-25 | W000311 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-30 | 1 | Dimas | 8 | JC020626 35795
8 | 2026-05-25 | M000312 | Administrator Cadmatic Outfitting Data Base & trouble shooting Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-30 | 1 | Dimas | 8 | JC020626 35796
9 | 2026-05-25 | W000308 | E15331.17100 - Pipe Model Hot Water Sanitary | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-30 | 1 | Yasin | 46 | JC020626 35787
10 | 2026-05-25 | W000308 | E15555.17100 - Rev. Pipe model system local application system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-30 | 1 | Yasin | 46 | JC020626 35788
11 | 2026-05-25 | W000308 | E15513.17100 - Pipe Model Low air pressure | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-30 | 1 | Yasin | 46 | JC020626 35789
12 | 2026-05-25 | M000312 | E15240.17100 - Pipe Model system SW Cooling | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-30 | 1 | Yasin | 46 | JC020626 35798
13 | 2026-05-25 | M000312 | E15290.17100 - Pipe Model Bilge Ballast system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-30 | 1 | Yasin | 46 | JC020626 35800
14 | 2026-05-25 | W000307 | E15513.17100 - Pipe Modeling System Low Air Pressure | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-14 | 1 | Rizki R | 108 | JC020626 35779
15 | 2026-05-25 | W000307 | E15512.17100 - Pipe Modelling System Medium Pressure | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-15 | 2026-06-30 | 1 | Rizki R | 108 | JC020626 35780
16 | 2026-06-01 | W000308 | E15421.27100 - Pipe Modelling FO Service for Helicopter System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-30 | 1 | Syaiful | 60 | JC020626 35790
17 | 2026-06-01 | W000308 | E15282.27100 - Pipe Modelling & Ready Grey Water System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-30 | 1 | Syaiful | 60 | JC020626 35791
18 | 2026-06-01 | W000308 | E15161.27100 - Pipe Modelling & Ready Chilled Water System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-30 | 1 | Syaiful | 60 | JC020626 35792
19 | 2026-06-01 | W000305 | E15522,17100 - Pipe Modelling Oxygen Acetylene | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-30 | 1 | Erly | 38 | JC020626 35783
20 | 2026-06-01 | W000305 | E31693.17100 - Pipe Model Hydrolic for Torpedo Door | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-30 | 1 | Erly | 38 | JC020626 35784
21 | 2026-06-01 | W000305 | E15321.17100 - Revisi Pipe Modelling Central Fresh Water Cooling | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-30 | 1 | Erly | 38 | JC020626 35785
22 | 2026-06-01 | W000308 | E15330.27100 - Pipe Ready FW Sanitary. | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-30 | 1 | Erly | 38 | JC020626 35793
23 | 2026-06-01 | W000308 | E15162.27100 - Pipe Modelling Refrigeration Provision Store. | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-30 | 1 | Erly | 38 | JC020626 35794
24 | 2 June 2026 | W000304 | CHECK OUTPUT DRAWING & DOCUMENT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 June 2026 | 30 June 2026 | 1 | STEVAN | 40 | JC020626 35851
25 | 2 June 2026 | W000306 | CHECK OUTPUT DRAWING & DOCUMENT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 June 2026 | 30 June 2026 | 1 | STEVAN | 20 | JC020626 35852
26 | 2 June 2026 | W000308 | CHECK OUTPUT DRAWING & DOCUMENT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 June 2026 | 30 June 2026 | 1 | STEVAN | 40 | JC020626 35853
27 | 2 June 2026 | M000312 | CHECK OUTPUT DRAWING & DOCUMENT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 June 2026 | 30 June 2026 | 1 | STEVAN | 40 | JC020626 35854
28 | 2 June 2026 | M000312 | TECHNICAL EVALUATION OF AC & MECHANICAL FANS - HVAC SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 June 2026 | 30 June 2026 | 1 | STEVAN | 40 | JC020626 35856
29 | 2 June 2026 | M000313 | TECHNICAL EVALUATION OF AC & MECHANICAL FANS - HVAC & PROVISION SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 June 2026 | 30 June 2026 | 1 | STEVAN | 40 | JC020626 35857
30 | 2 June 2026 | M000313 | R0 - E15141.28100 - DIAGRAM OF AIR CONDITION SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 15 June 2026 | 30 June 2026 | 1 | STEVAN | 100 | JC020626 35858
31 | 3 June 2026 | M000313 | PRELIMINARY SPEED POWER PREDICTION GEOMARINE V | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 June 2026 | 2 June 2026 | 1 | ARDAN | 16 | JC030626 35962 | JC190626 36558
32 | 3 June 2026 | M000312 | R0 - E12430.33100 - SHAFT ARRANGEMENT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 3 June 2026 | 5 June 2026 | 1 | ARDAN | 32 | JC030626 35963
33 | 3 June 2026 | A26AOP01 | TECHNICAL EVALUATION OF TORPEDO GRP 324, GRP 329 & FULL ALUMINIUM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 8 June 2026 | 8 June 2026 | 1 | ARDAN | 8 | JC030626 35964 | JC150626 36463 | deskripsi yg diubah
34 | 3 June 2026 | A26AOP01 | TECHNICAL EVALUATION OF VERTICAL THRUSTER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 9 June 2026 | 9 June 2026 | 1 | ARDAN | 8 | JC030626 35965
35 | 3 June 2026 | A26AOP01 | TECHNICAL EVALUATION OF PROPULSION SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 10 June 2026 | 10 June 2026 | 1 | ARDAN | 8 | JC030626 35966
36 | 3 June 2026 | A26AOP01 | CALCULATION & MODELLING STEERING SYSTEM KSOT 20 METER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 11 June 2026 | 19 June 2026 | 1 | ARDAN |  | JC030626 35967
37 | 3 June 2026 | A26AOP01 | R0 - E15620.21103 - HYDRAULIC STEERING SYSTEM CONFIGURATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 22 June 2026 | 30 June 2026 | 1 | ARDAN |  | JC030626 35968
38 | 8 June 2026 | W000308 | R1 - E25931.01100 - EST. QTY. MAT. FOR PIPING DIAGRAM OF SLUDGE & OILY BILGE SEPARATOR SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 June 2026 | 3 June 2026 | 1 | SATRIO | 20 | JC080626 36144
39 | 8 June 2026 | M000312 | SCHEMATIC DIAGRAM OF DECK SCUPPER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 4 June 2026 | 6 June 2026 | 1 | SATRIO | 25 | JC080626 36152
40 | 8 June 2026 | W000304 | FP - E15164.22100 - PIPING DIAGRAM OF CHILLED WATER DRAIN | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 8 June 2026 | 13 June 2026 | 1 | SATRIO | 30 | JC080626 36145
41 | 8 June 2026 | W000304 | FP - E15930.22100 - PIPING DIAGRAM OF OIL WASTE TREATMENT AND DISPOSAL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 8 June 2026 | 13 June 2026 | 1 | SATRIO | 30 | JC080626 36146
42 | 8 June 2026 | W000304 | FP - E15931.22100 - PIPING DIAGRAM OF OILY BILGE SEPARATOR SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 15 June 2026 | 20 June 2026 | 1 | SATRIO | 30 | JC080626 36147
43 | 8 June 2026 | W000304 | FP - E13410.22100 - PIPING DIAGRAM OF FO, LO, AND OILY WATER DRAIN SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 15 June 2026 | 20 June 2026 | 1 | SATRIO | 30 | JC080626 36148
44 | 8 June 2026 | M000313 | SCHEMATIC DIAGRAM OF FIRE MAIN & WAS DECK SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 22 June 2026 | 30 June 2026 | 1 | SATRIO | 30 | JC080626 36149
45 | 8 June 2026 | M000313 | SCHEMATIC DIAGRAM OF LOW PRESSURE AIR SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 22 June 2026 | 30 June 2026 | 1 | SATRIO | 30 | JC080626 36150
46 | 8 June 2026 | M000313 | SCHEMATIC DIAGRAM OF FO, LO, AND OILY WATER DRAIN SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 22 June 2026 | 30 June 2026 | 1 | SATRIO | 30 | JC080626 36151
47 | 2026-06-11 | W000305 | Check Piping Output: EP513P-R3, EK513P-R3, EP513S-R3, EK513S-R3, EP511S-R3, EP521S-R3, EP613C-R2, EP673P-R2, EP623C-R3, EP633C-R3, EP333C-R2, EK333C-R1, EP524P-R1, EP524S-R1, EP124P-R3, EK124P-R3, EP325S-R1, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-01 | 2026-06-05 | 1 | Asi Supeni | 40 | JC110626 36266
48 | 2026-06-11 | W000305 | Check Piping Output: EP533P-R2, EK533P-R2, EP134S-R3, EK134S-R3, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-08 | 2026-06-12 | 1 | Asi Supeni | 30 | JC110626 36267
49 | 2026-06-11 | W000308 | Check Piping Output: EP122U-R1, EK122U-R1, EP332U-R3, EK332U-R3, EP113P-R1, EK113P-R1. | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-08 | 2026-06-12 | 1 | Asi Supeni | 30 | JC110626 36268
50 | 2026-06-15 | M000312 | E15220.08100-R0-PIPING SCHEMATIC OF AUTO.WATER SPRINKLER FOR PUBLIC SPACES | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-01 | 2026-06-06 | 1 | NIZAR | 48 | JC170626 36474
51 | 2026-06-15 | M000312 | E15064.08100-R0-PIPING SCHEMATIC OF AIR & SOUNDING PIPE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-08 | 2026-06-10 | 1 | NIZAR | 30 | JC170626 36475
52 | 2026-06-15 | M000312 | E15290.08100-R0-PIPING SCHEMATIC OF BILGE & BALLAST SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-11 | 2026-06-12 | 1 | NIZAR | 20 | JC170626 36476
53 | 2026-06-15 | M000312 | E15211.08100-R0-PIPING SCHEMATIC OF FIRE & WASH DECK SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-13 | 2026-06-15 | 1 | NIZAR | 16 | JC170626 36477
54 | 2026-06-15 | M000312 | E25064.01100-R0-EST.QTY. MAT. FOR PIPING DIAGRAM OF AIR & SOUNDING PIPE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-16 | 2026-06-18 | 1 | NIZAR | 30 | JC170626 36478
56 | 15 June 2026 | W304 | R0 - E14560.22100 - PIPING DIAGRAM OF OXYGEN AND ACETYLENE GAS WELDING PLANT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 June 2026 | 11 June 2026 | 1 | IRFAN | 40 | JC170626 36481
57 | 15 June 2026 | W304 | R0 - E24560.22100 - EST. QTY. MAT. FOR PIPING DIAGRAM OF OXYGEN AND ACETYLENE GAS WELDING PLANT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 15 June 2026 | 17 June 2026 | 1 | IRFAN | 20 | JC170626 36482
58 | 15 June 2026 | M000312 | ROUTE & READY VENT IN BLOCK 322 (C), 122 (C) ,112 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 18 June 2026 | 30 June 2026 | 1 | IRFAN | 60 | JC170626 36484
59 | 15 June 2026 | M000312 | INPUT SPEC. - PIPE LINE PID & MODELING CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 June 2026 | 30 June 2026 | 1 | AHMAD KHUNAIFI | 72 | JC170626 36485
60 | 15 June 2026 | A26AOP01 | INPUT SPEC. - PIPE LINE PID & MODELING CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 June 2026 | 30 June 2026 | 1 | AHMAD KHUNAIFI | 32 | JC170626 36487
61 | 15 June 2026 | W000304 | UPDATE SPEC. - PIPE LINE PID & MODELING CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 June 2026 | 30 June 2026 | 1 | AHMAD KHUNAIFI | 16 | JC170626 36483
62 | 15 June 2026 | W000306 | UPDATE SPEC. - PIPE LINE PID & MODELING CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 June 2026 | 30 June 2026 | 1 | AHMAD KHUNAIFI | 40 | JC170626 36488
63 | 15 June 2026 | W000308 | UPDATE SPEC. - PIPE LINE PID & MODELING CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 June 2026 | 30 June 2026 | 1 | AHMAD KHUNAIFI | 32 | JC170626 36490
64 | 2026-06-19 | W311 | E25291.01100-EST. MATERIAL FOR PIPING DIAGRAM OF BILGE SYSTEM-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-02 | 2026-06-02 |  | AMAM | 8 | JC190626 36550
65 | 2026-06-19 | W311 | E25210.01100-EST. MATERIAL FOR PIPING DIAGRAM OF FIRE MAIN AND WASH DECK SYSTEM-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-03 | 2026-06-03 |  | AMAM | 8 | JC190626 36551
66 | 2026-06-19 | W311 | E25410.01100-EST. MATERIAL FOR PIPING DIAGRAM OF FUEL OIL SYSTEM-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-04 | 2026-06-04 |  | AMAM | 8 | JC190626 36552
67 | 2026-06-19 | W311 | E25240.01100-EST. MATERIAL FOR PIPING DIAGRAM OF SEA WATER COOLING SYSTEM-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-05 | 2026-06-05 |  | AMAM | 8 | JC190626 36553
68 | 2026-06-19 | W311 | E22590.01100-EST. MATERIAL FOR PIPING DIAGRAM OF EXHAUST GAS SYSTEM-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-08 | 2026-06-08 |  | AMAM | 8 | JC190626 36554
69 | 2026-06-19 | W311 | E25060.01100-EST. MATERIAL FOR PIPING DIAGRAM OF SOUNDING AND AIR PIPE-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-09 | 2026-06-09 |  | AMAM | 8 | JC190626 36555
70 | 2026-06-19 | W311 | E12430.33100-SHAFT ARRANGEMENT & ENGINE INSTALLATION-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-10 | 2026-06-17 |  | AMAM | 40 | JC190626 36556
71 | 2026-06-19 | R22PPCXA | E15410.22100-PIPING DIAGRAM OF FUEL OIL SERVICE (REPOWERED GENERATOR SET)-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-18 | 2026-06-22 |  | AMAM | 24 | JC010726 37026
72 | 2026-06-19 | R22PPCXA | E15240.22100-PIPING DIAGRAM OF SEA WATER COOLING SYSTEM (REPOWERED GENERATOR SET)-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-23 | 2026-06-25 |  | AMAM | 24 | JC010726 37027
73 | 2026-06-19 | R22PPCXA | E12590.22100-PIPING DIAGRAM OF EXHAUST GAS SYSTEM (REPOWERED GENERATOR SET)-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-26 | 2026-06-30 |  | AMAM | 24 | JC010726 37028
74 | 2026-06-12 | W000305 | Check Piping Output: EP243P-R3, EP243S-R3, EK243S-R3, EP433P-R3, EK433P-R3, EP433S-R3, EK433S-R3, EP423P-R3, EK423P-R3, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-15 | 2026-06-19 | 1 | Asi Supeni | 30 | JC190626 36568
75 | 2026-06-22 | M000312 | E25290.01100-R0-EST.QTY. MAT. FOR PIPING DIAGRAM OF BILGE & BALLAST SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-19 | 2026-06-25 | 1 | NIZAR | 48 | JC220626 36622
76 | 2026-06-22 | M000312 | E25211.01100-R0-EST.QTY. MAT. FOR PIPING DIAGRAM OF FIRE & WASH DECK SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-26 | 2026-06-30 | 1 | NIZAR | 32 | JC220626 36630
77 | 2026-06-23 | W000304 | E15000.01100_R0_PRINCIPAL PARTICULAR MACHINERY PART | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-01 | 2026-06-30 | 1 | DIAR | 32 | JC230626 36695
78 | 2026-06-23 | W000304 | E25281.01100_R5_EST. MAT. FOR PIPING DIAGRAM OF SEWAGE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-01 | 2026-06-30 | 1 | DIAR | 8 | JC230626 36696
79 | 2026-06-23 | W000304 | E25330.01100_A2_ESTIMATED MATERIAL FOR FRESH WATER SANITARY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-01 | 2026-06-30 | 1 | DIAR | 8 | JC230626 36697
80 | 2026-06-23 | W000304 | E25331.01100_A0_ESTIMATED MATERIAL FOR HOT WATER SANITARY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-01 | 2026-06-30 | 1 | DIAR | 16 | JC230626 36698
81 | 2026-06-23 | W000304 | E22000.01101_R1_EST. MAT. OF ADDITIONAL MATERIAL FOR ORDINARY SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-01 | 2026-06-30 | 1 | DIAR | 16 | JC230626 36699
82 | 2026-06-23 | W000304 | E25281.01100_R5_EST. MAT. FOR PIPING DIAGRAM OF SEWAGE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-01 | 2026-06-30 | 1 | DIAR | 8 | JC230626 36700
83 | 2026-06-23 | M000312 | E15281.08100 PIPING SCHEMATIC OF SEWAGE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-01 | 2026-06-30 | 1 | DIAR | 32 | JC230626 36701
84 | 26 June 2026 | W000307 | R0 - E15261.34200 - ROSE PLATE FOR DECK SCUPPER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 June 2026 | 4 June 2026 | 1 | RAFIKA |  | JC270626 36819
85 | 26 June 2026 | W000308 | PID OF COOLING SISTEM FOR TWS | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 5 June 2026 | 10 June 2026 | 1 | RAFIKA |  | JC270626 36820
86 | 26 June 2026 | W000308 | DETAIL PENETRATION FOR INSULATED PIPES | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 11 June 2026 | 16 June 2026 | 1 | RAFIKA |  | JC270626 36821
87 | 26 June 2026 | W000308 | R4 - E15161.22100 - PIPNG DIAGRAM CHILLED WATER SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 17 June 2026 | 23 June 2026 | 1 | RAFIKA |  | JC270626 36822
88 | 26 June 2026 | W000307 | R3 - E15280.22100 - PIPING DIAGRAM OF INSIDE SCUPPER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 24 June 2026 | 30 June 2026 | 1 | RAFIKA |  | JC270626 36823
89 | 2026-06-26 | W000308 | Check Piping Output: EP322U-R2, EK322U-R2, EP113U-R1, EK113U-R1, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-22 | 2026-06-26 | 1 | Asi Supeni | 30 | JC260626 36800
90 | 2026-06-26 | W000307-JW1 | Check Piping Output: EP5280-R1, EP5330-R1, EP5410-R1, EP5060-R1, EP5292-R1, EP5240-R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-22 | 2026-06-26 | 1 | Asi Supeni | 30 | JC260626 36801
91 | 28 June 2026 | M000312 | R0 - E15131.18100 - ARR'T & DETAIL OF VFENTILATOR HEAD FOR ENGINE ROOM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 June 2026 | 8 June 2026 | 1 | FIRMAN | 48 | JC290626 36838
92 | 28 June 2026 | M000312 | R0 - E25131.18100 - EST. MAT. OF VENTILATOR HEAD FOR ENGINE ROOM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 9 June 2026 | 10 June 2026 | 1 | FIRMAN | 16 | JC290626 36839
93 | 28 June 2026 | M000312 | R0 - E15142.18101 - ARR'T & DETAIL OF VENTILATOR HEAD FOR ACCOMMODATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 11 June 2026 | 18 June 2026 | 1 | FIRMAN | 48 | JC290626 36854
94 | 28 June 2026 | M000312 | R0 - E25142.18101 - EST. MAT OF VENTILATOR HEAD FOR ACCOMMODATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 19 June 2026 | 22 June 2026 | 1 | FIRMAN | 16 | JC290626 36856
95 | 28 June 2026 | M000312 | R0 - E15071.37100 - NAME PLATE FOR VENTILATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 23 June 2026 | 24 June 2026 | 1 | FIRMAN | 16 | JC290626 36857
96 | 28 June 2026 | M000312 | R0 - E25071.37100 - EST. MAT OF NAME PLATE FOR VENTILATION | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 23 June 2026 | 24 June 2026 | 1 | FIRMAN | 16 | JC290626 36858
97 | 28 June 2026 | M000312 | R0 - E1212C.18100 - ARR'T OF VENT. IN BLOCK 212 C | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 25 June 2026 | 30 June 2026 | 1 | FIRMAN | 32 | JC290626 36860
98 | 29 June 2026 | W000306 | READY PIPE FOR MEADUM PRESSURE SYSTEM (5512) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2 June 2026 | 5 June 2026 | 1 | FARIS NOVARIANSYAH | 28 | JC290626 36861
99 | 29 June 2026 | W000306 | READY PIPE FOR SLUDGE & OILY WATER SEPARATOR SYSTEM (5913) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 8 June 2026 | 12 June 2026 | 1 | FARIS NOVARIANSYAH | 32 | JC290626 36862
100 | 29 June 2026 | W000306 | READY PIPE FOR M/E HT&LT FRESH WATER COOLING SYSTEM (5321) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 15 June 2026 | 19 June 2026 | 1 | FARIS NOVARIANSYAH | 28 | JC290626 36865
101 | 29 June 2026 | W000306 | ROUTE & READY PIPE FOR ROUTE & READY REFRIGERATION PROVISION STORE SYSTEM (5162) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 22 June 2026 | 26 June 2026 | 1 | FARIS NOVARIANSYAH | 48 | JC290626 36866
102 | 2026-06-29 | R22FPBXA | Critical Design Review | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-08 | 2026-06-30 | 1 | SYAFRIL | 128 | JC010726 37029
103 | 2026-06-29 | M000312 | REVISI PIPING SCHEMATIC OF EXH. GAS, FO TRANSFER & SERVICE, LO TRANSFER & SERVICE, SEA WATER COOLING, AND FO, LO, & OILY WATER DRAIN_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-02 | 2026-06-19 | 1 | KRISDIYANTORO | 104 | JC300626 36967
104 | 2026-06-29 | W306 & W308 | REVIEW APPROVAL DRAWING RCVS_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-22 | 2026-06-26 | 1 | KRISDIYANTORO | 40 | JC300626 36982
105 | 2026-06-29 | M000312 | CREATE EST. MAT. PIPING SCHEMATIC OF FO TRANSFER & SERVICE_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-29 | 2026-06-30 | 1 | KRISDIYANTORO | 16 | JC300626 36968
106 | 2026-06-30 | M000313 | RUDDER STOCK CALCULATION | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-02 | 2026-06-30 | 1 | Aditya Prayoga | 8 | JC300626 36969
107 | 2026-06-30 | M000313 | 3D MODELING RUDDER STOCK AND FITTINGS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-02 | 2026-06-30 | 1 | Aditya Prayoga | 32 | JC300626 36970
108 | 2026-06-30 | M000312 | EVATEK ER PUMPS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-02 | 2026-06-30 | 1 | Aditya Prayoga | 8 | JC300626 36959
109 | 2026-06-30 | W000308 | E95000.92101_R0_YARD PLAN WEIGHT CALCULATION (KB03) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-02 | 2026-06-30 | 1 | Aditya Prayoga | 16 | JC300626 36983
110 | 2026-06-30 | M000312 | PROPELLER-INDUCED VIBRATION ANALYSIS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-02 | 2026-06-30 | 1 | Aditya Prayoga | 24 | JC300626 36971
111 | 2026-06-30 | M000313 | RUDDER STOCK CALCULATION (WITH SHOE/PINTLE) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-02 | 2026-06-30 | 1 | Aditya Prayoga | 16 | JC300626 36972
112 | 2026-06-30 | M000312 | EVATEK SERVICE AIR COMPRESSOR | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-02 | 2026-06-30 | 1 | Aditya Prayoga | 8 | JC300626 36973
113 | 2026-06-30 | W000306 | UPDATE KB04 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-02 | 2026-06-30 | 1 | Aditya Prayoga | 16 | JC300626 36984
114 | 2026-06-30 | W000306 | RUDDER FLANGE COUPLING TRIMMED NUT ANALYSIS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-02 | 2026-06-30 | 1 | Aditya Prayoga | 8 | JC300626 36985
115 | 2026-06-30 | M000312 | EVATEK STEERING GEAR | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-02 | 2026-06-30 | 1 | Aditya Prayoga | 8 | JC300626 36974
116 | 2026-06-30 | A26AOP01 | E15510.27100-PIPE MODELLING COMPRESSED AIR SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-01 | 2026-06-05 | 1 | MIEKAIL | 40 | JC300626 36975
117 | 2026-06-30 | A26AOP01 | E15291.27100-PIPE MODELLING BILGE SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-08 | 2026-06-12 | 1 | MIEKAIL | 40 | JC300626 36976
118 | 2026-06-30 | A26AOP01 | CADMATIC 3D MODELLING MACHINERY EQUIPMENT, SHAFTING AND PROPULTION-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-15 | 2026-06-19 | 1 | MIEKAIL | 40 | JC300626 36977
119 | 2026-06-30 | A26AOP01 | 3D MODELLING TANK LEVEL INDICATOR AND SENSOR-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-22 | 2026-06-26 | 1 | MIEKAIL | 40 | JC300626 36978
120 | 2026-06-30 | A26AOP01 | EVATEK MOTORIZE VALVE. SENSOR AND PUMP-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-29 | 2026-06-30 | 1 | MIEKAIL | 16 | JC300626 36979
121 | 2026-06-30 | A26AOP01 | E15293.27100-PIPE MODELLING COMPENSATING AND EMERGENCY BLOWING SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-09 | 2026-06-27 | 1 | MIEKAIL | 24 | JC300626 36980
122 | 2026-06-30 | A26AOP01 | PIPE READY COMPRESSED AIR SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-30 | 2026-06-30 | 1 | MIEKAIL | 3 | JC300626 36981
123 | 2026-06-30 | W311 | E12430.33100-SHAFT ARRANGEMENT & ENGINE INSTALLATION-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-05-13 | 2026-05-13 |  | AMAM | 4
124 | 2026-06-30 | R22PPCXA | E15410.22100-PIPING DIAGRAM OF FUEL OIL SERVICE (REPOWERED GENERATOR SET)-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-03 | 2026-06-03 |  | AMAM | 4 | JC010726 37025
125 | 2026-06-30 | W311 | E25291.01100-EST. MATERIAL FOR PIPING DIAGRAM OF BILGE SYSTEM-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-06-01 | 2026-06-01 |  | AMAM | 8 | JC010726 37030
126 | 2026-06-30 | W000308 | Check Piping Drawing Output: EP312U-R2, EK312U-R2, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-06-29 | 2026-06-30 | 1 | Asi Supeni | 16 | JC010726 37031
2026-07-26
1 | 2026-06-30 | CORP2026 | Improvment Program & Administrator Cadmatic Outfitting Data Base Design | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-01 | 2026-07-31 | 1 | Dimas | 24 | JC010726 37032
2 | 2026-06-30 | W000306-JW1 | R1-E12000.10100 Machinery Arrt in E/R | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-01 | 2026-07-05 | 1 | Dimas | 40 | JC010726 37050
3 | 2026-06-30 | W000307 | Check Isometric Drawing Output | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-01 | 2026-07-31 | 1 | Dimas | 180 | JC010726 37051
4 | 2026-06-30 | W000307 | E15513.17100 - Pipe Modeling System Low Air Pressure | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-01 | 2026-07-11 | 1 | Rizki R | 82 | JC010726 37052
5 | 2026-06-30 | W000307 | E15810.17100 - Pipe Modelling & Support System Hydraulic Deck Machinery | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-12 | 2026-07-31 | 1 | Rizki R | 150 | JC020726 37067
6 | 2026-06-30 | W000308 | E15161.27100 - Pipe Modelling Chilled Water System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-01 | 2026-07-31 | 1 | Syaiful | 72 | JC010726 37054
7 | 2026-06-30 | W000308 | E15330.27100 - Pipe Modelling FW Sanitary Service System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-01 | 2026-07-31 | 1 | Syaiful | 72 | JC020726 37056
8 | 2026-06-30 | W000308 | E15421.27100 - Pipe Modelling FO Service for Helicopter System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-01 | 2026-07-31 | 1 | Syaiful | 72 | JC020726 37057
9 | 2026-06-30 | CORP2026 | TOT FACM (Full Attack Craft Missiles) "Design Capability for Local Defence Industry" | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-01 | 2026-07-31 | 1 | Erly | 184 | JC010726 37039
10 | 2026-06-30 | CORP2026 | M00312-E15211.17100 - Pipe model system Fire | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-01 | 2026-07-31 | 1 | Yasin | 52 | JC010726 37040
11 | 2026-06-30 | CORP2026 | M00312-E12590.17100 - Pipe model system exhaust | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-01 | 2026-07-31 | 1 | Yasin | 52 | JC020726 37069
12 | 2026-06-30 | CORP2026 | M00312-E15330.17100 - Pipe model system FW & Hot water sanitary | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-01 | 2026-07-31 | 1 | Yasin | 52 | JC010726 37044
13 | 2026-06-30 | CORP2026 | M00312-E15064.17100 - Pipe model system Air pipe & Sounding | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-01 | 2026-07-31 | 1 | Yasin | 52 | JC010726 37047
14 | 7 July 2026 | W000306 | - MODELLING - READY PIPE FOR LOCAL APPLICATION SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 July 2026 | 3 July 2026 | 1 | FARIZ NOVARIANSYAH | 21 | JC090726 37382
15 | 7 July 2026 | A26AOP01 | - MODELLING - PERHITUNGAN, DESAIN & MODELLING SISTEM PROPULSI KSOT MASS PRODUCT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 July 2026 | 31 July 2026 | 1 | ARDAN |  | JC090726 37384
16 | 7 July 2026 | CORP2026 | CALCULATION OF HVAC SYSTEM PROJECT KAPAL DREDGER 8500M3 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 July 2026 | 11 July 2026 | 1 | STEVAN |  | JC090726 37385
17 | 7 July 2026 | CORP2026 | CALCULATION OF HVAC SYSTEM PROJECT KAPAL LNG CARRIER 3000 CBM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 13 July 2026 | 25 July 2026 | 1 | STEVAN |  | JC090726 37386
18 | 7 July 2026 | W000304 | CHECK OUTPUT DRAWING & DOCUMENT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 July 2026 | 31 July 2026 | 1 | STEVAN | 40 | JC090726 37387
19 | 7 July 2026 | W000306 | CHECK OUTPUT DRAWING & DOCUMENT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 July 2026 | 31 July 2026 | 1 | STEVAN | 20 | JC090726 37388
20 | 7 July 2026 | W000308 | CHECK OUTPUT DRAWING & DOCUMENT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 July 2026 | 31 July 2026 | 1 | STEVAN | 40 | JC090726 37389
21 | 7 July 2026 | M000312 | CHECK OUTPUT DRAWING & DOCUMENT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 July 2026 | 31 July 2026 | 1 | STEVAN | 40 | JC090726 37390
22 | 2026-07-09 | M000313 | M000313-E12000.10100 Machinery Arrt in E/R R0 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-05 | 2026-07-31 | 1 | Dimas | 80 | JC090726 37391
23 | 2026-07-10 | W000308 | Check Piping Drawing Output: EP213U-R2, EK213U-R1, EP121U-R1, EK121U-R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-01 | 2026-07-03 | 1 | Asi Supeni | 24 | JC130726 37571
24 | 2026-07-10 | W000308 | Check Piping Drawing Output: EP233U-R2, EK233U-R2, EP311U-R1, EK311U-R1, EP333U-R2, EK333U-R1, ES441U-R0 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-06 | 2026-07-10 | 1 | Asi Supeni | 40 | JC130726 37572
25 | 10 July 2026 | W000304 | FP - E15261.22100 - PIPING DIAGRAM OF SCUPPER AND DECK DRAINS | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 July 2026 | 11 July 2026 | 1 | SATRIO | 40 | JC130726 37573
26 | 10 July 2026 | W000304 | REV.2 - E14551.22100 - PIPING DIAGRAM OF HAN IFF ANTENNA COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 6 July 2026 | 11 July 2026 | 1 | SATRIO | 20 | JC130726 37575
27 | 10 July 2026 | M000313 | R0 - E15211.08100 - SCHEMATIC DIAGRAM OF FIRE MAIN & WAS DECK SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 6 July 2026 | 18 July 2026 | 1 | SATRIO | 30 | JC130726 37576
28 | 10 July 2026 | M000313 | R0 - E15513.08100 - SCHEMATIC DIAGRAM OF LOW PRESSURE AIR SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 6 July 2026 | 18 July 2026 | 1 | SATRIO | 30 | JC130726 37577
29 | 10 July 2026 | M000313 | R0 - E13410.08100 - SCHEMATIC DIAGRAM OF FO, LO, AND OILY WATER DRAIN | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 20 July 2026 | 25 July 2026 | 1 | SATRIO | 30 | JC130726 37578
30 | 10 July 2026 | M000313 | R0 - E25513.01100 - EST. QTY. MAT. FOR PID OF LOW PRESSURE AIR SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 20 July 2026 | 31 July 2026 | 1 | SATRIO | 24 | JC130726 37579
31 | 10 July 2026 | M000313 | R0 - E23410.01100 - EST. QTY. MAT. FOR PID OF FO, LO, AND OILY WATER DRAIN | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 20 July 2026 | 31 July 2026 | 1 | SATRIO | 24 | JC130726 37580
32 | 10 July 2026 | M000313 | R0 - E25211.01100 - EST. QTY. MAT. FOR PID OF FIRE MAIN & WAS DECK SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 20 July 2026 | 31 July 2026 | 1 | SATRIO | 24 | JC130726 37581
33 | 10 July 2026 | M000312 | R0 - E15261.22100 - PIPING DIAGRAM OF DECK SCUPPER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 20 July 2026 | 31 July 2026 | 1 | SATRIO | 24 | JC130726 37582
34 | 10 July 2026 | M000312 | R0 - E15261.01100 - EST. QTY. MAT. FOR PID OF DECK SCUPPER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 20 July 2026 | 31 July 2026 | 1 | SATRIO | 12 | JC130726 37583
35 | 2026-07-14 | W000305 | E15292.17100 Pipe modelling Ballast System 13-17 Juli 2026 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-13 | 2026-07-17 | 1 | Dimas | 49 | JC150726 37661
36 | 15 July 2026 | - | TOT OFFSET 2 - DESIGN CAPABILITY TRAINING FOR LOCAL DEFENCE INDUSTRY | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 6 July 2026 | 31 July 2026 | 1 | ARDAN |  | JC160726 37688
37 | 15 July 2026 | W000306 | - MODEL - ROUTE & READY RO-RO HYDROLIC SYSTEM (5750) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 6 July 2026 | 14 July 2026 | 1 | FARIS NOVARIANSYAH | 48 | JC150726 37663
38 | 15 July 2026 | W000306 | - MODEL - ROUTE & READY HYDRAULIC MACHINERY SYSTEM (5810) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 15 July 2026 | 17 July 2026 | 1 | FARIS NOVARIANSYAH | 21 | JC150726 37664
39 | 15 July 2026 | M000312 | ROUTE & READY VENT IN BLOCK 511 (C), 521 (C) ,512 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 July 2026 | 18 July 2026 |  | IRFAN | 80 | JC160726 37689
40 | 2026-07-17 | W000308 | Check Piping Drawing Output: ES452U-R0, EP322U-R2, EK322U-R2, Check Pipe Modelling: E15931-22100, E15412-22100, E12590-22100 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-13 | 2026-07-17 | 1 | Asi Supeni | 24 | JC200726 37788
41 | 2026-07-20 | M000312 | E25220.01100-R0-EST MAT FOR AUTOMATIC WATER SPRAYING SYSTEM FOR PUBLIC SPACES | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-01 | 2026-07-03 | 1 | NIZAR | 24 | JC210726 37896
42 | 2026-07-20 | W000308 | E14372.22100-R3-PID OF TANK LEVEL & DRAFT GAUGING SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-04 | 2026-07-04 | 1 | NIZAR | 6 | JC210726 37897
43 | 2026-07-20 | M000312 | E15064.08100-R1-PIPING SCHEMATIC OF AIR & SOUNDING PIPE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-06 | 2026-07-21 | 1 | NIZAR | 24 | JC210726 37898
44 | 2026-07-20 | W000306 | EVATEK VALVE BATCH 2 VENDOR QINGDAO RONGKANG | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-08 | 2026-07-18 | 1 | NIZAR | 40 | JC210726 37899
45 | 2026-07-20 | W000304 | E15515.22101-R3-AIR RESERVOIR AND CONTROL VALVE CABINET FOR EMERGENCY SHUTT-OFF VALVE (PNEU.OPER.) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-13 | 2026-07-31 | 1 | NIZAR | 40 | JC210726 37901
46 | 2026-07-20 | W000305 | EVATEK PIPE & FITTING BATCH 1 VENDOR SJ METAL | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-14 | 2026-07-15 | 1 | NIZAR | 16 | JC210726 37902
47 | 2026-07-20 | W000306 | REKAP LIST VALVE BATCH 1 - BATCH 2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-17 | 2026-07-17 | 1 | NIZAR | 8 | JC210726 37900
49 | 2026-07-23 | M000312 | E25281.01100_R0_ESTIMATED MATERIAL FOR PIPING DIAGRAM OF DRAINAGE AND SEWAGE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-01 | 2026-07-03 | 1 | DIAR | 24 | JC230726 37941
50 | 2026-07-23 | M000312 | E25330.01100_R0_ESTIMATED MATERIAL FOR PIPING DIAGRAM OF FRESH WATER & HOT WATER SANITARY SERVICE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-06 | 2026-07-08 | 1 | DIAR | 24 | JC230726 37942
51 | 2026-07-23 | M000312 | E25240.01101_R0_ESTIMATED MATERIAL FOR PIPING DIAGRAM OF SEA WATER SANITARY SERVICE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-09 | 2026-07-10 | 1 | DIAR | 16 | JC230726 37943
52 | 2026-07-23 | W000308 | E15280.22100_R3_PID OF INSIDE SCUPPER & DRAINAGE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-13 | 2026-07-15 | 1 | DIAR | 24 | JC230726 37944
53 | 2026-07-23 | W000308 | E15261.22100_R3_PID OF OUTSIDE DECK SCUPPER | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-16 | 2026-07-20 | 1 | DIAR | 24 | JC230726 37945
54 | 2026-07-23 | M000312 | E15240.22101_R0_PIPING DIAGRAM OF SEA WATER SANITARY SERVICE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-21 | 2026-07-23 | 1 | DIAR | 24 | JC230726 37947
55 | 2026-07-23 | M000312 | E15330.22100_R0_PIPING DIAGRAM OF FRESH WATER & HOT WATER SANITARY SERVICE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-24 | 2026-07-28 | 1 | DIAR | 24 | JC230726 37948
56 | 2026-07-23 | M000312 | E15281.22100_R0_PIPING DIAGRAM OF DRAINAGE AND SEWAGE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-29 | 2026-07-31 | 1 | DIAR | 24 | JC230726 37949
57 | 23 July 2026 | M000312 | ROUTE & READY VENT IN BLOCK 522 (C), 531 (C) ,532 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 17 July 2026 | 31 July 2026 | 1 | IRFAN | 80 | JC240726 37975
58 | 2026-07-27 | M000312 | CREATING A REVIEW DRAWING BASED ON COMMENTS BY BKI | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-16 | 2026-07-16 | 1 | NIZAR | 8 | JC280726 38177
59 | 2026-07-27 | W000306 | EVATEK BATCH 2 VALVE STANDARD INTERNATIONAL VENDOR EURONAVIG-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-16 | 2026-07-18 | 1 | NIZAR | 16 | JC280726 38179
60 | 2026-07-27 | M000312 | E15290.08100-R1-PIPING SCHEMATIC OF BILGE & BALLAST SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-21 | 2026-07-22 | 1 | NIZAR | 16 | JC280726 38180
61 | 2026-07-27 | M000312 | E15220.08100-R1-PIPING SCHEMATIC OF AUTOMATIC WATER SPRAYING SYSTEM FOR PUBLIC SPACES | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-23 | 2026-07-31 | 1 | NIZAR | 24 | JC280726 38181
62 | 2026-07-27 | M000312 | E22590.01100-R0-EST QTY MAT. OF MIST PIPE & EXHAUST GAS SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-24 | 2026-07-31 | 1 | NIZAR | 24 | JC280726 38182
63 | 27 July 2026 | M000313 | R0 - E15261.08100 - SCHEMATIC PIPING OF DECK SCUPPER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 July 2026 | 8 July 2026 | 1 | RAFIKA |  | JC280726 38183
64 | 27 July 2026 | M000313 | R0 - E15292.08100 - SCHEMATIC PIPING OF BILGE BALLAST SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 9 July 2026 | 15 July 2026 | 1 | RAFIKA |  | JC280726 38184
65 | 27 July 2026 | W000308 | R0 - E14610.22100 - PIPING DIAGRAM OF SONAR COOLING SYSTEM (TWS) COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 16 July 2026 | 21 July 2026 | 1 | RAFIKA |  | JC280726 38185
66 | 27 July 2026 | W000308 | R0 - E14522.22100 - PIPING DIAGRAM OF IRST COOLING SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 22 July 2026 | 31 July 2026 | 1 | RAFIKA |  | JC280726 38186
67 | 27 July 2026 | W000306 | R0 - E1211P.12100 - ARRANGEMENT BLOCK 211 (P) E/R DECK | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 20 July 2026 | 23 July 2026 | 1 | FARIS NOVARIANSYAH | 28 | JC280726 38188
68 | 27 July 2026 | W000306 | R0 - E1211S.12100 - ARRANGEMENT BLOCK 211 (S) E/R DECK | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 24 July 2026 | 24 July 2026 | 1 | FARIS NOVARIANSYAH | 7 | JC280726 38189
69 | 27 July 2026 | W000306 | R0 - E1213P.12100 - ARRANGEMENT BLOCK 213 (P) E/R DECK | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 27 July 2026 | 29 July 2026 | 1 | FARIS NOVARIANSYAH | 21 | JC280726 38190
70 | 27 July 2026 | W000306 | R0 - E1212C.18100 - ARR'T OF VENT IN BLOCK 212 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 30 July 2026 | 31 July 2026 | 1 | FARIS NOVARIANSYAH | 14 | JC280726 38192
71 | 27 July 2026 | M000312 | R0 - E1211C.18100 - ARR'T OF VENT IN BLOCK 211 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 July 2026 | 7 July 2026 | 1 | FIRMAN | 40 | JC280726 38193
72 | 27 July 2026 | M000312 | R0 - E1211C.18100 - ARR'T OF VENT IN BLOCK 211 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 8 July 2026 | 13 July 2026 | 1 | FIRMAN | 32 | JC280726 38194
73 | 27 July 2026 | M000312 | R0 - E1422C.18100 - ARR'T OF VENT IN BLOCK 422 (C) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 14 July 2026 | 20 July 2026 | 1 | FIRMAN | 40 | JC280726 38195
74 | 27 July 2026 | W000308 | R2 - E95555.01100 - TECHNICAL REPORT OF FIRE EXTINGUISHING SYSTEM (HYDRAULIC CALCULATION) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 21 July 2026 | 31 July 2026 | 1 | FIRMAN | 72 | JC280726 38198
75 | 2026-07-29 | R22PPCXA | ANALYSIS REPORT - EVALUASI KECUKUPAN SISTEM PERPIAAN SEBAGAI DAMPAK REPOWERING GENERATOR SET PADA KRI PARCHIM CLASS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-01 | 2026-07-09 | 1 | AMAM | 56 | JC310726 38278
76 | 2026-07-29 | R22PPCXA | ANALYSIS REPORT - EVALUASI KECUKUPAN SISTEM PERPIAAN SEBAGAI DAMPAK REPOWERING MAIN ENGINE AND GENERATOR SET PADA KRI FPB 57 CLASS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-10 | 2026-07-20 | 1 | AMAM | 56 | JC310276 38279
77 | 2026-07-29 | W311 | E25291.01100_EST. MATERIAL FOR PIPING DIAGRAM OF BILGE SYSTEM_R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-21 | 2026-07-21 | 1 | AMAM | 8 | JC310726 38262
78 | 2026-07-29 | W311 | E25410.01100_EST. MATERIAL FOR PIPING DIAGRAM OF FUEL OIL SYSTEM_R2 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-22 | 2026-07-22 | 1 | AMAM | 8 | JC310726 38271
79 | 2026-07-29 | A26AOP01 | E15620.22100_HYDRAULIC STEERING SYSTEM CONFIGURATION_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-23 | 2026-07-29 | 1 | AMAM | 40 | JC310726 38272
80 | 2026-07-29 | A26AOP01 | E12430.33100_SHAFT ARRANGEMENT_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-30 | 2026-07-31 | 1 | AMAM | 16 | JC310726 38273
81 | 2026-07-30 | W000308 | Check Piping Modelling: E13410,22100, E15421,22100, E15062,22100, Check Piping Output: E1111U-R2, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-20 | 2026-07-24 | 1 | Asi Supeni | 40 | JC300726 38245
82 | 2026-07-30 | W000308 | Check Piping Output: EP232U-R2, EP364U-R0, EP112-R2, | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-07-27 | 2026-07-31 | 1 | Asi Supeni | 40 | JC310726 38260
83 | 2026-07-30 | R41 | HULL RESISTANCE ANALYSIS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-01 | 2026-07-03 | 1 | Aditya Prayoga | 24 | JC310726 38329
84 | 2026-07-30 | M000313 | E12300.75100_R0_MAIN EQUIPMENT LIST | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-06 | 2026-07-07 | 1 | Aditya Prayoga | 16 | JC310726 38274
85 | 2026-07-30 | M000313 | E95620.91100_R0_CALCULATION OF RUDDER STOCK | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-08 | 2026-07-08 | 1 | Aditya Prayoga | 8 | JC310726 38275
86 | 2026-07-30 | M000313 | E95610.91100_R0_CALCULATION OF STEERING GEAR | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-09 | 2026-07-09 | 1 | Aditya Prayoga | 8 | JC310726 38276
87 | 2026-07-30 | M000313 | E15620.63100_R0_RUDDER STOCK AND FITTINGS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-10 | 2026-07-10 | 1 | Aditya Prayoga | 8 | JC310726 38277
88 | 2026-07-30 | M000312 | E35330.50101_R0_M000312_ATO ER PUMPS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-13 | 2026-07-13 | 1 | Aditya Prayoga | 8 | JC310726 38280
89 | 2026-07-30 | W000314 | E12300.75100_R0_MAIN EQUIPMENT LIST | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-14 | 2026-07-15 | 1 | Aditya Prayoga | 16 | JC310726 38281
90 | 2026-07-30 | W000304 | E12300.75100_R2_EST. QTY. MATERIAL OF CHOCKING RESIN FOR SHAFT BEARING | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-16 | 2026-07-16 | 1 | Aditya Prayoga | 8 | JC310726 38288
91 | 2026-07-30 | W000306 | E15721.11100_R0_ARRANGEMENT OF PROVISION CRANE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-17 | 2026-07-17 | 1 | Aditya Prayoga | 8 | JC310726 38290
92 | 2026-07-30 | M000312 | EVATEK EQUIPMENT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-01 | 2026-07-31 | 1 | Aditya Prayoga | 16 | JC310726 38282
93 | 2026-07-30 | W000306 | CHOCKING AREA PLAN | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-21 | 2026-07-21 | 1 | Aditya Prayoga | 8 | JC310726 38292
94 | 2026-07-30 | W000308 | E15721.11100_R0_ARRANGEMENT OF PROVISION CRANE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-22 | 2026-07-22 | 1 | Aditya Prayoga | 8 | JC310726 38293
95 | 2026-07-30 | M000312 | E15620.63100_R1_RUDDER STOCK AND FITTINGS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-23 | 2026-07-24 | 1 | Aditya Prayoga | 16 | JC310726 38283
96 | 2026-07-30 | M000312 | E12300.75100_R1_MAIN EQUIPMENT LIST MACHINERY PART | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-27 | 2026-07-27 | 1 | Aditya Prayoga | 8 | JC310726 38284
97 | 2026-07-30 | M000313 | E12430.33100_R0_SHAFT ARRANGEMENT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-28 | 2026-07-30 | 1 | Aditya Prayoga | 24 | JC310726 38285
98 | 2026-07-31 | W306 | LIST AND MAT. LIST TOOLS & INVENTORY MACH. PART-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-01 | 2026-07-10 | 1 | KRISDIYANTORO | 64 | JC310726 38294
99 | 2026-07-31 | W308 | REVIEW APPROVAL DRAWING RCVS-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-13 | 2026-07-17 | 1 | KRISDIYANTORO | 40 | JC310726 38295
100 | 2026-07-31 | M312 | REVISI PIPING SCHEMATIC OF EXH. GAS, FO TRANSFER & SERVICE, LO TRANSFER & SERVICE, SEA WATER COOLING, AND FO, LO, & OILY WATER DRAIN-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-20 | 2026-07-24 | 1 | KRISDIYANTORO | 40 | JC310726 38286
101 | 2026-07-31 | M312 | PIPING DIAGRAM AND MAT. LIST OF MIST PIPE & EXH. GAS SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-27 | 2026-07-31 | 1 | KRISDIYANTORO | 40 | JC310726 38287
102 | 2026-07-31 | A26AOP01 | E15293.27100-PIPE READY COMPENSATING TANK AND EMCY BLOWING SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-01 | 2026-07-03 | 1 | Miekail | 24 | JC310726 38316
103 | 2026-07-31 | A26AOP01 | E15510.27100-PIPE READY SYSTEM COMPRESSED AIR-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-06 | 2026-07-08 | 1 | Miekail | 24 | JC310726 38317
104 | 2026-07-31 | A26AOP01 | E15291.27100-PIPE READY BILGE SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-09 | 2026-07-10 | 1 | Miekail | 16 | JC310726 38318
105 | 2026-07-31 | A26AOP01 | E15240.27100-PIPE READY SW COOLING SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-13 | 2026-07-14 | 1 | Miekail | 16 | JC310726 38319
106 | 2026-07-31 | A26AOP01 | E15291.01100-PIPING DIAGRAM OF BILGE SYSTEM -R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-15 | 2026-07-17 | 1 | Miekail | 24 | JC310726 38320
107 | 2026-07-31 | A26AOP01 | E15240.01100-PIPING DIAGRAM OF SW COOLING SYSTEM -R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-20 | 2026-07-24 | 1 | Miekail | 40 | JC310726 38321
108 | 2026-07-31 | A26AOP01 | E15291.22100-EST. QTY. MATERIAL FOR PID OF SEA WATER COOLING SYSTEM-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-27 | 2026-07-28 | 1 | Miekail | 16 | JC310726 38322
109 | 2026-07-31 | A26AOP01 | E15240.22100-EST. QTY. MATERIAL FOR PID OF SEA WATER COOLING SYSTEM-R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-29 | 2026-07-31 | 1 | Miekail | 24 | JC310726 38323
110 | 2026-07-31 | A26AOP01 | E15510.27100-PIPE READY SYSTEM COMPRESSED AIR-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-02 | 2026-07-02 | 1 | Miekail | 8 | JC310726 38324
111 | 2026-07-31 | A26AOP01 | E15293.27100-PIPE READY COMPENSATING TANK AND EMCY BLOWING SYSTEM-R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-04 | 2026-07-04 | 1 | Miekail | 8 | JC310726 38326
112 | 2026-07-31 | A26AOP01 | E15291.01100-PIPING DIAGRAM OF BILGE SYSTEM -R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-18 | 2026-07-18 | 1 | Miekail | 8 | JC310726 38327
113 | 2026-07-31 | A26AOP01 | E15240.01100-PIPING DIAGRAM OF SW COOLING SYSTEM -R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-25 | 2026-07-25 | 1 | Miekail | 8 | JC310726 38328
114 | 2026-07-31 | A26AOP01 | E15620.2100 Hydraulic Steering System Configuration | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-02 | 2026-07-02 | 1 | Amam | 4 | JC310726 38339
115 | 2026-07-31 | A26AOP01 | E12430.33100 Shaft Arrangement | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-07-09 | 2026-07-09 | 1 | Amam | 3 | JC310726 38340
116 | 31 July 2026 | W304 | REVIEW DAFTAR PENGADAAN VALVE & KOMPONEN BATCH IV | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-07-27 | 2026-07-31 | 1 | AHMAD KHUNAIFI | 40 | JC010826 38347
117 | 31 July 2026 | W304 | FP - E55240.01100 - PID OF SEA WATER COOLING | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-07-23 | 2026-07-25 | 1 | AHMAD KHUNAIFI | 16 | JC010826 38348
118 | 31 July 2026 | M000312 | UPDATE SPEC. & MODELING VALVE-COMPONENT CADMATIC FOR PIPING SCHEMATIC (ALL SYSTEM) PROJECT KAPAL PHINISI | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-07-01 | 2026-07-31 | 1 | AHMAD KHUNAIFI | 80 | JC010826 38349
119 | 31 July 2026 | A26AOP01 | UPDATE SPEC. & MODELING VALVE-COMPONENT CADMATIC FOR PIPING DIAGRAM (ALL SYSTEM) PROJECT KSOT | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-07-01 | 2026-07-31 | 1 | AHMAD KHUNAIFI | 24 | JC010826 38350
120 | 31 July 2026 | W000308 | UPDATE SPEC. & MODELING VALVE-COMPONENT CADMATIC FOR PIPING DIAGRAM (ALL SYSTEM)PROJECT LPD UAE | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-07-01 | 2026-07-31 | 1 | AHMAD KHUNAIFI | 56 | JC010826 38351
121 | 31 July 2026 | W000311 | UPDATE SPEC. & MODELING VALVE-COMPONENT CADMATIC FOR PIPING DIAGRAM (ALL SYSTEM) PROJECT KSSR | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-07-01 | 2026-07-31 | 1 | AHMAD KHUNAIFI | 24 | JC010826 38352
122 | 2026-08-03 | W000305 | Check Drawing Piping Output | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-03 | 2026-08-31 | 1 | Djoko Santoso | 136 | JC070826 38568
123 | 13 August 2026 | A26AOP01 | REVIEW SPESIFIKASI TEKNIS KSOT SURVEILLANCE 20 METER & COMBAT 15 METER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 3 August 2026 | 31 August 2026 | 1 | ARDAN | 24 | JC140826 38947
124 | 13 August 2026 | GEOMARIN | SPEED POWER PREDICTION GEOMARIN | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 6 August 2026 | 31 August 2026 | 1 | ARDAN | 16 | JC140826 38948
125 | 13 August 2026 | W000314 | SPEED POWER PREDICTION KSR 20 M | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 10 August 2026 | 31 August 2026 | 1 | ARDAN | 16 | JC140826 38949
126 | 13 August 2026 | A26AOP01 | R4 - E15620.21103 - HYDRAULIC STEERING | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 12 August 2026 | 31 August 2026 | 1 | ARDAN | 24 | JC140826 38951
127 | 13 August 2026 | GEOMARIN | - MODELING DUCT - ROUTE & READY-MECHANICAL VENT SYSTEM (ALL BLOCK) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 3 August 2026 | 31 August 2026 | 1 | IRFAN | 160 | JC140826 38952
128 | 18 August 2026 | A26AOP01 | PERHITUNGAN BOUYANCY DAN BERAT KONFIGURASI TORPEDO DENGAN WARHEAD | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 12 August 2026 | 31 August 2026 | 1 | ARDAN | 8 | JC180826 39138
129 | 18 August 2026 | A26AOP01 | UPDATE MODEL TORPEDO WARHEAD | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 13 August 2026 | 31 August 2026 | 1 | ARDAN | 16 | JC180826 39139
130 | 18 August 2026 | A26AOP01 | KAJIAN TEKNIS MOBILISASI KSOT COMBAT KE JAKARTA | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 17 August 2026 | 31 August 2026 | 1 | ARDAN | 24 | JC180826 39145
131 | 2026-08-21 | W000312 | E15281.17100 - Pipe Modeling pinisi | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-03 | 2026-08-07 | 1 | MOCH YASIN | 60 | JC210826 39243
132 | 2026-08-21 | W000308 | E15412.17100 - ADD. Pipe Model system FO Service | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-10 | 2026-08-14 | 1 | MOCH YASIN | 60 | JC210826 39245
133 | 2026-08-21 | W000304 | E15040.33101 - REV. Level Gauge FO.SERV no.1, 2, 3, 4 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-17 | 2026-08-21 | 1 | MOCH YASIN | 40 | JC210826 39246
134 | 2026-08-21 | W000304 | E15410.17100 - ADD. pipe model outlet purifier to waste tank | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-24 | 2026-08-31 | 1 | MOCH YASIN | 60 | JC210826 39248
135 | 2026-08-21 | M000313 | E12000.10100 - Machinery Arrt | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-01 | 2026-08-03 | 1 | DIMAS LUTFI | 15 | JC210826 39250
136 | 2026-08-21 | M000313 | E15281.17100 - Pipe modeling scupper system | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-04 | 2026-08-07 | 1 | DIMAS LUTFI | 40 | JC210826 39251
137 | 2026-08-21 | M000313 | E11675.10100 - Arrt of bottom plug | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-10 | 2026-08-11 | 1 | DIMAS LUTFI | 20 | JC210826 39252
138 | 2026-08-21 | M000313 | E15290.17100 - Pipe modeling bilge ballast | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-12 | 2026-08-21 | 1 | DIMAS LUTFI | 80 | JC210826 39253
139 | 2026-08-21 | M000313 | E15211.17100 - Pipe modeling fire wash deck | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-24 | 2026-08-31 | 1 | DIMAS LUTFI | 70 | JC210826 39254
140 | 2026-08-21 | W000308 | E15560.27100 - Pipe Modeling & Pipe Support System Hydraulic Roro Equipment Block 223P & 213P | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-03 | 2026-08-14 | 1 | RIZKY ROMADHONI | 120 | JC210826 39257
141 | 2026-08-21 | W000308 | E15560.27100 - Pipe Modeling & Pipe Support System Hydraulic Roro Equipment Block 223S & 213S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-17 | 2026-08-21 | 1 | RIZKY ROMADHONI | 50 | JC210826 39258
142 | 2026-08-21 | W000308 | E15560.27100 - Pipe Modeling & Pipe Support System Hydraulic Roro Equipment Block 434S & 424S | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-24 | 2026-08-31 | 1 | RIZKY ROMADHONI | 70 | JC210826 39259
143 | 2026-08-21 | W000308 | E15282.27100 - Pipe Modelling Grey Water System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-03 | 2026-08-12 | 1 | SYAIFUL BACHRI | 85 | JC210826 39260
144 | 2026-08-21 | W000308 | E15161.27100 - Pipe Modelling Chilled Water System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-13 | 2026-08-21 | 1 | SYAIFUL BACHRI | 70 | JC210826 39261
145 | 2026-08-21 | W000308 | E15421.27100 - Pipe Modelling FO Service for Helicopter System | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-24 | 2026-08-31 | 1 | SYAIFUL BACHRI | 70 | JC210826 39262
146 | 2026-08-21 | W000308 | Pipe Isometric Check for ES423U-R0, EP112U-R2, EK112U-R2, EP353U-R1, EK353U-R1 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-03 | 2026-08-07 | 1 | ASI SUPENI | 50 | JC210826 39263
147 | 2026-08-21 | W000308 | Pipe Isometric Check for EP232U-R2, EK232U-R2, EP231U-R2, EK231U-R2, EP222U-R3 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-10 | 2026-08-14 | 1 | ASI SUPENI | 50 | JC210826 39264
148 | 2026-08-21 | W000308 | Pipe Isometric Check for EP222U-R3, EK222U-R3 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-17 | 2026-08-19 | 1 | ASI SUPENI | 30 | JC210826 39265
149 | 2026-08-21 | W000308 | Pipe Model Check for E15512.22100, E15531.22101 | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-20 | 2026-08-31 | 1 | ASI SUPENI | 70 | JC210826 39266
150 | 2026-08-21 | W000304 | E15330.27100 - Pipe Modelling FW Sanitary (ADD) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-03 | 2026-08-07 | 1 | ERLY PUTRI | 60 | JC210826 39267
151 | 2026-08-21 | W000304 | E15431.27100 - Pipe Modelling LO service & transfer (REVISI) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-10 | 2026-08-14 | 1 | ERLY PUTRI | 60 | JC210826 39269
152 | 2026-08-21 | W000304 | E14551.27100 - Pipe Modelling Han Iff Antena Cooling System (ADD) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-17 | 2026-08-21 | 1 | ERLY PUTRI | 60 | JC210826 39270
153 | 2026-08-21 | W000304 | E15282.27100 - Pipe Modelling Grey Water System (ADD) | 1CJ200 - Biro Desain Pengaturan Permesinan | 2026-08-24 | 2026-08-31 | 1 | ERLY PUTRI | 70 | JC210826 39271
154 | 21 August 2026 | A26AOP01 | PEMBUATAN PAPARAN PERGESERAN KSOT MENGGUNAKAN LPD | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 20 August 2026 | 31 August 2026 | 1 | ARDAN | 28 | JC260826 39442
155 | 21 August 2026 | W000304 | ESTIMASI PANJANG KABEL KONTROL RCV PENGADAAN BATCH IV | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 11 August 2026 | 12 August 2026 | 1 | AHMAD KHUNAIFI | 6 | JC260826 39443
156 | 21 August 2026 | W000304 | R5 - E25512.01100 - EST. QTY. MAT. FOR PIPING DIAGRAM OF MEDIUM PRESSURE AIR SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 11 August 2026 | 11 August 2026 | 1 | AHMAD KHUNAIFI | 4 | JC260826 39444
157 | 21 August 2026 | W000305 | UPDATE SPEC. & MODELING VALVE & COMPONENT CADMATIC FOR PIPING DIAGRAM (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 3 August 2026 | 31 August 2026 | 1 | AHMAD KHUNAIFI | 16 | JC280826 39500
158 | 21 August 2026 | W000308 | UPDATE SPEC. & MODELING VALVE & COMPONENT CADMATIC FOR PIPING DIAGRAM (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 3 August 2026 | 31 August 2026 | 1 | AHMAD KHUNAIFI | 56 | JC280826 39501
159 | 21 August 2026 | W000306 | UPDATE SPEC. & MODELING VALVE & COMPONENT CADMATIC FOR PIPING DIAGRAM (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 3 August 2026 | 31 August 2026 | 1 | AHMAD KHUNAIFI | 16 | JC280826 39502
160 | 2026-08-27 | W000308 | EVATEK VALVE BATCH 2 VENDOR KDI | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-03 | 2026-08-07 | 1 | Diar | 40 | JC280826 39508
161 | 2026-08-27 | M000312 | E25330.01100_R1_ESTIMATED MATERIAL FOR PIPING DIAGRAM OF FRESH WATER & HOT WATER SANITARY SERVICE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-10 | 2026-08-10 | 1 | Diar | 8 | JC280826 39509
162 | 2026-08-27 | M000312 | E25281.01100_R1_ESTIMATED MATERIAL FOR PIPING DIAGRAM OF DRAINAGE AND SEWAGE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-11 | 2026-08-11 | 1 | Diar | 8 | JC280826 39510
163 | 2026-08-27 | M000312 | E25240.01101_R1_ESTIMATED MATERIAL FOR PIPING DIAGRAM OF SEA WATER SANITARY SERVICE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-12 | 2026-08-12 | 1 | Diar | 4 | JC280826 39511
164 | 2026-08-27 | M000312 | E15240.22101_R1_PIPING DIAGRAM OF SEA WATER SANITARY SERVICE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-12 | 2026-08-12 | 1 | Diar | 4 | JC280826 39512
165 | 2026-08-27 | M000312 | E15281.22100_R1_PIPING DIAGRAM OF DRAINAGE AND SEWAGE SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-13 | 2026-08-13 | 1 | Diar | 8 | JC280826 39516
166 | 2026-08-27 | M000312 | E15330.22100_R1_PIPING DIAGRAM OF FRESH WATER & HOT WATER SANITARY SERVICE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-14 | 2026-08-31 | 1 | Diar | 16 | JC280826 39517
167 | 2026-08-27 | W000304 | E22000.01101_R1_EST. MAT. OF ADDITIONAL MATERIAL FOR ORDINARY SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-18 | 2026-08-18 | 1 | Diar | 2 | JC280826 39518
168 | 2026-08-27 | W000304 | E25331.01100_A2_ESTIMATED MATERIAL FOR HOT WATER SANITARY | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-18 | 2026-08-18 | 1 | Diar | 6 | JC280826 39519
169 | 2026-08-27 | W000308 | E25280.01100_R3_ESTIMATED MATERIAL FOR INSIDE SCUPPER & DRAINAGE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-19 | 2026-08-19 | 1 | Diar | 8 | JC280826 39520
170 | 2026-08-27 | M000312 | E25330.01100_R2_ESTIMATED MATERIAL FOR PIPING DIAGRAM OF FRESH WATER & HOT WATER SANITARY SERVICE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-20 | 2026-08-21 | 1 | Diar | 16 | JC280826 39521
171 | 2026-08-27 | W000304 | E22000.01101_R2_EST. MAT. OF ADDITIONAL MATERIAL FOR ORDINARY SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-24 | 2026-08-24 | 1 | Diar | 2 | JC280826 39522
172 | 2026-08-27 | W000308 | E15280.22100_R3_PID OF INSIDE SCUPPER & DRAINAGE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-24 | 2026-08-31 | 1 | Diar | 30 | JC280826 39523
173 | 27 August 2026 | M000312 | UPDATE SPEC & MODELING VALVE & COMPONENT CADMATIC FOR PIPING SCHEMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 3 August 2026 | 31 August 2026 | 1 | AHMAD KHUNAIFI | 56 | JC280826 39503
174 | 27 August 2026 | A26AOP01 | UPDATE MODEL VALVE, INSTRUMENT & COMPONENT CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 3 August 2026 | 31 August 2026 | 1 | AHMAD KHUNAIFI | 24 | JC280826 39506
175 | 27 August 2026 | M000313 | INPUT SPEC., PIPE LINE PID & MODELING CADMATIC (ALL SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 27 August 2026 | 31 August 2026 | 1 | AHMAD KHUNAIFI | 24 | JC280826 39505
176 | 27 August 2026 | W000304 | FP - E55930.22100 - PIPING DIAGRAM OF OIL WASTE TREATMENT AND DISPOSAL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 August 2026 | 15 August 2026 | 1 | SATRIO | 30 | JC280826 39524
177 | 27 August 2026 | W000304 | FP - E55931.22100 - PIPING DIAGRAM OF OILY BILGE SEPARATOR SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 August 2026 | 15 August 2026 | 1 | SATRIO | 30 | JC280826 39525
178 | 27 August 2026 | W000304 | FP - E53410.22100 - PIPING DIAGRAM OF FO, LO, AND OILY WATER DRAIN SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 August 2026 | 15 August 2026 | 1 | SATRIO | 30 | JC280826 39526
179 | 27 August 2026 | W000304 | FP - E55261.22100 - PIPING DIAGRAM OF SCUPPER AND DECK DRAINS | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 1 August 2026 | 15 August 2026 | 1 | SATRIO | 30 | JC280826 39527
180 | 27 August 2026 | M000313 | R0 - E15211.08100 - SCHEMATIC DIAGRAM OF FIRE MAIN & WAS DECK SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 17 August 2026 | 31 August 2026 | 1 | SATRIO | 35 | JC280826 39528
181 | 27 August 2026 | M000313 | R0 - E15513.08100 - SCHEMATIC DIAGRAM OF LOW PRESSURE AIR SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 17 August 2026 | 31 August 2026 | 1 | SATRIO | 35 | JC280826 39529
182 | 27 August 2026 | M000313 | R0 - E25211.01100 - EST. QTY. MAT. FOR PID OF FIRE MAIN & WAS DECK SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 17 August 2026 | 31 August 2026 | 1 | SATRIO | 20 | JC280826 39530
183 | 27 August 2026 | M000313 | R0 - E25513.01100 - EST. QTY. MAT. FOR PID OF LOW PRESSURE AIR SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 17 August 2026 | 31 August 2026 | 1 | SATRIO | 20 | JC280826 39531
185 | 28 August 2026 | M000313 | R0 - E15292.08100 - PIPING SCHEMATIC OF BALLAST AND BILGE SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 10 August 2026 | 14 August 2026 | 1 | RAFIKA |  | JC280826 39532
186 | 28 August 2026 | M000313 | R0 - E15292.08100 - EST. QTY. MAT. FOR PIPING SCHEMATIC OF BALLAST AND BILGE SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 17 August 2026 | 21 August 2026 | 1 | RAFIKA |  | JC280826 39533
186 | 28 August 2026 | W306-307 | R5 - E15292.22101 - PIPING DIAGRAM OF BALLAST AND DOCKWELL SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 3 August 2026 | 7 August 2026 | 1 | RAFIKA |  | JC280826 39535
187 | 28 August 2026 | A26AOP01 | ARRANGEMENT OF KSOT IN LPD DOCKWELL | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 24 August 2026 | 31 August 2026 | 1 | ARDAN | 40 | JC280826 39536
188 | 28 August 2026 | A26AOP01 | EST. MAT. OF KSOT IN LPD DOCKWELL | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 24 August 2026 | 31 August 2026 | 1 | ARDAN | 16 | JC280826 39537
189 | 28 August 2026 | M000312 | R0 - E1211C.18100 - ARR'T OF VENTILATION IN BLOCK 211C - R0 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 3 August 2026 | 7 August 2026 | 1 | FIRMAN | 40 | JC280826 39541
190 | 28 August 2026 | M000312 | R0 - ED112C.48100 - VENT SKETCHES IN BLOCK 112C-R0 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 10 August 2026 | 11 August 2026 | 1 | FIRMAN | 16 | JC280826 39545
191 | 28 August 2026 | M000312 | R0 - ED122C.48100 - VENT SKETCHES IN BLOCK 122C-R0 | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 12 August 2026 | 13 August 2026 | 1 | FIRMAN | 16 | JC280826 39546
192 | 28 August 2026 | M000313 | R0 - E15281.08100 - PIPING SCHEMATIC OF SEWAGE SYSTEM | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 24 August 2026 | 27 August 2026 | 1 | RAFIKA |  | JC280826 39547
193 | 28 August 2026 | M000313 | R0 - E15261.08100 - PIPING SCHEMATIC OF DECK SCUPPER | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 28 August 2026 | 31 August 2026 | 1 | RAFIKA |  | JC280826 39548
194 | 28 August 2026 | W000308 | R2 - E95211.91100 - TECHNICAL REPORT OF FIRE EXTINGUISHING SYSTEM (SPRINKLER AND WATER SPRAY SYSTEM) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 14 August 2026 | 25 August 2026 | 1 | FIRMAN | 64 | JC290826 39591
195 | 28 August 2026 | M000312 | R0 - ED511C.48100 - VENT SKETCHES IN BLOCK 511 C | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 26 August 2026 | 27 August 2026 | 1 | FIRMAN | 16 | JC290826 39592
196 | 28 August 2026 | W306-307 | R1 - E1212P.12100 - PIPING ARRANGEMENT IN E/R DECK BLOCK : 212 P | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 3 August 2026 | 7 August 2026 | 1 | FARIS NOVARIANSYAH | 35 | JC290826 39593
197 | 28 August 2026 | M000312 | R0 - ED521C.48100 - VENT SKETCHES IN BLOCK 521 C | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 28 August 2026 | 31 August 2026 | 1 | FIRMAN | 16 | JC290826 39594
198 | 28 August 2026 | W306-307 | R1 - E1212S.12100 - PIPING ARRANGEMENT IN E/R DECK BLOCK : 212 S | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 10 August 2026 | 14 August 2026 | 1 | FARIS NOVARIANSYAH | 35 | JC290826 39595
199 | 28 August 2026 | W000308 | R0 - MODEL - DRAWING ACCUMULATOR INTERCEPTOR FOR HYD. CARGO HANDLING | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 17 August 2026 | 17 August 2026 | 1 | FARIS NOVARIANSYAH | 7 | JC290826 39596
200 | 28 August 2026 | W000308 | DRAWING RHIB DAVIR CONTROL FOR HYD. CARGO HANDLING | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 18 August 2026 | 18 August 2026 | 1 | FARIS NOVARIANSYAH | 7 | JC290826 39597
201 | 28 August 2026 | W000308 | DRAWING SIDE RAMP P/S STANDBY VALVE FOR HYD CARGO HANDLING | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 20 August 2026 | 20 August 2026 | 1 | FARIS NOVARIANSYAH | 7 | JC290826 39598
202 | 28 August 2026 | W000308 | DRAWING TURN TABLE BLOCK STANBY VALVE FOR HYD CARGO HANDLING | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 21 August 2026 | 21 August 2026 | 1 | FARIS NOVARIANSYAH | 7 | JC290826 39599
203 | 28 August 2026 | W000308 | DRAWING WINDLASS ANCHOR P/S FOR HYD. MACHINERY INCLUDE CONTROL VALVE (FDM08AC3) | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 26 August 2026 | 27 August 2026 | 1 | FARIS NOVARIANSYAH | 14 | JC290826 39600
204 | 28 August 2026 | W000308 | DRAWING SNATCH WINCH FOR HYD. MACHINERY | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 31 August 2026 | 2026-09-01 | 1 | FARIS NOVARIANSYAH | 14 | JC290826 39601
205 | 2026-08-31 | A26AOP01 | E12430.33100_SHAFT ARRANGEMENT_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-03 | 2026-08-05 | 1 | Amam | 24 | JC010926 39757
206 | 2026-08-31 | A26AOP01 | E15510.21102_COMPENSATING COMPRESS PROFF TANK_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-06 | 2026-08-07 | 1 | Amam | 16 | JC010926 39758
207 | 2026-08-31 | W306-W307 | E15320.25100_RECOMMENDABLE OF WATER COOLANT_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-10 | 2026-08-11 | 1 | Amam | 16 | JC010926 39759
208 | 2026-08-31 | M313 | E15330.08100_PIPING SCHEMATIC OF FRESH WATER SANITARY SERVICE_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-12 | 2026-08-17 | 1 | Amam | 32 | JC310826 39712
209 | 2026-08-31 | M313 | E15331.08100_PIPING SCHEMATIC OF HOT WATER SANITARY SERVICE_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-18 | 2026-08-21 | 1 | Amam | 32 | JC310826 39713
210 | 2026-08-31 | M313 | E15240.08101_PIPING SCHEMATIC OF SEA WATER SANITARY SERVICE_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-24 | 2026-08-27 | 1 | Amam | 32 | JC310826 39714
211 | 2026-08-31 | M313 | E12590.08100_PIPING SCHEMATIC OF EXHAUST GAS SYSTEM_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-28 | 2026-08-31 | 1 | Amam | 16 | JC310826 39716
212 | 2026-08-31 | A26AOP01 | E15620.22100_HYDRAULIC STEERING SYSTEM CONFIGURATION_R3 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-20 | 2026-08-20 | 1 | Amam | 4 | JC010926 39760
213 | 2026-08-31 | M312 | PIPING DIAGRAM OF FO TRANSFER & SERVICE, LO TRANSFER & SERVICE, SEA WATER COOLING, AND FO, LO, & OILY WATER DRAIN _R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-03 | 2026-08-21 | 1 | Krisdiyantoro | 120 | JC310826 39733
214 | 2026-08-31 | W304 | EVATEK TOOLS & INVENTORY, VENDOR CV HASNA MULIA JAYA, CV AJK, DAN CV JAYA LAKSA_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-24 | 2026-08-31 | 1 | Krisdiyantoro | 48 | JC310826 39736
215 | 2026-08-31 | W000306 | E95000.92102_R0_PRODUCTION PLAN WEIGHT CALCULATION (KB04) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-03 | 2026-08-04 | 1 | Aditya Prayoga | 16 | JC010926 39761
216 | 2026-08-31 | M000312 | E35510.50100_R0_M000312_ATO COMPRESSED AIR SYSTEM | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-05 | 2026-08-05 | 1 | Aditya Prayoga | 8 | JC310826 39734
217 | 2026-08-31 | M000313 | E95620.91100_R0_CALCULATION OF RUDDER STOCK | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-10 | 2026-08-10 | 1 | Aditya Prayoga | 8 | JC310826 39721
218 | 2026-08-31 | W000304 | ANALYSIS OF WINDLASS SUPPORTING STRUCTURE | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-11 | 2026-08-12 | 1 | Aditya Prayoga | 16 | JC310826 39738
219 | 2026-08-31 | W000306 | E11672.22100_R0_PIPING DIAGRAM OF HYDRAULIC OF WATER TIGHT SLIDING DOOR | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-13 | 2026-08-14 | 1 | Aditya Prayoga | 16 | JC010926 39762
220 | 2026-08-31 | W000306 | E21672.01100_R0_MAT LIST PIPING DIAGRAM HYD WATER TIGHT SLIDING DOOR | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-18 | 2026-08-18 | 1 | Aditya Prayoga | 8 | JC010926 39763
221 | 2026-08-31 | M000312 | M000312_E35621.50100_R0_ATO RUDDER STOCK & FITTINGS | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-19 | 2026-08-19 | 1 | Aditya Prayoga | 8 | JC310826 39735
222 | 2026-08-31 | W000308 | E95000.92102_R0_PRODUCTION PLAN WEIGHT CALCULATION (KB04) | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-20 | 2026-08-21 | 1 | Aditya Prayoga | 16 | JC310826 39742
223 | 2026-08-31 | M000313 | EVATEK EQUIPMENT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-01 | 2026-08-31 | 1 | Aditya Prayoga | 48 | JC310826 39723
224 | 2026-08-31 | A26AOP01 | E15291.27100_PIPE MODEL AND READY BILGE SYSTEM_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-03 | 2026-08-04 | 1 | Miekail | 16 | JC010926 39764
225 | 2026-08-31 | A26AOP01 | EVATEK HYDRAULIC VERTICAL THRUSTER | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-05 | 2026-08-05 | 1 | Miekail | 8 | JC010926 39765
226 | 2026-08-31 | A26AOP01 | EVATEK HYDRAULIC ANCHOR WINCH | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-06 | 2026-08-06 | 1 | Miekail | 8 | JC010926 39766
227 | 2026-08-31 | A26AOP01 | EVATEK HYDRAULIC BUOY WINCH & HYDRO GENERATOR | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-10 | 2026-08-10 | 1 | Miekail | 8 | JC010926 39768
228 | 2026-08-31 | A26AOP01 | EVATEK HYDRAULIC POWER UNIT | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-11 | 2026-08-11 | 1 | Miekail | 8 | JC010926 39769
229 | 2026-08-31 | A26AOP01 | E15240.27100_PIPE MODEL AND SEA WATER COOLING SYSTEM_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-12 | 2026-08-14 | 1 | Miekail | 24 | JC010926 39770
230 | 2026-08-31 | A26AOP01 | E15293.27100_PIPE MODEL AND READY COMPENSATING TANK AND EMCY BLOWING SYSTEM_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-18 | 2026-08-19 | 1 | Miekail | 16 | JC010926 39771
231 | 2026-08-31 | A26AOP01 | E15510.27100_PIPE MODEL AND READY COMPRESSED AIR SYSTEM_R1 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-20 | 2026-08-26 | 1 | Miekail | 24 | JC010926 39772
233 | 2026-08-31 | M000311 | FAT HYDRAULIC SYSTEM FOR CANISTER MISSILE LAUNCHER | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-27 | 2026-08-28 | 1 | Miekail | 16 | JC310826 39743
234 | 2026-08-31 | M000314 | E15060.22100_PID OF AIR VENT AND SOUNDING_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-31 | 2026-08-31 | 1 | Miekail | 8 | JC310826 39744
235 | 2026-08-31 | M000313 | E15240.22100_PIPING DIAGRAM OF SW COOLING SYSTEM_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-01 | 2026-08-01 | 1 | Miekail | 6 | JC310826 39724
236 | 2026-08-31 | M000314 | E15060.22100_PID OF AIR VENT AND SOUNDING_R0 | 1CJ100 - Biro Desain Sistem Permesinan Propulsi | 2026-08-15 | 2026-08-15 | 1 | Miekail | 6 | JC310826 39745
184 | 27 August 2026 | M000313 | R0 - E13410.08100 - SCHEMATIC DIAGRAM OF FO, LO, AND OILY WATER DRAIN | 1CJ300 - Biro Desain Sistem HVAC Miscellaneous | 2026-09-01 | 2026-09-12 | 1 | SATRIO | 30 | JC090926 40238

## Dept. EO
wp | [9 empty] | Diisi Planner
No | Tanggal Permintaan JC ditulis | Project | Task Name | Work Center | Schedule Start date | Schedule End date | Total Personil yang mengerjakan | PIC | JO | Kode Job Card | Keterangan | Planner
| DD / MM / YYYY | KODE PROYEK | REVISI KE - NO DOC / DWG - DESC PEKERJAAN | KODE BIRO - DESC BIRO | DD / MM / YYYY | DD / MM / YYYY | (DALAM ANGKA) | (NAMA) | (ANGKA) | JC010624 0001 |  | 023066812-Hashfi Moch Adam
CONTOH
1 | 2024-06-20 | W000308 | E12521.25200 - ONE LINE DIAGRAM OF PROPULSION CONTROL SYSTEM | 1CL200 - Biro Desain Sistem Kontrol Otomasi | 2024-06-05 | 2024-06-28 | 1 |  |  | JC200624 2617 |  | 023066812-Hashfi Moch Adam
1 | 2025-03-03 | W000304 | Cek Wiring Diagram of Power Distribution 220V System | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-03 | 2025-03-07 | 1 | Hari |  | JC040325 15901
2 | 2025-03-03 | W000304 | Cek Wiring diagram Power Distribution 24V system | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-10 | 2025-03-14 | 1 | Hari |  | JC040325 15932
3 | 2025-03-03 | W000304 | Cek Wiring diagram Mechanical Ventilation system | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-17 | 2025-03-21 | 1 | Hari |  | JC040325 15933
4 | 2025-03-03 | W000304 | Evaluasi maker approval drawing MSB & MCC | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-24 | 2025-03-27 | 1 | Hari |  | JC040325 15934
5 | 2025-03-03 | W000304 | Cek Wiring diagram Oily Bilge/Sludge system | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-03 | 2025-03-05 | 1 | priyono |  | JC040325 15927
6 | 2025-03-03 | W000304 | Cek Wiring diagram Fresh Water system | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-06 | 2025-03-10 | 1 | priyono |  | JC040325 15936
7 | 2025-03-03 | W000304 | Cek Install MCW block 642S, 624P, 652P, 652S, 521P, | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-11 | 2025-03-27 | 1 | priyono |  | JC040325 15935
8 | 2025-03-03 | W000304 | Cek Wiring Diagram of reverse osmosis System | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-03 | 2025-03-05 | 1 | rendra |  | JC040325 15928
9 | 2025-03-03 | W000304 | Cek Wiring Diagram of STP System | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-06 | 2025-03-10 | 1 | rendra |  | JC040325 15930
10 | 2025-03-03 | W000304 | Cek Install MCW block 541S, 532P | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-11 | 2025-03-21 | 1 | rendra |  | JC040325 15877
11 | 2025-03-03 | W000304 | Evatek lighting Wooshin | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-24 | 2025-03-27 | 1 | rendra |  | JC040325 15878
12 | 2025-03-03 | W000304 | Add. Install MCW degaussing system block 414P | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-03 | 2025-03-07 | 1 | Noval |  | JC040325 15929
13 | 2025-03-03 | W000304 | Add. Install MCW degaussing system block 414S | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-10 | 2025-03-14 | 1 | Noval |  | JC040325 15880
14 | 2025-03-03 | W000304 | Add. Install MCW degaussing system block 424P | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-17 | 2025-03-21 | 1 | Noval |  | JC040325 15881
15 | 2025-03-03 | W000304 | Add. Install MCW degaussing system block 424S | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-24 | 2025-03-27 | 1 | Noval |  | JC040325 15882
16 | 2025-03-03 | W000304 | Add. Install MCW degaussing system block 434P | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-03 | 2025-03-07 | 1 | Yogi |  | JC040325 15931
17 | 2025-03-03 | W000304 | Add. Install MCW degaussing system block 434S | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-10 | 2025-03-14 | 1 | Yogi |  | JC040325 15883
18 | 2025-03-03 | W000304 | Add. Install MCW degaussing system block 214P | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-17 | 2025-03-21 | 1 | Yogi |  | JC040325 15884
19 | 2025-03-03 | W000304 | Add. Install MCW degaussing system block 214S | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-24 | 2025-03-27 | 1 | Yogi |  | JC040325 15886
20 | 2025-03-03 | W000304 | Cek Install MCW block 532S, 542S, 532P, 532S, 523P, 523S, 533P, 533S, 524S, 521S | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-03 | 2025-03-27 | 1 | Adi |  | JC040325 15887
21 | 2025-03-03 | W000308 | Wiring diagram sea water cooling system | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-03 | 2025-03-07 | 1 | Aldo |  | JC030325 15836
22 | 2025-03-03 | W000308 | Wiring diagram Fresh water cooling system | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-10 | 2025-03-14 | 1 | Aldo |  | JC040325 15937
23 | 2025-03-03 | W000308 | Wiring diagram Lubricating Oil system | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-17 | 2025-03-21 | 1 | Aldo |  | JC040325 15938
24 | 2025-03-03 | W000308 | Wiring diagram Fuel Oil system | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-03 | 2025-03-07 | 1 | Aldi |  | JC040325 15939
25 | 2025-03-03 | W000308 | Wiring diagram Bilge/sludge oil system | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-10 | 2025-03-14 | 1 | Aldi |  | JC040325 15940
26 | 2025-03-03 | W000308 | Wiring diagram ballast system | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-17 | 2025-03-21 | 1 | Aldi |  | JC040325 15941
27 | 2025-03-03 | W000308 | Evatek MSB set TTS | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-24 | 2025-03-27 | 2 | Aldo, Aldi |  | JC240325 16970
28 | 2025-03-03 | W000304 | EL144S.31200 INST. DWG. OF ELECT. & ELECTRO. EQUIP. SEAT 2 DK_BLOCK : 144 (S) TR4 (S) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-03-04 | 2025-03-10 | 1 | CANDRA |  | JC240325 16963
29 | 2025-03-03 | W000304 | EL414S.31200 INST. DWG. OF ELECT. & ELECTRO. EQUIP. SEAT 2 DK_BLK : 414 (P) AP3 (S) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-03-04 | 2025-03-10 | 1 | ALAM |  | JC240325 16964
30 | 2025-03-03 | W000304 | EL224S.31200 INST. DWG. OF ELECT. & ELECTRO. EQUIP. SEAT 2 DK_BLK : 224 (S) ATR4 (S) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-03-04 | 2025-03-10 | 1 | REGINA |  | JC240325 16965
31 | 2025-03-03 | W000304 | EL214P.31200 INST. DWG. OF ELECT. & ELECTRO. EQUIP. SEAT 2 DK_BLK : 214 (P) ATR5 (P) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-03-11 | 2025-03-17 | 1 | CANDRA |  | JC240325 16966
32 | 2025-03-03 | W000304 | EL214S.31200 INST. DWG. OF ELECT. & ELECTRO. EQUIP. SEAT 2 DK_BLK : 214 (S) ATR5 (S) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-03-18 | 2025-03-24 | 1 | ALAM |  | JC240325 16967
33 | 2025-03-03 | W000304 | WIRING DIAGRAM OF RCV (FOR FO TRANSFER & OVERFLOW, OILY BILGE, DEWATERING SYSTEM, BALLAST SYSTEM, COOL SEA WATER SYSTEM ) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-03-03 | 2025-03-10 | 1 | RIANTO |  | JC240325 16968
34 | 2025-03-04 | W000304 | E14391.27300 - WIRING DIAGRAM OF CCTV (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-03-03 | 2025-03-10 | 1 | nisa |  | JC040325 15943
35 | 2025-03-04 | W000308 | E14201.25300-ONE LINE DIAGRAM OF IBS | 1CL400 - Biro Desain Sistem Elektronika | 2025-03-03 | 2025-03-10 | 1 | azis |  | JC040325 15945
36 | 2025-03-04 | W000304 | E14321.27300 - WIRING DIAGRAM OF AUTOMATIC EXCHANGE TELEPHONE (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-03-03 | 2025-03-10 | 1 | ferry |  | JC040325 15944
37 | 2025-03-04 | W000304 | ARRANGEMENT OF INTEGRATED PLATFORM MANAGEMENT SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-03-11 | 2025-03-17 | 1 | RIANTO |  | JC040325 15946
38 | 2025-03-04 | W000304 | ARRANGEMENT OF ACTIVE STABILIZING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-03-17 | 2025-03-24 | 1 | RIANTO |  | JC040325 15947
39 | 2025-03-04 | W000304 | CABLE ROUTING OF ACTIVE STABILIZING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-03-24 | 2025-03-28 | 1 | RIANTO |  | JC040325 15948
40 | 2025-03-04 | W000304 | CABLE ROUTING OF AVIATION FUEL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-03-11 | 2025-03-18 | 1 | ALAM |  | JC040325 15949
41 | 2025-03-04 | W000304 | CABLE ROUTING OF SERVICE AND WORKING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-03-25 | 2025-03-29 | 1 | ALAM |  | JC040325 15950
42 | 2025-03-04 | W000304 | ROUTING & WIRING DIAGRAM OF FIXED GAS FIRE EXTINGUISHING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-03-17 | 2025-03-28 | 1 | CANDRA |  | JC040325 15951
43 | 2025-03-04 | W000308 | REVISI E14930.16200 - ARRANGEMENT OF LOCAL AREA NETWORK | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-03-11 | 2025-03-17 | 1 | REGINA |  | JC040325 15954
44 | 2025-03-04 | W000304 | CABLE ROUTING OF TANK LEVEL & DRAUGHT INDICATING | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-03-18 | 2025-03-24 | 1 | REGINA |  | JC040325 15952
45 | 2025-03-04 | W000304 | CABLE ROUTING OF MARINE GROWTH PREVENTION SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-03-24 | 2025-03-28 | 1 | REGINA |  | JC040325 15953
46 | 2025-03-11 | W000304 | E14391.27300 - WIRING DIAGRAM OF CCTV (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-03-11 | 2025-03-18 | 1 | nisa |  | JC110325 16407
47 | 2025-03-11 | W000304 | LAYOUT BRIDGE | 1CL400 - Biro Desain Sistem Elektronika | 2025-03-11 | 2025-03-18 | 1 | azis |  | JC110325 16411
48 | 2025-03-11 | W000304 | E14321.27300 - WIRING DIAGRAM OF AUTOMATIC EXCHANGE TELEPHONE (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-03-11 | 2025-03-18 | 1 | ferry |  | JC110325 16412
49 | 2025-03-19 | W000304 | E14391.16300 - ARR'T. OF CCTV (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-03-19 | 2025-03-29 | 1 | nisa |  | JC190325 16773
50 | 2025-03-19 | W000304 | E14263.16300 - ARRANGEMENT OF NAVIGATION RADAR | 1CL400 - Biro Desain Sistem Elektronika | 2025-03-19 | 2025-03-29 | 1 | azis |  | JC190325 16775
51 | 2025-03-19 | W000304 | E14321.16300 - ARR'T. OF AUTOMATIC EXCHANGE TELEPHONE (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-03-19 | 2025-03-29 | 1 | ferry |  | JC190325 16778
52 | 2025-03-26 | W000304 | REV.1 ONE LINE DIAGRAM AC SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-28 | 2025-04-11 | 1 | Hari | 48 | JC270325 17106
53 | 2025-03-26 | W000304 | Cek ARR'T OF ELECTRIC MECHANICAL VENT. FAN SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-28 | 2025-04-11 | 1 | PRIYONO | 48 | JC270325 17109
54 | 2025-03-26 | W000304 | ESTIMASI PANJANG KABEL | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-28 | 2025-04-11 | 1 | YOGI |  | JC270325 17110
55 | 2025-03-26 | W000304 | ARR'T OF ELECTRIC MOORING AND TOWING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-28 | 2025-04-11 | 1 | NOVAL | 48 | JC270325 17111
56 | 2025-03-26 | W000304 | REV. 3D MODEL ELECTRIC EQUIPMENT | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-28 | 2025-04-11 | 1 | ADI | 48 | JC270325 17112
57 | 2025-03-26 | W000304 | ESTIMASI MATERIAL MCT | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-28 | 2025-04-11 | 2 | ALDI, RENDRA | 48 | JC270325 17113
58 | 2025-03-26 | W000308 | WIRING DIAGRAM OF FRESH WATER SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-03-28 | 2025-04-11 | 1 | ALDO | 48 | JC270325 17114
2025-04-01
59 | 2025-04-07 | W000305 | WIRING DIAGRAM OF SERVICE AND WORKING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-04-07 | 2025-04-14 | 1 | ALAM |  | JC070425 17293
60 | 2025-04-07 | W000305 | ROUTING & WIRING DIAGRAM OF POWER MANAGEMENT SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-04-14 | 2025-04-21 | 1 | ALAM |  | JC070425 17295
61 | 2025-04-07 | W000305 | ROUTING & WIRING DIAGRAM OF IMPRESSED CURRENT CATHODIC PROTECTION | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-04-21 | 2025-04-28 | 1 | ALAM |  | JC070425 17297
62 | 2025-04-07 | W000305 | ROUTING & WIRING DIAGRAM OF AMMUNITION ELEVATOR | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-04-29 | 17-May-25 | 1 | ALAM |  | JC070425 17320
63 | 2025-04-07 | W000305 | WIRING DIAGRAM OF MARINE GROWTH PREVENTION SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-04-07 | 2025-04-12 | 1 | REGINA |  | JC070425 17322
64 | 2025-04-07 | W000305 | ROUTING & WIRING DIAGRAM OF HELICOPTER HANGAR DOOR | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-04-14 | 2025-04-25 | 1 | REGINA |  | JC070425 17323
65 | 2025-04-07 | W000305 | ROUTING & WIRING DIAGRAM OF ELEVATORS, SHIP | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-04-25 | 5-May-25 | 2 | REGINA |  | JC070425 17324
66 | 2025-04-07 | W000305 | ROUTING & WIRING DIAGRAM OF STEERING GEAR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 5-May-25 | 23-May-25 | 1 | REGINA |  | JC070425 17325
67 | 2025-04-07 | W000305 | ROUTING & WIRING DIAGRAM OF INTEGRATED PLATFORM MANAGEMENT SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-04-07 | 9-May-25 | 1 | CANDRA |  | JC070425 17326
68 | 2025-04-07 | W000305 | WIRING DIAGRAM OF ACTIVE STABILIZING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-04-07 | 2025-04-12 | 1 | RIANTO |  | JC070425 17327
69 | 2025-04-07 | W000305 | CABLE RE-ROUTING OF PROPULSION CONTROL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-04-14 | 2025-04-28 | 1 | RIANTO |  | JC070425 17328
70 | 2025-04-07 | W000305 | E14391.25300 - ONE LINE DIAGRAM OF CCTV (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-04-07 | 2025-04-14 | 1 | nisa |  | JC080425 17470
71 | 2025-04-07 | W000305 | E16254.25300-ONE LINE DIAGRAM OF WINDOW WIPPERS AND CLEAR VIEW SCREEN | 1CL400 - Biro Desain Sistem Elektronika | 2025-04-07 | 2025-04-14 | 1 | azis |  | JC090425 17483
72 | 2025-04-07 | W000305 | E14321.25300 -ONE LINE DIAGRAM OF AUTOMATIC EXCHANGE TELEPHONE (rev.2) | 1CL400 - Biro Desain Sistem Elektronika | 2025-04-07 | 2025-04-14 | 1 | ferry |  | JC080425 17474
73 | 2025-04-08 | W000305 | REVIEW CABLE EMC ZONE | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-04-14 | 2025-04-17 | 1 | Hari |  | JC090425 17481
74 | 2025-04-08 | W000305 | UPDATE DIAGRAM 220V SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-04-21 | 2025-04-25 | 1 | Hari |  | JC090425 17482
75 | 2025-04-08 | W000305 | CEK WIRING DIAGRAM BALLAST SYSTEM, & AIR CRAFT SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-04-28 | 2025-05-02 | 1 | Hari |  | JC090425 17507
76 | 2025-04-08 | W000305 | CEK WIRING DIAGRAM WORKSHOP EQ'T, MOORING & TOWING, ACCOMODATION LADDER & GALLEY EQ'T SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-04-14 | 2025-05-02 | 1 | PRIYONO |  | JC090425 17508
77 | 2025-04-08 | W000305 | DATA LIST CABLE IN MCT | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-04-14 | 2025-05-02 | 1 | RENDRA |  | JC090425 17509
78 | 2025-04-08 | W000305 | ARR'T MODULE MCT | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-04-14 | 2025-05-02 | 2 | ALDI, ALDO |  | JC090425 17510
79 | 2025-04-08 | W000305 | RE-ROUTING CABLE POWER SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-04-14 | 2025-05-02 | 1 | YOGI |  | JC090425 17513
80 | 2025-04-08 | W000305 | ADD. MCW DEGAUSSING BLOCK 541P, 541S, 155P | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-04-14 | 2025-05-02 | 1 | NOVAL |  | JC090425 17514
81 | 2025-04-08 | W000305 | TYPICAL ELECTRIC EQ'T SEAT | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-04-14 | 2025-04-25 | 1 | ADI |  | JC090425 17515
82 | 2025-04-08 | W000305 | ESTIMASI MCT FRAME EMC | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-04-28 | 2025-05-02 | 1 | ADI |  | JC090425 17516
83 | 2025-04-15 | W000304 | E14391.16300 - ARR'T. OF CCTV(rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-04-15 | 2025-04-22 | 1 | nisa |  | JC150425 17943
84 | 2025-04-15 | W000305 | E14263.16300-ARR'T. OF NAVIGATION RADAR (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-04-15 | 2025-04-22 | 1 | azis |  | JC150425 17944
85 | 2025-04-15 | W000304 | E14321.16300 -ARR'T. OF AUTOMATIC EXCHANGE TELEPHONE (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-04-15 | 2025-04-22 | 1 | ferry |  | JC150425 17945
86 | 2025-04-23 | W000304 | E14263.16300-Cadmatic ARR'T. OF NAVIGATION RADAR (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-04-23 | 2025-04-30 | 1 | nisa |  | JC230425 18291
87 | 2025-04-23 | W000304 | E14201.27300-WIRING. OF NAVIGATION RADAR (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-04-23 | 2025-04-30 | 1 | azis |  | JC230425 18292
88 | 2025-04-23 | W000308 | E14200.16303 -ARR'T. OF CHART CONSOLE | 1CL400 - Biro Desain Sistem Elektronika | 2025-04-23 | 2025-04-30 | 1 | ferry |  | JC230425 18293
2025-05-01
89 | 2025-04-30 | W000305 | ARR'T MODULE MCT | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-05-05 | 2025-05-23 | 2 | ALDI, ALDO |  | JC050525 18960
90 | 2025-04-30 | W000306 | EVATEK LIGHTING FIXTURES HAIXING | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-05-26 | 2025-05-30 | 1 | ALDI |  | JC050525 18961
91 | 2025-04-30 | W000308 | EVATEK MSB SET TTS | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-05-26 | 2025-05-30 | 1 | ALDO |  | JC050525 18962
92 | 2025-04-30 | W000305 | REVISI ARR'T PD 440V & 115V | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-05-05 | 2025-05-09 | 1 | YOGI |  | JC020525 18716
93 | 2025-04-30 | W000305 | KB03 | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-05-13 | 2025-05-16 | 1 | YOGI |  | JC020525 18718
94 | 2025-04-30 | W000305 | CEK INSTALL MCW DEGAUSSING BLOCK 423P, 423S, 213P, 213S, 223S,434P, 434S,214P, 214S, 2224P | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-05-05 | 2025-05-30 | 1 | ADI |  | JC020525 18720
95 | 2025-04-30 | W000305 | FUNCTIONAL DESIGN DESCRIPTION (FDS) FOR THE INDIVIDUAL SHIP SYSTEMS FOR IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-04-29 | 28-May-25 | 1 | RIANTO |  | JC300425 18668
96 | 2025-04-30 | W000305 | DATA LIST CABLE IN MCT | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-05-05 | 2025-05-23 | 1 | RENDRA |  | JC020525 18737
97 | 2025-04-30 | W000305 | REV. EST. MATERIAL (ADD. MATERIAL MCT SET, CONSUMABLE ELECTRIK) | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-05-26 | 2025-05-30 | 1 | RENDRA |  | JC020525 18738
98 | 2025-04-30 | W000305 | REVISI ONE LINE DIAGRAM PD 440V, 220V, 115V/60HZ, 115V/400HZ & 24V | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-05-05 | 2025-05-30 | 1 | Hari |  | JC020525 18739
99 | 2025-04-30 | W000305 | CEK WIRING LAUNDRY, MONO RAIL, RHIB DAVIT, EMERGENCY STOP | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-05-05 | 2025-05-16 | 1 | PRIYONO |  | JC050525 18972
100 | 2025-04-30 | W000305 | CEK INSTALL SEAT BLOCK 432P, 432S, 212P, 212S, 222P, 222S | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-05-19 | 2025-05-30 | 1 | PRIYONO |  | JC020525 18740
101 | 2025-04-30 | W000305 | WIRING DIAGRAM EMERGENCY LIGHTING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-05-05 | 2025-05-23 | 1 | NOVAL |  | JC020525 18741
102 | 2025-04-30 | W000305 | INSTALL SEAT BLOCK 232P | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-05-26 | 2025-05-30 | 1 | NOVAL |  | JC020525 18742
103 | 2-May-25 | W000308 | E14391.25300-ONE LINE DIAGRAM OF CCTV (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2-May-25 | 9-May-25 | 1 | nisa |  | JC020525 18767
104 | 2-May-25 | W000304 | E14231.27300-WIRING DIAGRAM OF GLOBAL POSITIONING SYSTEM (GPS) (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2-May-25 | 9-May-25 | 1 | azis |  | JC020525 18768
105 | 2-May-25 | W000308 | E14391.16300 - ARR'T. OF CCTV(rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2-May-25 | 9-May-25 | 1 | ferry |  | JC020525 18772
106 | 2025-05-05 | W000305 | ROUTING & WIRING DIAGRAM OF INTEGRATED PLATFORM MANAGEMENT SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-05-06 | 2025-05-20 | 1 | CANDRA |  | JC050525 18863
107 | 14-May-25 | W000304 | E14391.27300 - WIRING DIAGRAM OF CCTV (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 13-May-25 | 22-May-25 | 1 | nisa |  | JC140525 19357
108 | 14-May-25 | W000304 | E14201.25300 -ONE LINE DIAGRAM OF IBS (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 13-May-25 | 22-May-25 | 1 | azis |  | JC150525 19431
109 | 14-May-25 | W000308 | E14263.16300- CADMATIC ARR'T. OF NAVIGATION RADAR (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 13-May-25 | 22-May-25 | 1 | ferry |  | JC150525 19430
110 | 19-May-25 | W000305 | REVIEW & MENYESUAIKAN DENGAN MAKER DWG INST. DWG. OF ELECT. & ELECTRO. EQUIP. SEAT 2 DK_BLK : 414 (S) (EL414S.31200) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 19-May-25 | 24-May-25 | 1 | ALAM |  | JC190525 19559
111 | 2025-05-21 | W000305 | ROUTING & WIRING DIAGRAM OF INTEGRATED PLATFORM MANAGEMENT SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-05-21 | 2025-05-28 | 1 | CANDRA |  | JC210525 19688
112 | 2025-05-22 | W000305 | Re-Routing cable socket outlet system | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-05-19 | 2025-05-30 | 1 | YOGI |  | JC220525 19725
113 | 23-May-25 | W000308 | E14391.25300-ONE LINE DIAGRAM OF CCTV | 1CL400 - Biro Desain Sistem Elektronika | 23-May-25 | 31-May-25 | 1 | nisa |  | JC230525 19733
114 | 23-May-25 | W000304 | Check Wiring Diagram of Rudder Angle Indicator | 1CL400 - Biro Desain Sistem Elektronika | 23-May-25 | 31-May-25 | 1 | azis |  | JC230525 19734
115 | 23-May-25 | W000304 | Check RoutingDiagram of Coil Degaussing system | 1CL400 - Biro Desain Sistem Elektronika | 23-May-25 | 31-May-25 | 1 | ferry |  | JC230525 19735
116 | 2025-05-26 | W000305 | ROUTING & WIRING DIAGRAM OF STEERING GEAR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 26-May-25 | 30-May-25 | 1 | REGINA |  | JC260525 19872
117 | 2025-05-26 | W000305 | WEIGHT CONTROL OF CONTROL & AUTOMATION OUTFITTING (KB03) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 26-May-25 | 30-May-25 | 1 | ALAM |  | JC260525 19873
118 | 2025-05-26 | W000305 | FUNCTIONAL DESIGN DESCRIPTION (FDS) FOR THE INDIVIDUAL SHIP SYSTEMS FOR IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-05-30 | 2025-06-14 | 1 | RIANTO |  | JC260525 19876
119 | 2025-05-26 | W000305 | RESUME MATERIAL OF CABLE FOR CONTROL & AUTOMATION | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-05-30 | 2025-06-07 | 1 | CANDRA |  | JC260525 19877
120 | 2025-05-27 | W000305 | EVATEK MAKER HULL OUFITTING | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-06-02 | 2025-06-05 | 1 | HARI |  | JC270525 19969
121 | 2025-05-27 | W000305 | REVISI ONE LINE DIAGRAM AC SYSTEM, MECHANICAL VENT SYSTEM, AHU SYSTEM & SUMMARY CABLE | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-06-09 | 2025-06-30 | 1 | HARI |  | JC270525 19970
122 | 2025-05-27 | W000306 | EVATEK MAKER MSB, ESB, MCC, DB440V, DB220V, DB115V, DB 24V, STARTER & SHORE CONNECTION ARAKANMARINE AUTOMATION | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-06-02 | 2025-06-10 | 1 | PRIYONO |  | JC270525 19971
123 | 2025-05-27 | W000305 | CEK WIRING EMERGENCY LIGHTING | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-06-11 | 2025-06-20 | 1 | PRIYONO |  | JC270525 19972
124 | 2025-05-27 | W000305 | CEK WIRING SOCKET OUTLET | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-06-23 | 2025-06-30 | 1 | PRIYONO |  | JC270525 19973
125 | 2025-05-27 | W000305 | CEILING PLAN (ARR'T LIGHTING UNDER CEILING) | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-06-02 | 2025-06-20 | 1 | RENDRA |  | JC270525 19974
126 | 2025-05-27 | W000305 | SPAREPART LIGHTING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-06-23 | 2025-06-30 | 1 | RENDRA |  | JC270525 19975
127 | 2025-05-27 | W000308 | EVATEK MAKER TRAFO TRAFINDO & BAMBANG JAYA | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-06-02 | 2025-06-10 | 1 | ALDO |  | JC270525 19976
128 | 2025-05-27 | W000305 | ARR'T MODULE MCT | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-06-11 | 2025-06-30 | 1 | ALDO |  | JC270525 19977
129 | 2025-05-27 | W000305 | ARR'T MODULE MCT | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-06-02 | 2025-06-30 | 1 | ALDI |  | JC270525 19978
130 | 2025-05-27 | W000305 | RE-ROUTING (CADMATIC) EMERGENCY POWER GENERATION SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-06-02 | 2025-06-05 | 1 | NOVAL |  | JC270525 19979
131 | 2025-05-27 | W000305 | RE-ROUTING (CADMATIC) MAIN POWER GENERATION SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-06-09 | 2025-06-13 | 1 | NOVAL |  | JC270525 19980
132 | 2025-05-27 | W000305 | RE-ROUTING (CADMATIC) POWER DISTRIBUTION 220V | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-06-16 | 2025-06-30 | 1 | NOVAL |  | JC270525 19981
133 | 2025-05-27 | W000305 | RE-ROUTING (CADMATIC) POWER DISTRIBUTION 440V | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-06-02 | 2025-06-13 | 1 | YOGI |  | JC270525 19982
134 | 2025-05-27 | W000305 | RE-ROUTING (CADMATIC) POWER DISTRIBUTION 24VDC | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-06-16 | 2025-06-20 | 1 | YOGI |  | JC270525 19983
135 | 2025-05-27 | W000305 | RE-ROUTING (CADMATIC) POWER DISTRIBUTION 115V/400HZ | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-06-23 | 2025-06-27 | 1 | YOGI |  | JC270525 19984
136 | 2025-05-27 | W000305 | RE-ROUTING (CADMATIC) POWER DISTRIBUTION 115V/60HZ | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-06-30 | 2025-07-04 | 1 | YOGI |  | JC270525 19985
137 | 2025-05-27 | W000305 | CEK INSTALL SEAT BLOCK 232P, 232S, 132P, 132S, 122P, 122S | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-06-02 | 2025-06-20 | 1 | ALDI |  | JC270525 19986
138 | 2025-05-27 | W000305 | CEK REV. INSTALL MCW BLOCK 244S, 254P, 114P, 114S, 124P, 124S | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-06-23 | 2025-07-04 | 1 | ALDI |  | JC270525 19987
139 | 2025-06-02 | W000305 | WIRING DIAGRAM OF HELICOPTER HANGAR DOOR | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-06-02 | 2025-06-07 | 1 | REGINA |  | JC020625 20206
117 | 2025-06-02 | W000305 | WEIGHT CONTROL OF CONTROL & AUTOMATION OUTFITTING (KB03) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-05-31 | 2025-06-05 | 1 | ALAM |  | JC020625 20241
141 | 2025-06-02 | W000308 | E14391.16300 - ARR'T OF CCTV (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-06-02 | 2025-06-11 | 1 | nisa |  | JC020625 20212
142 | 2025-06-02 | W000304 | E14231.27300-check WIRING DIAGRAM OF GLOBAL POSITIONING SYSTEM (GPS) (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-06-02 | 2025-06-11 | 1 | azis |  | JC020625 20223
143 | 2025-06-02 | W000304 | E16254.25300 - ONE LINE DIAGRAM OF WINDOW WIPER SYSTEM(rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-06-02 | 2025-06-11 | 1 | ferry |  | JC020625 20225
144 | 2025-06-05 | W000305 | REVIEW WIRING DIAGRAM OF ELEVATORS, SHIP | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-06-07 | 2025-06-09 | 2 | ALAM |  | JC050625 20404
145 | 2025-06-09 | W000305 | REVIEW WIRING DIAGRAM OF REMOTE CONTROL VALVE (PART RELAY BOX NO.2-4) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-06-09 | 2025-06-16 | 1 | REGINA |  | JC090625 20510
146 | 2025-06-09 | W000305 | REVIEW WIRING DIAGRAM OF REMOTE CONTROL VALVE (PART RELAY BOX NO.5-7) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-06-10 | 2025-06-16 | 1 | ALAM |  | JC090625 20512
147 | 2025-06-09 | W000305 | REVIEW WIRING DIAGRAM OF REMOTE CONTROL VALVE (PART RELAY BOX NO.8-9) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-06-10 | 2025-06-16 | 1 | RIANTO |  | JC090625 20531
148 | 2025-06-09 | W000305 | REVIEW WIRING DIAGRAM OF IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-06-10 | 2025-06-16 | 1 | CANDRA |  | JC090625 20532
149 | 2025-06-13 | W000304 | E14339.16300 - ARR'T. OF TIME INDICATOR (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-06-12 | 2025-06-23 | 1 | nisa |  | JC130625 20710
150 | 2025-06-13 | W000304 | E14211.27300 WIRING DIAGRAM OF MAGNETIC COMPASS (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-06-12 | 2025-06-23 | 1 | azis |  | JC130625 20712
151 | 2025-06-13 | W000304 | E16254.16300 - ARR'T. OF WINDOW WIPER SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2025-06-12 | 2025-06-23 | 1 | ferry |  | JC130625 20718
152 | 2025-06-16 | W000305 | REVISI-3 ESTIMATE QUANTITY OF MATERIAL LIST CONTROL & AUTOMATION PART | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-06-17 | 2025-06-21 | 1 | CANDRA |  | JC160625 20890
153 | 2025-06-16 | W000305 | FUNCTIONAL DESIGN DESCRIPTION (FDS) FOR PROPULSION CONTROL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-06-17 | 2025-06-21 | 1 | RIANTO |  | JC160625 20893
154 | 2025-06-16 | W000305 | FUNCTIONAL DESIGN DESCRIPTION (FDS) FOR STEERING GEAR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-06-23 | 2025-06-25 | 1 | RIANTO |  | JC160625 20901
155 | 2025-06-16 | W000305 | FUNCTIONAL DESIGN DESCRIPTION (FDS) FOR REMOTE CONTROL VALVE SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-06-26 | 2025-07-02 | 1 | RIANTO |  | JC160625 20908
156 | 2025-06-16 | W000305 | REVISI-1 ONE LINE DIAGRAM OF LOCAL AREA NETWORK (LAN) SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-06-17 | 2025-06-20 | 1 | REGINA |  | JC160625 20917
157 | 2025-06-16 | W000305 | CABLE CUTTING LIST FOR ICCP, MGPS & SLC | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-06-17 | 2025-06-21 | 1 | ALAM |  | JC160625 20938
158 | 2025-06-23 | W000305 | REVISI-3 ESTIMATE QUANTITY OF MATERIAL LIST CONTROL & AUTOMATION PART | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-06-23 | 2025-06-23 | 1 | CANDRA |  | JC230625 21225
159 | 2025-06-23 | W000305 | CEK WIRING DIAGRAM, MENYESUAIKAN DENGAN REVISI OLD POWER DISTRIBUTION SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-06-23 | 2025-06-27 | 1 | ALAM |  | JC230625 21226
160 | 2025-06-23 | W000305 | UPDATE REVISI OLD OF IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-06-24 | 2025-06-30 | 1 | CANDRA |  | JC230625 21227
161 | 2025-06-23 | W000305 | RE-ROUTING STEERING GEAR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-06-23 | 2025-06-24 | 1 | REGINA |  | JC230625 21228
162 | 2025-06-24 | W000304 | E14339.16300 - ARR'T. OF TIME INDICATOR (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-06-24 | 2025-06-30 | 1 | nisa |  | JC240625 21286
163 | 2025-06-24 | W000304 | E14211.25300 - ONE LINE DIAGRAM OF MAGNETIC COMPASS (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-06-24 | 2025-06-30 | 1 | azis |  | JC240625 21287
164 | 2025-06-24 | W000304 | E14321.16300 - ARR'T. OF AUTOMATIC EXCHANGE TELEPHONE (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-06-24 | 2025-06-30 | 1 | ferry |  | JC240625 21288
165 | 2025-06-25 | W000305 | list equipment for control & Automation part | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-06-25 | 2025-06-25 | 1 | REGINA |  | JC250625 21302
166 | 2025-06-25 | W000308 | review revisi 3 W308 OLD & Arrangement LAN system | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-06-26 | 2025-06-30 | 1 | REGINA |  | JC250625 21303
167 | 2025-06-25 | W000305 | CEK WIRING DIAGRAM, MENYESUAIKAN DENGAN REVISI OLD POWER DISTRIBUTION SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-06-30 | 2025-06-30 | 1 | ALAM |  | JC250625 21304
168 | 2025-06-26 | W000305 | EVATEK MAKER MCC (TTS) | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-07-01 | 2025-07-04 | 1 | HARI |  | JC260625 21347
169 | 2025-06-26 | W000305 | REVISI ONE LINE DIAGRAM EMERGENCY STOP, MOORING AND TOWING, ANCHOR WINCH/CAPSTANS, MONORAIL, LUBRICATING OIL SYSTEM, FUEL OIL SYSTEM, FRESH WATER SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-07-07 | 02-Aug-25 | 1 | HARI |  | JC260625 21349
170 | 2025-06-26 | W000305 | REVISI ARR'T GENERAL ILLUMINATION & EMERGENCY LIGHTING | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-07-01 | 2025-07-11 | 1 | RENDRA |  | JC260625 21350
171 | 2025-06-26 | W000305 | REVISI ONE LINE DIAGRAM RO, STP, NAVIGATION LT, SOCKET OUTLET, GENERAL ILLUMINATION, EMERGENCY LIGHTING, & DECORATION LIGHTING | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-07-14 | 02-Aug-25 | 1 | RENDRA |  | JC110725 22088
172 | 2025-06-26 | W000306 | Evatek MSB set, maker AMA | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-07-01 | 2025-07-04 | 1 | PRIYONO |  | JC260625 21365
173 | 2025-06-26 | W000305 | REVISI ONE LINE DIAGRAM WORKSHOP EQ'T, GALLEY EQ'T, ACCOMODATION LADDER, BALLAST WATER, OILY BILGE/SLUDGE OIL SYSTEM, AIRCRAFT HANDLING SYSTEM, RHIB DAVIT | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-07-07 | 02-Aug-25 | 1 | PRIYONO |  | JC260625 21366
174 | 2025-06-26 | W000305 | REV. WIRING DIAGRAM WORKSHOP EQ'T, GALLEY EQ'T, ACCOMODATION LADDER, BALLAST WATER, OILY BILGE/SLUDGE OIL SYSTEM, AIRCRAFT HANDLING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-07-01 | 02-Aug-25 | 1 | NOVAL |  | JC260625 21369
175 | 2025-06-26 | W000305 | REVISI ONE LINE DIAGRAM EMERGENCY STOP, MOORING AND TOWING, ANCHOR WINCH/CAPSTANS, MONORAIL, LUBRICATING OIL SYSTEM, FUEL OIL SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-07-01 | 02-Aug-25 | 1 | YOGI |  | JC300625 21509
176 | 2025-06-26 | W000305 | ARR'T PENETRATION | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-07-01 | 02-Aug-25 | 1 | ALDI |  | JC110725 22089
177 | 2025-06-26 | W000305 | ARR'T MODULE MCT | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-07-01 | 02-Aug-25 | 1 | ALDO |  | JC260625 21372
178 | 2025-06-26 | W000305 | CEK REV. INSTALL MCW BLOCK 611P, 611S, 631P, 631S, 641P, 641S, 651P, 651S CEK INSTALL SEAT BLOCK 312C, 243P, 243S, 423P, 423S | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-07-01 | 02-Aug-25 | 1 | ADI |  | JC300625 21510
179 | 2025-07-01 | W000308 | E14210.16300 - ARR'T. OF WHISTLE SYSTEM (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-07-01 | 2025-07-08 | 1 | nisa |  | JC260625 21380
180 | 2025-07-01 | W000304 | E14231.25300-ONE LINE DIAGRAM OF GLOBAL POSITIONING SYSTEM (GPS) (re.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-07-01 | 2025-07-08 | 1 | azis |  | JC260625 21381
181 | 2025-07-01 | W000304 | E14321.25300 - ONE LINE DIAGRAM OF AUTOMATIC EXCHANGE TELEPHONE (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-07-01 | 2025-07-08 | 1 | ferry |  | JC260625 21382
182 | 2025-07-01 | W000308 | REVISI 4 W308 OLD & Arrangement LAN system | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-01 | 2025-07-02 | 1 | REGINA |  | JC010725 21588
183 | 2025-07-01 | W000305 | RE-ROUTING REMOTE CONTROL VALVE SYSTEM (RELAY BOX NO.8) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-02 | 2025-07-05 | 1 | REGINA |  | JC010725 21589
184 | 2025-07-01 | W000305 | RE-ROUTING REMOTE CONTROL VALVE SYSTEM (RELAY BOX NO.9) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-01 | 2025-07-05 | 1 | ALAM | 48 | JC010725 21590
185 | 2025-07-01 | W000305 | REVISI 3D MODEL EQUIPMENT & ARRANGEMENT | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-07 | 2025-07-12 | 1 | ALAM |  | JC010725 21599
186 | 2025-07-01 | W000305 | RE-ROUTING REMOTE CONTROL VALVE SYSTEM (RELAY BOX NO.6-7) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-01 | 2025-07-05 | 1 | RIANTO | 48 | JC010725 21602
187 | 2025-07-01 | W000305 | REVISI-1 OLD OF INTEGRATED PLATFORM MANAGEMENT SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-01 | 2025-07-12 | 1 | CANDRA |  | JC010725 21603
188 | 2025-07-07 | W000308 | REVIEW REVISI 4 W308 OLD & Arrangement LAN system | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-07 | 2025-07-08 | 1 | REGINA |  | JC070725 21892
189 | 2025-07-07 | W000305 | EVALUASI TEKNIK REMOTE CONTROL VALVE SYSTEM BATCH-2 | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-07 | 2025-07-08 | 1 | RIANTO |  | JC070725 21893
190 | 2025-07-09 | W000305 | RE-ROUTE CABLE RCV SYSTEM MENYESUAIKAN DENGAN MCT | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-09 | 2025-07-12 | 1 | RIANTO |  | JC090725 22060
191 | 2025-07-09 | W000305 | RE-ROUTE CABLE LOCAL AREA NETWORK | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-09 | 2025-07-12 | 1 | REGINA |  | JC090725 22061
192 | 2025-07-09 | W000304 | E14363.16300 - ARR'T. OF LOCK-IN ALARM SYSTEM (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-07-09 | 2025-07-16 | 1 | nisa |  | JC090725 22062
193 | 2025-07-09 | W000304 | E14231.16300-ARR'T. OF GPS (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-07-09 | 2025-07-16 | 1 | azis |  | JC090725 22063
194 | 2025-07-09 | W000304 | E14321.16300 - ARR'T. OF AUTOMATIC EXCHANGE TELEPHONE (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-07-09 | 2025-07-16 | 1 | ferry |  | JC090725 22064
195 | 2025-07-14 | W000305 | REVISI ARRT LOCAL AREA NETWORK | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-14 | 2025-07-16 | 1 | REGINA |  | JC140725 22196
196 | 2025-07-14 | W000305 | UPDATE LIST OF DOOR & HATCH FOR ALARM LIST | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-14 | 2025-07-16 | 1 | CANDRA |  | JC140725 22197
197 | 2025-07-14 | W000305 | ADD SYSTEM CITADEL LIGHT COLUMN UNTUK IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-17 | 2025-07-21 | 1 | CANDRA |  | JC140725 22200
198 | 2025-07-14 | W000305 | RE-ROUTE CABLE LAN SYSTEM MENYESUAIKAN DENGAN CABLE TRAY DAN MCT | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-14 | 2025-07-19 | 1 | ALAM |  | JC140725 22204
199 | 2025-07-14 | W000305 | REVISI OLD OF PCS BASED ON APPROVAL MAKER DWG | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-14 | 2025-07-21 | 1 | RIANTO |  | JC140725 22216
200 | 2025-07-17 | W000305 | REVISI NODE MCT CADMATIC 02 DECK & 01 DECK | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-16 | 2025-07-23 | 1 | ALAM |  | JC170725 22357
201 | 2025-07-18 | W000304 | E14210.25300 -One Line Diagram of Ship's Whistle System (rev.2) | 1CL400 - Biro Desain Sistem Elektronika | 2025-07-17 | 2025-07-23 | 1 | nisa |  | JC180725 22376
202 | 2025-07-18 | W000304 | E14201.25300 -ONE LINE DIAGRAM OF IBS (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-07-17 | 2025-07-23 | 1 | azis |  | JC180725 22377
203 | 2025-07-18 | W000304 | E14321.25300 - ONE LINE DIAGRAM OF AUTOMATIC EXCHANGE TELEPHONE (rev.2) | 1CL400 - Biro Desain Sistem Elektronika | 2025-07-17 | 2025-07-23 | 1 | ferry |  | JC180725 22378
204 | 2025-07-21 | W000305 | REVISI ARRT LOCAL AREA NETWORK | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-21 | 2025-07-21 | 1 | REGINA |  | JC210725 22559
205 | 2025-07-21 | W000305 | REVISI WIRING DIAGRAM LOCAL AREA NETWORK | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-22 | 2025-07-24 | 1 | REGINA |  | JC210725 22560
206 | 2025-07-22 | W000305 | UPDATE DOOR & HATCH LIST FOR OLD OF IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-22 | 2025-07-24 | 1 | CANDRA |  | JC220725 22570
207 | 2025-07-22 | W000305 | UPDATE POWER DISTRIBUTION FOR OLD OF IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-25 | 2025-07-29 | 1 | CANDRA |  | JC220725 22571
208 | 2025-07-22 | W000305 | REVISI OLD FOR MAIN ENGINE BASED ON APPROVAL MAKER DWG | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-22 | 2025-07-29 | 1 | RIANTO |  | JC220725 22575
209 | 2025-07-24 | W000305 | REVISI WIRING DIAGRAM LOCAL AREA NETWORK | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-25 | 2025-07-25 | 1 | REGINA |  | JC240725 22662 |  | perpanjangan
210 | 2025-07-24 | W000305 | REVISI NAMING COAMING CADMATIC 02 DECK & 01 DECK | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-24 | 2025-07-30 | 1 | ALAM |  | JC240725 22663
211 | 2025-07-24 | W000305 | REVISI NAMING RING CADMATIC 02 DECK & 01 DECK | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-31 | 2025-08-06 | 1 | ALAM |  | JC240725 22664
212 | 2025-07-24 | W000305 | UPDATE 3D MODEL EQUIPMENT IN CADMATIC | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-28 | 2025-07-31 | 1 | REGINA |  | JC240725 22665
213 | 2025-07-24 | W000308 | E14391.16300 - ARR'T OF CCTV (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-07-24 | 2025-07-31 | 1 | nisa |  | JC240725 22666
214 | 2025-07-24 | W000304 | E14201.25300 -ONE LINE DIAGRAM OF IBS (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-07-24 | 2025-07-31 | 1 | azis |  | JC240725 22667
215 | 2025-07-24 | W000304 | E94000.92303 - WEIGHT CONTROL OF ELECTRONIC OUT FITTING (KB03) | 1CL400 - Biro Desain Sistem Elektronika | 2025-07-24 | 2025-07-31 | 1 | ferry |  | JC240725 22668
2025-08-01
216 | 2025-07-29 | W000305 | EVATEK APPROVAL DRAWING MSB, ESB, MCC (TTS), FIRE DAMPER (HH) | 1CL100 - Biro Desain Sistem Kelistrikan | 04-Aug-25 | 12-Aug-25 | 1 | HARI | 67 | JC290725 22908
217 | 2025-07-29 | W000305 | - REV. ONE LINE DIAGRAM EM'CY STOP (FIRE DAMPER SYSTEM) - CEK ARRANGEMENT & WIRING OF FIRE DAMPER. - PAPARAN DIAGRAM DAN ARR'T KE SATGAS | 1CL100 - Biro Desain Sistem Kelistrikan | 13-Aug-25 | 30-Aug-25 | 1 | HARI | 149 | JC290725 22911
218 | 2025-07-29 | W000306 | EVATEK PENAWARAN MSB, ESB, MCC, DB, BATTERY CHARGE, SCB & BATTERY PT AMA | 1CL100 - Biro Desain Sistem Kelistrikan | 04-Aug-25 | 12-Aug-25 | 1 | PRIYONO | 67 | JC290725 22912
219 | 2025-07-29 | W000305 | CEK CUTTING LIST : - MAIN POWER GENERATION, - EMERGENCY POWER GENERATION, - 440V DISTRIBUTION SYSTEM - 24V DISTRIBUTION SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 13-Aug-25 | 30-Aug-25 | 1 | PRIYONO | 149 | JC290725 22913
220 | 2025-07-29 | W000305 | REV. ESTIMASI MATERIAL LIGHTING FIXTURES | 1CL100 - Biro Desain Sistem Kelistrikan | 04-Aug-25 | 06-Aug-25 | 1 | RENDRA | 30 | JC290725 22914
221 | 2025-07-29 | W000305 | CEK CUTTING LIST : - GENERAL ILLUMINATION SYSTEM - EMERGENCY LIGHTING SYSTEM - SOCKET OUTLET - NAVIGATION & SIGNAL LIGHT - DECORATION LIGHT | 1CL100 - Biro Desain Sistem Kelistrikan | 07-Aug-25 | 30-Aug-25 | 1 | RENDRA | 196 | JC290725 22917
222 | 2025-07-29 | W000305 | RE-ROUTING WIRING POWER DISTRIBUTION 24VDC | 1CL100 - Biro Desain Sistem Kelistrikan | 04-Aug-25 | 08-Aug-25 | 1 | YOGI | 49 | JC290725 22919
223 | 2025-07-29 | W000305 | ARRANGEMENT MCT 1 DECK | 1CL100 - Biro Desain Sistem Kelistrikan | 11-Aug-25 | 30-Aug-25 | 1 | YOGI | 170 | JC290725 22920
224 | 2025-07-29 | W000305 | REVISI : - ARR'T EM'CY POWER GENERATION - ARR'T ACCOMODATION LADDER - ARR'T POWER DISTRIBUTION 220V - WIRING GENERAL ILLUMINATION LIGHTING - EMERGENCY LIGHTING | 1CL100 - Biro Desain Sistem Kelistrikan | 04-Aug-25 | 30-Aug-25 | 1 | NAUFAL | 227 | JC290725 22921
225 | 2025-07-29 | W000308 | EVATEK TRANSFORMER (BAMBANG DJAYA & TRAFINDO) | 1CL100 - Biro Desain Sistem Kelistrikan | 04-Aug-25 | 09-Aug-25 | 1 | ALDO | 57 | JC290725 22922
226 | 2025-07-29 | W000308 | - ARR'T. OF POWER DISTRIBUTION 115V/60HZ SYSTEM - WIRING DIAGRAM OF ELECTRIC MAIN POWER GENERATION SYSTEM - WIRING DIAGRAM OF ELECTRIC EM'CY POWER GENERATION SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 11-Aug-25 | 30-Aug-25 | 1 | ALDO | 170 | JC290725 22923
227 | 2025-07-29 | W000305 | ARR'T MODULE MCT | 1CL100 - Biro Desain Sistem Kelistrikan | 04-Aug-25 | 30-Aug-25 | 1 | ALDI | 227 | JC290725 22924
228 | 2025-07-29 | W000305 | CEK : - INSTALL SEAT BLOCK 123P, 123S. 223P, 223S, 323P, 323S, 153P, 153S, 133P, 133S - INSTALL MCW BLOCK 313P, 313S, 541P, 541S | 1CL100 - Biro Desain Sistem Kelistrikan | 04-Aug-25 | 30-Aug-25 | 1 | ADI | 227 | JC290725 22925
229 | 2025-07-30 | W000305 | REVISI OLD START AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-30 | 1-Aug-25 | 1 | RIANTO |  | JC300725 22952
230 | 2025-07-30 | W000305 | REVISI OLD SERVICE & WORKING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 4-Aug-25 | 6-Aug-25 | 1 | RIANTO |  | JC300725 22953
231 | 2025-07-30 | W000305 | UPDATE LAYOUT SYSTEM IPMS BASE ON MAKER | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-07-30 | 4-Aug-25 | 1 | CANDRA |  | JC300725 22954
232 | 2025-08-01 | W000305 | UPDATE ARRANGEMENT EQUIPMENT IN CADMATIC | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-08-01 | 5-Aug-25 | 1 | REGINA |  | JC010825 23026
233 | 2025-08-01 | W000305 | UPDATE FIRE DAMPER SYSTEM INTEGRASI DENGAN IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-08-05 | 9-Aug-25 | 1 | CANDRA |  | JC010825 23027
234 | 2025-08-01 | W000305 | REVISI OLD START AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-08-02 | 2-Aug-25 | 1 | RIANTO |  | JC010825 23028 |  | lembur
235 | 1-Aug-25 | W000304 | E14921.16300 - ARR'T. OF HELICOPTER VISUAL LANDING AID (rev.2) | 1CL400 - Biro Desain Sistem Elektronika | 1-Aug-25 | 7-Aug-25 | 1 | nisa |  | JC010825 23029
236 | 1-Aug-25 | W000304 | E14941.25300-ONE LINE DIAGRAM OF METEOROLOGICAL SYSTEM(re.1) | 1CL400 - Biro Desain Sistem Elektronika | 1-Aug-25 | 7-Aug-25 | 1 | azis |  | JC010825 23030
237 | 1-Aug-25 | W000304 | E93000.92103- WEIGHT CONTROL OF ELECTRIC OUT FITTING (KB03) | 1CL400 - Biro Desain Sistem Elektronika | 1-Aug-25 | 7-Aug-25 | 1 | ferry |  | JC010825 23031
238 | 2025-08-05 | W000305 | UPDATE ARRANGEMENT EQUIPMENT IN CADMATIC | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-08-06 | 8-Aug-25 | 1 | REGINA |  | JC050825 23321 |  | extend
239 | 2025-08-05 | W000305 | REVISI OLD SERVICE & WORKING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 7-Aug-25 | 11-Aug-25 | 1 | RIANTO |  | JC050825 23322 |  | extend
240 | 2025-08-05 | W000305 | REVISI NAMING RING CADMATIC 02 DECK & 01 DECK | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-08-07 | 2025-08-12 | 1 | ALAM |  | JC050825 23323 |  | extend
241 | 8-Aug-25 | W000304 | E14341.16300 - ARR'T. OF CENTRAL AERIAL SYSTEM (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 8-Aug-25 | 15-Aug-25 | 1 | nisa |  | JC080825 23412
242 | 8-Aug-25 | W000304 | E14262.25300-ONE LINE DIAGRAM OF SPEED LOG SYSTEM(re.1) | 1CL400 - Biro Desain Sistem Elektronika | 8-Aug-25 | 15-Aug-25 | 1 | azis |  | JC080825 23413
243 | 8-Aug-25 | W000304 | E93000.92103- WEIGHT CONTROL OF ELECTRIC OUT FITTING (KB03) | 1CL400 - Biro Desain Sistem Elektronika | 8-Aug-25 | 15-Aug-25 | 1 | ferry |  | JC080825 23414
244 | 2025-08-11 | W000305 | REVISI OLD HANGAR DOOR BASED ON APPROVAL DRAWING | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-08-11 | 13-Aug-25 | 1 | REGINA |  | JC110825 23483
245 | 2025-08-11 | W000305 | UPDATE CIRCUIT BREAKER ALARM PADA OLD OF IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-08-11 | 13-Aug-25 | 1 | candra |  | JC110825 23486
246 | 2025-08-12 | W000305 | REVISI OLD OF FIN STABILIZER BASED ON APPROVAL DRAWING | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-08-12 | 16-Aug-25 | 1 | RIANTO |  | JC120825 23603
247 | 13-Aug-25 | W000305 | REVISI INSTALL SEAT BLOK 434S | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 13-Aug-25 | 15-Aug-25 | 1 | ALAM |  | JC130825 23637
248 | 14-Aug-25 | W000305 | REVISI INSTALL SEAT BLOK 144P/S, 144P/S | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 14-Aug-25 | 19-Aug-25 | 1 | CANDRA |  | JC140825 23657
249 | 14-Aug-25 | W000305 | REVISI INSTALL SEAT BLOK 244P | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 14-Aug-25 | 15-Aug-25 | 1 | REGINA |  | JC140825 23650
250 | 14-Aug-25 | W000304 | E14471.25300 - ONE LINE DIAGRAM OF CCTV (rev.2) | 1CL400 - Biro Desain Sistem Elektronika | 16-Aug-25 | 31-Aug-25 | 1 | nisa |  | JC140825 23651
251 | 14-Aug-25 | W000304 | E14241.25300-ONE LINE DIAGRAM OF ECHO SOUNDER(re.1) | 1CL400 - Biro Desain Sistem Elektronika | 16-Aug-25 | 31-Aug-25 | 1 | azis |  | JC140825 23653
252 | 14-Aug-25 | W000304 | E14282.16300- ARR'T. OF RUDDER ANGLE INDICATOR (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 16-Aug-25 | 31-Aug-25 | 1 | ferry |  | JC140825 23654
253 | 18-Aug-25 | W000305 | REVISI INSTALL SEAT BLOK 434P | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 18-Aug-25 | 20-Aug-25 | 1 | ALAM |  | JC190825 23848
254 | 18-Aug-25 | W000305 | REVISI INSTALL SEAT BLOK 254 S | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 18-Aug-25 | 19-Aug-25 | 1 | REGINA |  | JC190825 23850
255 | 2025-08-18 | W000308 | EVATEK APPROVAL DRAWING STEERING GEAR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-08-18 | 19-Aug-25 | 1 | RIANTO |  | JC190825 23852
256 | 2025-08-18 | W000305 | REVISI OLD OF FIN STABILIZER BASED ON APPROVAL DRAWING | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-08-20 | 22-Aug-25 | 1 | RIANTO |  | JC190825 23856
257 | 18-Aug-25 | W000305 | REVISI R4 MATERIAL LIST | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 20-Aug-25 | 20-Aug-25 | 1 | CANDRA |  | JC190825 23857
258 | 20-Aug-25 | W000305 | REVISI INSTALL SEAT BLOK 254 P | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 20-Aug-25 | 22-Aug-25 | 1 | REGINA |  | JC210825 23935
259 | 22-Aug-25 | W000305 | REVISI INSTALL SEAT BLOK 424S | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 21-Aug-25 | 26-Aug-25 | 1 | ALAM |  | JC250825 24039
260 | 22-Aug-25 | W000305 | EVATEK APPROVAL DRAWING SLC | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-08-21 | 22-Aug-25 | 1 | CANDRA |  | JC250825 24042
261 | 22-Aug-25 | W000305 | EVATEK APPROVAL DRAWING HELI REFUELING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-08-25 | 26-Aug-25 | 1 | CANDRA |  | JC250825 24047
262 | 25-Aug-25 | W000308 | OLD OF ICCP | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 25-Aug-25 | 29-Aug-25 | 1 | REGINA |  | JC250825 24048
263 | 2025-08-25 | W000308 | EVATEK REMOTE CONTROL VALVE SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-08-25 | 26-Aug-25 | 1 | RIANTO |  | JC250825 24052
264 | 27-Aug-25 | W000305 | REVISI INSTALL SEAT BLOK 134 P/S | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-08-27 | 2025-09-02 | 1 | CANDRA |  | JC270825 24174
265 | 27-Aug-25 | W000305 | REVISI INSTALL SEAT BLOK 144 P/S | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-03 | 2025-09-09 | 1 | CANDRA |  | JC270825 24175
266 | 27-Aug-25 | W000305 | REVISI INSTALL SEAT BLOK 424P | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 27-Aug-25 | 1-Sept-25 | 1 | ALAM |  | JC270825 24176
267 | 27-Aug-25 | W000308 | Arrangement OF ICCP | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 1-sept-25 | 3-sept-25 | 1 | REGINA |  | JC270825 24177
268 | 2025-08-27 | W000305 | FUNCTIONAL DESIGN SPECIFICATION OF DG, HG & EDG | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-08-27 | 2025-08-29 | 1 | RIANTO |  | JC270825 24178
2025-09-01
269 | 29 Agust. 2025 | W000305 | EVATEK APPROVAL DRAWING : - MSB, - ESB, - MCC, - DB (440V, 230V, 115V/60HZ, 115/400HZ, 24VDC) | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-09-01 | 2025-09-13 | 1 | HARI | 96 | JC300825 24272
270 | 29 Agust. 2025 | W000305 | - EVALUASI MAKER MONORAIL - REVISI ONE LINE DIAGRAM MONORAIL - REVISI ELECTRICAL ARR'T MONORAIL - REVISI ONE LINE POWER DISTRIBUTION 440V SYSTEM - HELI HANGAR CRANE - CEK WIRING DIAGRAM MONORAIL - EVALUASI MAKER HVAC - REVISI ONE LINE POWER DISTRIBUTION 24VDC | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-09-15 | 2025-09-30 | 1 | HARI | 120 | JC300825 24273
272 | 29 Agust. 2025 | W000306 | - EVATEK PENAWARAN MSB, ESB, MCC, DB, BATTERY CHARGE, SCB & BATTERY PT AMA - EVATEK PENAWARAN MSB, ESB, MCC, DB, BATTERY CHARGE, SCB & BATTERY PT TTS | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-09-01 | 2025-09-13 | 1 | PRIYONO | 96 | JC300825 24274
273 | 29 Agust. 2025 | W000305 | - CEK REVISI WIRING DIAGRAM POWER DISTRIBUTION 440V SYSTEM - CEK CUTTING LIST POWER DISTRIBUTION 440V SYSTEM - CEK REVISI WIRING POWER DISTRIBUTION 220V SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-09-15 | 2025-09-30 | 1 | PRIYONO | 120 | JC300825 24275
274 | 29 Agust. 2025 | W000305 | - EVATEK LIGHTING FIXTURES GLAMOX - EVATEK LIGHTING FIXTURES International Offshore Industries - REVISI MATERIAL LIST OF ELECTRIC PART | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-09-01 | 2025-09-20 | 1 | RENDRA | 144 | JC300825 24276
275 | 29 Agust. 2025 | W000305 | - CEK CUTTING LIST FO SYSTEM - CEK CUTTING LIDT LO SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-09-22 | 2025-09-30 | 1 | RENDRA | 80 | JC300825 24277
276 | 29 Agust. 2025 | W000305 | CEK REVISI INSTALL. MAIN CABLE WAY BLOCK : 522P, 522S, 532P, 532S, 542P, 542S, 513P, 513S, 523P, 523S, 533P, 533S. | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-09-01 | 2025-09-30 | 1 | ADI | 230 | JC300825 24278
277 | 29 Agust. 2025 | W000305 | - ARR'T MODULE MCT '- EVATEK MCT ACCESSORIES | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-09-01 | 2025-09-13 | 1 | ALDI | 96 | JC300825 24279
278 | 29 Agust. 2025 | W000308 | - ROUTING NODE OF MAIN CABLE WAY E/R DECK - ROUTING NODE OF MAIN CABLE WAY 1 DECK - ROUTING NODE OF MAIN CABLE WAY 01 DECK | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-09-15 | 2025-09-30 | 1 | ALDI | 128 | JC300825 24280
279 | 29 Agust. 2025 | W000308 | - VOLTAGE DROP CALCULATION - EVATEK HULL OUTFITTING EQUIPMENT - EVATEK MACHINERY OUTFITTING EQUIPMENT | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-09-01 | 2025-09-30 | 1 | ALDO | 230 | JC300825 24281
280 | 29 Agust. 2025 | W000308 | - ROUTING NODE OF MAIN CABLE WAY 02 DECK - ROUTING NODE OF MAIN CABLE WAY 03 DECK - ROUTING NODE OF MAIN CABLE WAY 04 DECK - ROUTING NODE OF MAIN CABLE WAY TOP DECK | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-09-01 | 2025-09-30 | 1 | NOVAL | 230 | JC300825 24282
281 | 29 Agust. 2025 | W000305 | - DETAIL OF ELECTRIC PENETRATION 1 DECK - CEK CUTTING LIST LUBCRICATING OIL SYSTEM - CEK CUTTING LIST FRESH WATER COOLING SYSTEM - CEK CUTTING LIST OF SEA WATER COOLING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-09-01 | 2025-09-30 | 1 | YOGI | 230 | JC010925 24469
282 | 2025-09-01 | W000304 | E14391.16300 -ARR'T. OF CCTV (rev.3) | 1CL400 - Biro Desain Sistem Elektronika | 2025-09-01 | 2025-09-08 | 1 | nisa |  | JC010925 24440
283 | 2025-09-01 | W000304 | E14941.16300-ARR'T. OF METEOROLOGICAL SYSTEML SYSTEM (rev.2) | 1CL400 - Biro Desain Sistem Elektronika | 2025-09-01 | 2025-09-08 | 1 | azis |  | JC010925 24441
284 | 2025-09-01 | W000304 | E14363.16300-ARR'T. OF LOCK-IN ALARM SYSTEM (rev.2) | 1CL400 - Biro Desain Sistem Elektronika | 2025-09-01 | 2025-09-08 | 1 | ferry |  | JC010925 24443
285 | 2025-09-01 | W000305 | REVISI-2 OLD & ARRT OF FIN STABILIZER BASED ON APPROVAL DRAWING | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-01 | 2025-09-06 | 1 | RIANTO |  | JC010925 24446
286 | 2025-09-02 | W000305 | REVISI WIRING DIAGRAM OF STARTING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-02 | 2025-09-05 | 1 | ALAM |  | JC020925 24503
287 | 2025-09-02 | W000305 | REVISI WIRING DIAGRAM OF SERVICE WORKING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-06 | 2025-09-09 | 1 | ALAM |  | JC020925 24505
288 | 2025-09-02 | W000305 | REVISI OLD OF SIGNAL LIGHT COLUMN | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-03 | 2025-09-05 | 1 | CANDRA |  | JC020925 24506
289 | 2025-09-02 | W000308 | OLD OF MGPS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-04 | 2025-09-09 | 1 | REGINA |  | JC020925 24507
290 | 2025-09-02 | W000308 | ARRANGEMENT OF MGPS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-10 | 2025-09-12 | 1 | REGINA |  | JC020925 24508
291 | 2025-09-08 | W000305 | REVISI ARRANGEMENT OF SIGNAL LIGHT COLUMN | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-08 | 2025-09-10 | 1 | CANDRA |  | JC080925 24772
292 | 2025-09-08 | W000305 | REVISI-2 OLD & ARRT OF FIN STABILIZER BASED ON APPROVAL DRAWING | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-08 | 2025-09-09 | 1 | RIANTO |  | JC080925 24775
293 | 2025-09-09 | W000304 | E14200.16301 -ARR'T OF BRIDGE CONTROL CONSOLE (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-09-09 | 2025-09-16 | 1 | nisa |  | JC090925 24825
294 | 2025-09-09 | W000304 | E14263.16300-ARR'T. OF NAVIGATION RADAR (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-09-09 | 2025-09-16 | 1 | azis |  | JC090925 24826
295 | 2025-09-09 | W000304 | E16254.16300-ARR'T. OF WINDOW WIPER SYSTEM (rev.2) | 1CL400 - Biro Desain Sistem Elektronika | 2025-09-09 | 2025-09-16 | 1 | ferry |  | JC090925 24828
296 | 2025-09-10 | W000305 | UPDATE MCT FORSTARTING AIR SYSTEM & SERVICE WORKING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-10 | 2025-09-12 | 1 | ALAM |  | JC100925 24865
297 | 2025-09-10 | W000305 | EVALUASI APPROVAL DRAWING FIN STABILIZER | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-10 | 2025-09-11 | 1 | RIANTO |  | JC100925 24866
298 | 2025-09-11 | W000305 | REVISI INSTALL SEAT BLOK 124 P/S | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-11 | 2025-09-13 | 1 | CANDRA |  | JC110925 24871
299 | 2025-09-12 | W000305 | EVALUASI TEKNIS CBRN SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-12 | 2025-09-15 | 1 | RIANTO |  | JC120925 24931
300 | 2025-09-12 | W000305 | UPDATE MCT FORSTARTING AIR SYSTEM & SERVICE WORKING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-13 | 2025-09-13 | 1 | ALAM |  | JC130925 24944 |  | LEMBUR
301 | 2025-09-15 | W000305 | CONNECTION DIAGRAM OF ICCP | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-15 | 2025-09-17 | 1 | REGINA |  | JC150925 25068
302 | 2025-09-15 | W000305 | CONNECTION DIAGRAM OF MGPS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-18 | 2025-09-22 | 1 | REGINA |  | JC150925 25099
303 | 2025-09-15 | W000305 | CONNECTION DIAGRAM OF FIN STABILZER | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-15 | 2025-09-19 | 1 | CANDRA |  | JC150925 25105
304 | 2025-09-15 | W000305 | UPDATE SISTEM PRPULSION CONTROL BASE ON MAKER DRAWING | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-16 | 2025-09-20 | 1 | RIANTO |  | JC150925 25107
305 | 2025-09-15 | W000305 | REVISI WIRING DIAGRAM SLC | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-15 | 2025-09-17 | 1 | ALAM |  | JC150925 25108
306 | 2025-09-15 | W000305 | UPDATE MCT FOR SLC | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-18 | 2025-09-20 | 1 | ALAM |  | JC150925 25109
307 | 2025-09-17 | W000304 | E14282.27301 -WIRING DIAGRAM OF RUDDER ANGLE INDICATOR (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-09-17 | 2025-09-23 | 1 | nisa |  | JC180925 25174
308 | 2025-09-17 | W000304 | E14241.27300-WIRING DIAGRAM OF ECHO SOUNDER (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-09-17 | 2025-09-23 | 1 | azis |  | JC180925 25175
309 | 2025-09-17 | W000304 | E14200.16304-ARR'T OF RADIO CONSOLE (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-09-17 | 2025-09-23 | 1 | ferry |  | JC180925 25176
310 | 2025-09-19 | W000305 | RE-ROUTING CABLE FOR IPMS BASED ON OLD REV-1 | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-19 | 2025-09-26 | 1 | CANDRA |  | JC190925 25209
311 | 2025-09-22 | W000304 | UPDATE MCT FOR SLC | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-22 | 2025-09-22 | 1 | ALAM |  | JC230925 25380
312 | 2025-09-22 | W000304 | UPDATE WIRING PMS & MCT FOR PMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-23 | 2025-09-25 | 1 | ALAM |  | JC230925 25382
313 | 2025-09-22 | W000304 | REVISI OLD & ARRT OF MGPS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-23 | 2025-09-25 | 1 | REGINA |  | JC230925 25383
314 | 2025-09-23 | W000304 | E14200.16301 -ARR'T OF BRIDGE CONTROL CONSOLE (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-09-24 | 2025-09-30 | 1 | nisa |  | JC240925 25436
315 | 2025-09-23 | W000304 | E14263.27300-WIRING DIAGRAM OF NAVIGATION RADAR(rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-09-24 | 2025-09-30 | 1 | azis |  | JC240925 25437
316 | 2025-09-23 | W000304 | E14282.27300-WIRING DIAGRAM OF AUTOPILOT SYSTEM (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-09-24 | 2025-09-30 | 1 | ferry |  | JC240925 25443
317 | 2025-09-24 | W000304 | REVISI OLD & ARR'T STARTING AIR SYSTEM & SERVICE WORKING AIR SYSTEM BASE ON COMMENT SATGAS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-24 | 2025-09-25 | 1 | RIANTO |  | JC240925 25440
318 | 2025-09-24 | W000308 | EVATEK RCV SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-26 | 2025-09-29 | 1 | RIANTO |  | JC240925 25441
318 | 2025-09-24 | W000304 | UPDATE SISTEM PROPULSION CONTROL BASE ON MAKER DRAWING | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-30 | 2025-10-02 | 1 | RIANTO |  | JC240925 25442
312 | 2025-09-26 | W000304 | UPDATE WEIGHT CONTROL (KB-03) (CADMATIC) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-26 | 2025-09-30 | 1 | ALAM |  | JC260925 25486
313 | 2025-09-26 | W000308 | ESTIMASI QUANTITY OF MATERIAL CONTROL & AUTOMATION PART | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-26 | 2025-10-01 | 1 | REGINA |  | JC260925 25487
2025-10-01
314 | 30 Sept. 2025 | W000305 | - EVATEK APPROVAL DRAWING MSB SET - CEK CUTTING LIST OF ANCHOR WINCH/CAPSTAN - CEK CUTTING LIST OF GALLEY EQUIPMENT - CEK CUTTING LIST OF EMERGENCY STOP - CEK CUTTING LIST OF GALLEY EQUIPMENT | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Oct-25 | 2025-11-01 | 1 | HARI | 226 | JC300925 25716
315 | 30 Sept. 2025 | W000306 | - EVATEK PENAWARAN MSB, ESB, MCC, DB, BATTERY CHARGE, SCB & BATTERY PT AMA - EVATEK PENAWARAN MSB, ESB, MCC, DB, BATTERY CHARGE, SCB & BATTERY PT TTS | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Oct-25 | 11-Oct-25 | 1 | PRIYONO | 82 | JC300925 25717
316 | 30 Sept. 2025 | W000305 | - CEK REVISI WIRING DIAGRAM LIGHTING SYSTEM - CEK CUTTING LIST LIGHTING SYSTEM - CEK CUTTING LIST NAVIGATION LIGHT | 1CL100 - Biro Desain Sistem Kelistrikan | 13-Oct-25 | 2025-11-01 | 1 | PRIYONO | 153 | JC300925 25718
317 | 30 Sept. 2025 | W000305 | - EVATEK LIGHTING FIXTURES GLAMOX - EVATEK LIGHTING FIXTURES International Offshore Industries - CEK CUTTING LIST EMERGENCY LIGHTING SYSTEM - CEK CUTTING LIST OF GPU - CEK CUTTING LIST OF LAUNDRY EQUIPMENT | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Oct-25 | 2025-11-01 | 1 | RENDRA | 144 | JC300925 25719
318 | 30 Sept. 2025 | W000308 | CEK INSTALL. MAIN CABLE WAY BLOCK : 323P/S (1 DK), 323P/S (01 DK), 424P, 424S (02 DK), 611P, 611S, 531P, 531S, 631P, 631S (03 DK) | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Oct-25 | 2025-11-01 | 1 | ADI | 250 | JC300925 25720
319 | 30 Sept. 2025 | W000306 | - LIGHTING FIXTURE DAEYANG | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Oct-25 | 08-Oct-25 | 1 | ALDI | 66 | JC300925 25721
320 | 30 Sept. 2025 | W000306 | - REVISI ONE LINE DIAGRAM GENERAL ILLUMINATION SYSTEM - REVISI ONE LINE DIAGRAM EMERGENCY LIGHTING - REVISI ARR'T LIGHTING 05 DEK | 1CL100 - Biro Desain Sistem Kelistrikan | 09-Oct-25 | 22-Oct-25 | 1 | ALDI | 101 | JC300925 25722
321 | 30 Sept. 2025 | W000308 | - ROUTING CABLE MAIN POWER GENERATION SYSTEM - ROUTING CABLE EMERGENCY POWER GENERATION | 1CL100 - Biro Desain Sistem Kelistrikan | 23-Oct-25 | 2025-11-01 | 1 | ALDI | 77 | JC300925 25723
322 | 30 Sept. 2025 | W000305 | - UNBALLANCE ANALYSIS - HARMONIC ANALYSIS | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Oct-25 | 21-Oct-25 | 1 | ALDO | 156 | JC300925 25724
323 | 30 Sept. 2025 | W000308 | - EVATEK MAKER MACHINERY EQUIPMENT - EVATEK HULL OUTFITTING EQUIPMENT | 1CL100 - Biro Desain Sistem Kelistrikan | 22-Oct-25 | 2025-11-01 | 1 | ALDO | 88 | JC300925 25725
324 | 30 Sept. 2025 | W000308 | - ROUTING CABLE 440V SYSTEM - ROUTING CABLE 230V SYSTEM - ROUTING CABLE 24V SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Oct-25 | 2025-11-01 | 1 | NOVAL | 244 | JC300925 25726
325 | 30 Sept. 2025 | W000305 | CEK CUTTING LIST : - MECHANICAL VENTILATION FAN SYSTEM - MONORAIL SYSTEM - MOORING & TOWING SYSTEM - RHIB DAVIT DOOR - CEK CUTTING LIST SOCKET OUTLET | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Oct-25 | 2025-11-01 | 1 | YOGI | 244 | JC300925 25727
326 | 2025-09-30 | W000305 | RE-ROUTING CABLE FOR IPMS BASED ON OLD REV-1 | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-09-29 | 2025-09-30 | 1 | CANDRA |  | JC300925 25732
327 | 1-Oct-25 | W000304 | E14282.25300 -ONE LINE DIAGRAM OF RUDDER ANGLE INDICATOR (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 1-Oct-25 | 8-Oct-25 | 1 | nisa |  | JC011025 25767
328 | 1-Oct-25 | W000304 | E14262.25300-ONE LINE DIAGRAM OF SPEED LOG (rev.2) | 1CL400 - Biro Desain Sistem Elektronika | 1-Oct-25 | 8-Oct-25 | 1 | azis |  | JC011025 25768
329 | 1-Oct-25 | W000304 | E14282.25300-ONE LINE DIAGRAM OF AUTOPILOT SYSTEM (rev.2) | 1CL400 - Biro Desain Sistem Elektronika | 1-Oct-25 | 8-Oct-25 | 1 | ferry |  | JC011025 25769
330 | 2-Oct-25 | W000304 | ARRT OF HIGH PRESSURE SEA WATER SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2-Oct-25 | 8-Oct-25 | 1 | REGINA |  | JC021025 25814
331 | 2-Oct-25 | W000306 | EVATEK HELI REFUELING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 1-Oct-25 | 2-Oct-25 | 1 | CANDRA |  | JC021025 25816
332 | 2-Oct-25 | W000304 | RE-WIRING FOR CABLE IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2-Oct-25 | 15-Oct-25 | 1 | CANDRA |  | JC021025 25825
333 | 2-Oct-25 | W000305 | OLD OF HIGH PRESSURE SEA WATER SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 3-Oct-25 | 8-Oct-25 | 1 | RIANTO |  | JC021025 25820
334 | 2-Oct-25 | W000305 | ROUTING & WIRING DIAGRAM OF HPSW | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 3-Oct-25 | 11-Oct-25 | 1 | ALAM |  | JC021025 25821
335 | 2-Oct-25 | W000304 | UPDATE JALUR MCT SISTEM LAN | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 1-Oct-25 | 2-Oct-25 | 1 | ALAM |  | JC021025 25826
336 | 9-Oct-25 | W000308 | EVATEK RCV FOR DEWATERING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 9-Oct-25 | 10-Oct-25 | 1 | RIANTO |  | JC091025 26161
337 | 9-Oct-25 | W000306 | ESTIMATION CABLE CUTTING FOR ICCP | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 9-Oct-25 | 13-Oct-25 | 1 | REGINA |  | JC091025 26162
338 | 9-Oct-25 | W000306 | ESTIMATION CABLE CUTTING FOR MGPS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 14-Oct-25 | 16-Oct-25 | 1 | REGINA |  | JC091025 26163
339 | 10-Oct-25 | W000304 | E14282.16300 -ARR'T. OF RUDDER ANGLE INDICATOR (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 9-Oct-25 | 16-Oct-25 | 1 | nisa |  | JC101025 26188
340 | 10-Oct-25 | W000304 | E14262.16300 - ARR'T. OF SPEED LOG(rev.2) | 1CL400 - Biro Desain Sistem Elektronika | 9-Oct-25 | 16-Oct-25 | 1 | azis |  | JC101025 26189
341 | 10-Oct-25 | W000304 | E14282.26300-CONNECTION DIAGRAM OF AUTOPILOT SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 9-Oct-25 | 16-Oct-25 | 1 | ferry |  | JC101025 26190
342 | 13-Oct-25 | W000308 | EVATEK RCV FOR PREWETTING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 13-Oct-25 | 15-Oct-25 | 1 | RIANTO |  | JC131025 26341
343 | 13-Oct-25 | W000306 | ESTIMATION CABLE CUTTING FOR PROP. CONTROL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 13-Oct-25 | 18-Oct-25 | 1 | ALAM |  | JC131025 26342
344 | 15-Oct-25 | W000308 | REVIEW & EVALUASI APPROVAL DRAWING MAKER STEERING GEAR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 16-Oct-25 | 17-Oct-25 | 1 | RIANTO |  | JC151025 26427
345 | 15-Oct-25 | W000306 | REVISI-1 OLD OF RO-RO EQUIPMENT SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 16-Oct-25 | 21-Oct-25 | 1 | CANDRA |  | JC151025 26428
346 | 15-Oct-25 | W000306 | REVISI-1 ARR'T OF RO-RO EQUIPMENT SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 22-Oct-25 | 24-Oct-25 | 1 | CANDRA |  | JC151025 26429
347 | 2025-10-17 | W000304 | REVISI-1 OLD OF PROPULSION CONTROL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-10-20 | 2025-10-27 | 1 | RIANTO |  | JC171025 26472
348 | 17-Oct-25 | W000306 | UPDATE KONTROL BERAT (KB-02) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 17-Oct-25 | 21-Oct-25 | 1 | REGINA |  | JC171025 26477
349 | 17-Oct-25 | W000306 | ESTIMATION CABLE CUTTING FOR HANGAR DOOR | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 22-Oct-25 | 27-Oct-25 | 1 | REGINA |  | JC171025 26478
350 | 17-Oct-25 | W000306 | ESTIMATION CABLE CUTTING FOR LAN | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 28-Oct-25 | 2025-11-05 | 1 | REGINA |  | JC171025 26479
351 | 17-Oct-25 | W000306 | ESTIMATION CABLE CUTTING FOR SLC | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 20-Oct-25 | 22-Oct-25 | 1 | ALAM |  | JC171025 26482
352 | 17-Oct-25 | W000306 | ESTIMATION CABLE CUTTING FOR STARTING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 23-Oct-25 | 28-Oct-25 | 1 | ALAM |  | JC171025 26483
353 | 17-Oct-25 | W000306 | ESTIMATION CABLE CUTTING FOR SERVICE & WORKING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 29-Oct-25 | 31-Oct-25 | 1 | ALAM |  | JC171025 26484
354 | 17-Oct-25 | W000306 | REVIEW & EVALUASI APPROVAL DRAWING MAKER HELI REFUELING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 27-Oct-25 | 28-Oct-25 | 1 | CANDRA |  | JC171025 26485
355 | 17-Oct-25 | W000304 | E14282.26301 -CONNECTION DIAGRAM OF RUDDER ANGLE INDICATOR (RAI) | 1CL400 - Biro Desain Sistem Elektronika | 17-Oct-25 | 23-Oct-25 | 1 | nisa |  | JC171025 26486
356 | 17-Oct-25 | W000304 | E14241.26300 -CONNECTION DIAGRAM OF ECHO SOUNDER | 1CL400 - Biro Desain Sistem Elektronika | 17-Oct-25 | 23-Oct-25 | 1 | azis |  | JC171025 26490
357 | 17-Oct-25 | W000308 | E14000.75300-MAIN EQUIPMENT LIST OF ELECTRONIC SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 17-Oct-25 | 23-Oct-25 | 1 | ferry |  | JC171025 26491
358 | 23-Oct-25 | W000306 | E24000.01300 -ESTIMATE QUANTITY OF MATERIAL ELECTRONIC PART (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 24-Oct-25 | 31-Oct-25 | 1 | nisa |  | JC231025 26733
359 | 23-Oct-25 | W000304 | E14262.26300 -CONNECTION DIAGRAM OF SPEED LOG | 1CL400 - Biro Desain Sistem Elektronika | 24-Oct-25 | 31-Oct-25 | 1 | azis |  | JC231025 26734
360 | 23-Oct-25 | W000308 | E24000.01300 -ESTIMATE QUANTITY OF MATERIAL ELECTRONIC PART | 1CL400 - Biro Desain Sistem Elektronika | 24-Oct-25 | 31-Oct-25 | 1 | ferry |  | JC231025 26735
361 | 29-Oct-25 | W000306 | REVIEW & EVALUASI APPROVAL DRAWING MAKER RO-RO EQUIPMENT SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 29-Oct-25 | 31-Oct-25 | 1 | CANDRA |  | JC291025 26966
362 | 2025-10-29 | W000304 | REVISI-1 OLD OF PROPULSION CONTROL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-10-28 | 2025-10-31 | 1 | RIANTO |  | JC291025 26967
2025-11-01
363 | 2025-10-30 | W000305 | - EVATEK APPROVAL DRAWING MCC, DB, MSB, ESB - CONNECTION MAIN POWER GENERATION - CONNECTION POWER DISTRIBUTION 440V SYSTEM - CONNECTION POWER DISTRIBUTION 230V SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-11-03 | 2025-11-29 | 1 | HARI | 200 | JC311025 27036
364 | 2025-10-30 | W000305 | - CEK REVISI WIRING NAVIGATION LIGHTING SYSTEM - CEK RECUTTING CABLE NAVIGATION LIGHT - CEK CABLE CUTTING AC SYSTEM - CEK CABLE CUTTING AHU SYSTEM - CEK CABLE CUTTING COOLING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-11-03 | 2025-11-29 | 1 | PRIYONO | 200 | JC311025 27037
365 | 2025-10-30 | W000305 | - EVATEK LIGHTING FIXTURES WESCO - EVATEK LIGHTING FIXTURES International Offshore Industries - EVATEK LIGHTING FIXTURES DAEYANG - EVATEK LIGHTING FIXTURES NAWASENA - CEK CUTTING LIST EMERGENCY LIGHTING SYSTEM - CEK CUTTING LIST SOCKET OUTLET | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-11-03 | 2025-11-29 | 1 | RENDRA | 220 | JC311025 27038
366 | 2025-10-30 | W000308 | CEK INSTALL. MAIN CABLE WAY BLOCK : 412P/S (1 DK), 533P/S (01 DK), 353P/S (01 DK), 343P/S (01 DK), 353P/S (01 DK), 511P/S (03 DK), 621P/S (03 DK) | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-11-03 | 2025-11-29 | 1 | ADI | 220 | JC311025 27039
367 | 2025-10-30 | W000306 | - EVATEK LIGHTING FIXTURE DAEYANG - EVATEK LIGHTING FIXTURE HAIXING (K POWER) - EVATEK LIGHTING FIXTURE GLAMOX (KARISMA TEKINDO) - EVATEK LIGHTING FIXTURE KOTA MINYAK - REVIEW COMMENT OWNER O.L.D POWER DISTRIBUTION 440V SYSTEM - REVIEW COMMENT OWNER O.L.D POWER DISTRIBUTION 220V SYSTEM - REVIEW COMMENT OWNER O.L.D POWER DISTRIBUTION 115V/60HZ SYSTEM - REVIEW COMMENT OWNER O.L.D POWER DISTRIBUTION 24V SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-11-03 | 2025-11-29 | 1 | ALDI | 220 | JC061125 27332
368 | 2025-10-30 | W000308 | - EVATEK MAKER MACHINERY EQUIPMENT - EVATEK HULL OUTFITTING EQUIPMENT - REVISI O.L.D GALLEY EQUIPMENT SYSTEM - REVISI ELECTRICAL ARR'T GALLEY EQUIPMENT - REVISI O.L.D SOCKET OUTLET - REVISI ELECTRICAL ARR'T SOCKET OUTLET | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-11-03 | 2025-11-29 | 1 | ALDO | 220 | JC311025 27042
369 | 2025-10-30 | W000308 | - ROUTING CABLE POWER DISTRIBUTION 115V/60HZ SYSTEM - ROUTING CABLE POWER DISTRIBUTION 115V/400HZ SYSTEM - ROUTING CABLE SEA WATER COOLING SYSTEM - ROUTING CABLE OF FRESH WATER COOLING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-11-03 | 2025-11-29 | 1 | NOVAL | 220 | JC311025 27043
370 | 2025-10-30 | W000305 | - ELECTRICAL ARR'T MECHANICAL VENTILATION FAN SYSTEM - CEK CUTTING LIST LAUNDRY EQUIPMENT - CEK CUTTING LIST G.P.U | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-11-03 | 2025-11-22 | 1 | YOGI | 165 | JC311025 27044
371 | 2025-10-30 | W000308 | - ROUTING CABLE FUEL OIL SYSTEM - ROUTING CABLE LUBRICATING OIL SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-11-24 | 2025-11-29 | 1 | YOGI | 55 | JC311025 27067
372 | 2025-11-03 | W000304 | E14339.27300 -WIRING DIAGRAM OF TIME INDICATION SYSTEM (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-11-03 | 2025-11-10 | 1 | nisa |  | JC031125 27170
373 | 2025-11-03 | W000304 | E14241.27300-WIRING DIAGRAM OF ECHO SOUNDER (rev.2) | 1CL400 - Biro Desain Sistem Elektronika | 2025-11-03 | 2025-11-10 | 1 | azis |  | JC031125 27171
374 | 2025-11-03 | W000304 | E14282.27300-WIRING DIAGRAM OF AUTOPILOT SYSTEM(rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-11-03 | 2025-11-10 | 1 | ferry |  | JC031125 27172
375 | 2025-11-03 | W000306 | UPDATE 3D MODEL FOR RO-RO EQUIPMENT | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-11-03 | 2025-11-05 | 1 | CANDRA |  | JC031125 27190
376 | 2025-11-03 | W000306 | ESTIMATION CABLE CUTTING FOR STEERING GEAR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-11-03 | 2025-11-10 | 1 | ALAM |  | JC031125 27191
377 | 2025-11-03 | W000306 | ESTIMATION CABLE CUTTING FOR TANK LEVEL & DRAUGHT INDICATING | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-11-06 | 2025-11-12 | 1 | REGINA |  | JC031125 27192
378 | 2025-11-03 | W000304 | REVISI-1 OLD OF STEERING GEAR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-11-03 | 2025-11-11 | 1 | RIANTO |  | JC031125 27195
379 | 2025-11-03 | W000304 | RE-ROUTING CABLE FOR PROPULSION CONTROL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-11-06 | 2025-11-12 | 1 | CANDRA |  | JC031125 27196
380 | 2025-11-03 | W000304 | RE-WIRING DIAGRAM OF PROPULSION CONTROL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-11-13 | 2025-11-19 | 1 | CANDRA |  | JC031125 27197
381 | 2025-11-10 | W000304 | E14363.27300 -WIRING DIAGRAM OF LOCK-IN ALARM SYSTEM (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-11-11 | 2025-11-18 | 1 | nisa |  | JC101125 27565
382 | 2025-11-10 | W000304 | E14262.27300-WIRING DIAGRAM OF SPEED LOG(rev.2) | 1CL400 - Biro Desain Sistem Elektronika | 2025-11-11 | 2025-11-18 | 1 | azis |  | JC101125 27568
383 | 2025-11-10 | W000304 | E14282.27301 - WIRING DIAGRAM OF RUDDER ANGLE INDICATOR (RAI)(rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-11-11 | 2025-11-18 | 1 | ferry |  | JC101125 27570
384 | 2025-11-11 | W000306 | ESTIMATION CABLE CUTTING FOR BOW THRUSTER SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-11-11 | 2025-11-17 | 1 | ALAM |  | JC121125 27621
385 | 2025-11-11 | W000304 | REVISI-1 OLD OF STEERING GEAR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-11-12 | 2025-11-14 | 1 | RIANTO |  | JC121125 27622
386 | 2025-11-14 | W000304 | UPDATE 3D MODEL FOR PCS EQUIPMENT | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-11-13 | 2025-11-14 | 1 | REGINA |  | JC141125 27708
387 | 14 Nop. 2025 | W000304 | - REV. WIRING DIAGRAM SOCKET OUTLET - REV. WIRING DIAGRAM MAIN POWER GENERATION | 1CL100 - Biro Desain Sistem Kelistrikan | 2025-11-12 | 2025-11-29 | 1 | ARIZAL | 134 | JC141125 27711
388 | 2025-11-17 | W000304 | WEIGHT CONTROL OF CONTROL & AUTOMATION OUTFITTING (KB04) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-11-18 | 2025-11-24 | 1 | ALAM |  | JC171125 27833
389 | 2025-11-17 | W000306 | ESTIMATION CABLE CUTTING FOR IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-11-25 | 2025-12-08 | 1 | ALAM |  | JC171125 27834
390 | 2025-11-17 | W000304 | PRINCIPLE PARTICULAR OF CONTROL & AUTOMATION | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-11-17 | 2025-11-24 | 1 | REGINA |  | JC171125 27835
391 | 2025-11-17 | W000304 | LIST OF SPARE PART CONTROL & AUTOMATION SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-11-25 | 2025-11-28 | 1 | REGINA |  | JC171125 27836
392 | 2025-11-17 | W000306 | WEIGHT CONTROL OF CONTROL & AUTOMATION OUTFITTING (KB03) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-12-01 | 2025-12-08 | 1 | REGINA |  | JC171125 27839
393 | 2025-11-17 | W000304 | UPDATE EQUIPMENT 3D MODEL OF STEERING GEAR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-11-17 | 2025-11-19 | 1 | RIANTO |  | JC171125 27841
394 | 2025-11-17 | W000304 | CONNECTION DIAGRAM OF STEERING GEAR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-11-20 | 2025-11-28 | 1 | RIANTO |  | JC171125 27843
395 | 2025-11-17 | W000304 | REVISI-1 E15553.25200 OLD OF FIXED GAS FIRE EXTINGUISHING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-11-20 | 2025-11-22 | 1 | CANDRA |  | JC171125 27844
396 | 2025-11-17 | W000304 | REVISI-1 E14370.25200 OLD OF TANK LEVEL AND DRAUGHT INDICATING | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-11-24 | 2025-11-25 | 1 | CANDRA |  | JC171125 27846
397 | 2025-11-17 | W000304 | CONNECTION DIAGRAM OF ACTIVE STABILIZING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-11-26 | 2025-11-29 | 1 | CANDRA |  | JC171125 27850
398 | 2025-11-18 | W000304 | E14339.26300 -CONNECTION DIAGRAM OF TIME INDICATION SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2025-11-19 | 2025-11-25 | 1 | nisa |  | JC181125 27890
399 | 2025-11-18 | W000304 | E14211.16300-ARR'T. OF MAGNETIC COMPASS(rev.2) | 1CL400 - Biro Desain Sistem Elektronika | 2025-11-19 | 2025-11-25 | 1 | azis |  | JC181125 27891
400 | 2025-11-18 | W000304 | E94000.92304 - WEIGHT CONTROL OF ELECTRONIC OUT FITTING (KB04) | 1CL400 - Biro Desain Sistem Elektronika | 2025-11-19 | 2025-11-25 | 1 | ferry |  | JC181125 27892
401 | 2025-11-26 | W000304 | E14363.27300 -WIRING DIAGRAM OF LOCK-IN ALARM SYSTEM (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2025-11-26 | 2025-11-29 | 1 | nisa |  | JC261125 28151
402 | 2025-11-26 | W000304 | E14262.26300-CONNECTION DIAGRAM OF SPEED LOG | 1CL400 - Biro Desain Sistem Elektronika | 2025-11-26 | 2025-11-29 | 1 | azis |  | JC261125 28152
403 | 2025-11-26 | W000304 | E14321.26300 -CONNECTION DIAGRAM OF AUTOMATIC EXCHANGE TELEPHONE | 1CL400 - Biro Desain Sistem Elektronika | 2025-11-26 | 2025-11-29 | 1 | ferry |  | JC261125 28153
2025-12-01
404 | 1-Dec-25 | W000304 | E14210.26300 -CONNECTION DIAGRAM OF WHISTLE SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 1-Dec-25 | 8-Dec-25 | 1 | nisa |  | JC011225 28397
405 | 1-Dec-25 | W000304 | E14942.26300-CONNECTION DIAGRAM OF WEATHER FACSIMILE RECEIVER | 1CL400 - Biro Desain Sistem Elektronika | 1-Dec-25 | 8-Dec-25 | 1 | azis |  | JC011225 28398
406 | 1-Dec-25 | W000304 | E14321.27300-WIRING DIAGRAM OF AUTOMATIC EXCHANGE TELEPHONE(rev.2) | 1CL400 - Biro Desain Sistem Elektronika | 1-Dec-25 | 8-Dec-25 | 1 | ferry |  | JC011225 28399
407 | 2025-12-01 | W000305 | - EVATEK APPROVAL DRAWING MCC, DB, MSB, ESB - EVATEK HULL EQUIPMENT - EVATEK MACHINERY EQUIPMENT - CHECK CONNECTION OF EMERGENCY POWER GENERATION - CHECK CONNECTION OF GALLEY EQUIPMENT - CHECK CONNECTION OF LAUNDRY EQUIPMENT - CHECK CONNECTION OF WORKSHOP EQUIPMENT - CHECK CONNECTION OF BALLAST WATER EQUIPMENT - CHECK CONNECTION OF ANCHOR WINCH/CAPSTANS - CHECK CONNECTION OF MOORING & TOWING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Dec-25 | 31-Dec-25 | 1 | HARI | 208 | JC011225 28401
408 | 2025-12-01 | W000305 | - REVIEW MCW BLOCK 223P, 223S, 233P, 233S, 243P, 243S, 153P, 153S, 323C, 244P, 244S, 254P, 254S, 154P, 154S | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Dec-25 | 20-Dec-25 | 1 | PRIYONO | 162 | JC011225 28402
409 | 2025-12-01 | W000306 | - EVATEK MSB SET | 1CL100 - Biro Desain Sistem Kelistrikan | 22-Dec-25 | 31-Dec-25 | 1 | PRIYONO | 54 | JC011225 28403
410 | 2025-12-01 | W000305 | - EVATEK LIGHTING FIXTURE BATCH 2 - REVISI MATERIAL LIST - LIST OF TOOL - REVIEW MCW BLOCK 611P, 611S, 621P, 621S, 631P, 631S, 641P, 641S, 641P, 641S | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Dec-25 | 31-Dec-25 | 1 | RENDRA | 228 | JC011225 28406
411 | 2025-12-01 | W000305 | REVIEW & CEK REVISI MCW BLOCK 651P, 651S, 541P, 541S, 155P, 155S, 315P, 612P, 612S, 622P, 622S, 632P, 632S, 642P, 642S, 652P, 652S,542P, 542S, 623P, 623S | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Dec-25 | 31-Dec-25 | 1 | ADI | 228 | JC011225 28407
412 | 2025-12-01 | W000306 | - EVATEK LIGHTING FIXTURE DAEYANG - EVATEK LIGHTING FIXTURE HAIXING (K POWER) - EVATEK LIGHTING FIXTURE GLAMOX (KARISMA TEKINDO) - EVATEK LIGHTING FIXTURE KOTA MINYAK | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Dec-25 | 13-Dec-25 | 1 | ALDI | 110 | JC011225 28404
413 | 2025-12-01 | W000305 | "- REVIEW ARR'T MCT & DETAIL PENETRATION | 1CL100 - Biro Desain Sistem Kelistrikan | 15-Dec-25 | 31-Dec-25 | 1 | ALDI | 118 | JC011225 28408
414 | 2025-12-01 | W000308 | - EVATEK TRANSFORMER, TRANSFORMER CALCULATION | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Dec-25 | 13-Dec-25 | 1 | ALDO | 110 | JC011225 28414
415 | 2025-12-01 | W000305 | "- REVIEW ARR'T MCT & DETAIL PENETRATION - PRINCIPAL PARTICULAR OF ELECTRIC EQUIPMENT | 1CL100 - Biro Desain Sistem Kelistrikan | 15-Dec-25 | 31-Dec-25 | 1 | ALDO | 118 | JC011225 28409
416 | 2025-10-30 | W000305 | - REVIEW WIRING DIAGRAM EMERGENCY LIGHTING SYSTEM - REVISI WIRING DIAGRAM 220V SYSTEM - UPDATE CONNECTION DIAGRAM OF MONORAIL - UPDATE CONNECTION AIR CRAFT HANDLING & SERVICE SYSTEM - UPDATE CONNECTION OF COOLING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Dec-25 | 31-Dec-25 | 1 | NOVAL | 228 | JC011225 28410
417 | 2025-10-30 | W000305 | "- REVIEW MCW BLOCK 503P, 503S, 513P, 513S, 523P, 523S, 533P, 533S, 514C, 524P, 524S, 515C & DETAIL PENETRATION | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Dec-25 | 31-Dec-25 | 1 | YOGI | 228 | JC011225 28411
418 | 2025-12-01 | W000305 | "- REVIEW ARR'T MCT & DETAIL PENETRATION | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Dec-25 | 31-Dec-25 | 1 | ARIZAL | 228 | JC011225 28412
419 | 2025-12-02 | W000304 | CONNECTION DIAGRAM OF STEERING GEAR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-12-01 | 2025-12-05 | 1 | RIANTO |  | JC021225 28514
420 | 2025-12-02 | W000304 | RE-CHECK PENETRASI MCT UNTUK SISTEM IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-12-01 | 2025-12-06 | 1 | CANDRA |  | JC021225 28515
421 | 2025-12-08 | W000304 | REVISI WIRING OF STEERING GEAR SYSTEM, TANK LEVEL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-12-08 | 2025-12-13 | 1 | REGINA |  | JC081225 28764
422 | 2025-12-08 | W000304 | REVISI WIRING OF IPMS, PCS, AVIATION FUEL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-12-08 | 2025-12-19 | 1 | CANDRA |  | JC081225 28766
423 | 2025-12-08 | W000304 | REVISI WIRING OF ACTIVE STABILIZER SYSTEM, RCV | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-12-08 | 2025-12-19 | 1 | RIANTO |  | JC081225 28767
424 | 2025-12-08 | W000304 | REVISI WIRING OF SIGNAL LIGHT COLUMN | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-12-08 | 2025-12-13 | 1 | ALAM |  | JC081225 28765
425 | 9-Dec-25 | W000304 | E14210.27300 -WIRING DIAGRAM OF WHISTLE SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 9-Dec-25 | 16-Dec-25 | 1 | nisa |  | JC091225 28900
426 | 9-Dec-25 | W000304 | E14211.26300-CONNECTION DIAGRAM OF MAGNETIC COMPASS | 1CL400 - Biro Desain Sistem Elektronika | 9-Dec-25 | 16-Dec-25 | 1 | azis |  | JC091225 28901
427 | 9-Dec-25 | W000304 | E14321.27300-WIRING DIAGRAM OF AUTOMATIC EXCHANGE TELEPHONE(rev.2) | 1CL400 - Biro Desain Sistem Elektronika | 9-Dec-25 | 16-Dec-25 | 1 | ferry |  | JC091225 28902
428 | 10-Dec-25 | W000306 | E94000.92303 - WEIGHT CONTROL OF ELECTRONIC OUT FITTING (KB03) | 1CL400 - Biro Desain Sistem Elektronika | 10-Dec-25 | 16-Dec-25 | 1 | nisa |  | JC101225 28922
429 | 2025-12-15 | W000304 | REVISI WIRING OF IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-12-15 | 2025-12-20 | 1 | CANDRA | 54 | JC151225 29127
430 | 2025-12-15 | W000304 | REVISI WIRING OF PCS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-12-15 | 2025-12-20 | 1 | ALAM | 54 | JC151225 29128
431 | 2025-12-15 | W000304 | REVISI WIRING OF TANK LEVEL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-12-15 | 2025-12-15 | 1 | REGINA |  | JC151225 29129
432 | 2025-12-15 | W000304 | REVISI WIRING OF RCV | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-12-15 | 2025-12-20 | 1 | RIANTO | 54 | JC151225 29130
433 | 2025-12-16 | W000304 | REVISI WIRING OF IPMS (RTU-16) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-12-16 | 2025-12-20 | 1 | REGINA |  | JC161225 29166
434 | 17-Dec-25 | W000304 | E14341.27300 -WIRING DIAGRAM OF CENTRAL AERIAL SYSTEM (rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 17-Dec-25 | 31-Dec-25 | 1 | nisa |  | JC171225 29213
435 | 17-Dec-25 | W000304 | E14263.26300-CONNECTION DIAGRAM OF NAVIGATION RADAR | 1CL400 - Biro Desain Sistem Elektronika | 17-Dec-25 | 31-Dec-25 | 1 | azis |  | JC171225 29214
436 | 17-Dec-25 | W000304 | E14331.26300-CONNECTION DIAGRAM OF PUBLIC ADDRESS SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 17-Dec-25 | 31-Dec-25 | 1 | ferry |  | JC171225 29215
437 | 2025-12-22 | W000304 | PENYELESAIAN PEKERJAAN REVISI DRAWING WIRING DIAGRAM IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-12-22 | 2025-12-31 | 1 | CANDRA |  | JC221225 29385
438 | 2025-12-22 | W000304 | PENYELESAIAN PEKERJAAN REVISI DRAWING WIRING DIAGRAM PCS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-12-22 | 2025-12-31 | 1 | ALAM |  | JC221225 29386
439 | 2025-12-22 | W000304 | PENYELESAIAN PEKERJAAN REVISI DRAWING WIRING DIAGRAM ST. GEAR SYSTEM & TANK LEVEL & INDICATION SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-12-22 | 2025-12-31 | 1 | REGINA |  | JC221225 29388
440 | 2025-12-22 | W000304 | PENYELESAIAN PEKERJAAN REVISI DRAWING WIRING DIAGRAM PCS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2025-12-22 | 2025-12-31 | 1 | RIANTO |  | JC221225 29389
2026-01-01
441 | 2025-12-31 | W000305 | - EVATEK APPROVAL DRAWING MSB SET | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-01-02 | 2026-01-31 | 1 | HARI | 200 | JC311225 29708
442 | 2025-12-31 | W000306 | - EVATEK APPROVAL DRAWING MSB SET - ATO MSB - ATO ESB - ATO DB 440V PS - ATO DB 220V LS - ATO DB 220V WS - ATO DB 115V/60HZ - ATO DB 115V/400HZ - ATO INDIVIDUAL STARTER - ATO MCC - ATO BATTERY CHARGER - ATO BATTERY | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-01-02 | 2026-01-31 | 1 | PRIYONO | 200 | JC311225 29709
443 | 2025-12-31 | W000311 | - ARR'T MCW - OLD ELECTRIC SYSTEM - ARR'T OF ELECTRIC SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-01-02 | 2026-01-31 | 1 | RENDRA | 214 | JC311225 29711
444 | 2025-12-31 | W000306 | - REVIEW INSTALL MAIN CABLE WAY ALL DECK | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-01-02 | 2026-01-10 | 1 | ADI | 60 | JC311225 29712
445 | 2025-12-31 | W000308 | - CEK INSTALL MCW BLOCK 512P, 522P, 522S, 532P, 622P, 622S,642P, 642S, 632P, 632S | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-01-12 | 2026-01-31 | 1 | ADI | 160 | JC311225 29713
446 | 2025-12-31 | W000306 | - REV. ONE LINE DIAGRAM OF EMERGENCY LIGHTING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-01-02 | 2026-01-10 | 1 | ALDI | 54 | JC311225 29714
447 | 2025-12-31 | W000308 | - WIRING DIAGRAM POWER DISTRIBUTION 220V SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-01-12 | 2026-01-31 | 1 | ALDI | 166 | JC311225 29715
448 | 2025-12-31 | W000308 | - WIRING DIAGRAM POWER DISTRIBUTION 440V SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-01-02 | 2026-01-31 | 1 | ALDO | 214 | JC311225 29716
449 | 2025-12-31 | W000306 | - WIRING DIAGRAM LIGHTING SYSTEM E/R DECK - WIRING DIAGRAM LIGTHTING SYSTEM MAIN DECK | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-01-02 | 2026-01-31 | 1 | NOVAL | 214 | JC311225 29718
450 | 2025-12-31 | W000306 | - WIRING DIAGRAM LIGHTING SYSTEM 01 DECK - WIRING DIAGRAM LIGTHTING SYSTEM 02 DECK | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-01-02 | 2026-01-31 | 1 | YOGI | 214 | JC311225 29719
451 | 2025-12-31 | W000306-JW1 | - ARR'T MCW - OLD ELECTRIC SYSTEM - ARR'T OF ELECTRIC SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-01-02 | 2026-01-31 | 1 | ARIZAL | 214 | JC311225 29720
452 | w | W000304 | PENYELESAIAN PEKERJAAN REVISI DRAWING WIRING DIAGRAM PCS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-01-02 | 2026-01-02 | 1 | ALAM |  | JC020126 29791
453 | 2026-01-02 | W000304 | PENYELESAIAN PEKERJAAN REVISI DRAWING WIRING DIAGRAM PCS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-01-02 | 2026-01-02 | 1 | RIANTO |  | JC020126 29792
454 | 2026-01-02 | W000304 | E14341.26300 -CONNECTION DIAGRAM OF CENTRAL AERIAL SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-01-02 | 2026-01-10 | 1 | nisa |  | JC020126 29793
455 | 2026-01-02 | W000304 | E14263.27300-WIRING DIAGRAM OF NAVIGATION RADAR( rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2026-01-02 | 2026-01-10 | 1 | azis |  | JC020126 29794
456 | 2026-01-02 | W000304 | E14282.27300-WIRING DIAGRAM OF AUTOPILOT SYSTEM ( rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2026-01-02 | 2026-01-10 | 1 | ferry |  | JC020126 29795
457 | 2026-01-05 | W000304 | PENYELESAIAN PEKERJAAN REVISI DRAWING WIRING DIAGRAM PCS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-01-05 | 2026-01-12 | 1 | ALAM | 56 | JC050126 29973
458 | 2026-01-05 | W000304 | PENYELESAIAN PEKERJAAN REVISI DRAWING WIRING DIAGRAM PCS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-01-05 | 2026-01-12 | 1 | RIANTO | 56 | JC050126 29974
459 | 2026-01-05 | W000304 | UPDATE & REVIEW 3D MODEL ARRANGEMENT PERALATAN SISTEM PROPULSI | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-01-05 | 2026-01-09 | 1 | REGINA |  | JC050126 29975
460 | 2026-01-05 | W000304 | REVIEW ROUTING & CABLE CUTTING LIST UNTUK SISTEM IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-01-05 | 2026-01-24 | 1 | CANDRA | 150 | JC050126 29976
461 | 2026-01-12 | W000304 | E14921.26300 -CONNECTION DIAGRAM OF HELICOPTER VISUAL LANDING AID | 1CL400 - Biro Desain Sistem Elektronika | 2026-01-12 | 2026-01-19 | 1 | nisa |  | JC120126 30228
462 | 2026-01-12 | W000304 | E14263.26300-CONNECTION DIAGRAM OF NAVIGATION RADAR | 1CL400 - Biro Desain Sistem Elektronika | 2026-01-12 | 2026-01-19 | 1 | azis |  | JC120126 30229
463 | 2026-01-12 | W000304 | E16254.26300-CONNECTION DIAGRAM OF WINDOW WIPER SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-01-12 | 2026-01-19 | 1 | ferry |  | JC120126 30230
464 | 2026-01-12 | W000304 | PENYELESAIAN PEKERJAAN REVISI DRAWING WIRING DIAGRAM RCV (RELAY BOX VALVE NO.11~14 | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-01-13 | 2026-01-26 | 1 | ALAM | 120 | JC120126 30262
465 | 2026-01-12 | W000304 | PENYELESAIAN PEKERJAAN REVISI DRAWING WIRING DIAGRAM RCV (RELAY BOX VALVE NO.1~5 | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-01-13 | 2026-01-26 | 1 | RIANTO | 120 | JC120126 30263
466 | 2026-01-12 | W000304 | PENYELESAIAN PEKERJAAN REVISI DRAWING WIRING DIAGRAM RCV (RELAY BOX VALVE NO.6~10 | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-01-12 | 2026-01-24 | 1 | REGINA | 120 | JC120126 30264
467 | 2026-01-20 | W000304 | E14921.27300-WIRING DIAGRAM OF HELICOPTER VISUAL LANDING AID | 1CL400 - Biro Desain Sistem Elektronika | 2026-01-20 | 2026-01-26 | 1 | nisa |  | JC200126 30564
468 | 2026-01-20 | W000311 | ONE LINE DIAGRAM KSSR NAVIGATION | 1CL400 - Biro Desain Sistem Elektronika | 2026-01-20 | 2026-01-26 | 1 | azis |  | JC200126 30567
469 | 2026-01-20 | W000304 | E14331.26300-CONNECTION DIAGRAM OF PUBLIC ADDRESS SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-01-20 | 2026-01-26 | 1 | ferry |  | JC200126 30566
470 | 2026-01-27 | W000304 | E14391.26300-CONNECTION DIAGRAM OF CCTV | 1CL400 - Biro Desain Sistem Elektronika | 2026-01-27 | 2026-01-31 | 1 | nisa |  | JC270126 30789
471 | 2026-01-27 | W000311 | ONE LINE DIAGRAM KSSR NAVIGATION | 1CL400 - Biro Desain Sistem Elektronika | 2026-01-27 | 2026-01-31 | 1 | azis |  | JC270126 30790
472 | 2026-01-27 | W000304 | E14331.26300-CONNECTION DIAGRAM OF PUBLIC ADDRESS SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-01-27 | 2026-01-31 | 1 | ferry |  | JC270126 30791
473 | 2026-01-27 | W000304 | REVIEW REVISI DRAWING WIRING DIAGRAM PROPULSION CONTROL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-01-26 | 2026-02-07 | 1 | RIANTO |  | JC270126 30802
474 | 2026-01-27 | W000304 | PENYELESAIAN PEKERJAAN REVISI DRAWING WIRING DIAGRAM RCV (RELAY BOX VALVE NO.11~14) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-01-26 | 2026-01-31 | 1 | ALAM |  | JC270126 30803
475 | 2026-01-27 | W000304 | PENYELESAIAN PEKERJAAN REVISI DRAWING WIRING DIAGRAM RCV (RELAY BOX VALVE NO.1~5) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-01-26 | 2026-01-31 | 1 | REGINA |  | JC270126 30804
476 | 2026-01-27 | W000304 | REVIEW ROUTING & CABLE CUTTING LIST UNTUK SISTEM IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-01-26 | 2026-01-31 | 1 | REGINA |  | JC270126 30805
2026-02-01 | [11 empty] | NO JC RAMADHAN HOURS
477 | 2026-02-02 | R22PCCXA | - ONE LINE DIAGRAM OF ELECTRIC SYSTEM - WIRING DIAGRAM OF ELECTRIC SYSTEM - MATERIAL LIST OF ELECTRIC SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-02-02 | 2026-02-21 | 1 | HARI | 144 | JC020226 31078 | jika sudah tgl 18, request JC kembali | JC180226 31797 | utk tgl 19-21 februari 2026
478 | 2026-02-02 | W000305 | EVATEK APPROVAL DRAWING UPS, CONVERTER DAN MSB SET | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-02-23 | 2026-02-28 | 1 | HARI | 40 |  | jo ramadhan (revisi) | JC180226 31717 | utk tgl 23-28 februari 2026
479 | 2026-02-02 | W000307 | - CEK WIRING DIAGRAM LIGHTING SYSTEM E/R DECK - CEK WIRING DIAGRAM LIGHTING SYSTEM MAIN DECK - ESTIMATE CABLE CUTTING LIGHTING SYSTEM IN E/R DECK - ESTIMATE CABLE CUTTING LIGHTING SYSTEM IN MAIN DECK | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-02-02 | 2026-02-28 | 1 | PRIYONO | 184 | JC030226 31153 | utk tgl 02-18 februari 2026, sisa Jo 73 jam | JC180226 31718 | utk tgl 19-28 februari 2026
480 | 2026-02-02 | W000311 | - OLD ELECTRIC SYSTEM - ARR'T OF ELECTRIC SYSTEM - WIRING DIAGRAM OF ELECTRIC SYSTEM - ESTIMATE MATERIAL OF ELECTRIC SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-02-02 | 2026-02-28 | 1 | RENDRA | 198 | JC030226 31146 | utk tgl 02-18 februari 2026, sisa Jo 79 jam | JC180226 31719 | utk tgl 19-28 februari 2026
481 | 2026-02-02 | W000308 | - CEK INSTALL MCW BLOCK 513C, 523P, 523S, 633C, 623C, 613C, 525C, 634C, 641P, 641S | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-02-02 | 2026-02-21 | 1 | ADI | 144 | JC030226 31149 | utk tgl 02-18 februari 2026, sisa Jo 20 jam | JC180226 31720 | utk tgl 19-21 februari 2026
482 | 2026-02-02 | W000307 | - CEK REV. INSTALL MCW BLOCK 213P, 213S, 323P, 323S, 413P, 413S | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-02-23 | 2026-02-28 | 1 | ADI | 55 |  | jo ramadhan (revisi) | JC180226 31721
483 | 2026-02-02 | W000305 | - REVISI ARR'T MCT | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-02-02 | 2026-02-07 | 1 | ALDI | 55 | JC020226 31006
484 | 2026-02-02 | W000307 | - EVATEK LIGHTING FIXTURES | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-02-09 | 2026-02-14 | 1 | ALDI | 29 | JC020226 31010
485 | 2026-02-02 | W000308 | - WIRING DIAGRAM POWER DISTRIBUTION 24V SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-02-16 | 2026-02-28 | 1 | ALDI | 113 | JC030226 31156 | utk tgl 16-18 februari 2026, sisa Jo 95 jam | JC180226 31722 | utk tgl 19-28 februari 2026
486 | 2026-02-02 | W000308 | - ROUTING CABLE OF ELECTRIC POWER DISTRIBUTION 115V/60HZ SYSTEM - ROUTING CABLE OF FUEL OIL SYSTEM - ROUTING CABLE OF LUBRICATING OIL SYSTEM - EVATEK ELECTRIC EQUIPMENT, HULL EQUIPMENT | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-02-02 | 2026-02-28 | 1 | ALDO | 158 | JC030226 31157 | utk tgl 02-18 februari 2026, sisa Jo 64 jam | JC180226 31723 | utk tgl 19-28 februari 2026
487 | 2026-02-02 | W000307 | - WIRING DIAGRAM LIGHTING SYSTEM 1 DECK - WIRING DIAGRAM LIGTHTING SYSTEM 03 DECK | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-02-02 | 2026-02-28 | 1 | NOVAL | 189 | JC030226 31158 | utk tgl 02-18 februari 2026, sisa Jo 76 jam | JC180226 31724 | utk tgl 19-28 februari 2026
488 | 2026-02-02 | W000305 | - CONNECTION DIAGRAM OF PD 440V SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-02-02 | 2026-02-07 | 1 | YOGI | 46 | JC020226 31015
489 | 2026-02-02 | W000307 | - WIRING DIAGRAM LIGHTING SYSTEM 04 DECK - WIRING DIAGRAM LIGHTING SYSTEM TOP DECK | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-02-09 | 2026-02-28 | 1 | YOGI | 183 | JC030226 31159 | utk tgl 09-18 februari 2026, sisa Jo 73 jam | JC180226 31725 | utk tgl 19-28 februari 2026
490 | 2026-02-02 | W000306-JW1 | - OLD ELECTRIC SYSTEM - ARR'T OF ELECTRIC SYSTEM - WIRING DIAGRAM OF ELECTRIC SYSTEM - ESTIMATE MATERIAL OF ELECTRIC SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-02-02 | 2026-02-28 | 1 | ARIZAL | 198 | JC030226 31160 | utk tgl 02-18 februari 2026, sisa Jo 79 jam | JC180226 31731 | utk tgl 19-28 februari 2026
491 | 2026-02-02 | W000304 | E14341.27300-WIRING DIAGRAM OF CENTRAL AERIAL SYSTEM ( rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2026-02-02 | 2026-02-09 | 1 | nisa |  | JC020226 31035
492 | 2026-02-02 | W000311 | ONE LINE DIAGRAM KSSR NAVIGATION | 1CL400 - Biro Desain Sistem Elektronika | 2026-02-02 | 2026-02-09 | 1 | azis |  | JC020226 31037
493 | 2026-02-02 | W000304 | E14321.27300-WIRING DIAGRAM OF AUTOMATIC EXCHANGE TELEPHONE ( rev.2) | 1CL400 - Biro Desain Sistem Elektronika | 2026-02-02 | 2026-02-09 | 1 | ferry |  | JC020226 31036
494 | 2026-02-03 | W000304 | ROUTING CHECK FOR MCT WIRING DIAGRAM RCV (RELAY BOX VALVE NO.9~14) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-02-02 | 2026-02-06 | 1 | ALAM |  | JC030226 31175
495 | 2026-02-03 | W000304 | ROUTING CHECK FOR MCT WIRING DIAGRAM RCV (RELAY BOX VALVE NO.1~8) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-02-02 | 2026-02-06 | 1 | REGINA |  | JC030226 31177
496 | 2026-02-03 | W000304 | REVISI ONE LINE DIAGRAM OF FIX GAS FIRE EXTINGUISHING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-02-02 | 2026-02-06 | 1 | CANDRA |  | JC030226 31178
497 | 2026-02-10 | W000304 | REVISI ONE LINE DIAGRAM OF AVIATION FUEL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-02-09 | 2026-02-14 | 1 | CANDRA |  | JC100226 31488
498 | 2026-02-10 | W000304 | CONNECTION DIAGRAM OF AVIATION FUEL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-02-16 | 2026-02-21 | 1 | CANDRA |  | JC100226 31491 | utk tgl 16-18 februari 2026 | JC180226 31732 | utk tgl 19-21 februari 2026
499 | 2026-02-10 | W000304 | ROUTING CHECK FOR MCT WIRING DIAGRAM PROPULSION COTROL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-02-08 | 2026-02-13 | 1 | RIANTO |  | JC100226 31489
500 | 2026-02-10 | W000305 | ONE LINE DIAGRAM OF PROPULSION COTROL SYSTEM REV.2 | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-02-16 | 2026-02-20 | 1 | RIANTO |  | JC100226 31492 | utk tgl 16-18 februari 2026 | JC180226 31734 | utk tgl 19-20 februari 2026
501 | 2026-02-10 | W000304 | CONNECTION DIAGRAM OF FIXED GAS FIRE EXTINGUISHING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-02-23 | 2026-02-28 | 1 | CANDRA |  |  |  | JC180226 31783
502 | 2026-02-11 | W000304 | Cutting List kabel sistem RCV part-2 | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-02-09 | 2026-02-13 | 1 | ALAM |  | JC110226 31504
503 | 2026-02-11 | W000304 | Cutting List kabel sistem RCV part-1 | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-02-09 | 2026-02-13 | 1 | REGINA |  | JC110226 31505
504 | 2026-02-11 | W000308 | Weight kontrol (KB-03) & 3D Cadmatic Model Update | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-02-13 | 2026-02-20 | 1 | REGINA |  | JC110226 31506 | utk tgl 13-18 februari 2026 | JC180226 31736 | utk tgl 19-20 februari 2026
505 | 2026-02-11 | W000308 | E94000.92303-WEIGHT CONTROL OF ELECTRONIC OUT FITTING (KB03) | 1CL400 - Biro Desain Sistem Elektronika | 2026-02-10 | 2026-02-17 | 1 | nisa |  | JC110226 31508
506 | 2026-02-11 | W000304 | E14263.27300-WIRING DIAGRAM OF NAVIGATION RADAR( rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2026-02-10 | 2026-02-17 | 1 | azis |  | JC110226 31509
507 | 2026-02-11 | W000304 | E14331.26300-CONNECTION DIAGRAM OF PUBLIC ADDRESS SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-02-10 | 2026-02-17 | 1 | ferry |  | JC110226 31510
508 | 2026-02-18 | W000308 | E94000.92303-WEIGHT CONTROL OF ELECTRONIC OUT FITTING (KB03) | 1CL400 - Biro Desain Sistem Elektronika | 2026-02-18 | 2026-02-28 | 1 | nisa |  | JC180226 31777 | utk tgl 18 februari 2026 | JC180226 31782 | utk tgl 19-28 februari 2026
509 | 2026-02-18 | W000304 | E14263.27300-WIRING DIAGRAM OF NAVIGATION RADAR( rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2026-02-18 | 2026-02-28 | 1 | azis |  | JC180226 31778 | utk tgl 18 februari 2026 | JC180226 31781 | utk tgl 19-28 februari 2026
510 | 2026-02-18 | W000304 | E14331.26300-CONNECTION DIAGRAM OF PUBLIC ADDRESS SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-02-18 | 2026-02-28 | 1 | ferry |  | JC180226 31779 | utk tgl 18 februari 2026 | JC180226 31780 | utk tgl 19-28 februari 2026
511 | 2026-02-20 | W000304 | E12521.27200 WIRING DIAGRAM OF PROPULSION COTROL SYSTEM REVISI-1 | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-02-21 | 2026-02-28 | 1 | RIANTO |  | JC200226 31882
512 | 2026-02-20 | W000306 | Weight kontrol (KB-03) & 3D Cadmatic Model Update | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-02-18 | 2026-02-28 | 1 | REGINA |  | JC200226 31885 | utk tgl 18 februari 2026 | JC200226 31888 | utk tgl 19-28 februari 2026
513 | 2026-02-20 | W000304 | PENYELESAIAN REVISI WIRING DIAGRAM OF LAN PENYELESAIAN REVISI WIRING DIAGRAM OF ICCP PENYELESAIAN REVISI WIRING DIAGRAM OF STARTING AIR SYSTEM PENYELESAIAN REVISI WIRING DIAGRAM OF SERVICE AIR SYSTEM PENYELESAIAN REVISI WIRING DIAGRAM OF SLC PENYELESAIAN REVISI WIRING DIAGRAM OF PMS PENYELESAIAN REVISI WIRING DIAGRAM OF HPSW | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-02-16 | 2026-02-28 | 1 | ALAM |  | JC200226 31890 | utk tgl 16-18 februari 2026 | JC200226 31891 | utk tgl 19-28 februari 2026
514 | 2026-02-20 | W000304 | E14380.27200 Wiring diagram of IPMS rev 1 | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-02-19 | 2026-02-28 | 1 | CANDRA |  | JC200226 31892
515 | 2026-02-23 | W000306 | revisi OLD of RCV Sytsem revisi OLD of Ro-ro Equipment system | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-02-23 | 2026-02-28 | 1 | CANDRA |  | JC230226 31928
516 | 2026-02-23 | W000306 | revisi OLD of heli hangar door Sytsem | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-02-23 | 2026-02-28 | 1 | regina |  | JC230226 31929
2026-03-01
517 | 2026-02-25 | W000305 | CEK CONNECTION : - POWER DISTRIBUTION 115V/400HZ SYSTEM - EMERGENCY STOP SYSTEM - ACCOMMODATION LADDER SYSTEM - GENERAL ILLUMINATION LIGHTING - EMERGENCY LIGHTING - NAVIGATION LIGHTING SYSTEMS - SEA WATER COOLING SYSTEM - FRESH WATER COOLING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-03-02 | 2026-03-17 | 1 | HARI | 105 | JC250226 32128
518 | 2026-02-25 | W000305 | CEK CONNECTION : - FUEL OIL SYSTEM - LUBRICATING OIL SYSTEM - RHIB DAVIT DOOR | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-03-25 | 2026-03-31 | 1 | HARI | 46 | JC250226 32129
519 | 2026-02-25 | W000307 | CEK WIRING DIAGRAM : - LIGHTING SYSTEM 1 DECK - LIGTHTING SYSTEM 03 DECK - LIGHTING SYSTEM 04 DECK - LIGHTING SYSTEM TOP DECK | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-03-02 | 2026-03-17 | 1 | PRIYONO | 105 | JC250226 32132
520 | 2026-02-25 | W000307 | CEK CUTTING LIST : - LIGHTING SYSTEM 1 DECK - LIGTHTING SYSTEM 03 DECK | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-03-25 | 2026-03-31 | 1 | PRIYONO | 46 | JC250226 32133
521 | 2026-02-25 | W000311 | - ELECTRIC LOAD BALLANCE - BATTERY CAPACITY CALCULATION - REV. ESTIMATE MATERIAL OF ELECTRIC SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-03-02 | 2026-03-17 | 1 | RENDRA | 105 | JC250226 32134
522 | 2026-02-25 | W000305 | - EVATEK LIGHTING FIXTURES - REV. OLD GENERAL LIGHITNG SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-03-25 | 2026-03-31 | 1 | RENDRA | 46 | JC250226 32130
523 | 2026-02-25 | W000307 | - CEK INSTALL MCW BLOCK 113P, 113S, 313P, 213P, 213S, 233P, 233S - CEK INSTALL SEAT BLOCK 412P, 412S, 432P, 432S, 212P | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-03-02 | 2026-03-17 | 1 | ADI | 105 | JC250226 32135
524 | 2026-02-25 | W000307 | - CEK INSTALL SEAT BLOCK 212S, 222P, 222S | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-03-25 | 2026-03-31 | 1 | ADI | 46 | JC250226 32136
525 | 2026-02-25 | W000308 | - WIRING DIAGRAM OF ELECTRIC POWER DISTRIBUTION 115V/60HZ SYSTEM - CUTTING LIST OF POWER DISTRIBUTION 24V SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-03-02 | 2026-03-17 | 1 | ALDI | 105 | JC250226 32143
526 | 2026-02-25 | W000305 | - REVISI ARR'T MCT | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-03-25 | 2026-03-31 | 1 | ALDI | 46 | JC250226 32131
527 | 2026-02-25 | W000308 | - BATTERY CAPACITY CALCULATIONS - RE-WIRING DIAGRAM POWER DISTRIBUTION 440V SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-03-02 | 2026-03-17 | 1 | ALDO | 105 | JC250226 32144
528 | 2026-02-25 | W000308 | CUTTING LIST OF MAIN POWER GENERATION SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-03-25 | 2026-03-31 | 1 | ALDO | 46 | JC250226 32145
529 | 2026-02-25 | W000307 | - WIRING DIAGRAM SOCKET OUTLET - WIRING DIAGRAM COOLING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-03-02 | 2026-03-17 | 1 | NOVAL | 105 | JC250226 32137
530 | 2026-02-25 | W000307 | - WIRING DIAGRAM LIGHTING SYSTEM 05 DECK | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-03-25 | 2026-03-31 | 1 | NOVAL | 46 | JC250226 32138
531 | 2026-02-25 | W000307 | CEK CUTTING LIST : - MAIN POWER GENERATION SYSTEM - EM'CY POWER GENERATION SYSTEM - POWER DISTRIBUTION 440V SYSTEM - POWER DISTRIBUTION 220V SYSTEM - POWER DISTRIBUTION 115V/60HZ SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-03-02 | 2026-03-17 | 1 | YOGI | 105 | JC250226 32139
532 | 2026-02-25 | W000307 | CEK CUTTING LIST : - POWER DISTRIBUTION 115V/400HZ SYSTEM - POWER DISTRIBUTION 24V SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-03-25 | 2026-03-31 | 1 | YOGI | 46 | JC250226 32140
533 | 2026-02-25 | W000306-JW1 | - BATTERY CAPACITY CALCULATIONS - ARR'T OF ELECTRIC LIGHTING SYSTEM - WIRING DIAGRAM OF ELECTRIC LIGHTING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-03-02 | 2026-03-17 | 1 | ARIZAL | 105 | JC250226 32141
534 | 2026-02-25 | W000306-JW1 | - INSTALL. DWG OF MCW BLOCK AP - INSTALL. DWG OF MCW BLOCK FP | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-03-25 | 2026-03-31 | 1 | ARIZAL | 46 | JC250226 32142
535 | 2026-03-02 | W000306 JW1 | ARR'T OF BRIDGE CONTROL CONSOLE | 1CL400 - Biro Desain Sistem Elektronika | 2026-03-02 | 2026-03-09 | 1 | nisa |  | JC020326 32358
536 | 2026-03-02 | W000304 | E14941.26300 - CONNECTION DIAGRAM OF WEATHER SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-03-02 | 2026-03-09 | 1 | azis |  | JC020326 32360
537 | 2026-03-02 | W000308 | E14200.16302-ARR'T OF OVERHEAD PANEL ( rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2026-03-02 | 2026-03-09 | 1 | ferry |  | JC020326 32362
538 | 2026-03-03 | W000304 | E12521.26200 CONNECTION DIAGRAM OF PROPULSION CONTROL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-02 | 2026-03-14 | 1 | RIANTO |  | JC030326 32456
539 | 2026-03-03 | W000304 | E11691.26200 CONNECTION DIAGRAM OF HELICOPTER HANGAR DOOR | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-02 | 2026-03-07 | 1 | REGINA |  | JC030326 32458
540 | 2026-03-03 | W000304 | E14380.26200 CONNECTION DIAGRAM OF INTEGRATED PLATFORM MANAGEMENT SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-02 | 2026-03-14 | 1 | CANDRA |  | JC030326 32457
541 | 2026-03-03 | W000304 | PENYELESAIAN REVISI WIRING DIAGRAM OF LAN PENYELESAIAN REVISI WIRING DIAGRAM OF SLC | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-02 | 2026-03-07 | 1 | ALAM |  | JC030326 32459
542 | 2026-03-09 | W000311 | E14380.16200 ARR'T. OF INTEGRATED CONTROL AND MONITORING SYSTEM (ICMS) E14380.27200 WIRING DIAGRAM OF INTEGRATED CONTROL AND MONITORING SYSTEM (ICMS) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-09 | 2026-03-17 | 1 | REGINA |  | JC090326 32645
543 | 2026-03-09 | W000311 | E14361.16200 ARR'T. OF FIRE DETECTION AND ALARM SYSTEM E14361.27200 WIRING DIAGRAM OF FIRE DETECTION AND ALARM SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-09 | 2026-03-14 | 1 | ALAM |  | JC090326 32646
544 | 2026-03-09 | W000311 | E94000.92202 WEIGHT CONTROL OF CONTROL & AUTOMATION OUT FITTING (KB02) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-16 | 2026-03-18 | 1 | ALAM |  | JC090326 32647
545 | 2026-03-10 | W000306 | E14921.16300 - ARR'T OF FLIGHT DECK LIGHTING ( rev.5) | 1CL400 - Biro Desain Sistem Elektronika | 2026-03-10 | 2026-03-19 | 1 | nisa |  | JC100326 32699
546 | 2026-03-10 | W000304 | E14941.26300 - WIRING DIAGRAM OF METEOROLOGICAL SYSTEM ( rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2026-03-10 | 2026-03-19 | 1 | azis |  | JC100326 32702
547 | 2026-03-10 | W000304 | E14000.01300-PRINCIPLE PARTICULAR OF ELECTRONIC | 1CL400 - Biro Desain Sistem Elektronika | 2026-03-10 | 2026-03-19 | 1 | ferry |  | JC100326 32704
548 | 2026-03-25 | W000306 JW1 | ARR'T OF BRIDGE CONTROL CONSOLE | 1CL400 - Biro Desain Sistem Elektronika | 2026-03-25 | 2026-03-31 | 1 | nisa |  | JC100326 32700
549 | 2026-03-25 | W000304 | E14231.26300 - CONNECTION DIAGRAM OF GLOBAL POSITIONING SYSTEM (GPS) | 1CL400 - Biro Desain Sistem Elektronika | 2026-03-25 | 2026-03-31 | 1 | azis |  | JC100326 32706
550 | 2026-03-25 | W000304 | E14282.26300-CONNECTION DIAGRAM OF AUTOPILOT SYSTEM ( rev.1) | 1CL400 - Biro Desain Sistem Elektronika | 2026-03-25 | 2026-03-31 | 1 | ferry |  | JC100326 32708
551 | 2026-03-16 | W000304 | E12521.26200 CONNECTION DIAGRAM OF PROPULSION CONTROL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-16 | 2026-03-17 | 1 | RIANTO |  | JC160326 32940
552 | 2026-03-16 | W000304 | E14380.26200 CONNECTION DIAGRAM OF INTEGRATED PLATFORM MANAGEMENT SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-16 | 2026-03-17 | 1 | CANDRA |  | JC160326 32941
553 | 2026-03-16 | W000305 | REVIEW MCR CONSOLE FWD & AFT | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-16 | 2026-03-17 | 1 | RIANTO |  | JC250326 33150
554 | 2026-03-16 | A24AOP01 | EVALUASI MAKER STEERING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-16 | 2026-03-17 | 1 | CANDRA |  | JC160326 32965
555 | 2026-03-26 | W000307 | EVALUASI APPROVAL DRAWING MAKER RCV & TLI SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-25 | 2026-03-27 | 1 | CANDRA |  | JC260326 33215
556 | 2026-03-26 | W000311 | E14380.27200 WIRING DIAGRAM OF INTEGRATED CONTROL AND MONITORING SYSTEM (ICMS) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-25 | 2026-03-27 | 1 | REGINA |  | JC260326 33219
557 | 2026-03-26 | W000305 | EVALUASI TEKNIS LAYOUT MCR CONSOLE FWD & AFT | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-25 | 2026-03-26 | 1 | RIANTO |  | JC260326 33217
558 | 2026-03-26 | W000307 | EVALUASI APPROVAL DRAWING MAKER HANGAR DOOR | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-26 | 2026-03-27 | 1 | RIANTO |  | JC260326 33216
559 | 2026-03-26 | W000305 | PENYELESAIAN REVISI WIRING DIAGRAM OF REMOTE CONTROL VALVE SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-25 | 2026-03-28 | 1 | ALAM |  | JC260326 33218
560 | 2026-03-27 | W000305 | CONNECTION DIAGRAM OF INTEGRATED PLATFORM MANAGEMENT SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-28 | 2026-03-28 | 1 | CANDRA |  | JC270326 33249
561 | 2026-03-31 | W000306 | REVIEW I/O list IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-30 | 2026-04-06 | 1 | RIANTO |  | JC310326 33434
562 | 2026-03-31 | W000308 | E16333.16200 ARRANGEMENT OF MGPS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-30 | 2026-04-03 | 1 | REGINA |  | JC310326 33435
563 | 2026-03-31 | W000308 | E16332.16200 ARRANGEMENT OF ICCP | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-30 | 2026-04-03 | 1 | ALAM |  | JC310326 33436
564 | 2026-03-31 | W000308 | E15681.25200 OLD OF BOW THRUSTER | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-03-31 | 2026-04-08 | 1 | CANDRA |  | JC310326 33437
2026-04-01
565 | 2026-04-02 | W000311 | ARR'T OF BRIDGE CONTROL CONSOLE | 1CL400 - Biro Desain Sistem Elektronika | 2026-04-01 | 2026-04-08 | 1 | nisa |  | JC020426 33563
566 | 2026-04-02 | W000308 | CHECK ROUTING CABLE OF WEATHER SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-04-01 | 2026-04-08 | 1 | azis |  | JC020426 33565
567 | 2026-04-02 | W000311 | ARR'T OF NAVIGATION AND COMMUNICATION | 1CL400 - Biro Desain Sistem Elektronika | 2026-04-01 | 2026-04-08 | 1 | ferry |  | JC020426 33564
568 | 2026-04-01 | W000305 | Revisi : - R5, OLD POWER DIST. 440V SYSTEM - R3, OLD POWER DIST. 230V - R2, OLD POWER DIST. 115V 60HZ - R1, OLD POWER DIST. 115V 400HZ - R2, OLD MECHANICAL FAN | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-04-01 | 2026-04-22 | 1 | HARI | 156 | JC020426 33579
569 | 2026-04-01 | W000307 | CEK WIRING : - LIGHTING SYSTEM MAIN DECK - LIGHTING SYSTEM 01 DECK | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-04-23 | 2026-04-30 | 1 | HARI | 60 | JC020426 33580
570 | 2026-04-01 | W000307 | 1. ATO BATTERY & BATTERY CHARGE 2. ATO CONVERTER 3. ATO INDIVIDUAL STARTER 4. CEK CUTTING LIST : - FO SYSTEM - LO SYSTEM - STORE CRANE & HOIST - ANCHOR HANDLING - AIR CRAFT TRAVERSING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-04-01 | 2026-04-30 | 1 | PRIYONO | 222 | JC020426 33581
571 | 2026-04-01 | W000311 | - INST. MCW - WIRING DIAGRAM ELECTRIC SYSTEM - REV. ESTIMATE MATERIAL OF ELECTRIC SYSTEM - EVATEK MSB & DB - EVATEK UPS, BATTERY & BATTERY CHARGE | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-04-01 | 2026-04-30 | 1 | RENDRA | 222 | JC020426 33588
572 | 2026-04-01 | W000307 | CEK REV. INSTALL MCW BLOCK : 214P, 214S, 22P, 224S, 234P, 234S, 314P, 314S, 414P, 414S, 424P, 424S, 124P, 124S, 324P, 324S. | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-04-01 | 2026-04-30 | 1 | ADI | 222 | JC020426 33582
573 | 2026-04-01 | W000308 | - EVATEK LIGHTING FIXTURES - REV. OLD SOCKET OUTLET - REV. ARR'T SOCKET OUTLET - ARR'T MODULE MCT | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-04-01 | 2026-04-30 | 1 | ALDI | 222 | JC020426 33587
574 | 2026-04-01 | W000308 | - EVATEK HVAC SYSTEM - ONE LINE DIAGRAM OF AC (AHU) SYSTEM - ONE LINE DIAGRAM OF COOLING SYSTEM - ARR'T. OF AC (AHU) SYSTEM - ARR'T. OF COOLING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-04-01 | 2026-04-30 | 1 | ALDO | 222 | JC020426 33586
575 | 2026-04-01 | W000307 | 1 'WIRING DIAGRAM LIGHTING SYSTEM 05 DECK 2 CEK CUTTING LIST: - GALLEY EQUIPMENT SYSTEM - LAUNDRY EQUIPMENT SYSTEM - WORKSHOP EQUIPMENT SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-04-01 | 2026-04-30 | 1 | NOVAL | 222 | JC020426 33583
576 | 2026-04-01 | W000307 | CEK CUTTING LIST : - AC (AHU) SYSTEM - COOLING SYSTEM - SEA WATER COOLING SYSTEM - SEWAGE TREATMENT SYSTEM - REVERSE OSMOSIS PLANT - FRESH WATER COOLING SYSTEM - FRESH WATER SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-04-01 | 2026-04-30 | 1 | YOGI | 222 | JC020426 33584
577 | 2026-04-01 | W000306-JW1 | - ARR'T OF ELECTRIC POWER SYSTEM - WIRING DIAGRAM POWER SYSTEM - WIRING DIAGRAM LIGHTING SYSTEM - REV. MATERIAL LIST | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-04-01 | 2026-04-30 | 1 | ARIZAL | 222 | JC020426 33585
578 | 2026-04-02 | W000308 | E16332.16200 ARRANGEMENT OF ICCP | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-04-04 | 2026-04-04 | 1 | ALAM |  | JC020426 33612
579 | 2026-04-02 | W000305 | CONNECTION DIAGRAM OF RCV | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-04-06 | 2026-04-10 | 1 | RIANTO |  | JC020426 33622
580 | 2026-04-02 | W000308 | E16333.27200 WIRING DIAGRAM OF MGPS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-04-06 | 2026-04-11 | 1 | REGINA |  | JC020426 33613
581 | 2026-04-02 | W000308 | E16332.27200 WIRING DIAGRAM OF ICCP | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-04-06 | 2026-04-11 | 1 | ALAM |  | JC020426 33614
582 | 2026-04-02 | W000308 | E15681.16200 ARRANGEMENT OF BOW THRUSTER | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-04-13 | 2026-04-20 | 1 | REGINA |  | JC020426 33615
583 | 2026-04-02 | W000308 | E15681.27200 WIRING DIAGRAM OF BOW THRUSTER | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-04-20 | 2026-04-27 | 1 | REGINA |  | JC020426 33616
584 | 2026-04-02 | W000308 | E15681.25200 OLD OF RO-RO EQUIPMENT | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-04-09 | 2026-04-18 | 1 | CANDRA |  | JC020426 33617
585 | 2026-04-02 | W000306 JW1 | E12521.16200 ARRANGEMENT OF PROPULSION CONTROL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-04-13 | 2026-04-18 | 1 | ALAM |  | JC020426 33618
586 | 2026-04-02 | W000306 JW1 | E12521.27200 WIRING DIAGRAM OF PROPULSION CONTROL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-04-20 | 2026-04-24 | 1 | ALAM |  | JC020426 33619
587 | 2026-04-02 | W000306 JW1 | E14370.16200 ARRANGEMENT OF TANK LEVEL & DRAUGHT INDICATING | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-04-25 | 2026-04-30 | 1 | ALAM |  | JC020426 33620
588 | 2026-04-02 | W000306 JW1 | E14370.27200 WIRING DIAGRAM OF TANK LEVEL & DRAUGHT INDICATING | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-04-30 | 2026-05-05 | 1 | ALAM |  | JC020426 33621
589 | 2026-04-10 | W000308 | ROUTING CABLE OF LOCK IN ALARM SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-04-09 | 2026-04-16 | 1 | nisa |  | JC100426 33864
590 | 2026-04-10 | W000308 | ROUTING CABLE OF MAGNETIC COMPASS SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-04-09 | 2026-04-16 | 1 | azis |  | JC100426 33865
591 | 2026-04-10 | W000308 | ROUTING CABLE OF RUDDER ANGLE INDICATOR SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-04-09 | 2026-04-16 | 1 | ferry |  | JC100426 33866
592 | 2026-04-10 | W000304 | CONNECTION DIAGRAM OF SLC | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-04-11 | 2026-04-15 | 1 | RIANTO |  | JC100426 33903
593 | 2026-04-10 | W000304 | CONNECTION DIAGRAM OF LAN | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-04-16 | 2026-04-20 | 1 | RIANTO |  | JC100426 33904
594 | 2026-04-17 | W000306 | E14413.27303 - UPDATE ROUTING CABLE OF CELLULER | 1CL400 - Biro Desain Sistem Elektronika | 2026-04-17 | 2026-04-23 | 1 | nisa |  | JC170426 34100
595 | 2026-04-17 | W000304 | E14211.27300 - ROUTING CABLE OF MAGNETIC COMPASS SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-04-17 | 2026-04-23 | 1 | azis |  | JC170426 34102
596 | 2026-04-17 | W000306 | E14282.27300 - ROUTING CABLE OF AUTOPILOT SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-04-17 | 2026-04-23 | 1 | ferry |  | JC170426 34101
597 | 2026-04-17 | W000308 | E15421.25200 OLD OF AVIATION FUEL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-04-20 | 2026-04-25 | 1 | CANDRA |  | JC170426 34123
598 | 2026-04-17 | W000304 | CONNECTION DIAGRAM OF FOAM FIRE EXTINGUISHING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-04-21 | 2026-04-25 | 1 | RIANTO |  | JC170426 34124
599 | 2026-04-27 | W000308 | E15611.16200 ARRT OF STEERING GEAR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-04-28 | 6-May-26 | 1 | REGINA |  | JC270426 34439
600 | 2026-04-27 | W000308 | E15421.16200 ARRT OF AVIATION FUEL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-04-27 | 4-May-26 | 1 | CANDRA |  | JC270426 34440
601 | 2026-04-27 | W000305 | CONNECTION DIAGRAM OF PROPULSION CONTROL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-04-27 | 5-May-26 | 1 | RIANTO |  | JC270426 34441
602 | 2026-04-27 | W000306 | E14413.25303 - UPDATE ONE LINE OF CELULLAR SIGNAL REPEATER | 1CL400 - Biro Desain Sistem Elektronika | 2026-04-24 | 2026-04-30 | 1 | nisa |  | JC270426 34442
603 | 2026-04-27 | W000308 | E14262.25300 - UPDATE ONE LINE DIAGRAM OF SPEED LOG | 1CL400 - Biro Desain Sistem Elektronika | 2026-04-24 | 2026-04-30 | 1 | azis |  | JC270426 34444
604 | 2026-04-27 | W000306 | E14282.25300 - UPDATE ONE LINE DIAGRAM OF AUTOPILOT SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-04-24 | 2026-04-30 | 1 | ferry |  | JC270426 34447
2026-05-01
605 | 4-May-26 | W000308 | E14391.25300 - UPDATE ONE LINE DIAGRAM OF CCTV | 1CL400 - Biro Desain Sistem Elektronika | 4-May-26 | 11-May-26 | 1 | nisa |  | JC040526 34787
606 | 4-May-26 | W000308 | E14241.25300 - UPDATE ONE LINE DIAGRAM OF ECHO SOUNDER | 1CL400 - Biro Desain Sistem Elektronika | 4-May-26 | 11-May-26 | 1 | azis |  | JC040526 34788
607 | 4-May-26 | W000308 | E14200.16305 - UPDATE ARR'T OF CHART CONSOLE | 1CL400 - Biro Desain Sistem Elektronika | 4-May-26 | 11-May-26 | 1 | ferry |  | JC040526 34790
608 | 03-May-26 | W000305 | Revisi : - R5, OLD POWER MAIN GENERATION SYSTEM - R3, OLD FW COOLING SYST - R3, OLD MONORAIL - R3, OLD MOORING & TOWING - R4, OLD GALLEY EQP | 1CL100 - Biro Desain Sistem Kelistrikan | 04-May-26 | 23-May-26 | 1 | HARI | 146 | JC050526 34808
609 | 03-May-26 | W000307 | CEK REV. INSTALL MCW BLOCK : 413P, 413S, 123P, 123S, 213P, 213S | 1CL100 - Biro Desain Sistem Kelistrikan | 25-May-26 | 30-May-26 | 1 | HARI | 33 | JC050526 34810
610 | 03-May-26 | W000307 | Revisi : - R1, OLD SEA WATER COOLING SYSTEM - R2, OLD FRESH WATER COOLING SYSTEM - R1, OLD FRESH WATER SYST - R2, OLD RO SYST - R3, OLD AIR CRAFT - R1, OLD STORE & CRANE HOIST - R1, OLD BALLAST SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 04-May-26 | 30-May-26 | 1 | PRIYONO | 182 | JC050526 34811
611 | 03-May-26 | W000311 | - WEIGHT CONTROL OF ELECTRIC OUT FITTING (KB02) - WEIGHT CONTROL OF ELECTRIC OUT FITTING (KB03) - INST. DWG. OF ELECT. & ELECTRO. EQUIP. SEAT WHEEL HOUSE | 1CL100 - Biro Desain Sistem Kelistrikan | 04-May-26 | 30-May-26 | 1 | RENDRA | 182 | JC050526 34819
612 | 03-May-26 | W000307 | CEK REV. INSTALL MCW BLOCK : 612P, 612S, 622P, 622S, 632P, 632S, 642P, 642S, 512P, 512S, 522P, 522S, 532P, 532S | 1CL100 - Biro Desain Sistem Kelistrikan | 04-May-26 | 30-May-26 | 1 | ADI | 182 | JC050526 34812
613 | 03-May-26 | W000307 | Revisi : - REV. OLD SOCKET OUTLET - REV. ARR'T SOCKET OUTLET - WEIGHT CONTROL OF ELECTRIC OUT FITTING (KB03) | 1CL100 - Biro Desain Sistem Kelistrikan | 04-May-26 | 23-May-26 | 1 | ALDI | 149 | JC050526 34813
614 | 03-May-26 | W000308 | - OLD GALLEY EQP SYST - ARR'T GALLEY EQP SYST | 1CL100 - Biro Desain Sistem Kelistrikan | 25-May-26 | 30-May-26 | 1 | ALDI | 33 | JC050526 34817
615 | 03-May-26 | W000308 | - EVATEK RECOMPRESSOR CHAMBER - EVATEK GALLEY EQUIPMENT - ARR'T. OF POWER DIST. 115V 60HZ | 1CL100 - Biro Desain Sistem Kelistrikan | 04-May-26 | 30-May-26 | 1 | ALDO | 182 | JC050526 34818
616 | 03-May-26 | W000307 | CEK CUTTING LIST : - MAIN LIGHTING SYSTEM - EM'CY LIGHTING SYSTEM - SOCKET OUTLET SYSTEM - ANCHOR & MOORING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 04-May-26 | 30-May-26 | 1 | NOVAL | 182 | JC050526 34814
617 | 03-May-26 | W000307 | CEK CUTTING LIST : - EM'CY STOP SYSTEM - BALLAST SYSTEM - OILY BILGE/SLUDGE OIL SYSTEM - MECHANICAL VENT. FAN SYSTEM - ACCOMMODATION LADDER | 1CL100 - Biro Desain Sistem Kelistrikan | 04-May-26 | 30-May-26 | 1 | YOGI | 182 | JC050526 34815
618 | 03-May-26 | W000305 | - REV WIRING MAIN POWER GENERATION SYSTEM - REV. CUTTING LIST MAIN POWER GENERATION SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 04-May-26 | 09-May-26 | 1 | ARIZAL | 55 | JC050526 34809
619 | 03-May-26 | W000306-JW1 | - WEIGHT CONTROL OF ELECTRIC OUT FITTING (KB02) - OLD LIGTHING SYSTEM - ARR'T LIGHTING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 11-May-26 | 30-May-26 | 1 | ARIZAL | 127 | JC050526 34816
620 | 6-May-26 | W000308 | UPDATE 3D MODEL EQUIPMENT IN CADMATIC | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 6-May-26 | 13-May-26 | 1 | ALAM |  | JC060526 34822
621 | 6-May-26 | W000308 | E15611.27200 WIRING DIAGRAM OF STEERING GEAR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 7-May-26 | 18-May-26 | 1 | REGINA |  | JC060526 34823
622 | 6-May-26 | W000308 | E11672.25200 OLD OF WT SLIDING DOOR | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 5-May-26 | 9-May-26 | 1 | CANDRA |  | JC060526 34830
623 | 6-May-26 | W000308 | E11672.16200 ARRT OF WT SLIDING DOOR | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 11-May-26 | 16-May-26 | 1 | CANDRA |  | JC060526 34825
624 | 6-May-26 | W000308 | E15512.25200 OLD OF STARTING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 6-May-26 | 11-May-26 | 1 | RIANTO |  | JC060526 34831
625 | 6-May-26 | W000308 | E15512.16200 ARRT OF STARTING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 12-May-26 | 18-May-26 | 1 | RIANTO |  | JC060526 34827
626 | 6-May-26 | W000308 | E15513.25200 OLD OF SERVICE & WORKING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 19-May-26 | 23-May-26 | 1 | RIANTO |  | JC060526 34832
627 | 6-May-26 | W000308 | E15513.16200 ARRT OF SERVICE & WORKING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 25-May-26 | 30-May-26 | 1 | RIANTO |  | JC060526 34828
628 | 11-May-26 | W000308 | REV1SI-1 E12521.25200 OLD OF PROPULSION CONTROL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 11-May-26 | 22-May-26 | 1 | RIANTO | 64 | JC110526 34933
629 | 12-May-26 | W000306 | E14211.27300 - WIRING DIAGRAM OF NAVIGATION & COMMUNICATION SYSTEM (LCU) | 1CL400 - Biro Desain Sistem Elektronika | 12-May-26 | 20-May-26 | 1 | nisa |  | JC120526 35035
630 | 12-May-26 | W000308 | E14231.25300- UPDATE ONE LINE DIAGRAM OF GLOBAL POSITIONING SYSTEM (GPS) | 1CL400 - Biro Desain Sistem Elektronika | 12-May-26 | 20-May-26 | 1 | azis |  | JC120526 35034
631 | 12-May-26 | W000311 | UPDATE ARR'T OF NAVIGATION AND COMMUNICATION (CADMATIC) | 1CL400 - Biro Desain Sistem Elektronika | 12-May-26 | 20-May-26 | 1 | ferry |  | JC120526 35036
632 | 13-May-26 | W000307 | cable cutting list for IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 14-May-26 | 22-May-26 | 1 | ALAM | 56 | JC130526 35080
633 | 2026-04-01 | CORP2026 | DINAS PELATIHAN MAINTANANCE GUN 12.7 MM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-04-03 | 2026-04-13 | 1 | ADI |  | JC180526 35262
634 | 19-May-26 | W000306 | REVISI OLD OF ICCP & ARRT OF ICCP | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 18-May-26 | 21-May-26 | 1 | CANDRA |  | JC190526 35339
635 | 19-May-26 | W000306 | REVISI OLD OF MGPS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 22-May-26 | 25-May-26 | 1 | CANDRA |  | JC190526 35340
636 | 19-May-26 | W000311 | UPDATE 3D MODEL EQUIPMENT IN CADMATIC | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 19-May-26 | 22-May-26 | 1 | REGINA |  | JC190526 35341
637 | 22-May-26 | W000304 | E14391.26300 - CONNECTION DIAGRAM OF CCTV | 1CL400 - Biro Desain Sistem Elektronika | 21-May-26 | 30-May-26 | 1 | nisa |  | JC220526 35445
638 | 22-May-26 | W000308 | E14201.25300- UPDATE ONE LINE DIAGRAM OF IBS | 1CL400 - Biro Desain Sistem Elektronika | 21-May-26 | 30-May-26 | 1 | azis |  | JC220526 35446
639 | 22-May-26 | W000311 | UPDATE BRIDGE CONTROL CONSOLE (CADMATIC) | 1CL400 - Biro Desain Sistem Elektronika | 21-May-26 | 30-May-26 | 1 | ferry |  | JC220526 35447
640 | 25-May-26 | W000307 | WEIGHT CONTROL (KB-04) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 25-May-26 | 29-May-26 | 1 | REGINA |  | JC250526 35554
641 | 25-May-26 | W000304 | REVISI CONNECTION DIAGRAM OF IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 25-May-26 | 6-June-26 | 1 | CANDRA |  | JC250526 35556
642 | 25-May-26 | W000308 | UPDATE 3D MODEL EQUIPMENT IPMS IN CADMATIC | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 26-May-26 | 5-june-26 | 1 | ALAM |  | JC250526 35567
2026-06-01
643 | 29-May-26 | W000307 | Revisi : - R1, OLD POWER DISTRIBUTION 440V SYSTEM - R1, OLD POWER DISTRIBUTION 220V SYSTEM - R1, OLD POWER DISTRIBUTION 115V 400HZ SYSTEM - EVATEK MSB & ESB | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-06-01 | 2026-06-30 | 1 | PRIYONO | 214 | JC020626 35809
644 | 29-May-26 | M000312 | - BASIC DIAGRAM - OLD POWER DISTRIBUTION SYSTEM - MOUNTING HEIGH OF ELECTRIC APPARATUS | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-06-01 | 2026-06-30 | 1 | RENDRA | 214 | JC020626 35812
645 | 29-May-26 | M000313 | PLANNING & 3D MODEL MCW 2 DK, 1 DK, 01 DK, 02 DK | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-06-01 | 2026-06-30 | 1 | ADI | 214 | JC020626 35813
646 | 29-May-26 | M000313 | - ELECTRICAL LOAD BALANCE - MAIN EQUIPMENT LIST OF ELECTRIC SYSTEM - STANDARD DRAWING OF MAIN CABLE WAY - MOUNTING HEIGH OF ELECTRIC APPARATUS | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-06-01 | 2026-06-30 | 1 | ALDI | 214 | JC020626 35814
647 | 29-May-26 | W000308 | - EVATEK MSB SET - 3D MODEL MSB SET IN CADMATIC | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-06-01 | 2026-06-30 | 1 | ALDO | 214 | JC020626 35817
648 | 29-May-26 | M000312 | PLANNING & 3D MODEL MCW UNDER MAIN DECK, MAIN DECK, FCASTLE DECK, NAV DECK, TOP DECK | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-06-01 | 2026-06-30 | 1 | NOVAL | 214 | JC020626 35815
649 | 29-May-26 | W000307 | CEK CUTTING LIST : - DECORATION LIGHTING - NAVIGATION LIGHTING SYSTEM - GROUND POWER UNIT - AIRCRAFT TRAVERSING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-06-01 | 2026-06-30 | 1 | YOGI | 214 | JC020626 35810
650 | 29-May-26 | M000312 | - OLD POWER GENERATION SYSTEM - OLD LIGTHING SYSTEM - STANDARD DRAWING OF MAIN CABLE WAY | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-06-01 | 2026-06-30 | 1 | ARIZAL | 214 | JC020626 35816
651 | 2026-06-03 | W000304 | CONNECTION DIAGRAM OF PCS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-01 | 2026-06-02 | 1 | RIANTO |  | JC030626 35925
652 | 2026-06-03 |  | SURVEY KAPAL GEOMARINE | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-03 | 2026-06-05 | 1 | RIANTO |  | JC030626 35934
653 | 2026-06-03 | W000304 | E55611.25200 ONE LINE DIAGRAM OF STEERING GEAR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-02 | 2026-06-05 | 1 | REGINA |  | JC030626 35926
654 | 2026-06-03 | W000304 | E55611.16200 ARRT OF STEERING GEAR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-06 | 2026-06-10 | 1 | REGINA |  | JC030626 35930
655 | 2026-06-03 | W000304 | E55651.25200 ONE LINE DIAGRAM OF ACTIVE STABILISING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-11 | 2026-06-15 | 1 | REGINA |  | JC030626 35927
656 | 2026-06-03 | W000304 | E55651.16200 ARRT OF ACTIVE STABILISING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-16 | 2026-06-19 | 1 | REGINA |  | JC030626 35931
657 | 2026-06-03 | W000304 | E56332.25200 ONE LINE DIAGRAM OF IMPRESSED CURRENT CATHODIC PROTECTION | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-20 | 2026-06-24 | 1 | REGINA |  | JC030626 35928
658 | 2026-06-03 | W000304 | E56332.16200 ARRT OF IMPRESSED CURRENT CATHODIC PROTECTION | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-25 | 2026-06-29 | 1 | REGINA |  | JC030626 35932
659 | 2026-06-03 | W000304 | E56333.25200 ONE LINE DIAGRAM OF MARINE GROWTH PREVENTION SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-30 | 2026-07-02 | 1 | REGINA |  | JC030626 35929
660 | 2026-06-03 | W000304 | E56333.16200 ARRT OF MARINE GROWTH PREVENTION SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-07-03 | 2026-07-07 | 1 | REGINA |  | JC030626 35933
661 | 2026-06-03 | W000306 | E94000.92304 - WEIGHT CONTROL OF ELECTRONIC OUT FITTING (KB04) | 1CL400 - Biro Desain Sistem Elektronika | 2026-06-01 | 2026-06-09 | 1 | nisa |  | JC030626 35959
662 | 2026-06-03 | W000308 | E14201.25300 - UPDATE ONE LINE DIAGRAM OF IBS | 1CL400 - Biro Desain Sistem Elektronika | 2026-06-01 | 2026-06-09 | 1 | azis |  | JC030626 35961
663 | 2026-06-03 | W000306 | E14321.25300 - UPDATE ONE LINE DIAGRAM OF AUTOMATIC EXCHANGE TELEPHONE | 1CL400 - Biro Desain Sistem Elektronika | 2026-06-01 | 2026-06-09 | 1 | ferry |  | JC030626 35960
664 | 29-May-26 | R22PCCXA | - ONE LINE DIAGRAM OF ELECTRIC SYSTEM (KRI KERAPU) - MATERIAL LIST OF ELECTRIC SYSTEM (KRI KERAPU) | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-06-01 | 2026-06-06 | 1 | HARI | 44 | JC080626 36167
665 |  | M000312 | - MAIN EQUIPMENT LIST - EVALUASI MSB, SC, DB - CEK BASIC DIAGRAM, JALUR MCW | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-06-08 | 2026-06-20 | 1 | HARI | 93 | JC080626 36132
666 |  | M000313 | - CEK JALUR MCW - CEK BASIC DIAGRAM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-06-22 | 2026-06-30 | 1 | HARI | 71 | JC080626 36133
667 | 2026-06-09 | W000305 | REVISI CONNECTION DIAGRAM OF IPMS Network | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-08 | 2026-06-15 | 1 | CANDRA |  | JC100626 36212
668 | 2026-06-09 | W000311 | I/O LIST OF ICMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-08 | 2026-06-12 | 1 | RIANTO |  | JC100626 36213
669 | 2026-06-09 | W000308 | UPDATE KONTROL BERAT (KB03) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-08 | 2026-06-10 | 1 | ALAM |  | JC100626 36214
670 | 2026-06-10 | W000304 | CHECK CADMATIC OF CCTV SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-06-10 | 2026-06-18 | 1 | nisa |  | JC100626 36251
671 | 2026-06-10 | W000308 | CHECK CADMATIC OF IBS | 1CL400 - Biro Desain Sistem Elektronika | 2026-06-10 | 2026-06-18 | 1 | azis |  | JC100626 36250
672 | 2026-06-10 | W000304 | E15883.16300 - UPDATEA RR'T OF HELI CONTROL CONSOLE | 1CL400 - Biro Desain Sistem Elektronika | 2026-06-10 | 2026-06-18 | 1 | ferry |  | JC100626 36252
673 | 2026-06-11 | W000305 | REVISI ARRT OF PCS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-11 | 2026-06-12 | 1 | ALAM |  | JC120626 36286
674 | 2026-06-18 | W000305 | REVISI ARRT OF PCS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-15 | 2026-06-19 | 1 | ALAM |  | JC180626 36523
675 | 2026-06-18 | W000305 | REVISI CONNECTION DIAGRAM OF IPMS RTU-10, RTU-09, RTU-02 | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-15 | 2026-06-19 | 1 | CANDRA |  | JC180626 36524
676 | 2026-06-18 | W000305 | REVISI CONNECTION DIAGRAM OF IPMS RTU-03, RTU-04, RTU-05, RTU-07, RTU-13 | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-22 | 2026-06-30 | 1 | CANDRA |  | JC180626 36525
677 | 2026-06-18 | W000305 | REVIEW & CHECK FINAL DRAWING OLD & ARRANGEMENT | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-15 | 2026-06-27 | 1 | RIANTO |  | JC180626 36526
678 | 2026-06-18 | W000308 | REVIEW FUNCTIONAL DESIGN SPECIFICATION (FDS) FOR IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-19 | 2026-06-30 | 1 | RIANTO |  | JC180626 36527
679 | 2026-06-19 | W000304 | CHECK CADMATIC OF HVLA SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-06-19 | 2026-06-30 | 1 | nisa |  | JC220626 36603
680 | 2026-06-19 | W000308 | CHECK CADMATIC OF SPEED LOG SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-06-19 | 2026-06-30 | 1 | azis |  | JC220626 36605
681 | 2026-06-19 | W000304 | UPDATE MATERIAL LIST OF ELECTRONIC SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-06-19 | 2026-06-30 | 1 | ferry |  | JC220626 36604
682 | 2026-06-23 | W000306 | CABLE CUTTING LIST FOR CONTROL & AUTOMATION SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-22 | 2026-06-30 | 1 | ALAM |  | JC230626 36691
683 | 2026-06-24 | W000311 | KONTROL BERAT (KB-03) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-06-24 | 2026-06-26 | 1 | ALAM |  | JC240626 36719
2026-07-01
684 | 2026-07-01 | W000304 | E14391.26300 - CONNECTION DIAGRAM OF CCTV | 1CL400 - Biro Desain Sistem Elektronika | 2026-07-01 | 2026-07-09 | 1 | nisa |  | JC020726 37058
685 | 2026-07-01 | W000311 | E14000.27300 - WIRING DIAGRAM OF NAVIGATION AND COMMUNICATION SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-07-01 | 2026-07-09 | 1 | azis |  | JC020726 37059
686 | 2026-07-01 | W000306 | E16254.25300 - ONE LINE DIAGRAM OF WINDOW WIPERS AND CLEAR VIEW SCREEN | 1CL400 - Biro Desain Sistem Elektronika | 2026-07-01 | 2026-07-09 | 1 | ferry |  | JC020726 37060
687 | 2026-06-30 | W000307 | Revisi : - WIRING POWER DISTRIBUTION 440V SYSTEM - WIRING POWER DISTRIBUTION 115V 400HZ SYSTEM - EVATEK MSB & ESB | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-07-01 | 2026-07-31 | 1 | PRIYONO | 238 | JC030726 37096
688 | 2026-06-30 | M000312 | - BATTERY CAPACITY CALCULATIONS - OLD ENVIRONMENT POLUTION SYSTEM - ARRT POWER DISTRIBUTION SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-07-01 | 2026-07-31 | 1 | RENDRA | 238 | JC030726 37097
689 | 2026-06-30 | M000312 | CEK MCW 3 DK,2 DK, 1 DK, 01 DK, 02 DK | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-07-01 | 2026-07-31 | 1 | ADI | 238 | JC030726 37098
690 | 2026-06-30 | M000313 | - BASIC DIAGRAM OF ELECTRIC SYSTEM - OLD POWER GENERATION SYSTEM - STANDARD DRAWING OF MAIN CABLE WAY - MOUNTING HEIGH OF ELECTRIC APPARATUS | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-07-01 | 2026-07-31 | 1 | ALDI | 238 | JC030726 37099
691 | 2026-06-30 | W000306 | - BATTERY CAPACITY CALCULATIONS | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-07-01 | 2026-07-11 | 1 | ALDO | 85 | JC030726 37100
| 2026-06-30 | W000308 | - CEK WIRING MAIN POWER GENERATION - CEK WIRING EM'CY POWER GENERATION - CEK WIRING POWER DISTS. 440V | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-07-13 | 2026-07-31 | 1 | ALDO | 153 | JC030726 37101
692 | 2026-06-30 | M000312 | - ARRT MCW 3 DK - ARRT MCW 2 DK - MCW OF FRESH WATER SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-07-01 | 2026-07-31 | 1 | NOVAL | 238 | JC030726 37102
693 | 2026-06-30 | W000312 | - ARRT MCW 1 DK - ARRT MCW 01 DK - OLD OF CLIMATE SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-07-01 | 2026-07-31 | 1 | YOGI | 238 | JC030726 37103
694 | 2026-06-30 | M000312 | - ARRT OF MAIN POWER GENERATION SYSTEM - ARRT OF ELECTRIC LIGHTING EQUIPMENT 3 DECK - ARRT OF ELECTRIC LIGHTING EQUIPMENT 2 DECK | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-07-01 | 2026-07-31 | 1 | ARIZAL | 238 | JC030726 37104
695 | 2026-06-30 | M000313 | - BASIC DIAGRAM OF ELECTRIC SYSTEM - OLD POWER GENERATION SYSTEM - OLD LIGTHING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-07-01 | 2026-07-31 | 1 | ALDI | 238 | JC030726 37099
696 | 2026-07-08 | W000308 | OLD OF SERVICE AND WORKING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-07-01 | 2026-07-10 | 1 | RIANTO |  | JC090726 37392
697 | 2026-07-08 | W000308 | OLD OF STARTING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-07-01 | 2026-07-11 | 1 | RIANTO |  | JC090726 37393
698 | 2026-07-08 | W000308 | ARRT OF SERVICE AND WORKING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-07-13 | 2026-07-20 | 1 | RIANTO |  | JC090726 37394
699 | 2026-07-08 | W000308 | ARRT OF STARTING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-07-13 | 2026-07-20 | 1 | RIANTO |  | JC090726 37395
700 | 2026-07-08 | W000308 | OLD OF FIXED GAS FIRE EXTINGUISHING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-07-01 | 2026-07-11 | 1 | CANDRA |  | JC090726 37396
701 | 2026-07-08 | W000308 | OLD OF RO-RO EQUIPMENT | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-07-13 | 2026-07-21 | 1 | CANDRA |  | JC090726 37397
702 | 2026-07-08 | W000308 | ARRT OF FIXED GAS FIRE EXTINGUISHING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-07-21 | 2026-07-27 | 1 | CANDRA |  | JC090726 37399
703 | 2026-07-08 | W000308 | ARRT OF RO-RO EQUIPMENT | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-07-27 | 4-Aug-26 | 1 | CANDRA |  | JC090726 37400
704 | 2026-07-08 | W000308 | OLD OF ELEVATORS, SHIP | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-07-08 | 2026-07-15 | 1 | REGINA |  | JC090726 37401
705 | 2026-07-08 | W000308 | OLD OF AMMUNITION ELEVATORS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-07-16 | 2026-07-23 | 1 | REGINA |  | JC090726 37403
706 | 2026-07-08 | W000308 | ARRT OF ELEVATORS, SHIP | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-07-08 | 2026-07-15 | 1 | REGINA |  | JC090726 37402
707 | 2026-07-08 | W000308 | ARRT OF AMMUNITION ELEVATORS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-07-16 | 2026-07-23 | 1 | REGINA |  | JC090726 37404
708 | 2026-07-10 | W000306 | Cek routing OF CCTV, VDR and Meteorogical | 1CL400 - Biro Desain Sistem Elektronika | 2026-07-10 | 2026-07-20 | 1 | nisa |  | JC130726 37564
709 | 2026-07-10 | W000306 | Cek routing OF IBS and Weather Fax | 1CL400 - Biro Desain Sistem Elektronika | 2026-07-10 | 2026-07-20 | 1 | azis |  | JC130726 37568
710 | 2026-07-10 | W000306 | Cek routing OF IP PBX, Autopilot and RAI | 1CL400 - Biro Desain Sistem Elektronika | 2026-07-10 | 2026-07-20 | 1 | ferry |  | JC130726 37570
711 | 2026-07-21 | W000308 | Review ONE LINE DIAGRAM OF TIME INDICATION SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-07-21 | 2026-07-27 | 1 | nisa |  | JC210726 37906
712 | 2026-07-21 | W000304 | Review MCT of GPS system | 1CL400 - Biro Desain Sistem Elektronika | 2026-07-21 | 2026-07-27 | 1 | azis |  | JC210726 37908
713 | 2026-07-21 | W000306 | Connection Diagram Of IP PBX system | 1CL400 - Biro Desain Sistem Elektronika | 2026-07-21 | 2026-07-27 | 1 | ferry |  | JC210726 37910
714 | 2026-07-22 | W000308 | OLD OF SHUTTER DOOR | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-07-21 | 2026-07-27 | 1 | RIANTO |  | JC220726 37917
715 | 2026-07-22 | W000308 | OLD OF EM'CY FIRE FIGHTING | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-07-28 | 1-Aug-26 | 1 | RIANTO |  | JC220726 37918
716 | 2026-07-22 | W000308 | OLD OF HELICOPTER HANGAR DOOR | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-07-24 | 2026-07-31 | 1 | REGINA |  | JC220726 37919
717 | 2026-07-28 | W000308 | Review Routing OF TIME INDICATION SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-07-28 | 2026-07-31 | 1 | nisa |  | JC290726 38224
718 | 2026-07-28 | W000308 | Review wiring diagram of weather system | 1CL400 - Biro Desain Sistem Elektronika | 2026-07-28 | 2026-07-31 | 1 | azis |  | JC290726 38225
719 | 2026-07-28 | W000306 | Review Wiring Diagram Of IP PBX system | 1CL400 - Biro Desain Sistem Elektronika | 2026-07-28 | 2026-07-31 | 1 | ferry |  | JC290726 38226
2026-08-01
720 | 1-Aug-26 | W000306 | Update ONE LINE DIAGRAM OF CENTRAL AERIAL SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 1-Aug-26 | 10-Aug-26 | 1 | nisa |  | JC070826 38567
721 | 1-Aug-26 | W000308 | Check WIRING DIAGRAM OF METEOROLOGICAL SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 1-Aug-26 | 10-Aug-26 | 1 | azis |  | JC070826 38569
722 | 1-Aug-26 | W000304 | Update Connection DIAGRAM OF WINDOW WIPERS | 1CL400 - Biro Desain Sistem Elektronika | 1-Aug-26 | 10-Aug-26 | 1 | ferry |  | JC070826 38570
723 | 7-Aug-26 | M000312 | E14361.16200 ARRANGEMENT OF FIRE DETECTING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 1-Aug-26 | 7-Aug-26 | 1 | REGINA |  | JC150826 39000
724 | 7-Aug-26 | M000312 | E14000.16200 ARRANGEMENT OF INSTRUMENT & ALARM SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 1-Aug-26 | 7-Aug-26 | 1 | REGINA |  | JC150826 39001
725 | 7-Aug-26 | W000308 | OLD OF EM'CY FIRE FIGHTING | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 1-Aug-26 | 1-Aug-26 | 1 | RIANTO |  | JC150826 39002
726 | 7-Aug-26 | M000312 | EVATEK AMS & FDS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 3-Aug-26 | 7-Aug-26 | 1 | RIANTO |  | JC150826 39003
727 | 7-Aug-26 | M000313 | EVATEK AMS & FDS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 3-Aug-26 | 7-Aug-26 | 1 | RIANTO |  | JC150826 39004
728 | 7-Aug-26 | W000311 | EVATEK AMS & FDS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 3-Aug-26 | 7-Aug-26 | 1 | RIANTO |  | JC150826 39005
729 | 7-Aug-26 | W000314 | EVATEK AMS & FDS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 3-Aug-26 | 7-Aug-26 | 1 | RIANTO |  | JC150826 39006
730 | 7-Aug-26 | A26AOP01 | E14000.16200 ARRANGEMENT OF INSTRUMENT & ALARM SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 3-Aug-26 | 7-Aug-26 | 1 | CHANDRA |  | JC150826 38984
731 | 7-Aug-26 | A26AOP01 | EVATEK AMS & FDS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 3-Aug-26 | 7-Aug-26 | 1 | CHANDRA |  | JC150826 39007
732 | 7-Aug-26 | W000308 | E15553.25200 ONE LINE DIAGRAM OF FIXED GAS FIRE EXTINGUISHING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 3-Aug-26 | 8-Aug-26 | 1 | CHANDRA |  | JC150826 39008
733 | 7-Aug-26 | W000308 | E15553.16200 ARRT OF FIXED GAS FIRE EXTINGUISHING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 3-Aug-26 | 8-Aug-26 | 1 | CHANDRA |  | JC150826 39009
734 | 2026-07-31 | W000307 | Revisi : - EVATEK MSB & ESB | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Aug-26 | 08-Aug-26 | 1 | PRIYONO | 55 | JC110826 38726
735 | 2026-07-31 | W000306 | APPROVAL DRAWINGS FOR OWNER COMMENT : BASIC DIAGRAM OF ELECTRIC SYSTEM ONE LINE DIAGRAM OF EM'CY POWER GENERATION SYSTEM ONE LINE DIAGRAM OF POWER DISTRIBUTION 440V SYSTEM ONE LINE DIAGRAM OF POWER DISTRIBUTION 220V SYSTEM ONE LINE DIAGRAM OF POWER DISTRIBUTION 115V/60HZ SYSTEM ONE LINE DIAGRAM OF POWER DISTRIBUTION 115V/400HZ SYSTEM ONE LINE DIAGRAM OF POWER DISTRIBUTION 24V SYSTEM ARRANGEMENT OF POWER DISTRIBUTION 24V DC SYSTEM ARRANGEMENT OF POWER DISTRIBUTION 440V SYSTEM ARRANGEMENT OF EMERGENCY POWER GENERATION SYSTEM ARRANGEMENT OF POWER DISTRIBUTION 220V SYSTEM ELECTRICAL ARRANGEMENT OF POWER DISTRIBUTION 115V/400HZ ARRANGEMENT OF MAIN POWER GENERATION SYSTEM ONE LINE DIAGRAM OF MECHANICAL VENTILATION SYSTEM ONE LINE DIAGRAM OF AC (AHU) SYSTEM ONE LINE DIAGRAM OF COOLING SYSTEM ONE LINE DIAGRAM OF SEWAGE TREATMENT SYSTEM ONE LINE DIAGRAM OF OILY BILGE/SLUDGE OIL SYSTEM ONE LINE DIAGRAM OF GALLEY AND PANTRY EQUIPMENT SYSTEM ONE LINE DIAGRAM OF WORKSHOP EQUIPMENT SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 10-Aug-26 | 31-Aug-26 | 1 | PRIYONO | 151 | JC110826 38728 JC140826 38957 JC140826 38958 JC140826 38963 JC140826 38964 JC150826 38985 JC150826 38986 JC150826 38987 JC150826 38988 JC150826 38989 JC150826 38990 JC150826 38991 JC150826 38992 JC150826 38993 JC150826 38994 JC150826 38995 JC150826 38996 JC150826 38997 JC150826 38998 JC150826 38999
736 | 2026-07-31 | M000314 | - ELECTRIC LOAD ANALYSIS | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Aug-26 | 08-Aug-26 | 1 | RENDRA | 55 | JC110826 38731
737 | 2026-07-31 | W000311 | REVISI - OLD POWER SYSTEM (R2) - ARRT POWER SYSTEM (R2) - ARRT LIGHTING SYSTEM (R3) | 1CL100 - Biro Desain Sistem Kelistrikan | 10-Aug-26 | 31-Aug-26 | 1 | RENDRA | 154 | JC110826 38733 JC110826 38767 JC110826 38768
738 | 2026-07-31 | M000313 | - ARRANGEMENT OF MAIN CABLE WAY 2 DECK - ARRANGEMENT OF MAIN CABLE WAY PARTIAL DECK - ARRANGEMENT OF MAIN CABLE WAY 1 DECK | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Aug-26 | 31-Aug-26 | 1 | ADI | 209 | JC110826 38736
739 | 2026-07-31 | M000313 | - OLD OF POWER DISTRIBUTION SYSTEM - OLD OF FUEL & LUBRICATING SYSTEM - OLD OF FRESH WATER SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Aug-26 | 31-Aug-26 | 1 | ALDI | 241 | JC110826 38743
740 | 2026-07-31 | W000308 | -REV OLD MAIN POWER GENERATION - REV WIRING POWER DIST.440V & 690V - EVATEK MSB SET - REV OLD, ARRT & WIRING SEWAGE TREATHMENT PLANT | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Aug-26 | 31-Aug-26 | 1 | ALDO | 177 | JC110826 38745 JC110826 38746 JC110826 38748 JC140826 38959 JC110826 38749 JC140826 38960
741 | 2026-07-31 | M000312 | - WIRING DIAGRAM OF POWER GENERATION SYSTEM - WIRING DIAGRAM OF DISTRIBUTION SYSTEM - WIRING DIAGRAM OF FRESH WATER SYSTEM - WIRING DIAGRAM OF ENVIRONMENT POLUTION SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Aug-26 | 31-Aug-26 | 1 | NOVAL | 241 | JC110826 38751
742 | 2026-07-31 | M000312 | - WIRING DIAGRAM OF CLIMATE SYSTEM - WIRING DIAGRAM OF FUEL OIL & LUBRICATING SYSTEM - WIRING DIAGRAM OF MECHANICAL HANDLING SYSTEMS | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Aug-26 | 31-Aug-26 | 1 | YOGI | 241 | JC110826 38752
743 | 2026-07-31 | M000312 | - WEIGHT CONTROL OF ELECTRONIC OUTFITTING (KB02) - PRINCIPLE PARTICULAR OF ELECTRIC PART - CEK WIRING: CLIMATE SYSTEM MECHANICAL HANDLING FO & LO SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Aug-26 | 31-Aug-26 | 1 | ARIZAL | 241 | JC120826 38860
744 | 11-Aug-26 | W000306 | WEIGHT KONTROL (KB-04) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 13-Aug-26 | 15-Aug-26 | 1 | REGINA |  | JC150826 39010
745 | 11-Aug-26 | W000305 | REVIEW LAYOUT & MAKER DWG MCR CONSOLE | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 10-Aug-26 | 11-Aug-26 | 1 | RIANTO |  | JC150826 39011
746 | 11-Aug-26 | W000305 | REVIEW PROPULSION CONTROL SYSTEM EQUIPMENT | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 12-Aug-26 | 15-Aug-26 | 1 | RIANTO |  | JC150826 39012
747 | 11-Aug-26 | W000305 | REVISI CONNECTION DIAGRAM OF PCS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 12-Aug-26 | 15-Aug-26 | 1 | RIANTO |  | JC150826 39013
748 | 11-Aug-26 | W000308 | ARRANGEMENT OF IPMS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 10-Aug-26 | 13-Aug-26 | 1 | CHANDRA |  | JC150826 39014
749 | 11-Aug-26 | W000305 | REVISI MATERIAL LIST OF CONTROL & AUTOMATION | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 12-Aug-26 | 12-Aug-26 | 1 | CHANDRA |  | JC150826 39015
750 | 11-Aug-26 | W000311 | OLD OF SURFACE DRIVE PROPELLER SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 13-Aug-26 | 19-Aug-26 | 1 | CHANDRA |  | JC150826 39016
751 | 11-Aug-26 | W000306 | Update ONE LINE DIAGRAM OF FILGHT DECK LIGHTING SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 11-Aug-26 | 19-Aug-26 | 1 | nisa |  | JC130826 38936
752 | 11-Aug-26 | W000306 | Update ONE LINE DIAGRAM OF IBS SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 11-Aug-26 | 19-Aug-26 | 1 | azis |  | JC130826 38937
753 | 11-Aug-26 | W000306 | Connection DIAGRAM OF WINDOW WIPERS | 1CL400 - Biro Desain Sistem Elektronika | 11-Aug-26 | 19-Aug-26 | 1 | ferry |  | JC130826 38938
754 | 19-Aug-26 | W000311 | ARRT OF SURFACE PIERCING PROPELLER CONTROL AND ALARM SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 18-Aug-26 | 21-Aug-26 | 1 | REGINA |  | JC190826 39198
755 | 19-Aug-26 | W000306 | REVISI OLD TANK LEVEL & DRAUGHT INDICATING REVISI OLD OF ELEVATOR, SHIP REVISI OLD OF AVIATION FUEL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 18-Aug-26 | 24-Aug-26 | 1 | CHANDRA |  | JC190826 39195 JC190826 39196 JC190826 39197
756 | 19-Aug-26 | W000313 | EVATEK AMS & FDS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 18-Aug-26 | 19-Aug-26 | 1 | RIANTO |  | JC190826 39199
757 | 19-Aug-26 | W000306-JW1 | REVISI OLD TANK LEVEL & DRAUGHT INDICATING | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 19-Aug-26 | 20-Aug-26 | 1 | RIANTO |  | JC190826 39200
758 | 24-Aug-26 | W000306 | Review CONNECTION DIAGRAM OF FILGHT DECK LIGHTING SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 20-Aug-26 | 31-Aug-26 | 1 | nisa |  | JC240826 39325
759 | 24-Aug-26 | W000306 | Review Connection DIAGRAM OF IBS SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 20-Aug-26 | 31-Aug-26 | 1 | azis |  | JC240826 39326
760 | 24-Aug-26 | W000306 | Wiring DIAGRAM OF WINDOW WIPERS | 1CL400 - Biro Desain Sistem Elektronika | 20-Aug-26 | 31-Aug-26 | 1 | ferry |  | JC240826 39327
761 | 24-Aug-26 | M000312 | KONTROL BERAT KB-02 & KB-03 | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 24-Aug-26 | 27-Aug-26 | 1 | REGINA |  | JC260826 39439
762 | 24-Aug-26 | W000306 | REVISI ESTIMATE QUANTITY MATERIAL CONTROL & AUTOMATION PART | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 26-Aug-26 | 27-Aug-26 | 1 | CHANDRA |  | JC260826 39440
763 | 24-Aug-26 | W000311 | REVIEW MAKER DRAWING SURFACE DRIVE PROPELLER SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 21-Aug-26 | 24-Aug-26 | 1 | RIANTO |  | JC260826 39441
764 | 28-Aug-26 | W000311 | ARRT OF PROPULSION CONTROL SYSTEM & SURRFACE PIERCING PROPELLER CONTROL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 28-Aug-26 | 2026-09-02 | 1 | REGINA |  | JC280826 39549
765 | 28-Aug-26 | W000311 | REVIEW MAKER DRAWING MAIN ENGINE | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 28-Aug-26 | 28-Aug-26 | 1 | CHANDRA |  | JC280826 39550
766 | 28-Aug-26 | W000306 | REVISI OLD OF AVIATION FUEL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 29-Aug-26 | 31-Aug-26 | 1 | CHANDRA |  | JC280826 39551
767 | 28-Aug-26 | W000308 | REVIEW MAKER DRAWING HANGAR DOOR, AMMO LIFT & BOWTHRUSTER SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 26-Aug-26 | 31-Aug-26 | 1 | RIANTO |  | JC280826 39552
2026-09-01
769 | 2026-09-01 | W000306 | CONNECTION DIAGRAM OF ELEVATORS, SHIP | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-09-02 | 2026-09-04 | 1 | REGINA |  | JC020926 39864
770 | 2026-09-01 | W000306 | CONNECTION DIAGRAM OF AMMUNITION ELEVATOR | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-09-05 | 2026-09-08 | 1 | REGINA |  | JC020926 39865
771 | 2026-09-01 | W000308 | CONNECTION DIAGRAM OF PROPULSION CONTROL SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-09-01 | 2026-09-08 | 1 | RIANTO |  | JC020926 39866
772 | 2026-09-01 | W000308 | CONNECTION DIAGRAM OF STEERING GEAR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-09-09 | 2026-09-12 | 1 | RIANTO |  | JC020926 39867
773 | 2026-09-01 | W000308 | CONNECTION DIAGRAM OF BOW THRUSTER SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-09-09 | 2026-09-12 | 1 | CANDRA |  | JC020926 39868
774 | 2026-09-01 | W000308 | WIRING DIAGRAM OF STARTING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-09-09 | 2026-09-11 | 1 | REGINA |  | JC020926 39869
775 | 2026-09-01 | W000308 | WIRING DIAGRAM OF SERVICE AND WORKING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-09-12 | 2026-09-15 | 1 | REGINA |  | JC020926 39870
776 | 2026-09-01 | W000304 | Update arrangement diagram of steering control | 1CL400 - Biro Desain Sistem Elektronika | 2026-09-01 | 2026-09-09 | 1 | nisa |  | JC080926 40075
777 | 2026-09-01 | W000306 | Update ONE LINE DIAGRAM OF VDR SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-09-01 | 2026-09-09 | 1 | azis |  | JC080926 40076
778 | 2026-09-01 | W000311 | Update Arrangement of Bridge Control Console | 1CL400 - Biro Desain Sistem Elektronika | 2026-09-01 | 2026-09-09 | 1 | ferry |  | JC080926 40077
779 | 2026-09-01 | W000306 | Approval Drawings for owner comment : ELECTRICAL ARRANGEMENT OF GALLEY AND PANTRY EQUIPMENT SYSTEM ELECTRICAL ARRANGEMENT OF WORKSHOP EQUIPMENT SYSTEM ELECTRICAL ARRANGEMENT OF LAUNDRY EQUIPMENT SYSTEM ARRANGEMENT OF EMERGENCY POWER GENERATION SYSTEM ARRANGEMENT OF ELECTRIC STORES CRANE AND HOIST ARRANGEMENT OF MECHANICAL VENTILATION SYSTEM ELECTRICAL ARRANGEMENT OF FRESH WATER COOLING SYSTEM ELECTRICAL ARRANGEMENT OF EMERGENCY STOP SYSTEM ELECTRICAL ARRANGEMENT OF LUBRICATING OIL SYSTEM ARRANGEMENT OF ELECTRIC BALLAST WATER SYSTEM ARRANGEMENT OF FRESH WATER SYSTEM ELECTRICAL ARRANGEMENT OF COOLING SYSTEM ARRANGEMENT OF SEAWATER COOLING SYSTEM | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-09-01 | 2026-09-30 | 1 | PRIYONO |  | JC080926 40082 JC080926 40103 JC080926 40107 JC080926 40108 JC080926 40109 JC080926 40110 JC080926 40111 JC080926 40112 JC080926 40113 JC080926 40114 JC080926 40115 JC080926 40116 JC080926 40117
780 | 2026-09-01 | M000312 | Approval Drawings for owner comment : Basic Diagaram of Electric System Electric Load Analisy OLD Power Distribution System OLD Fuel & Lubricating System OLD Environment Polution System | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-09-01 | 2026-09-30 | 1 | RENDRA |  | JC080926 40118 JC080926 40119 JC080926 40120 JC080926 40121 JC080926 40122
781 | 2026-09-01 | M000312 | - CEK WIRING POWER GENERATION SYSTEM - CEK WIRING LIGHTING 1 DK - INST. DWG. OF ELECTRIC & ELECTRONIC SEAT ON 3 DECK BLOCK 211C - INST. DWG. OF ELECTRIC & ELECTRONIC SEAT ON 2 DECK BLOCK 422C - INST. DWG. OF ELECTRIC & ELECTRONIC SEAT ON 2 DECK BLOCK 212C - INST. DWG. OF ELECTRIC & ELECTRONIC SEAT ON 2 DECK BLOCK 112C - INST. DWG. OF ELECTRIC & ELECTRONIC SEAT ON 2 DECK BLOCK 122C - INST. DWG. OF ELECTRIC & ELECTRONIC SEAT ON 2 DECK BLOCK 322C | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-09-01 | 2026-09-22 | 1 | ADI |  | JC080926 40123 JC080926 40124 JC080926 40125 JC080926 40126 JC080926 40127 JC080926 40128 JC080926 40129 JC080926 40130
782 | 2026-09-01 | M000313 | CEK : - ARR'T MCW 3 DK - ARR'T MCW 2 DK - ARR'T MCW 1 DK | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-09-23 | 2026-09-30 | 1 | ADI |  | JC080926 40131 JC080926 40132 JC080926 40133
783 | 2026-09-01 | M000313 | - EVATEK MSB SET - ESTIMATION MATERIAL OF ELECTRIC PART | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-09-01 | 2026-09-10 | 1 | ALDI |  | JC080926 40140 JC080926 40134
784 | 2026-09-01 | M000313 | - BATTERY CAPACITY CALCULATION | 1CL100 - Biro Desain Sistem Kelistrikan | 01-Aug-26 | 2026-09-05 | 1 | ALDO |  | JC080926 40135
785 | 2026-09-01 | W000308 | - EVATEK MSB SET REVISI : - WIRING DIAGRAM POWER DISTRIBUTION 440V | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-09-07 | 2026-09-10 | 1 | ALDO |  | JC080926 40137 JC080926 40138
786 | 2026-09-01 | M000313 | - ONE LINE DIAGRAM OF FRESH WATER SYSTEM - ONE LINE DIAGRAM OF FUEL & LUBRICATING SYSTEM - ARRANGEMENT OF ELECTRIC POWER EQUIPMENT 1 DECK | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-09-01 | 2026-09-30 | 1 | NOVAL |  | JC080926 40142 JC080926 40143 JC080926 40144
787 | 2026-09-01 | W000313 | - ONE LINE DIAGRAM OF CLIMATE SYSTEM - ONE LINE DIAGRAM OF MECHANICAL HANDLING SYSTEM - ARRANGEMENT OF ELECTRIC POWER EQUIPMENT 2 DECK | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-09-01 | 2026-09-30 | 1 | YOGI |  | JC080926 40145 JC080926 40146 JC080926 40147
788 | 2026-09-01 | M000313 | - CEK : - WIRING CLIMATE SYSTEM SYSTEM - WIRING LIGHTING 2 DK - WIRING LIGHTING 01 DK - WEIGHT CONTROL OF ELECTRONIC OUTFITTING (KB03) - ATO MSB SET - REVISI MATERIAL LIST | 1CL100 - Biro Desain Sistem Kelistrikan | 2026-09-01 | 2026-09-30 | 1 | ARIZAL |  | JC080926 40148 JC080926 40149 JC080926 40150 JC080926 40151 JC080926 40152 JC080926 40153
789 | 2026-09-11 | W000306 | WEIGHT CONTROL OF ELECTRONIC OUTFITTING (KB03) -LCU | 1CL400 - Biro Desain Sistem Elektronika | 2026-09-10 | 2026-09-16 | 1 | nisa |  | JC110926 40294
790 | 2026-09-11 | W000306 | Update ONE LINE DIAGRAM OF IBS SYSTEM | 1CL400 - Biro Desain Sistem Elektronika | 2026-09-10 | 2026-09-16 | 1 | azis |  | JC110926 40295
791 | 2026-09-11 | M000314 | Arrangement of Bridge Control Console | 1CL400 - Biro Desain Sistem Elektronika | 2026-09-10 | 2026-09-16 | 1 | ferry |  | JC110926 40296
792 | 2026-09-14 | W000308 | CONNECTION DIAGRAM OF STARTING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-09-14 | 2026-09-17 | 1 | RIANTO |  | JC150926 40514
793 | 2026-09-14 | W000308 | CONNECTION DIAGRAM OF SERVICE AND WORKING AIR SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-09-18 | 2026-09-21 | 1 | RIANTO |  | JC150926 40515
794 | 2026-09-14 | W000308 | CONNECTION DIAGRAM OF FIRE DETECTING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-09-22 | 2026-09-26 | 1 | RIANTO |  | JC150926 40516
795 | 2026-09-14 | W000308 | CONNECTION DIAGRAM OF MGPS | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-09-28 | 2026-09-29 | 1 | RIANTO |  | JC150926 40517
796 | 2026-09-14 | W000308 | CONNECTION DIAGRAM OF ICCP | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-09-30 | 1-Oct-26 | 1 | RIANTO |  | JC150926 40518
797 | 2026-09-14 | - | TUGAS NEGARA - KOMPONEN CADANGAN (KOMCAD) | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-09-14 | 2026-09-30 | 1 | CANDRA |  | JC150926 40519
798 | 2026-09-14 | W000308 | WIRING DIAGRAM OF SHUTTER DOOR | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-09-15 | 2026-09-17 | 1 | REGINA |  | JC150926 40520
799 | 2026-09-14 | W000308 | WIRING DIAGRAM OF REMOTE CONTROL VALVE | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-09-18 | 2026-09-25 | 1 | REGINA |  | JC150926 40521
800 | 2026-09-14 | W000308 | WIRING DIAGRAM OF FOAM FIRE EXTINGUISHING SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2026-09-26 | 1-Oct-26 | 1 | REGINA |  | JC150926 40522
801 | 2026-09-14 | W000308 | WIRING DIAGRAM OF RO-RO EQUIPMENT SYSTEM | 1CL201 - Biro Desain Sistem Kontrol Otomasi | 2-Oct-26 | 10-Oct-26 | 1 | REGINA |  | JC150926 40523